## Sheet1
| CR | Ticket | State | Group | Assign | Act. Effort | Est. Effort | Plan Finish | plan Start | Criterion 2 | Criterion 3 | Criterion 4 | Criterion 5 | Criterion 6 | Criterion 7 | Short Description | Start Developing | Target QA Completion Date | Actual QA completion date | UAT Passed Date | Ready for Production Date | Deployed to Staging Date | Deployment Finish | Actual Release Date | Approved for Production Date | Date Closed | Ticket.1 | UI path | Module code | Deployment Week | Deployment Month | Total Actual Efforts | Total Estimated Efforts | Development duration | CTASK Number | Related team | Related members | Effort/duratoin | Dev Emp Cd | Time in Project(Year) | Tester Tested | Bugs | Incident count | Efforts | Members | Duration | Deploy in week | Deploy in month | Dev Quality Rate | Dev Quality Rate by Exp. Year | Start Develop | ttl_bug_inc | is_bug_inc
0 | CR0013281 | CTASK0023549 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 6 | 2020-12-11 17:30 | 2020-12-01 10:29 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] Enhancement on PRD Call when there is any change on Shpr, Fwdr and Cnee | 2020-12-08 14:10 | 2020-12-24 01:00 | 2020-12-10 15:53 | 2021-04-14 08:23 | 2021-04-15 09:15 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-15 09:26 | 2021-05-27 14:00 | CR0013281 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W17 | 2021-04 | 34 | 40 | 139.8266 | 4 | 1 | 1 | 0.01 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 27 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
1 | CR0013281 | CTASK0023544 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal] Enhancement on PRD Call when there is any change on Shpr, Fwdr and Cnee | 2020-12-08 14:10 | 2020-12-24 01:00 | 2020-12-10 15:53 | 2021-04-14 08:23 | 2021-04-15 09:15 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-15 09:26 | 2021-05-27 14:00 | CR0013281 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W17 | 2021-04 | 34 | 40 | 139.8266 | 4 | 1 | 1 | 0.01 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 27 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
2 | CR0013281 | CTASK0023548 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 24 | 24 | 2020-11-20 18:31 | 2020-11-17 10:26 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal] Enhancement on PRD Call when there is any change on Shpr, Fwdr and Cnee | 2020-12-08 14:10 | 2020-12-24 01:00 | 2020-12-10 15:53 | 2021-04-14 08:23 | 2021-04-15 09:15 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-15 09:26 | 2021-05-27 14:00 | CR0013281 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W17 | 2021-04 | 34 | 40 | 139.8266 | 4 | 1 | 1 | 0.01 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 27 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
3 | CR0013281 | CTASK0023550 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal] Enhancement on PRD Call when there is any change on Shpr, Fwdr and Cnee | 2020-12-08 14:10 | 2020-12-24 01:00 | 2020-12-10 15:53 | 2021-04-14 08:23 | 2021-04-15 09:15 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-15 09:26 | 2021-05-27 14:00 | CR0013281 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W17 | 2021-04 | 34 | 40 | 139.8266 | 4 | 1 | 1 | 0.01 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 27 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
4 | CR0013082 | CTASK0025874 | Closed | OPUS-ACM | Huynh Tuan Khanh | 24 | 24 | 2021-04-30 14:29 | 2021-03-15 14:29 | Container | Support & Admin | Agent Commission Management | Audit |  |  | NA *ACM* Creating new calculation status in FF Compensation Audit | 2021-03-15 14:25 | 2021-04-30 14:25 | 2021-04-29 15:19 | 2021-05-13 14:55 | 2021-06-03 13:33 |  | 2021-06-15 13:33 | 2021-06-15 12:58 | 2021-06-11 16:38 | 2021-07-15 14:00 | CR0013082 | Support & AdminAgent Commission ManagementAudit | OPUS-ACM | 2021-W24 | 2021-06 | 30 | 30 | 91.9635 | 2 | 1 | 1 | 0.01 | 193499 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0 | 0 | 2021-03 | 0 | 0
5 | CR0013082 | CTASK0023679 | Closed | OPUS-ACM | Huynh Tuan Khanh | 6 | 6 | 2020-12-31 16:08 | 2020-11-20 16:08 | Container | Support & Admin | Agent Commission Management | Audit |  |  | NA *ACM* Creating new calculation status in FF Compensation Audit | 2021-03-15 14:25 | 2021-04-30 14:25 | 2021-04-29 15:19 | 2021-05-13 14:55 | 2021-06-03 13:33 |  | 2021-06-15 13:33 | 2021-06-15 12:58 | 2021-06-11 16:38 | 2021-07-15 14:00 | CR0013082 | Support & AdminAgent Commission ManagementAudit | OPUS-ACM | 2021-W24 | 2021-06 | 30 | 30 | 91.9635 | 2 | 1 | 1 | 0.01 | 193499 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0 | 0 | 2021-03 | 0 | 0
6 | CR0013319 | CTASK0023760 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 26 | 26 | 2021-01-06 18:30 | 2020-12-28 10:30 | Container | Service Management | Booking/Documentation | Booking | Compulsory Firm |  | [Development][CLT Internal] - Prevent to firm the bookings that already have Firm status (Compulsory Firm screen). | 2020-12-28 09:26 | 2021-02-04 01:00 | 2021-01-28 10:08 | 2021-01-28 16:28 | 2021-01-28 17:06 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 09:08 | 2021-04-01 14:00 | CR0013319 | Service ManagementBooking/DocumentationBookingCompulsory Firm | OPUS-BKG-M | 2021-W9 | 2021-03 | 40 | 40 | 64.0237 | 4 | 1 | 1 | 0.03 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
7 | CR0013319 | CTASK0023762 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-02-25 02:00 | 2021-02-22 11:27 | Container | Service Management | Booking/Documentation | Booking | Compulsory Firm |  | [Deployment][CLT Internal] - Prevent to firm the bookings that already have Firm status (Compulsory Firm screen). | 2020-12-28 09:26 | 2021-02-04 01:00 | 2021-01-28 10:08 | 2021-01-28 16:28 | 2021-01-28 17:06 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 09:08 | 2021-04-01 14:00 | CR0013319 | Service ManagementBooking/DocumentationBookingCompulsory Firm | OPUS-BKG-M | 2021-W9 | 2021-03 | 40 | 40 | 64.0237 | 4 | 1 | 1 | 0.03 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
8 | CR0013319 | CTASK0023651 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2020-11-24 12:55 | 2020-11-20 12:55 | Container | Service Management | Booking/Documentation | Booking | Compulsory Firm |  | [Design] [CLT Internal] - Prevent to firm the bookings that already have Firm status (Compulsory Firm screen). | 2020-12-28 09:26 | 2021-02-04 01:00 | 2021-01-28 10:08 | 2021-01-28 16:28 | 2021-01-28 17:06 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 09:08 | 2021-04-01 14:00 | CR0013319 | Service ManagementBooking/DocumentationBookingCompulsory Firm | OPUS-BKG-M | 2021-W9 | 2021-03 | 40 | 40 | 64.0237 | 4 | 1 | 1 | 0.03 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
9 | CR0013319 | CTASK0023761 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-01-29 19:59 | 2021-01-25 11:59 | Container | Service Management | Booking/Documentation | Booking | Compulsory Firm |  | [Testing][CLT Internal] - Prevent to firm the bookings that already have Firm status (Compulsory Firm screen). | 2020-12-28 09:26 | 2021-02-04 01:00 | 2021-01-28 10:08 | 2021-01-28 16:28 | 2021-01-28 17:06 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 09:08 | 2021-04-01 14:00 | CR0013319 | Service ManagementBooking/DocumentationBookingCompulsory Firm | OPUS-BKG-M | 2021-W9 | 2021-03 | 40 | 40 | 64.0237 | 4 | 1 | 1 | 0.03 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
10 | CR0011515 | CTASK0016013 | Closed | OPUS-BKG-M | Vinh Tran | 16 | 16 | 2019-10-18 15:41 | 2019-10-14 15:41 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | NA *BKG* When BKG is firm the Tier and Role data is removed (CSVC) | 2019-10-14 18:57 | 2019-10-29 | 2019-10-22 13:12 | 2019-10-25 03:27 | 2019-10-25 12:36 | 2019-10-22 13:12 | 2019-11-05 12:36 | 2019-11-05 11:28 | 2019-10-28 23:03 | 2019-11-08 04:17 | CR0011515 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2019-W45 | 2019-11 | 16 | 16 | 21.7355 | 1 | 1 | 1 | 0.03 | 193525 | 0.4 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 7 | 0 | 0.45455 | 2019-10 | 0 | 0
11 | CR0013675 | CTASK0025720 | Closed | OPUS-PRI | Ngan Nham | 32 | 32 | 2021-03-27 01:00 | 2021-03-09 01:00 | Data Integration | Customer |  |  |  |  | [Development] UPDATE API | 2021-03-09 10:05 | 2021-03-27 01:00 | 2021-03-19 17:05 | 2021-05-20 13:08 | 2021-05-20 13:11 |  | 2021-05-25 13:00 | 2021-05-25 11:00 | 2021-05-20 13:14 | 2021-06-24 14:00 | CR0013675 | Customer | OPUS-PRI | 2021-W21 | 2021-05 | 48 | 48 | 77.1216 | 2 | 1 | 1 | 0.03 | 193461 | 2.3 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0 | 0 | 2021-03 | 0 | 0
12 | CR0013675 | CTASK0026959 | Closed | OPUS-PRI | Ngan Nham | 16 | 16 | 2021-05-29 01:00 | 2021-05-12 01:00 | Data Integration | Customer |  |  |  |  | [Development] modify the message and add item in json | 2021-03-09 10:05 | 2021-03-27 01:00 | 2021-03-19 17:05 | 2021-05-20 13:08 | 2021-05-20 13:11 |  | 2021-05-25 13:00 | 2021-05-25 11:00 | 2021-05-20 13:14 | 2021-06-24 14:00 | CR0013675 | Customer | OPUS-PRI | 2021-W21 | 2021-05 | 48 | 48 | 77.1216 | 2 | 1 | 1 | 0.03 | 193461 | 2.3 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0 | 0 | 2021-03 | 0 | 0
13 | CR0012803 | CTASK0021898 | Closed | OPUS-SCG | Tu Nguyen | 21 | 20 | 2020-08-28 16:04 | 2020-08-01 16:04 | Container | Vessel Operation | Special Cargo |  |  |  | [CLV]Revision of "DG List for Vessel" | 2020-07-27 16:04 | 2020-09-01 16:03 | 2020-08-27 18:25 | 2020-09-04 13:09 | 2020-09-04 13:27 |  | 2020-09-08 09:30 | 2020-09-08 09:30 | 2020-09-04 13:39 | 2020-10-10 13:00 | CR0012803 | Vessel OperationSpecial Cargo | OPUS-SCG | 2020-W37 | 2020-09 | 109 | 102 | 42.7265 | 3 | 1 | 3 | 0.1 | 123045 | 1.8 | 0 | 0 | 0 | 2 | 1 | 1 | 9 | 36 | 0 | 0 | 2020-07 | 0 | 0
14 | CR0012803 | CTASK0021646 | Closed | OPUS-SCG | Trang Duy Thong | 76 | 70 | 2020-08-28 18:51 | 2020-08-01 10:50 | Container | Vessel Operation | Special Cargo |  |  |  | [CLV]Revision of "DG List for Vessel" | 2020-07-27 16:04 | 2020-09-01 16:03 | 2020-08-27 18:25 | 2020-09-04 13:09 | 2020-09-04 13:27 |  | 2020-09-08 09:30 | 2020-09-08 09:30 | 2020-09-04 13:39 | 2020-10-10 13:00 | CR0012803 | Vessel OperationSpecial Cargo | OPUS-SCG | 2020-W37 | 2020-09 | 109 | 102 | 42.7265 | 3 | 1 | 3 | 0.1 | 193511 | 0.1 | 0 | 0 | 0 | 2 | 1 | 1 | 9 | 36 | 0 | 0 | 2020-07 | 0 | 0
15 | CR0012803 | CTASK0021231 | Closed | OPUS-SCG | Thuan Tran | 12 | 12 | 2020-08-28 14:48 | 2020-08-01 14:48 | Container | Vessel Operation | Special Cargo |  |  |  | [CLV]Revision of "DG List for Vessel" | 2020-07-27 16:04 | 2020-09-01 16:03 | 2020-08-27 18:25 | 2020-09-04 13:09 | 2020-09-04 13:27 |  | 2020-09-08 09:30 | 2020-09-08 09:30 | 2020-09-04 13:39 | 2020-10-10 13:00 | CR0012803 | Vessel OperationSpecial Cargo | OPUS-SCG | 2020-W37 | 2020-09 | 109 | 102 | 42.7265 | 3 | 1 | 3 | 0.1 | 183423 | 1.7 | 0 | 0 | 0 | 2 | 1 | 1 | 9 | 36 | 0 | 0 | 2020-07 | 0 | 0
16 | CR0013004 | CTASK0022048 | Closed | OPUS-SCO | Cuong Tran Hung | 15 | 15 | 2020-08-31 09:10 | 2020-08-25 09:10 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [August][CLT Internal][Cuong] Restriction of DSO Inquiry terms | 2020-09-02 08:57 | 2020-09-15 08:57 | 2020-09-02 11:53 | 2020-09-07 13:03 | 2020-09-07 13:12 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-09-07 13:16 | 2020-10-16 13:00 | CR0013004 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2020-W38 | 2020-09 | 38 | 38 | 13.0439 | 3 | 1 | 3 | 0.12 | 193530 | 1.3 | 2 | 2 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.2222 | 2020-09 | 2 | 1
17 | CR0013004 | CTASK0022049 | Closed | OPUS-SCO | Mohamed Hary | 15 | 15 | 2020-08-31 09:11 | 2020-08-25 09:11 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [August][CLT Internal][Hary] Restriction of DSO Inquiry terms | 2020-09-02 08:57 | 2020-09-15 08:57 | 2020-09-02 11:53 | 2020-09-07 13:03 | 2020-09-07 13:12 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-09-07 13:16 | 2020-10-16 13:00 | CR0013004 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2020-W38 | 2020-09 | 38 | 38 | 13.0439 | 3 | 1 | 3 | 0.12 | 193489 | 1.3 | 2 | 2 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.63636 | 2020-09 | 2 | 1
18 | CR0013004 | CTASK0022050 | Closed | OPUS-SCO | Hang To | 8 | 8 | 2020-08-31 09:12 | 2020-08-25 09:12 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [August][CLT Internal][To Minh Hang] Restriction of DSO Inquiry terms | 2020-09-02 08:57 | 2020-09-15 08:57 | 2020-09-02 11:53 | 2020-09-07 13:03 | 2020-09-07 13:12 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-09-07 13:16 | 2020-10-16 13:00 | CR0013004 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2020-W38 | 2020-09 | 38 | 38 | 13.0439 | 3 | 1 | 3 | 0.12 | 183344 | 1.4 | 2 | 2 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 2.4286 | 2020-09 | 2 | 1
19 | CR0013325 | CTASK0024293 | Closed | OPUS-SCE | Son Nguyen The | 17 | 17 | 2020-12-31 13:33 | 2020-12-13 13:33 | Container | Service Management | SCEM | Customer Order Plan |  |  | [CLT Internal] OPUS Service enhancement for triggering NFD event #2 | 2020-12-18 13:11 | 2021-01-04 19:10 | 2020-12-24 16:01 | 2021-01-14 18:06 | 2021-01-14 23:00 |  | 2021-01-19 10:00 | 2021-01-19 09:14 | 2021-01-15 13:10 | 2021-01-20 16:59 | CR0013325 | Service ManagementSCEMCustomer Order Plan | OPUS-SCE | 2021-W3 | 2021-01 | 35 | 0 | 31.8676 | 4 | 1 | 2 | 0 | 193531 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 40 | 0 | 0 | 2020-12 | 0 | 0
20 | CR0013325 | CTASK0024351 | Closed | OPUS-SCE | VInh Bui | 6 | 6 | 2020-12-31 16:29 | 2020-12-01 16:29 | Container | Service Management | SCEM | Customer Order Plan |  |  | [CLT Internal] OPUS Service enhancement for triggering NFD event #2 | 2020-12-18 13:11 | 2021-01-04 19:10 | 2020-12-24 16:01 | 2021-01-14 18:06 | 2021-01-14 23:00 |  | 2021-01-19 10:00 | 2021-01-19 09:14 | 2021-01-15 13:10 | 2021-01-20 16:59 | CR0013325 | Service ManagementSCEMCustomer Order Plan | OPUS-SCE | 2021-W3 | 2021-01 | 35 | 0 | 31.8676 | 4 | 1 | 2 | 0 | 193469 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 40 | 0 | 0 | 2020-12 | 0 | 0
21 | CR0013325 | CTASK0023652 | Closed | OPUS-SCE | Son Nguyen The | 3 | 3 |  |  | Container | Service Management | SCEM | Customer Order Plan |  |  | [Documentation][CLT Internal] OPUS Service enhancement for triggering NFD event #2 | 2020-12-18 13:11 | 2021-01-04 19:10 | 2020-12-24 16:01 | 2021-01-14 18:06 | 2021-01-14 23:00 |  | 2021-01-19 10:00 | 2021-01-19 09:14 | 2021-01-15 13:10 | 2021-01-20 16:59 | CR0013325 | Service ManagementSCEMCustomer Order Plan | OPUS-SCE | 2021-W3 | 2021-01 | 35 | 0 | 31.8676 | 4 | 1 | 2 | 0 | 193531 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 40 | 0 | 0 | 2020-12 | 0 | 0
22 | CR0013325 | CTASK0024580 | Closed | OPUS-SCE | Son Nguyen The | 9 | 9 | 2021-01-31 12:01 | 2021-01-01 12:01 | Container | Service Management | SCEM | Customer Order Plan |  |  | [CLT Internal] OPUS Service enhancement for triggering NFD event #2 | 2020-12-18 13:11 | 2021-01-04 19:10 | 2020-12-24 16:01 | 2021-01-14 18:06 | 2021-01-14 23:00 |  | 2021-01-19 10:00 | 2021-01-19 09:14 | 2021-01-15 13:10 | 2021-01-20 16:59 | CR0013325 | Service ManagementSCEMCustomer Order Plan | OPUS-SCE | 2021-W3 | 2021-01 | 35 | 0 | 31.8676 | 4 | 1 | 2 | 0 | 193531 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 40 | 0 | 0 | 2020-12 | 0 | 0
23 | CR0013773 | CTASK0026474 | Closed | OPUS-BKG-M | Thien Lai | 10 | 10 | 2021-04-23 18:42 | 2021-04-19 18:42 | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing] NA *Booking* Add ETB Date and Time to BRN and A/N | 2021-04-14 12:54 | 2021-04-24 | 2021-04-23 13:39 | 2021-04-28 10:02 | 2021-04-28 10:06 |  | 2021-04-29 10:00 | 2021-04-29 10:00 | 2021-04-28 13:15 | 2021-05-29 14:00 | CR0013773 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W17 | 2021-04 | 42 | 56 | 14.8794 | 5 | 2 | 2 | 0.16 | 193567 | 1.7 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.5625 | 0.53333 | 2021-04 | 0 | 0
24 | CR0013773 | CTASK0026476 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking |  |  | [Deployment] NA *Booking* Add ETB Date and Time to BRN and A/N | 2021-04-14 12:54 | 2021-04-24 | 2021-04-23 13:39 | 2021-04-28 10:02 | 2021-04-28 10:06 |  | 2021-04-29 10:00 | 2021-04-29 10:00 | 2021-04-28 13:15 | 2021-05-29 14:00 | CR0013773 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W17 | 2021-04 | 42 | 56 | 14.8794 | 5 | 2 | 2 | 0.16 | 193567 | 1.7 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.5625 | 0.53333 | 2021-04 | 0 | 0
25 | CR0013773 | CTASK0026468 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-04-16 16:55 | 2021-04-12 16:55 | Container | Service Management | Booking/Documentation | Booking |  |  | [Design] NA *Booking* Add ETB Date and Time to BRN and A/N | 2021-04-14 12:54 | 2021-04-24 | 2021-04-23 13:39 | 2021-04-28 10:02 | 2021-04-28 10:06 |  | 2021-04-29 10:00 | 2021-04-29 10:00 | 2021-04-28 13:15 | 2021-05-29 14:00 | CR0013773 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W17 | 2021-04 | 42 | 56 | 14.8794 | 5 | 2 | 2 | 0.16 | 193567 | 1.7 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.5625 | 0.53333 | 2021-04 | 0 | 0
26 | CR0013773 | CTASK0026466 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 16 | 26 | 2021-04-23 16:39 | 2021-04-13 16:39 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development+ Testing+ Deployment] NA *Booking* Add ETB Date and Time to BRN and A/N | 2021-04-14 12:54 | 2021-04-24 | 2021-04-23 13:39 | 2021-04-28 10:02 | 2021-04-28 10:06 |  | 2021-04-29 10:00 | 2021-04-29 10:00 | 2021-04-28 13:15 | 2021-05-29 14:00 | CR0013773 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W17 | 2021-04 | 42 | 56 | 14.8794 | 5 | 2 | 2 | 0.16 | 193512 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.2963 | 0.3125 | 2021-04 | 0 | 0
27 | CR0013773 | CTASK0026472 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-04-23 18:42 | 2021-04-19 18:42 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development] NA *Booking* Add ETB Date and Time to BRN and A/N | 2021-04-14 12:54 | 2021-04-24 | 2021-04-23 13:39 | 2021-04-28 10:02 | 2021-04-28 10:06 |  | 2021-04-29 10:00 | 2021-04-29 10:00 | 2021-04-28 13:15 | 2021-05-29 14:00 | CR0013773 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W17 | 2021-04 | 42 | 56 | 14.8794 | 5 | 2 | 2 | 0.16 | 193567 | 1.7 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.5625 | 0.53333 | 2021-04 | 0 | 0
28 | CR0013565 | CTASK0024974 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 13 | 12 | 2021-02-02 19:30 | 2021-01-28 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (Origin Office) | Vessel Departure Transmit (HI) | [Development+Testing+Deployment][CLT Internal] HI EDA Update message to US CBP | 2021-01-29 09:48 | 2021-02-20 09:48 | 2021-02-04 11:11 | 2021-02-10 10:22 | 2021-02-10 10:25 |  | 2021-02-16 10:25 | 2021-02-16 09:30 | 2021-02-10 10:46 | 2021-03-20 14:00 | CR0013565 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (Origin Office)Vessel Departure Transmit (HI) | OPUS-BKG-MFT-M | 2021-W7 | 2021-02 | 14 | 13 | 18.0254 | 2 | 1 | 1 | 0.03 | 173280 | 2.1 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 21 | 0 | 1 | 2021-01 | 0 | 0
29 | CR0013565 | CTASK0024973 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 1 | 1 | 2021-01-27 19:30 | 2021-01-27 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (Origin Office) | Vessel Departure Transmit (HI) | [Analysis][CLT Internal] HI EDA Update message to US CBP | 2021-01-29 09:48 | 2021-02-20 09:48 | 2021-02-04 11:11 | 2021-02-10 10:22 | 2021-02-10 10:25 |  | 2021-02-16 10:25 | 2021-02-16 09:30 | 2021-02-10 10:46 | 2021-03-20 14:00 | CR0013565 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (Origin Office)Vessel Departure Transmit (HI) | OPUS-BKG-MFT-M | 2021-W7 | 2021-02 | 14 | 13 | 18.0254 | 2 | 1 | 1 | 0.03 | 173280 | 2.1 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 21 | 0 | 1 | 2021-01 | 0 | 0
30 | CR0013779 | CTASK0026303 | Closed | OPUS-SCG | Trang Duy Thong | 31 | 31 | 2021-04-16 18:07 | 2021-04-06 18:07 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | [CLV] Change logic for MP receive from Partner EDI | 2021-04-07 12:06 | 2021-04-16 12:05 | 2021-04-15 13:11 | 2021-04-20 10:40 | 2021-04-20 11:51 |  | 2021-04-27 11:49 | 2021-04-27 10:52 | 2021-04-20 14:39 | 2021-05-27 14:00 | CR0013779 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2021-W17 | 2021-04 | 38 | 38 | 19.9883 | 2 | 1 | 1 | 0.08 | 193511 | 0.8 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.81818 | 0 | 2021-04 | 0 | 0
31 | CR0013779 | CTASK0026302 | Closed | OPUS-SCG | Trang Duy Thong | 7 | 7 | 2021-04-16 18:07 | 2021-04-06 18:06 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | [Documentation] Change logic for MP receive from Partner EDI | 2021-04-07 12:06 | 2021-04-16 12:05 | 2021-04-15 13:11 | 2021-04-20 10:40 | 2021-04-20 11:51 |  | 2021-04-27 11:49 | 2021-04-27 10:52 | 2021-04-20 14:39 | 2021-05-27 14:00 | CR0013779 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2021-W17 | 2021-04 | 38 | 38 | 19.9883 | 2 | 1 | 1 | 0.08 | 193511 | 0.8 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.81818 | 0 | 2021-04 | 0 | 0
32 | CR0014173 | CTASK0028305 | Closed | OPUS-SAR | Lien Le | 13 | 12 | 2021-07-31 13:41 | 2021-07-22 13:41 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [July 2021][Lien Le][CLT Internal] Reinforce DSO Batch Structure | 2021-07-07 16:16 | 2021-07-30 18:00 | 2021-07-27 15:04 | 2021-07-29 10:37 | 2021-07-29 10:42 |  | 2021-07-29 10:00 | 2021-08-03 10:00 | 2021-07-30 10:32 | 2021-08-11 14:00 | CR0014173 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2021-W30 | 2021-07 | 13 | 12 | 21.7389 | 1 | 1 | 1 | 0.02 | 193441 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.42308 | 0 | 2021-07 | 0 | 0
33 | CR0011937 | CTASK0017409 | Closed | OPUS-PSO | Hieu Vu | 60 | 60 | 2019-12-23 11:27 | 2019-12-09 11:27 | Container | Vessel Operation | Port Service Order |  |  |  | PSO Canal Prepayment Fixes | 2020-01-02 15:04 | 2020-01-06 15:03 | 2020-01-03 16:44 |  | 2020-01-06 16:38 |  | 2020-01-14 12:00 | 2020-01-21 09:30 | 2020-01-08 12:02 | 2020-01-28 16:40 | CR0011937 | Vessel OperationPort Service Order | OPUS-PSO | 2020-W3 | 2020-01 | 60 | 60 | 11.8725 | 1 | 1 | 1 | 0.21 | 183375 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 10 | 0 | 0.125 | 2020-01 | 0 | 0
34 | CR0011000 | CTASK0014855 | Closed | OPUS-TPB | Manh Nguyen | 305 | 305 | 2020-04-30 13:43 | 2019-06-01 13:43 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [actual] TPB module enhancement | 2020-01-29 14:18 | 2020-02-01 | 2020-01-29 14:19 | 2020-03-26 07:40 | 2020-05-15 10:02 |  | 2020-05-26 09:59 | 2020-05-19 16:08 | 2020-05-15 14:11 | 2020-06-29 13:00 | CR0011000 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2020-W22 | 2020-05 | 321 | 0 | 117.8195 | 3 | 1 | 2 | 0 | 153138 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.25 | 2020-01 | 0 | 0
35 | CR0011000 | CTASK0018256 | Closed | OPUS-TPB | Thai Nguyen | 6 | 6 | 2020-03-31 10:46 | 2020-02-01 10:46 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [actual] TPB module enhancement | 2020-01-29 14:18 | 2020-02-01 | 2020-01-29 14:19 | 2020-03-26 07:40 | 2020-05-15 10:02 |  | 2020-05-26 09:59 | 2020-05-19 16:08 | 2020-05-15 14:11 | 2020-06-29 13:00 | CR0011000 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2020-W22 | 2020-05 | 321 | 0 | 117.8195 | 3 | 1 | 2 | 0 | 173249 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 2 | 2020-01 | 0 | 0
36 | CR0011000 | CTASK0013304 | Closed | OPUS-TPB | Manh Nguyen | 10 | 10 |  |  | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [actual]TPB module enhancement | 2020-01-29 14:18 | 2020-02-01 | 2020-01-29 14:19 | 2020-03-26 07:40 | 2020-05-15 10:02 |  | 2020-05-26 09:59 | 2020-05-19 16:08 | 2020-05-15 14:11 | 2020-06-29 13:00 | CR0011000 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2020-W22 | 2020-05 | 321 | 0 | 117.8195 | 3 | 1 | 2 | 0 | 153138 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.25 | 2020-01 | 0 | 0
37 | CR0012832 | CTASK0021443 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2020-08-31 13:49 | 2020-08-01 13:49 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] Constraint needs to show the contents even after some PRD related items are changed. | 2020-08-10 12:22 | 2020-08-27 | 2020-08-25 11:16 | 2020-09-01 20:36 | 2020-09-03 10:12 |  | 2020-09-29 10:00 | 2020-09-28 10:00 | 2020-09-03 13:40 | 2020-09-28 10:19 | CR0012832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W40 | 2020-09 | 41 | 37 | 49.9016 | 6 | 1 | 2 | 0.03 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.28571 | 2020-08 | 0 | 0
38 | CR0012832 | CTASK0021955 | Closed | OPUS-BKG-M | Loc Tran | 7 | 3 | 2020-08-31 18:24 | 2020-08-18 18:24 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] Constraint needs to show the contents even after some PRD related items are changed. | 2020-08-10 12:22 | 2020-08-27 | 2020-08-25 11:16 | 2020-09-01 20:36 | 2020-09-03 10:12 |  | 2020-09-29 10:00 | 2020-09-28 10:00 | 2020-09-03 13:40 | 2020-09-28 10:19 | CR0012832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W40 | 2020-09 | 41 | 37 | 49.9016 | 6 | 1 | 2 | 0.03 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.28571 | 2020-08 | 0 | 0
39 | CR0012832 | CTASK0021448 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2020-09-30 13:53 | 2020-09-01 13:53 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] Constraint needs to show the contents even after some PRD related items are changed. | 2020-08-10 12:22 | 2020-08-27 | 2020-08-25 11:16 | 2020-09-01 20:36 | 2020-09-03 10:12 |  | 2020-09-29 10:00 | 2020-09-28 10:00 | 2020-09-03 13:40 | 2020-09-28 10:19 | CR0012832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W40 | 2020-09 | 41 | 37 | 49.9016 | 6 | 1 | 2 | 0.03 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.28571 | 2020-08 | 0 | 0
40 | CR0012832 | CTASK0021283 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2020-07-31 13:48 | 2020-07-01 13:48 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] Constraint needs to show the contents even after some PRD related items are changed. | 2020-08-10 12:22 | 2020-08-27 | 2020-08-25 11:16 | 2020-09-01 20:36 | 2020-09-03 10:12 |  | 2020-09-29 10:00 | 2020-09-28 10:00 | 2020-09-03 13:40 | 2020-09-28 10:19 | CR0012832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W40 | 2020-09 | 41 | 37 | 49.9016 | 6 | 1 | 2 | 0.03 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.28571 | 2020-08 | 0 | 0
41 | CR0012832 | CTASK0021150 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-07-16 01:37 | 2020-07-09 10:37 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] Constraint needs to show the contents even after some PRD related items are changed. | 2020-08-10 12:22 | 2020-08-27 | 2020-08-25 11:16 | 2020-09-01 20:36 | 2020-09-03 10:12 |  | 2020-09-29 10:00 | 2020-09-28 10:00 | 2020-09-03 13:40 | 2020-09-28 10:19 | CR0012832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W40 | 2020-09 | 41 | 37 | 49.9016 | 6 | 1 | 2 | 0.03 | 153106 | 1.9 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.4 | 2020-08 | 0 | 0
42 | CR0012832 | CTASK0021446 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-08-31 13:52 | 2020-08-01 13:52 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] Constraint needs to show the contents even after some PRD related items are changed. | 2020-08-10 12:22 | 2020-08-27 | 2020-08-25 11:16 | 2020-09-01 20:36 | 2020-09-03 10:12 |  | 2020-09-29 10:00 | 2020-09-28 10:00 | 2020-09-03 13:40 | 2020-09-28 10:19 | CR0012832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W40 | 2020-09 | 41 | 37 | 49.9016 | 6 | 1 | 2 | 0.03 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.28571 | 2020-08 | 0 | 0
43 | CR0011521 | CTASK0015768 | Closed | OPUS-BKG-M | Nhan Le | 106 | 78 | 2019-07-19 15:49 | 2019-07-01 15:49 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [CLT Internal] CR0010257 - Extend pop up message to all tabs when multiple user access and updating concurrently in a booking. | 2019-08-01 18:57 | 2019-08-06 | 2019-08-01 18:58 | 2019-10-02 18:38 | 2019-10-02 18:39 | 2019-08-01 18:59 | 2019-10-15 18:39 | 2019-10-15 12:42 | 2019-10-02 18:39 | 2019-10-15 12:42 | CR0011521 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W42 | 2019-10 | 106 | 78 | 74.9872 | 1 | 1 | 1 | 0.04 | 183353 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-08 | 0 | 0
44 | CR0013584 | CTASK0025188 | Closed | OPUS-SCO | Nguyen Ha Vi | 8 | 8 | 2021-02-28 10:29 | 2021-02-04 10:29 | S/W | [5 empty] | [Vi Nguyen] Batch shell test | 2021-04-18 13:17 | 2021-04-26 13:17 | 2021-04-18 13:17 |  | 2021-04-18 13:18 |  | 2021-04-27 13:18 | 2021-04-27 15:50 | 2021-04-18 13:18 | 2021-04-29 15:50 | CR0013584 |  | OPUS-SCO | 2021-W17 | 2021-04 | 8 | 8 | 9.0004 | 1 | 1 | 1 | 0.04 | 203664 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0 | 1.2857 | 2021-04 | 0 | 0
45 | CR0011627 | CTASK0016637 | Closed | OPUS-SCO | Lien Le | 18 | 18 |  |  | Container | Statement Management | Statement Common | Setup | AP Cost Activity Information |  | Improve AP cost code activity UI | 2019-10-09 12:46 | 2019-12-31 12:46 | 2019-10-15 19:34 | 2019-10-16 10:14 | 2019-10-16 12:14 |  | 2019-10-22 12:13 | 2019-10-22 10:57 | 2019-10-16 12:18 | 2019-11-21 14:00 | CR0011627 | Statement ManagementStatement CommonSetupAP Cost Activity Information | OPUS-SCO | 2019-W43 | 2019-10 | 18 | 0 | 12.977 | 1 | 1 | 1 | 0 | 193441 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 10 | 0 | 0 | 2019-10 | 0 | 0
46 | CR0013513 | CTASK0025604 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-04-01 02:00 | 2021-03-18 15:13 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing]POP-UP Proposal to reduce the AMS penalties for late submission due to late VVD rolling | 2021-03-05 09:56 | 2021-04-03 02:00 | 2021-04-01 14:08 | 2021-05-25 13:49 | 2021-05-25 14:30 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-08 11:05 | 2021-07-15 14:00 | CR0013513 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W24 | 2021-06 | 70 | 70 | 102.0031 | 4 | 1 | 1 | 0.03 | 193488 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
47 | CR0013513 | CTASK0025605 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-06-10 02:00 | 2021-06-07 11:09 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment]POP-UP Proposal to reduce the AMS penalties for late submission due to late VVD rolling | 2021-03-05 09:56 | 2021-04-03 02:00 | 2021-04-01 14:08 | 2021-05-25 13:49 | 2021-05-25 14:30 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-08 11:05 | 2021-07-15 14:00 | CR0013513 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W24 | 2021-06 | 70 | 70 | 102.0031 | 4 | 1 | 1 | 0.03 | 193488 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
48 | CR0013513 | CTASK0025603 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 46 | 46 | 2021-03-20 02:00 | 2021-03-05 11:33 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development]POP-UP Proposal to reduce the AMS penalties for late submission due to late VVD rolling | 2021-03-05 09:56 | 2021-04-03 02:00 | 2021-04-01 14:08 | 2021-05-25 13:49 | 2021-05-25 14:30 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-08 11:05 | 2021-07-15 14:00 | CR0013513 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W24 | 2021-06 | 70 | 70 | 102.0031 | 4 | 1 | 1 | 0.03 | 193488 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
49 | CR0013513 | CTASK0025551 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 12 | 12 | 2021-03-02 11:24 | 2021-03-01 11:24 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design]POP-UP Proposal to reduce the AMS penalties for late submission due to late VVD rolling | 2021-03-05 09:56 | 2021-04-03 02:00 | 2021-04-01 14:08 | 2021-05-25 13:49 | 2021-05-25 14:30 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-08 11:05 | 2021-07-15 14:00 | CR0013513 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W24 | 2021-06 | 70 | 70 | 102.0031 | 4 | 1 | 1 | 0.03 | 193488 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
50 | CR0012233 | CTASK0018799 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 46 | 44 | 2020-04-30 18:00 | 2020-03-06 09:00 | Container | Service Management | Trans S/O |  |  |  | LA - EDI - Q SOLUTION (MX) - S/O REPORT (ECR0011415) | 2020-03-09 12:20 | 2020-04-17 18:00 | 2020-03-27 17:57 | 2020-05-06 20:31 | 2020-05-15 09:43 |  | 2020-05-26 11:00 | 2020-05-26 13:09 | 2020-05-18 20:55 | 2020-06-26 13:00 | CR0012233 | Service ManagementTrans S/O | OPUS-TRS | 2020-W22 | 2020-05 | 94 | 88 | 77.9447 | 2 | 1 | 2 | 0.05 | 183432 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0 | 2020-03 | 0 | 0
51 | CR0012233 | CTASK0018800 | Closed | OPUS-TRS | Giang Nguyen Hoang | 48 | 44 | 2020-04-30 18:00 | 2020-03-06 09:00 | Container | Service Management | Trans S/O |  |  |  | LA - EDI - Q SOLUTION (MX) - S/O REPORT (ECR0011415) | 2020-03-09 12:20 | 2020-04-17 18:00 | 2020-03-27 17:57 | 2020-05-06 20:31 | 2020-05-15 09:43 |  | 2020-05-26 11:00 | 2020-05-26 13:09 | 2020-05-18 20:55 | 2020-06-26 13:00 | CR0012233 | Service ManagementTrans S/O | OPUS-TRS | 2020-W22 | 2020-05 | 94 | 88 | 77.9447 | 2 | 1 | 2 | 0.05 | 183440 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0 | 2020-03 | 0 | 0
52 | CR0012593 | CTASK0020790 | Closed | OPUS-BKG-M | Loc Tran | 1 | 1 | 2020-06-26 19:03 | 2020-06-22 19:03 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Testing] DG Manifest Enhancement | 2020-06-05 13:19 | 2020-07-02 02:00 | 2020-06-24 13:39 | 2020-07-13 09:57 | 2020-07-13 14:02 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-20 14:34 | 2020-08-27 13:00 | CR0012593 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W31 | 2020-07 | 21 | 21 | 52.8617 | 5 | 1 | 1 | 0.02 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-06 | 0 | 0
53 | CR0012593 | CTASK0020493 | Closed | OPUS-BKG-M | Loc Tran | 5 | 5 | 2020-06-19 18:54 | 2020-06-05 18:54 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Testing] DG Manifest Enhancement | 2020-06-05 13:19 | 2020-07-02 02:00 | 2020-06-24 13:39 | 2020-07-13 09:57 | 2020-07-13 14:02 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-20 14:34 | 2020-08-27 13:00 | CR0012593 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W31 | 2020-07 | 21 | 21 | 52.8617 | 5 | 1 | 1 | 0.02 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-06 | 0 | 0
54 | CR0012593 | CTASK0020495 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2020-07-28 18:43 | 2020-07-21 18:43 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Deployment] DG Manifest Enhancement | 2020-06-05 13:19 | 2020-07-02 02:00 | 2020-06-24 13:39 | 2020-07-13 09:57 | 2020-07-13 14:02 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-20 14:34 | 2020-08-27 13:00 | CR0012593 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W31 | 2020-07 | 21 | 21 | 52.8617 | 5 | 1 | 1 | 0.02 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-06 | 0 | 0
55 | CR0012593 | CTASK0020488 | Closed | OPUS-BKG-M | Loc Tran | 5 | 5 | 2020-06-05 12:19 | 2020-06-01 12:19 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Design] DG Manifest Enhancement | 2020-06-05 13:19 | 2020-07-02 02:00 | 2020-06-24 13:39 | 2020-07-13 09:57 | 2020-07-13 14:02 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-20 14:34 | 2020-08-27 13:00 | CR0012593 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W31 | 2020-07 | 21 | 21 | 52.8617 | 5 | 1 | 1 | 0.02 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-06 | 0 | 0
56 | CR0012593 | CTASK0020489 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-06-13 02:00 | 2020-06-06 18:53 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Development] DG Manifest Enhancement | 2020-06-05 13:19 | 2020-07-02 02:00 | 2020-06-24 13:39 | 2020-07-13 09:57 | 2020-07-13 14:02 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-20 14:34 | 2020-08-27 13:00 | CR0012593 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W31 | 2020-07 | 21 | 21 | 52.8617 | 5 | 1 | 1 | 0.02 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-06 | 0 | 0
57 | CR0013178 | CTASK0027424 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 6 | 20 | 2021-06-30 19:59 | 2021-06-01 19:59 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare | DG Declare EDI Transmit | [PROD] EUA - enhance DG Declare EDI Transmit UI to allow manual input or copy - paste function | 2021-01-29 09:06 | 2021-02-11 | 2021-02-10 14:45 | 2021-05-20 11:59 | 2021-05-28 15:55 |  | 2021-06-08 10:00 | 2021-06-08 10:00 | 2021-05-28 16:06 | 2021-07-08 14:00 | CR0013178 | Service ManagementBooking/DocumentationOperationEU DG DeclareDG Declare EDI Transmit | OPUS-BKG-MFT-E | 2021-W23 | 2021-06 | 6 | 76 | 130.0375 | 2 | 1 | 2 | 0.02 | 193606 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 53 | 4.25 | 2.25 | 2021-01 | 0 | 0
58 | CR0013178 | CTASK0024861 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 56 | 56 | 2021-02-26 02:00 | 2021-02-01 02:00 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare | DG Declare EDI Transmit | [Dev-Test]EUA - enhance DG Declare EDI Transmit UI to allow manual input or copy - paste function | 2021-01-29 09:06 | 2021-02-11 | 2021-02-10 14:45 | 2021-05-20 11:59 | 2021-05-28 15:55 |  | 2021-06-08 10:00 | 2021-06-08 10:00 | 2021-05-28 16:06 | 2021-07-08 14:00 | CR0013178 | Service ManagementBooking/DocumentationOperationEU DG DeclareDG Declare EDI Transmit | OPUS-BKG-MFT-E | 2021-W23 | 2021-06 | 6 | 76 | 130.0375 | 2 | 1 | 2 | 0.02 | 193506 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 53 | 1.1212 | 1.25 | 2021-01 | 0 | 0
59 | CR0012608 | CTASK0021841 | Closed | OPUS-MNR | Tien Le | 44 | 44 | 2020-10-03 01:00 | 2020-09-01 10:00 | Container | Equipment Management | M.G. Set | Inventory | General Inventory |  | [CLT Internal] NA *MGS* General Inventory - Inconsistent Genset Data | 2020-11-03 15:36 | 2020-11-06 01:35 | 2020-11-05 18:58 | 2021-01-07 10:42 | 2021-01-13 13:59 |  | 2021-01-19 10:30 | 2021-01-19 11:01 | 2021-01-14 16:52 | 2021-02-19 14:00 | CR0012608 | Equipment ManagementM.G. SetInventoryGeneral Inventory | OPUS-MGS | 2021-W3 | 2021-01 | 83 | 146 | 76.7877 | 3 | 2 | 2 | 0.08 | 173286 | 2.1 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-11 | 0 | 0
60 | CR0012608 | CTASK0021840 | Closed | OPUS-MNR | Tuyen Truong | 52 | 62 | 2020-10-03 01:00 | 2020-09-01 10:00 | Container | Equipment Management | M.G. Set | Inventory | General Inventory |  | [CLT Internal] NA *MGS* General Inventory - Inconsistent Genset Data | 2020-11-03 15:36 | 2020-11-06 01:35 | 2020-11-05 18:58 | 2021-01-07 10:42 | 2021-01-13 13:59 |  | 2021-01-19 10:30 | 2021-01-19 11:01 | 2021-01-14 16:52 | 2021-02-19 14:00 | CR0012608 | Equipment ManagementM.G. SetInventoryGeneral Inventory | OPUS-MGS | 2021-W3 | 2021-01 | 83 | 146 | 76.7877 | 3 | 2 | 2 | 0.08 | 173255 | 2.1 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-11 | 0 | 0
61 | CR0012608 | CTASK0021839 | Closed | OPUS-MGS | Tuyen Truong | 31 | 40 | 2020-09-01 01:00 | 2020-08-14 11:00 | Container | Equipment Management | M.G. Set | Inventory | General Inventory |  | [Documentation][CLT Internal] NA *MGS* General Inventory - Inconsistent Genset Data | 2020-11-03 15:36 | 2020-11-06 01:35 | 2020-11-05 18:58 | 2021-01-07 10:42 | 2021-01-13 13:59 |  | 2021-01-19 10:30 | 2021-01-19 11:01 | 2021-01-14 16:52 | 2021-02-19 14:00 | CR0012608 | Equipment ManagementM.G. SetInventoryGeneral Inventory | OPUS-MGS | 2021-W3 | 2021-01 | 83 | 146 | 76.7877 | 3 | 2 | 2 | 0.08 | 173255 | 2.1 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-11 | 0 | 0
62 | CR0013378 | CTASK0024275 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 53 | 40 | 2021-03-10 02:00 | 2020-12-21 10:30 | Container | Service Management | Booking/Documentation | Booking | Booking | Container Information [Alt+4] | [BKG-OB] [CLT Internal] BKG-OB : Update cycle number in BKG | 2020-12-16 08:18 | 2021-01-15 08:13 | 2021-01-14 09:45 | 2021-02-15 17:13 | 2021-02-15 17:17 |  | 2021-02-23 17:17 | 2021-03-09 10:33 | 2021-02-25 09:51 | 2021-04-08 14:00 | CR0013378 | Service ManagementBooking/DocumentationBookingBookingContainer Information [Alt+4] | OPUS-BKG-OB | 2021-W8 | 2021-02 | 53 | 40 | 69.3742 | 1 | 1 | 1 | 0.02 | 193470 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 4 | 21 | 0.36842 | 0.17391 | 2020-12 | 0 | 0
63 | CR0011831 | CTASK0018567 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 10 | 10 | 2020-02-26 17:04 | 2020-02-24 17:04 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | TDEM (Toyota Daihatsu Engineering Manufacturing) Requirement : Customize email subject for SWB distribution | 2019-11-25 11:35 | 2019-12-23 11:35 | 2019-12-12 15:48 | 2020-02-28 02:10 | 2020-03-02 12:57 |  | 2020-03-10 12:00 | 2020-03-10 09:43 | 2020-03-02 15:25 | 2020-04-09 13:00 | CR0011831 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2020-W11 | 2020-03 | 14 | 14 | 106.0173 | 2 | 1 | 1 | 0.01 | 193512 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0.5 | 2019-11 | 0 | 0
64 | CR0011831 | CTASK0018742 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 4 | 4 |  | 2020-03-04 15:55 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [Deployment] TDEM (Toyota Daihatsu Engineering Manufacturing) Requirement : Customize email subject for SWB distribution | 2019-11-25 11:35 | 2019-12-23 11:35 | 2019-12-12 15:48 | 2020-02-28 02:10 | 2020-03-02 12:57 |  | 2020-03-10 12:00 | 2020-03-10 09:43 | 2020-03-02 15:25 | 2020-04-09 13:00 | CR0011831 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2020-W11 | 2020-03 | 14 | 14 | 106.0173 | 2 | 1 | 1 | 0.01 | 193512 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0.5 | 2019-11 | 0 | 0
65 | CR0012113 | CTASK0022184 | Closed | OPUS-JOO | Linh Nguyen | 30 | 30 | 2020-09-30 15:46 | 2020-08-20 15:45 | Container | Support & Admin | Joint Operation | Setup | Settlement Item List |  | [CLV] JOO module enhancement | 2020-02-03 13:18 | 2020-02-28 13:17 | 2020-02-26 15:52 | 2020-08-28 12:41 | 2020-09-11 08:04 |  | 2020-09-16 11:19 | 2020-09-15 10:48 | 2020-09-11 09:31 | 2020-10-15 13:00 | CR0012113 | Support & AdminJoint OperationSetupSettlement Item List | OPUS-JOO | 2020-W38 | 2020-09 | 30 | 30 | 225.9167 | 1 | 1 | 1 | 0.01 | 193464 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 9 | 36 | 0 | 0 | 2020-02 | 0 | 0
66 | CR0013112 | CTASK0026102 | Closed | OPUS-PRI | Nhien Nguyen | 50 | 80 | 2021-04-30 10:32 | 2021-04-01 10:32 | [6 empty] | NA *Tiger* T20 - 345 - Main UI_Estimate volume Indicator | 2021-03-26 11:14 | 2021-04-30 11:14 | 2021-03-26 13:03 | 2021-04-07 08:56 | 2021-04-07 09:12 |  | 2021-04-13 10:00 | 2021-04-13 10:23 | 2021-04-07 09:44 | 2021-05-13 14:00 | CR0013112 |  | OPUS-PRI | 2021-W15 | 2021-04 | 50 | 80 | 17.9486 | 1 | 1 | 1 | 0.19 | 183364 | 2.5 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 27 | 0 | 1.2 | 2021-03 | 0 | 0
67 | CR0012304 | CTASK0018603 | Closed | OPUS-BKG-M | Kieu Le | 3 | 3 | 2020-02-26 19:21 | 2020-02-25 02:20 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] [CLT Internal] Standby Booking Status Report OOME issue resolution | 2020-02-28 11:28 | 2020-04-02 | 2020-03-31 11:25 | 2020-03-31 11:52 | 2020-04-21 16:08 |  | 2020-04-28 10:00 | 2020-04-28 10:00 | 2020-04-21 16:08 | 2020-05-29 13:00 | CR0012304 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W18 | 2020-04 | 19 | 25 | 59.9389 | 4 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-02 | 0 | 0
68 | CR0012304 | CTASK0018625 | Closed | OPUS-BKG-M | Kieu Le | 7 | 12 | 2020-03-06 13:29 | 2020-03-02 13:29 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development][CLT Internal] Standby Booking Status Report OOME issue resolution | 2020-02-28 11:28 | 2020-04-02 | 2020-03-31 11:25 | 2020-03-31 11:52 | 2020-04-21 16:08 |  | 2020-04-28 10:00 | 2020-04-28 10:00 | 2020-04-21 16:08 | 2020-05-29 13:00 | CR0012304 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W18 | 2020-04 | 19 | 25 | 59.9389 | 4 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-02 | 0 | 0
69 | CR0012304 | CTASK0018629 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2020-04-29 01:51 | 2020-04-21 02:51 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment][CLT Internal] Standby Booking Status Report OOME issue resolution | 2020-02-28 11:28 | 2020-04-02 | 2020-03-31 11:25 | 2020-03-31 11:52 | 2020-04-21 16:08 |  | 2020-04-28 10:00 | 2020-04-28 10:00 | 2020-04-21 16:08 | 2020-05-29 13:00 | CR0012304 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W18 | 2020-04 | 19 | 25 | 59.9389 | 4 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-02 | 0 | 0
70 | CR0012304 | CTASK0018626 | Closed | OPUS-BKG-M | Kieu Le | 7 | 8 | 2020-03-13 13:30 | 2020-03-09 13:30 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing][CLT Internal] Standby Booking Status Report OOME issue resolution | 2020-02-28 11:28 | 2020-04-02 | 2020-03-31 11:25 | 2020-03-31 11:52 | 2020-04-21 16:08 |  | 2020-04-28 10:00 | 2020-04-28 10:00 | 2020-04-21 16:08 | 2020-05-29 13:00 | CR0012304 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W18 | 2020-04 | 19 | 25 | 59.9389 | 4 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-02 | 0 | 0
71 | CR0013326 | CTASK0023805 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-12-31 11:04 | 2020-12-01 11:04 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] Enhancement on VVD info update from PRD when 4 VVDs + WD which is led to 5 VVDs unexpectedly | 2020-12-28 09:30 | 2021-02-03 02:00 | 2021-01-28 10:51 | 2021-01-28 16:21 | 2021-01-28 17:02 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 09:07 | 2021-04-01 14:00 | CR0013326 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W9 | 2021-03 | 34 | 34 | 64.0206 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
72 | CR0013326 | CTASK0023809 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-02-26 11:08 | 2021-02-01 11:08 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] Enhancement on VVD info update from PRD when 4 VVDs + WD which is led to 5 VVDs unexpectedly | 2020-12-28 09:30 | 2021-02-03 02:00 | 2021-01-28 10:51 | 2021-01-28 16:21 | 2021-01-28 17:02 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 09:07 | 2021-04-01 14:00 | CR0013326 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W9 | 2021-03 | 34 | 34 | 64.0206 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
73 | CR0013326 | CTASK0023807 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-12-31 11:06 | 2020-12-01 11:06 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] Enhancement on VVD info update from PRD when 4 VVDs + WD which is led to 5 VVDs unexpectedly | 2020-12-28 09:30 | 2021-02-03 02:00 | 2021-01-28 10:51 | 2021-01-28 16:21 | 2021-01-28 17:02 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 09:07 | 2021-04-01 14:00 | CR0013326 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W9 | 2021-03 | 34 | 34 | 64.0206 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
74 | CR0013326 | CTASK0024164 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-01-29 19:33 | 2021-01-01 19:33 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] Enhancement on VVD info update from PRD when 4 VVDs + WD which is led to 5 VVDs unexpectedly | 2020-12-28 09:30 | 2021-02-03 02:00 | 2021-01-28 10:51 | 2021-01-28 16:21 | 2021-01-28 17:02 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 09:07 | 2021-04-01 14:00 | CR0013326 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W9 | 2021-03 | 34 | 34 | 64.0206 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
75 | CR0013326 | CTASK0023804 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2020-12-31 11:03 | 2020-12-01 11:03 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] Enhancement on VVD info update from PRD when 4 VVDs + WD which is led to 5 VVDs unexpectedly | 2020-12-28 09:30 | 2021-02-03 02:00 | 2021-01-28 10:51 | 2021-01-28 16:21 | 2021-01-28 17:02 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 09:07 | 2021-04-01 14:00 | CR0013326 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W9 | 2021-03 | 34 | 34 | 64.0206 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
76 | CR0012055 | CTASK0017505 | Closed | OPUS-MNR | Tien Le | 11 | 40 | 2019-12-30 11:44 | 2019-12-19 11:44 | Container | Equipment Management | M&R |  |  |  | GHQ - Remap MRDRPT account code | 2019-12-20 13:57 | 2019-12-30 15:19 | 2019-12-27 14:45 | 2020-01-05 14:49 | 2020-01-09 09:45 |  | 2020-01-22 09:45 | 2020-01-14 19:08 | 2020-01-09 13:26 | 2020-02-06 12:50 | CR0012055 | Equipment ManagementM&R | OPUS-MNR | 2020-W4 | 2020-01 | 11 | 40 | 32.825 | 1 | 1 | 1 | 0.05 | 173286 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 10 | 0 | 0 | 2019-12 | 0 | 0
77 | CR0013207 | CTASK0025052 | Closed | OPUS-TPB | Manh Nguyen | 27 | 27 | 2021-02-27 00:59 | 2021-02-01 01:00 | Container | Service Management | 3rd Party Billing |  |  |  | EUA- TPB Auto Interface(Feb) | 2021-02-23 14:05 | 2021-04-09 22:00 | 2021-04-09 11:27 | 2021-05-11 14:01 | 2021-05-12 14:09 |  | 2021-05-18 12:00 | 2021-05-18 10:16 | 2021-05-12 17:35 | 2021-06-17 14:00 | CR0013207 | Service Management3rd Party Billing | OPUS-TPB | 2021-W20 | 2021-05 | 56 | 64 | 83.9131 | 5 | 1 | 1 | 0.03 | 153138 | 2.4 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 0 | 0.16667 | 2021-02 | 0 | 0
78 | CR0013207 | CTASK0023819 | Closed | OPUS-TPB | Manh Nguyen | 10 | 10 | 2020-12-31 17:07 | 2020-12-01 17:07 | Container | Service Management | 3rd Party Billing |  |  |  | EUA- TPB Auto Interface | 2021-02-23 14:05 | 2021-04-09 22:00 | 2021-04-09 11:27 | 2021-05-11 14:01 | 2021-05-12 14:09 |  | 2021-05-18 12:00 | 2021-05-18 10:16 | 2021-05-12 17:35 | 2021-06-17 14:00 | CR0013207 | Service Management3rd Party Billing | OPUS-TPB | 2021-W20 | 2021-05 | 56 | 64 | 83.9131 | 5 | 1 | 1 | 0.03 | 153138 | 2.4 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 0 | 0.16667 | 2021-02 | 0 | 0
79 | CR0013207 | CTASK0026325 | Closed | OPUS-TPB | Manh Nguyen | 2 | 2 | 2021-05-01 01:00 | 2021-04-01 01:00 | Container | Service Management | 3rd Party Billing |  |  |  | [202104] EUA- TPB Auto Interface | 2021-02-23 14:05 | 2021-04-09 22:00 | 2021-04-09 11:27 | 2021-05-11 14:01 | 2021-05-12 14:09 |  | 2021-05-18 12:00 | 2021-05-18 10:16 | 2021-05-12 17:35 | 2021-06-17 14:00 | CR0013207 | Service Management3rd Party Billing | OPUS-TPB | 2021-W20 | 2021-05 | 56 | 64 | 83.9131 | 5 | 1 | 1 | 0.03 | 153138 | 2.4 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 0 | 0.16667 | 2021-02 | 0 | 0
80 | CR0013207 | CTASK0025627 | Closed | OPUS-TPB | Manh Nguyen | 10 | 15 | 2021-04-01 01:00 | 2021-03-01 01:00 | Container | Service Management | 3rd Party Billing |  |  |  | [202103] EUA- TPB Auto Interface | 2021-02-23 14:05 | 2021-04-09 22:00 | 2021-04-09 11:27 | 2021-05-11 14:01 | 2021-05-12 14:09 |  | 2021-05-18 12:00 | 2021-05-18 10:16 | 2021-05-12 17:35 | 2021-06-17 14:00 | CR0013207 | Service Management3rd Party Billing | OPUS-TPB | 2021-W20 | 2021-05 | 56 | 64 | 83.9131 | 5 | 1 | 1 | 0.03 | 153138 | 2.4 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 0 | 0.16667 | 2021-02 | 0 | 0
81 | CR0013207 | CTASK0026964 | Closed | OPUS-TPB | Manh Nguyen | 9 | 10 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | 3rd Party Billing |  |  |  | [202105] EUA- TPB Auto Interface | 2021-02-23 14:05 | 2021-04-09 22:00 | 2021-04-09 11:27 | 2021-05-11 14:01 | 2021-05-12 14:09 |  | 2021-05-18 12:00 | 2021-05-18 10:16 | 2021-05-12 17:35 | 2021-06-17 14:00 | CR0013207 | Service Management3rd Party Billing | OPUS-TPB | 2021-W20 | 2021-05 | 56 | 64 | 83.9131 | 5 | 1 | 1 | 0.03 | 153138 | 2.4 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 0 | 0.16667 | 2021-02 | 0 | 0
82 | CR0013001 | CTASK0023402 | Closed | OPUS-BKG-M | Kieu Le | 32 | 32 | 2020-12-31 13:04 | 2020-12-01 13:04 | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing] Automatic sending of BRN on Booking under GD1 (CONFIRM status) | 2020-11-11 08:38 | 2020-12-24 02:00 | 2020-12-22 12:14 | 2021-03-26 12:58 | 2021-04-12 16:40 |  | 2021-04-20 10:00 | 2021-04-20 10:00 | 2021-04-14 11:07 | 2021-05-21 14:00 | CR0013001 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W16 | 2021-04 | 154 | 163 | 160.0572 | 7 | 1 | 1 | 0.04 | 153106 | 2.1 | 1 | 0 | 1 | 2 | 1 | 3 | 5 | 27 | 0.22951 | 0.13043 | 2020-11 | 1 | 1
83 | CR0013001 | CTASK0026288 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-04-20 01:46 | 2021-04-07 02:46 | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing] Automatic sending of BRN on Booking under GD1 (CONFIRM status) | 2020-11-11 08:38 | 2020-12-24 02:00 | 2020-12-22 12:14 | 2021-03-26 12:58 | 2021-04-12 16:40 |  | 2021-04-20 10:00 | 2021-04-20 10:00 | 2021-04-14 11:07 | 2021-05-21 14:00 | CR0013001 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W16 | 2021-04 | 154 | 163 | 160.0572 | 7 | 1 | 1 | 0.04 | 153106 | 2.1 | 1 | 0 | 1 | 2 | 1 | 3 | 5 | 27 | 0.22951 | 0.13043 | 2020-11 | 1 | 1
84 | CR0013001 | CTASK0023399 | Closed | OPUS-BKG-M | Kieu Le | 65 | 74 | 2020-11-30 13:01 | 2020-11-09 02:01 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development] Automatic sending of BRN on Booking under GD1 (CONFIRM status) | 2020-11-11 08:38 | 2020-12-24 02:00 | 2020-12-22 12:14 | 2021-03-26 12:58 | 2021-04-12 16:40 |  | 2021-04-20 10:00 | 2021-04-20 10:00 | 2021-04-14 11:07 | 2021-05-21 14:00 | CR0013001 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W16 | 2021-04 | 154 | 163 | 160.0572 | 7 | 1 | 1 | 0.04 | 153106 | 2.1 | 1 | 0 | 1 | 2 | 1 | 3 | 5 | 27 | 0.22951 | 0.13043 | 2020-11 | 1 | 1
85 | CR0013001 | CTASK0023305 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2020-11-06 15:24 | 2020-11-02 02:24 | Container | Service Management | Booking/Documentation | Booking |  |  | [Design] Automatic sending of BRN on Booking under GD1 (CONFIRM status) | 2020-11-11 08:38 | 2020-12-24 02:00 | 2020-12-22 12:14 | 2021-03-26 12:58 | 2021-04-12 16:40 |  | 2021-04-20 10:00 | 2021-04-20 10:00 | 2021-04-14 11:07 | 2021-05-21 14:00 | CR0013001 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W16 | 2021-04 | 154 | 163 | 160.0572 | 7 | 1 | 1 | 0.04 | 153106 | 2.1 | 1 | 0 | 1 | 2 | 1 | 3 | 5 | 27 | 0.22951 | 0.13043 | 2020-11 | 1 | 1
86 | CR0013001 | CTASK0023405 | Closed | OPUS-BKG-M | Kieu Le | 14 | 14 | 2021-05-01 01:06 | 2021-04-12 02:06 | Container | Service Management | Booking/Documentation | Booking |  |  | [Deployment] Automatic sending of BRN on Booking under GD1 (CONFIRM status) | 2020-11-11 08:38 | 2020-12-24 02:00 | 2020-12-22 12:14 | 2021-03-26 12:58 | 2021-04-12 16:40 |  | 2021-04-20 10:00 | 2021-04-20 10:00 | 2021-04-14 11:07 | 2021-05-21 14:00 | CR0013001 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W16 | 2021-04 | 154 | 163 | 160.0572 | 7 | 1 | 1 | 0.04 | 153106 | 2.1 | 1 | 0 | 1 | 2 | 1 | 3 | 5 | 27 | 0.22951 | 0.13043 | 2020-11 | 1 | 1
87 | CR0013001 | CTASK0026287 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-04-10 01:43 | 2021-04-06 13:43 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development] Automatic sending of BRN on Booking under GD1 (CONFIRM status) | 2020-11-11 08:38 | 2020-12-24 02:00 | 2020-12-22 12:14 | 2021-03-26 12:58 | 2021-04-12 16:40 |  | 2021-04-20 10:00 | 2021-04-20 10:00 | 2021-04-14 11:07 | 2021-05-21 14:00 | CR0013001 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W16 | 2021-04 | 154 | 163 | 160.0572 | 7 | 1 | 1 | 0.04 | 153106 | 2.1 | 1 | 0 | 1 | 2 | 1 | 3 | 5 | 27 | 0.22951 | 0.13043 | 2020-11 | 1 | 1
88 | CR0013001 | CTASK0026286 | Closed | OPUS-BKG-M | Kieu Le | 3 | 3 | 2021-04-07 01:41 | 2021-04-06 02:41 | Container | Service Management | Booking/Documentation | Booking |  |  | [Design] Automatic sending of BRN on Booking under GD1 (CONFIRM status) | 2020-11-11 08:38 | 2020-12-24 02:00 | 2020-12-22 12:14 | 2021-03-26 12:58 | 2021-04-12 16:40 |  | 2021-04-20 10:00 | 2021-04-20 10:00 | 2021-04-14 11:07 | 2021-05-21 14:00 | CR0013001 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W16 | 2021-04 | 154 | 163 | 160.0572 | 7 | 1 | 1 | 0.04 | 153106 | 2.1 | 1 | 0 | 1 | 2 | 1 | 3 | 5 | 27 | 0.22951 | 0.13043 | 2020-11 | 1 | 1
89 | CR0011917 | CTASK0017385 | Closed | OPUS-PSO | Hieu Vu | 150 | 150 |  |  | Container | Vessel Operation | Port Service Order |  |  |  | GHQ - PSO Accrual Logic Correction | 2020-01-08 09:10 | 2020-02-14 17:00 | 2020-02-14 13:27 | 2020-03-16 10:27 | 2020-03-19 14:16 |  | 2020-03-17 16:16 | 2020-02-14 13:14 | 2020-03-24 12:44 | 2020-04-08 16:49 | CR0011917 | Vessel OperationPort Service Order | OPUS-PSO | 2020-W12 | 2020-03 | 150 | 150 | 69.2957 | 1 | 1 | 1 | 0.09 | 183375 | 1.3 | 0 | 0 | 0 | 2 | 1 | 2 | 5 | 25 | 0 | 0.125 | 2020-01 | 0 | 0
90 | CR0013159 | CTASK0023168 | Closed | OPUS-BKG-M | Vinh Tran | 16 | 16 | 2020-11-13 02:00 | 2020-11-02 02:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Trans. Request Order(I/B-Europe) |  | [Testing] EUA - CR0012144 : TRO Notice to be Bound EXCLUSIVE & TRO/I to Not show O/B TRO details | 2020-10-26 17:40 | 2020-11-12 | 2020-11-10 20:14 | 2020-11-16 11:23 | 2020-11-16 15:12 |  | 2020-12-01 10:00 | 2020-12-01 09:41 | 2020-11-17 09:24 | 2021-01-01 14:00 | CR0013159 | Service ManagementBooking/DocumentationInbound DocTrans. Request Order(I/B-Europe) | OPUS-BKG-M | 2020-W49 | 2020-12 | 29 | 33 | 35.6806 | 4 | 1 | 1 | 0.04 | 193525 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 10 | 30 | 0 | 0.47368 | 2020-10 | 0 | 0
91 | CR0013159 | CTASK0023166 | Closed | OPUS-BKG-M | Vinh Tran | 1 | 1 | 2020-10-24 02:00 | 2020-10-23 02:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Trans. Request Order(I/B-Europe) |  | [Design] EUA - CR0012144 : TRO Notice to be Bound EXCLUSIVE & TRO/I to Not show O/B TRO details | 2020-10-26 17:40 | 2020-11-12 | 2020-11-10 20:14 | 2020-11-16 11:23 | 2020-11-16 15:12 |  | 2020-12-01 10:00 | 2020-12-01 09:41 | 2020-11-17 09:24 | 2021-01-01 14:00 | CR0013159 | Service ManagementBooking/DocumentationInbound DocTrans. Request Order(I/B-Europe) | OPUS-BKG-M | 2020-W49 | 2020-12 | 29 | 33 | 35.6806 | 4 | 1 | 1 | 0.04 | 193525 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 10 | 30 | 0 | 0.47368 | 2020-10 | 0 | 0
92 | CR0013159 | CTASK0023167 | Closed | OPUS-BKG-M | Vinh Tran | 12 | 12 | 2020-10-31 02:00 | 2020-10-26 02:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Trans. Request Order(I/B-Europe) |  | [Development] EUA - CR0012144 : TRO Notice to be Bound EXCLUSIVE & TRO/I to Not show O/B TRO details | 2020-10-26 17:40 | 2020-11-12 | 2020-11-10 20:14 | 2020-11-16 11:23 | 2020-11-16 15:12 |  | 2020-12-01 10:00 | 2020-12-01 09:41 | 2020-11-17 09:24 | 2021-01-01 14:00 | CR0013159 | Service ManagementBooking/DocumentationInbound DocTrans. Request Order(I/B-Europe) | OPUS-BKG-M | 2020-W49 | 2020-12 | 29 | 33 | 35.6806 | 4 | 1 | 1 | 0.04 | 193525 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 10 | 30 | 0 | 0.47368 | 2020-10 | 0 | 0
93 | CR0013159 | CTASK0023169 | Closed | OPUS-BKG-M | Vinh Tran | 4 | 4 | 2020-12-01 02:00 | 2020-11-09 02:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Trans. Request Order(I/B-Europe) |  | [Deployment] EUA - CR0012144 : TRO Notice to be Bound EXCLUSIVE & TRO/I to Not show O/B TRO details | 2020-10-26 17:40 | 2020-11-12 | 2020-11-10 20:14 | 2020-11-16 11:23 | 2020-11-16 15:12 |  | 2020-12-01 10:00 | 2020-12-01 09:41 | 2020-11-17 09:24 | 2021-01-01 14:00 | CR0013159 | Service ManagementBooking/DocumentationInbound DocTrans. Request Order(I/B-Europe) | OPUS-BKG-M | 2020-W49 | 2020-12 | 29 | 33 | 35.6806 | 4 | 1 | 1 | 0.04 | 193525 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 10 | 30 | 0 | 0.47368 | 2020-10 | 0 | 0
94 | CR0013544 | CTASK0024934 | Closed | OPUS-SCG | Lanh Le | 4 | 6 | 2021-02-04 17:28 | 2021-02-02 17:27 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Approved Details |  | [CLV][CLT Internal] Adding PG in the DG Booking List for Stowage Instruction Inbox | 2021-02-02 15:45 | 2021-02-22 19:30 | 2021-02-08 18:02 | 2021-03-05 12:56 | 2021-03-05 13:39 |  | 2021-03-16 09:30 | 2021-03-16 13:12 | 2021-03-11 17:45 | 2021-04-15 14:00 | CR0013544 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Approved Details | OPUS-SCG | 2021-W11 | 2021-03 | 9 | 14 | 41.7395 | 2 | 1 | 1 | 0.01 | 183422 | 2.2 | 1 | 0 | 0 | 1 | 1 | 1 | 9 | 46 | 0 | 0 | 2021-02 | 0 | 0
95 | CR0013544 | CTASK0024933 | Closed | OPUS-SCG | Lanh Le | 5 | 8 | 2021-02-05 17:26 | 2021-02-01 17:25 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Approved Details |  | [Documentation][CLT Internal] Adding PG in the DG Booking List for Stowage Instruction Inbox | 2021-02-02 15:45 | 2021-02-22 19:30 | 2021-02-08 18:02 | 2021-03-05 12:56 | 2021-03-05 13:39 |  | 2021-03-16 09:30 | 2021-03-16 13:12 | 2021-03-11 17:45 | 2021-04-15 14:00 | CR0013544 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Approved Details | OPUS-SCG | 2021-W11 | 2021-03 | 9 | 14 | 41.7395 | 2 | 1 | 1 | 0.01 | 183422 | 2.2 | 1 | 0 | 0 | 1 | 1 | 1 | 9 | 46 | 0 | 0 | 2021-02 | 0 | 0
96 | CR0012467 | CTASK0019911 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 26 | 26 | 2020-05-29 11:07 | 2020-05-06 11:06 | Container | Service Management | Domestic | Transportation | Rail Billing Maintenance |  | NA *EDI* Customer - Domestic : Introduction of Railbill Acceptance Status in Subject Email for 824 EDI Response | 2020-05-07 13:31 | 2020-06-26 18:00 | 2020-06-25 09:26 | 2020-07-08 22:14 | 2020-07-09 09:51 |  | 2020-07-14 11:00 | 2020-07-14 11:00 | 2020-07-09 14:48 | 2020-07-14 16:26 | CR0012467 | Service ManagementDomesticTransportationRail Billing Maintenance | OPUS-DOM | 2020-W29 | 2020-07 | 52 | 52 | 67.8953 | 2 | 1 | 2 | 0.03 | 183432 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0 | 2020-05 | 0 | 0
97 | CR0012467 | CTASK0019912 | Closed | OPUS-DOM | Giang Nguyen Hoang | 26 | 26 | 2020-05-29 11:07 | 2020-05-06 11:07 | Container | Service Management | Domestic | Transportation | Rail Billing Maintenance |  | NA *EDI* Customer - Domestic : Introduction of Railbill Acceptance Status in Subject Email for 824 EDI Response | 2020-05-07 13:31 | 2020-06-26 18:00 | 2020-06-25 09:26 | 2020-07-08 22:14 | 2020-07-09 09:51 |  | 2020-07-14 11:00 | 2020-07-14 11:00 | 2020-07-09 14:48 | 2020-07-14 16:26 | CR0012467 | Service ManagementDomesticTransportationRail Billing Maintenance | OPUS-DOM | 2020-W29 | 2020-07 | 52 | 52 | 67.8953 | 2 | 1 | 2 | 0.03 | 183440 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0 | 2020-05 | 0 | 0
98 | CR0012402 | CTASK0020671 | Closed | OPUS-PRI | Ngan Nham | 128 | 120 | 2020-07-31 11:30 | 2020-06-01 11:30 | Container | Sales Management | Pricing |  |  |  | GHQ -PRI - validation & warning message for SC/ RFA rate deletions which will impact revenue audit | 2020-05-25 13:14 | 2020-07-31 13:14 | 2020-07-31 12:52 | 2021-04-08 09:58 | 2021-04-13 15:23 |  | 2021-04-20 15:22 | 2021-04-20 13:48 | 2021-04-13 18:14 | 2021-05-20 14:00 | CR0012402 | Sales ManagementPricing | OPUS-PRI | 2021-W16 | 2021-04 | 128 | 120 | 330.089 | 1 | 1 | 1 | 0.02 | 193461 | 1.5 | 0 | 0 | 0 | 2 | 1 | 4 | 5 | 27 | 0 | 0.28571 | 2020-05 | 0 | 0
99 | CR0012899 | CTASK0021586 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2020-07-30 01:00 | 2020-07-29 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [CLT Internal] Expdoc RPA BL Release - VVD discrepancy between batch report & OPUS | 2020-08-21 14:17 | 2020-08-27 | 2020-08-25 13:27 | 2020-09-17 10:12 | 2020-09-17 10:31 |  | 2020-09-29 10:00 | 2020-09-28 10:00 | 2020-09-17 13:09 | 2020-10-28 13:00 | CR0012899 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W40 | 2020-09 | 16 | 16 | 38.8217 | 3 | 1 | 1 | 0.02 | 193470 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.17391 | 2020-08 | 0 | 0
100 | CR0012899 | CTASK0022621 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2020-09-23 01:59 | 2020-09-22 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Deployment] [CLT Internal] Expdoc RPA BL Release - VVD discrepancy between batch report & OPUS | 2020-08-21 14:17 | 2020-08-27 | 2020-08-25 13:27 | 2020-09-17 10:12 | 2020-09-17 10:31 |  | 2020-09-29 10:00 | 2020-09-28 10:00 | 2020-09-17 13:09 | 2020-10-28 13:00 | CR0012899 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W40 | 2020-09 | 16 | 16 | 38.8217 | 3 | 1 | 1 | 0.02 | 193470 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.17391 | 2020-08 | 0 | 0
101 | CR0012899 | CTASK0022004 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 | 2020-08-25 02:00 | 2020-08-21 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [CLT Internal] Expdoc RPA BL Release - VVD discrepancy between batch report & OPUS | 2020-08-21 14:17 | 2020-08-27 | 2020-08-25 13:27 | 2020-09-17 10:12 | 2020-09-17 10:31 |  | 2020-09-29 10:00 | 2020-09-28 10:00 | 2020-09-17 13:09 | 2020-10-28 13:00 | CR0012899 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W40 | 2020-09 | 16 | 16 | 38.8217 | 3 | 1 | 1 | 0.02 | 193470 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.17391 | 2020-08 | 0 | 0
102 | CR0012825 | CTASK0021085 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 7 | 10 | 2020-07-24 18:33 | 2020-07-07 09:33 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Analysis][CLT Internal] Bug fix related to CLP version up | 2020-07-15 09:28 | 2020-07-31 23:27 | 2020-07-30 14:18 | 2020-08-03 16:35 | 2020-08-10 13:06 |  | 2020-09-01 13:05 | 2020-09-01 11:09 | 2020-08-26 11:52 | 2020-10-21 13:00 | CR0012825 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2020-W36 | 2020-09 | 13 | 17 | 48.1508 | 2 | 1 | 1 | 0.01 | 193512 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.3125 | 2020-07 | 0 | 0
103 | CR0012825 | CTASK0021242 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 6 | 7 | 2020-07-31 15:14 | 2020-07-15 09:14 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Development+ Testing+ Deployment][CLT Internal] Bug fix related to CLP version up | 2020-07-15 09:28 | 2020-07-31 23:27 | 2020-07-30 14:18 | 2020-08-03 16:35 | 2020-08-10 13:06 |  | 2020-09-01 13:05 | 2020-09-01 11:09 | 2020-08-26 11:52 | 2020-10-21 13:00 | CR0012825 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2020-W36 | 2020-09 | 13 | 17 | 48.1508 | 2 | 1 | 1 | 0.01 | 193512 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.3125 | 2020-07 | 0 | 0
104 | CR0012716 | CTASK0021011 | Closed | OPUS-SCO | Dinh Cong Tuan | 8 | 8 | 2020-07-31 10:55 | 2020-07-03 10:55 | Container | Statement Management | Statement Account Receivable | Monitoring EUA |  |  | [Tuan Dinh][EUA - Monitoring EUA Improvements - add customer name [CR5]] | 2020-08-20 16:51 | 2020-09-30 16:50 | 2020-08-28 09:05 | 2020-12-03 08:03 | 2020-12-05 02:07 |  | 2020-12-08 10:00 | 2020-12-28 10:00 | 2020-12-07 09:28 | 2021-01-19 20:48 | CR0012716 | Statement ManagementStatement Account ReceivableMonitoring EUA | OPUS-SCO | 2020-W50 | 2020-12 | 32 | 32 | 109.7147 | 4 | 1 | 4 | 0.01 | 193510 | 1.2 | 1 | 2 | 0 | 1 | 2 | 2 | 3 | 30 | 0 | 0 | 2020-08 | 2 | 1
105 | CR0012716 | CTASK0021008 | Closed | OPUS-SCO | Chuong Ta | 8 | 8 | 2020-07-31 10:51 | 2020-07-03 10:51 | Container | Statement Management | Statement Account Receivable | Monitoring EUA |  |  | [Chuong Ta][EUA - Monitoring EUA Improvements - add customer name [CR5]] | 2020-08-20 16:51 | 2020-09-30 16:50 | 2020-08-28 09:05 | 2020-12-03 08:03 | 2020-12-05 02:07 |  | 2020-12-08 10:00 | 2020-12-28 10:00 | 2020-12-07 09:28 | 2021-01-19 20:48 | CR0012716 | Statement ManagementStatement Account ReceivableMonitoring EUA | OPUS-SCO | 2020-W50 | 2020-12 | 32 | 32 | 109.7147 | 4 | 1 | 4 | 0.01 | 183379 | 1.4 | 1 | 2 | 0 | 1 | 2 | 2 | 3 | 30 | 0 | 0.38462 | 2020-08 | 2 | 1
106 | CR0012716 | CTASK0021010 | Closed | OPUS-SCO | Mohamed Hary | 8 | 8 | 2020-07-31 10:53 | 2020-07-03 10:53 | Container | Statement Management | Statement Account Receivable | Monitoring EUA |  |  | [Mohamed Hary][EUA - Monitoring EUA Improvements - add customer name [CR5]] | 2020-08-20 16:51 | 2020-09-30 16:50 | 2020-08-28 09:05 | 2020-12-03 08:03 | 2020-12-05 02:07 |  | 2020-12-08 10:00 | 2020-12-28 10:00 | 2020-12-07 09:28 | 2021-01-19 20:48 | CR0012716 | Statement ManagementStatement Account ReceivableMonitoring EUA | OPUS-SCO | 2020-W50 | 2020-12 | 32 | 32 | 109.7147 | 4 | 1 | 4 | 0.01 | 193489 | 1.2 | 1 | 2 | 0 | 1 | 2 | 2 | 3 | 30 | 0 | 0.63636 | 2020-08 | 2 | 1
107 | CR0012716 | CTASK0021009 | Closed | OPUS-SCO | Cuong Tran Hung | 8 | 8 | 2020-07-31 10:52 | 2020-07-03 10:52 | Container | Statement Management | Statement Account Receivable | Monitoring EUA |  |  | [Cuong Tran][EUA - Monitoring EUA Improvements - add customer name [CR5]] | 2020-08-20 16:51 | 2020-09-30 16:50 | 2020-08-28 09:05 | 2020-12-03 08:03 | 2020-12-05 02:07 |  | 2020-12-08 10:00 | 2020-12-28 10:00 | 2020-12-07 09:28 | 2021-01-19 20:48 | CR0012716 | Statement ManagementStatement Account ReceivableMonitoring EUA | OPUS-SCO | 2020-W50 | 2020-12 | 32 | 32 | 109.7147 | 4 | 1 | 4 | 0.01 | 193530 | 1.2 | 1 | 2 | 0 | 1 | 2 | 2 | 3 | 30 | 0 | 1.2222 | 2020-08 | 2 | 1
108 | CR0012123 | CTASK0021548 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 6 | 6 | 2020-07-31 18:36 | 2020-07-28 18:36 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EU Full Cntr Release / MT Return (Child CR to SR0066264 ) | 2020-04-13 11:27 | 2020-06-30 20:17 | 2020-06-30 13:29 | 2020-08-04 16:18 | 2020-09-22 14:09 |  | 2020-10-13 14:09 | 2020-10-13 10:14 | 2020-09-22 18:18 | 2020-11-12 14:00 | CR0012123 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2020-W42 | 2020-10 | 133 | 133 | 183.1119 | 5 | 1 | 1 | 0.03 | 193512 | 0.8 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 20 | 0 | 0.5 | 2020-04 | 0 | 0
109 | CR0012123 | CTASK0019598 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 77 | 77 | 2020-05-04 18:30 | 2020-04-14 10:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EU Full Cntr Release / MT Return (Child CR to SR0066264 ) | 2020-04-13 11:27 | 2020-06-30 20:17 | 2020-06-30 13:29 | 2020-08-04 16:18 | 2020-09-22 14:09 |  | 2020-10-13 14:09 | 2020-10-13 10:14 | 2020-09-22 18:18 | 2020-11-12 14:00 | CR0012123 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2020-W42 | 2020-10 | 133 | 133 | 183.1119 | 5 | 1 | 1 | 0.03 | 193512 | 0.8 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 20 | 0 | 0.5 | 2020-04 | 0 | 0
110 | CR0012123 | CTASK0020201 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 16 | 16 | 2020-05-30 11:34 | 2020-05-19 11:34 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Test] EU Full Cntr Release / MT Return (Child CR to SR0066264 ) | 2020-04-13 11:27 | 2020-06-30 20:17 | 2020-06-30 13:29 | 2020-08-04 16:18 | 2020-09-22 14:09 |  | 2020-10-13 14:09 | 2020-10-13 10:14 | 2020-09-22 18:18 | 2020-11-12 14:00 | CR0012123 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2020-W42 | 2020-10 | 133 | 133 | 183.1119 | 5 | 1 | 1 | 0.03 | 193512 | 0.8 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 20 | 0 | 0.5 | 2020-04 | 0 | 0
111 | CR0012123 | CTASK0021737 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 29 | 29 | 2020-08-28 18:11 | 2020-08-06 18:11 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EU Full Cntr Release / MT Return (Child CR to SR0066264 ) | 2020-04-13 11:27 | 2020-06-30 20:17 | 2020-06-30 13:29 | 2020-08-04 16:18 | 2020-09-22 14:09 |  | 2020-10-13 14:09 | 2020-10-13 10:14 | 2020-09-22 18:18 | 2020-11-12 14:00 | CR0012123 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2020-W42 | 2020-10 | 133 | 133 | 183.1119 | 5 | 1 | 1 | 0.03 | 193512 | 0.8 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 20 | 0 | 0.5 | 2020-04 | 0 | 0
112 | CR0012123 | CTASK0019461 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 5 | 5 | 2020-04-09 18:12 | 2020-04-08 18:12 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Analyze] EU Full Cntr Release / MT Return (Child CR to SR0066264 ) | 2020-04-13 11:27 | 2020-06-30 20:17 | 2020-06-30 13:29 | 2020-08-04 16:18 | 2020-09-22 14:09 |  | 2020-10-13 14:09 | 2020-10-13 10:14 | 2020-09-22 18:18 | 2020-11-12 14:00 | CR0012123 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2020-W42 | 2020-10 | 133 | 133 | 183.1119 | 5 | 1 | 1 | 0.03 | 193512 | 0.8 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 20 | 0 | 0.5 | 2020-04 | 0 | 0
113 | CR0011141 | CTASK0019447 | Closed | OPUS-PRI | Nhien Nguyen | 101 | 100 | 2020-05-22 19:29 | 2020-04-13 19:28 | Container | Sales Management | Pricing | RFA | Proposal & Amendment | RFA Proposal & Amendment Creation | EAS - PRI - Multiple Enhancement on RFA Maintenance and inquiry to improve Rating quality | 2020-04-06 17:25 | 2020-05-08 22:00 | 2020-05-08 16:38 | 2020-12-08 01:21 | 2020-12-09 11:08 |  | 2020-12-15 11:08 | 2021-01-05 11:27 | 2020-12-10 15:01 | 2021-02-04 14:00 | CR0011141 | Sales ManagementPricingRFAProposal & AmendmentRFA Proposal & Amendment Creation | OPUS-PRI | 2020-W51 | 2020-12 | 101 | 100 | 252.7382 | 1 | 1 | 1 | 0.02 | 183364 | 1.5 | 0 | 0 | 0 | 1 | 1 | 3 | 4 | 30 | 0 | 0 | 2020-04 | 0 | 0
114 | CR0011925 | CTASK0017066 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [CLT Internal] AS - OPUS CONTAINER - MULTIPLE SEARCH FUNCTION BUG | 2020-01-08 12:59 | 2020-02-04 | 2020-01-08 12:59 | 2020-01-08 14:20 | 2020-01-13 17:51 |  | 2020-02-04 17:51 | 2020-02-04 12:41 | 2020-01-30 12:38 | 2020-02-04 12:42 | CR0011925 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2020-W6 | 2020-02 | 0 | 0 | 27.2027 | 1 | 1 | 1 | 0 | 153106 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 13 | 0 | 0.4 | 2020-01 | 0 | 0
115 | CR0014256 | CTASK0028346 | Implemented | OPUS-SAR | Lien Le | 13 | 12 | 2021-07-31 22:35 | 2021-07-23 22:35 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection OTS History |  | [July 2021][Lien Le][CLT Internal] To prevent OOME issue on "Collection OTS History" function only for NA region | 2021-07-26 09:51 | 2021-08-13 18:00 | 2021-07-30 14:28 | 2021-08-10 10:23 | 2021-08-10 10:25 |  | 2021-08-12 10:00 | 2021-08-12 10:00 | 2021-08-10 14:31 |  | CR0014256 | Statement ManagementStatement Account ReceivableCollection ManagerCollection OTS History | OPUS-SAR | 2021-W32 | 2021-08 | 40 | 37 | 17.0065 | 3 | 2 | 3 | 0.09 | 193441 | 2.4 | 2 | 2 | 0 | 1 | 1 | 1 | 10 | 22 | 0.42308 | 0 | 2021-07 | 2 | 1
116 | CR0014256 | CTASK0028344 | Implemented | OPUS-SCO | Nguyen Ha Vi | 13 | 12 | 2021-07-31 22:34 | 2021-07-23 22:34 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection OTS History |  | [July 2021][Vi Nguyen][CLT Internal] To prevent OOME issue on "Collection OTS History" function only for NA region | 2021-07-26 09:51 | 2021-08-13 18:00 | 2021-07-30 14:28 | 2021-08-10 10:23 | 2021-08-10 10:25 |  | 2021-08-12 10:00 | 2021-08-12 10:00 | 2021-08-10 14:31 |  | CR0014256 | Statement ManagementStatement Account ReceivableCollection ManagerCollection OTS History | OPUS-SCO | 2021-W32 | 2021-08 | 40 | 37 | 17.0065 | 3 | 2 | 3 | 0.09 | 203664 | 1.1 | 2 | 2 | 0 | 1 | 1 | 1 | 10 | 22 | 1.8182 | 2.5 | 2021-07 | 2 | 1
117 | CR0014256 | CTASK0028345 | Implemented | OPUS-SCO | Chuong Ta | 14 | 13 | 2021-07-31 22:34 | 2021-07-23 22:34 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection OTS History |  | [July 2021][Chuong Ta][CLT Internal] To prevent OOME issue on "Collection OTS History" function only for NA region | 2021-07-26 09:51 | 2021-08-13 18:00 | 2021-07-30 14:28 | 2021-08-10 10:23 | 2021-08-10 10:25 |  | 2021-08-12 10:00 | 2021-08-12 10:00 | 2021-08-10 14:31 |  | CR0014256 | Statement ManagementStatement Account ReceivableCollection ManagerCollection OTS History | OPUS-SCO | 2021-W32 | 2021-08 | 40 | 37 | 17.0065 | 3 | 2 | 3 | 0.09 | 183379 | 2.4 | 2 | 2 | 0 | 1 | 1 | 1 | 10 | 22 | 0.32 | 0.375 | 2021-07 | 2 | 1
118 | CR0012580 | CTASK0019948 | Closed | OPUS-PRI | Man Hoang | 44 | 44 | 2020-05-08 12:18 | 2020-05-04 12:18 | Container | Sales Management | Pricing |  |  |  | [Development][CLT Internal] Changing amend logic as Backend job | 2020-05-06 16:27 | 2020-05-15 16:26 | 2020-05-13 16:20 | 2020-05-13 16:35 | 2020-05-13 17:33 |  | 2020-05-19 17:33 | 2020-06-02 16:07 | 2020-05-29 09:58 | 2020-08-23 13:00 | CR0012580 | Sales ManagementPricing | OPUS-PRI | 2020-W21 | 2020-05 | 44 | 44 | 13.0459 | 1 | 1 | 1 | 0.14 | 183431 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 26 | 0 | 0.66667 | 2020-05 | 0 | 0
119 | CR0014069 | CTASK0027939 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-07-16 19:45 | 2021-07-12 10:45 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development] Global*EDI* Booking confirmation New F/F items (S/I Flag & VGM Indicator) | 2021-07-12 09:24 | 2021-07-27 | 2021-07-23 09:45 | 2021-07-26 14:44 | 2021-07-26 15:24 |  | 2021-07-30 09:00 | 2021-07-30 10:00 | 2021-07-27 16:04 | 2021-08-06 14:00 | CR0014069 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W30 | 2021-07 | 98 | 98 | 17.983 | 7 | 2 | 2 | 0.23 | 193488 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.53659 | 0 | 2021-07 | 0 | 0
120 | CR0014069 | CTASK0027940 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-07-23 16:03 | 2021-07-20 16:02 | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing] Global*EDI* Booking confirmation New F/F items (S/I Flag & VGM Indicator) | 2021-07-12 09:24 | 2021-07-27 | 2021-07-23 09:45 | 2021-07-26 14:44 | 2021-07-26 15:24 |  | 2021-07-30 09:00 | 2021-07-30 10:00 | 2021-07-27 16:04 | 2021-08-06 14:00 | CR0014069 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W30 | 2021-07 | 98 | 98 | 17.983 | 7 | 2 | 2 | 0.23 | 193488 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.53659 | 0 | 2021-07 | 0 | 0
121 | CR0014069 | CTASK0027929 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 52 | 52 | 2021-07-16 23:00 | 2021-07-06 10:30 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development + Testing] Global*EDI* Booking confirmation New F/F items (S/I Flag & VGM Indicator) | 2021-07-12 09:24 | 2021-07-27 | 2021-07-23 09:45 | 2021-07-26 14:44 | 2021-07-26 15:24 |  | 2021-07-30 09:00 | 2021-07-30 10:00 | 2021-07-27 16:04 | 2021-08-06 14:00 | CR0014069 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W30 | 2021-07 | 98 | 98 | 17.983 | 7 | 2 | 2 | 0.23 | 193470 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.36842 | 0.11111 | 2021-07 | 0 | 0
122 | CR0014069 | CTASK0027889 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 16 | 16 | 2021-07-05 23:00 | 2021-07-01 10:30 | Container | Service Management | Booking/Documentation | Booking |  |  | [Design]Global*EDI* Booking confirmation New F/F items (S/I Flag & VGM Indicator) | 2021-07-12 09:24 | 2021-07-27 | 2021-07-23 09:45 | 2021-07-26 14:44 | 2021-07-26 15:24 |  | 2021-07-30 09:00 | 2021-07-30 10:00 | 2021-07-27 16:04 | 2021-08-06 14:00 | CR0014069 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W30 | 2021-07 | 98 | 98 | 17.983 | 7 | 2 | 2 | 0.23 | 193470 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.36842 | 0.11111 | 2021-07 | 0 | 0
123 | CR0014069 | CTASK0027941 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-07-30 19:28 | 2021-07-27 11:28 | Container | Service Management | Booking/Documentation | Booking |  |  | [Deployment] Global*EDI* Booking confirmation New F/F items (S/I Flag & VGM Indicator) | 2021-07-12 09:24 | 2021-07-27 | 2021-07-23 09:45 | 2021-07-26 14:44 | 2021-07-26 15:24 |  | 2021-07-30 09:00 | 2021-07-30 10:00 | 2021-07-27 16:04 | 2021-08-06 14:00 | CR0014069 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W30 | 2021-07 | 98 | 98 | 17.983 | 7 | 2 | 2 | 0.23 | 193488 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.53659 | 0 | 2021-07 | 0 | 0
124 | CR0014069 | CTASK0027882 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-07-06 19:30 | 2021-07-01 11:18 | Container | Service Management | Booking/Documentation | Booking |  |  | [Design] Global*EDI* Booking confirmation New F/F items (S/I Flag & VGM Indicator) | 2021-07-12 09:24 | 2021-07-27 | 2021-07-23 09:45 | 2021-07-26 14:44 | 2021-07-26 15:24 |  | 2021-07-30 09:00 | 2021-07-30 10:00 | 2021-07-27 16:04 | 2021-08-06 14:00 | CR0014069 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W30 | 2021-07 | 98 | 98 | 17.983 | 7 | 2 | 2 | 0.23 | 193488 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.53659 | 0 | 2021-07 | 0 | 0
125 | CR0014069 | CTASK0027930 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Booking |  |  | [Deployment] Global*EDI* Booking confirmation New F/F items (S/I Flag & VGM Indicator) | 2021-07-12 09:24 | 2021-07-27 | 2021-07-23 09:45 | 2021-07-26 14:44 | 2021-07-26 15:24 |  | 2021-07-30 09:00 | 2021-07-30 10:00 | 2021-07-27 16:04 | 2021-08-06 14:00 | CR0014069 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W30 | 2021-07 | 98 | 98 | 17.983 | 7 | 2 | 2 | 0.23 | 193470 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.36842 | 0.11111 | 2021-07 | 0 | 0
126 | CR0011022 | CTASK0016813 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 69 | 168 | 2020-02-29 18:00 | 2020-01-13 09:00 | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | [Actual] Add a Hard Code table with accepted yards to pass billing requests on containers with current status as OC | 2019-10-31 09:59 | 2020-02-21 18:00 | 2020-02-19 14:37 | 2020-03-28 11:07 | 2020-04-01 10:46 |  | 2020-04-07 11:00 | 2020-04-07 10:00 | 2020-04-02 00:24 | 2020-05-07 13:00 | CR0011022 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2020-W15 | 2020-04 | 69 | 168 | 159.0425 | 1 | 1 | 1 | 0.04 | 183432 | 0.6 | 0 | 0 | 0 | 2 | 1 | 3 | 4 | 16 | 0 | 0 | 2019-10 | 0 | 0
127 | CR0012933 | CTASK0022367 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 16 | 16 | 2020-09-30 13:00 | 2020-09-08 13:00 | Container | Service Management | Booking/Documentation | Manifest | Vietnam |  | [Develop-Testing] Modify the DEL location code mapping of Vietnam Manifest | 2020-09-16 16:38 | 2020-10-01 | 2020-09-28 15:42 | 2020-10-24 09:18 | 2020-11-03 12:59 |  | 2020-11-10 10:00 | 2020-11-10 10:00 | 2020-11-05 17:54 | 2020-12-10 14:00 | CR0012933 | Service ManagementBooking/DocumentationManifestVietnam | OPUS-BKG-MFT-A | 2020-W46 | 2020-11 | 32 | 32 | 54.7237 | 3 | 1 | 1 | 0.02 | 193506 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 16 | 0 | 1.25 | 2020-09 | 0 | 0
128 | CR0012933 | CTASK0023217 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 12 | 12 | 2020-11-10 02:00 | 2020-11-02 02:00 | Container | Service Management | Booking/Documentation | Manifest | Vietnam |  | [Deploy-Test]Modify the DEL location code mapping of Vietnam Manifest | 2020-09-16 16:38 | 2020-10-01 | 2020-09-28 15:42 | 2020-10-24 09:18 | 2020-11-03 12:59 |  | 2020-11-10 10:00 | 2020-11-10 10:00 | 2020-11-05 17:54 | 2020-12-10 14:00 | CR0012933 | Service ManagementBooking/DocumentationManifestVietnam | OPUS-BKG-MFT-A | 2020-W46 | 2020-11 | 32 | 32 | 54.7237 | 3 | 1 | 1 | 0.02 | 193506 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 16 | 0 | 1.25 | 2020-09 | 0 | 0
129 | CR0012933 | CTASK0022348 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 4 | 4 | 2020-09-18 13:00 | 2020-09-08 13:00 | Container | Service Management | Booking/Documentation | Manifest | Vietnam |  | [Analytics]Modify the DEL location code mapping of Vietnam Manifest | 2020-09-16 16:38 | 2020-10-01 | 2020-09-28 15:42 | 2020-10-24 09:18 | 2020-11-03 12:59 |  | 2020-11-10 10:00 | 2020-11-10 10:00 | 2020-11-05 17:54 | 2020-12-10 14:00 | CR0012933 | Service ManagementBooking/DocumentationManifestVietnam | OPUS-BKG-MFT-A | 2020-W46 | 2020-11 | 32 | 32 | 54.7237 | 3 | 1 | 1 | 0.02 | 193506 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 16 | 0 | 1.25 | 2020-09 | 0 | 0
130 | CR0013642 | CTASK0026645 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2021-04-26 23:00 | 2021-04-22 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print |  | [Deployment] [CLT Internal] UY - DOC/CSVC - OBL's qty could be modified despites BL Issue is Y | 2021-03-02 18:58 | 2021-03-08 18:57 | 2021-03-05 09:40 | 2021-04-21 09:59 | 2021-04-21 14:18 |  | 2021-04-27 10:00 | 2021-03-02 18:57 | 2021-04-22 15:03 | 2021-05-27 14:00 | CR0013642 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & Print | OPUS-BKG-OB | 2021-W17 | 2021-04 | 14 | 14 | 55.6266 | 2 | 1 | 1 | 0.01 | 193470 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 12 | 27 | 0 | 0.17391 | 2021-03 | 0 | 0
131 | CR0013642 | CTASK0025504 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 10 | 10 | 2021-03-26 23:00 | 2021-02-25 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print |  | [CLT Internal] UY - DOC/CSVC - OBL's qty could be modified despites BL Issue is Y | 2021-03-02 18:58 | 2021-03-08 18:57 | 2021-03-05 09:40 | 2021-04-21 09:59 | 2021-04-21 14:18 |  | 2021-04-27 10:00 | 2021-03-02 18:57 | 2021-04-22 15:03 | 2021-05-27 14:00 | CR0013642 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & Print | OPUS-BKG-OB | 2021-W17 | 2021-04 | 14 | 14 | 55.6266 | 2 | 1 | 1 | 0.01 | 193470 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 12 | 27 | 0 | 0.17391 | 2021-03 | 0 | 0
132 | CR0011488 | CTASK0016010 | Closed | OPUS-BKG-M | Vinh Tran | 62 | 84 | 2019-10-11 14:59 | 2019-09-23 14:59 | Container | Service Management | Trans S/O |  |  |  | EUA - PARIS Project : Optimization of transports using external Software - ETL requirements for OPUS interface to PARIS phase 'zero' | 2019-08-21 16:48 | 2019-10-31 18:00 | 2019-10-25 17:40 | 2019-12-04 20:36 | 2019-12-05 09:25 |  | 2019-12-10 11:00 | 2019-12-10 11:00 | 2019-12-05 09:45 | 2020-01-09 14:00 | CR0011488 | Service ManagementTrans S/O | OPUS-TRS | 2019-W50 | 2019-12 | 62 | 84 | 110.7587 | 1 | 1 | 1 | 0.03 | 193525 | 0.2 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 18 | 0 | 0.45455 | 2019-08 | 0 | 0
133 | CR0013600 | CTASK0025702 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 20 | 20 | 2021-04-09 15:36 | 2021-04-02 15:36 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Testing][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 193512 | 1.7 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.2963 | 0.3125 | 2021-03 | 0 | 0
134 | CR0013600 | CTASK0025581 | Closed | OPUS-BKG-OB | Nam Nguyen | 26 | 32 | 2021-05-21 20:53 | 2021-04-01 20:52 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Testing & Deployment][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 123048 | 2.5 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.22222 | 0.047619 | 2021-03 | 0 | 0
135 | CR0013600 | CTASK0025692 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 10 | 10 | 2021-04-17 02:00 | 2021-04-12 10:59 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Testing][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 193488 | 1.8 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
136 | CR0013600 | CTASK0025667 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 2 | 2 | 2021-03-05 12:10 | 2021-03-01 12:10 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Design][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 193512 | 1.7 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.2963 | 0.3125 | 2021-03 | 0 | 0
137 | CR0013600 | CTASK0025704 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 5 | 5 | 2021-04-17 15:38 | 2021-04-02 15:38 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Deployment][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 193512 | 1.7 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.2963 | 0.3125 | 2021-03 | 0 | 0
138 | CR0013600 | CTASK0026088 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 14 | 7 | 2021-03-31 11:19 | 2021-03-25 11:19 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [202104] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 183432 | 2 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.043478 | 0.22222 | 2021-03 | 0 | 0
139 | CR0013600 | CTASK0025638 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-03-04 11:29 | 2021-03-01 11:29 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Design][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 193488 | 1.8 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
140 | CR0013600 | CTASK0025694 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-05-08 02:00 | 2021-05-04 10:53 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Deployment][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 193488 | 1.8 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
141 | CR0013600 | CTASK0025580 | Closed | OPUS-BKG-OB | Nam Nguyen | 20 | 20 |  |  | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Development][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 123048 | 2.5 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.22222 | 0.047619 | 2021-03 | 0 | 0
142 | CR0013600 | CTASK0026089 | Closed | OPUS-TRS | Giang Nguyen Hoang | 13 | 7 | 2021-03-31 11:20 | 2021-03-25 11:20 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [202104] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 183440 | 2 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0 | 0 | 2021-03 | 0 | 0
143 | CR0013600 | CTASK0025701 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 30 | 30 | 2021-04-02 15:34 | 2021-03-22 09:34 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Development][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 193512 | 1.7 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.2963 | 0.3125 | 2021-03 | 0 | 0
144 | CR0013600 | CTASK0025690 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 24 | 24 | 2021-04-01 02:00 | 2021-03-19 18:56 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Development][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 193488 | 1.8 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
145 | CR0013600 | CTASK0025569 | Closed | OPUS-BKG-OB | Nam Nguyen | 8 | 8 | 2021-03-02 11:24 | 2021-03-01 11:24 | Container | Biz Common | EDI Setup | Setup | Logistics Vendor EDI Setup |  | [Design][CLT Internal] NA *EDI* VENDOR - INTERNAL CR - Flag in EDI SUP under OPUS Container not working correctly | 2021-03-22 09:39 | 2021-04-22 | 2021-04-21 13:42 | 2021-04-29 17:42 | 2021-04-30 13:41 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-30 16:07 | 2021-05-11 17:15 | CR0013600 | Biz CommonEDI SetupSetupLogistics Vendor EDI Setup | OPUS-MDA | 2021-W19 | 2021-05 | 188 | 181 | 50.0145 | 13 | 4 | 5 | 0.15 | 123048 | 2.5 | 1 | 0 | 0 | 2 | 2 | 2 | 6 | 28 | 0.22222 | 0.047619 | 2021-03 | 0 | 0
146 | CR0012881 | CTASK0021397 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2020-07-31 17:21 | 2020-07-20 09:21 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Design] [CLT Internal] Enhancement for row editing in DG Application and auto notification flag in BKG Creation | 2020-08-04 15:08 | 2020-08-27 | 2020-08-24 16:12 | 2020-08-24 21:21 | 2020-08-25 11:41 |  | 2020-09-15 11:40 | 2020-09-16 | 2020-09-04 18:09 | 2020-09-24 14:05 | CR0012881 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W38 | 2020-09 | 67 | 67 | 41.8553 | 9 | 2 | 2 | 0.07 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.53333 | 2020-08 | 0 | 0
147 | CR0012881 | CTASK0021465 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 4 | 4 | 2020-08-14 18:18 | 2020-08-10 18:18 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Testing][CLT Internal] Enhancement for row editing in DG Application and auto notification flag in BKG Creation | 2020-08-04 15:08 | 2020-08-27 | 2020-08-24 16:12 | 2020-08-24 21:21 | 2020-08-25 11:41 |  | 2020-09-15 11:40 | 2020-09-16 | 2020-09-04 18:09 | 2020-09-24 14:05 | CR0012881 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W38 | 2020-09 | 67 | 67 | 41.8553 | 9 | 2 | 2 | 0.07 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-08 | 0 | 0
148 | CR0012881 | CTASK0021484 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-08-31 12:02 | 2020-08-01 12:02 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Testing][CLT Internal] Enhancement for row editing in DG Application and auto notification flag in BKG Creation | 2020-08-04 15:08 | 2020-08-27 | 2020-08-24 16:12 | 2020-08-24 21:21 | 2020-08-25 11:41 |  | 2020-09-15 11:40 | 2020-09-16 | 2020-09-04 18:09 | 2020-09-24 14:05 | CR0012881 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W38 | 2020-09 | 67 | 67 | 41.8553 | 9 | 2 | 2 | 0.07 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.53333 | 2020-08 | 0 | 0
149 | CR0012881 | CTASK0021483 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-08-31 12:01 | 2020-08-01 12:01 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Development] [CLT Internal] Enhancement for row editing in DG Application and auto notification flag in BKG Creation | 2020-08-04 15:08 | 2020-08-27 | 2020-08-24 16:12 | 2020-08-24 21:21 | 2020-08-25 11:41 |  | 2020-09-15 11:40 | 2020-09-16 | 2020-09-04 18:09 | 2020-09-24 14:05 | CR0012881 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W38 | 2020-09 | 67 | 67 | 41.8553 | 9 | 2 | 2 | 0.07 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.53333 | 2020-08 | 0 | 0
150 | CR0012881 | CTASK0021464 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 12 | 12 | 2020-08-14 18:18 | 2020-08-04 18:18 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Development] [CLT Internal] Enhancement for row editing in DG Application and auto notification flag in BKG Creation | 2020-08-04 15:08 | 2020-08-27 | 2020-08-24 16:12 | 2020-08-24 21:21 | 2020-08-25 11:41 |  | 2020-09-15 11:40 | 2020-09-16 | 2020-09-04 18:09 | 2020-09-24 14:05 | CR0012881 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W38 | 2020-09 | 67 | 67 | 41.8553 | 9 | 2 | 2 | 0.07 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-08 | 0 | 0
151 | CR0012881 | CTASK0021427 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 10 | 10 | 2020-07-23 18:30 | 2020-07-22 14:09 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Design] [CLT Internal] Enhancement for row editing in DG Application and auto notification flag in BKG Creation | 2020-08-04 15:08 | 2020-08-27 | 2020-08-24 16:12 | 2020-08-24 21:21 | 2020-08-25 11:41 |  | 2020-09-15 11:40 | 2020-09-16 | 2020-09-04 18:09 | 2020-09-24 14:05 | CR0012881 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W38 | 2020-09 | 67 | 67 | 41.8553 | 9 | 2 | 2 | 0.07 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-08 | 0 | 0
152 | CR0012881 | CTASK0021485 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-09-30 12:02 | 2020-09-01 12:02 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Deployment][CLT Internal] Enhancement for row editing in DG Application and auto notification flag in BKG Creation | 2020-08-04 15:08 | 2020-08-27 | 2020-08-24 16:12 | 2020-08-24 21:21 | 2020-08-25 11:41 |  | 2020-09-15 11:40 | 2020-09-16 | 2020-09-04 18:09 | 2020-09-24 14:05 | CR0012881 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W38 | 2020-09 | 67 | 67 | 41.8553 | 9 | 2 | 2 | 0.07 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.53333 | 2020-08 | 0 | 0
153 | CR0012881 | CTASK0022017 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 3 | 3 | 2020-08-21 18:15 | 2020-08-20 10:14 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [CLT Internal] Enhancement for row editing in DG Application and auto notification flag in BKG Creation | 2020-08-04 15:08 | 2020-08-27 | 2020-08-24 16:12 | 2020-08-24 21:21 | 2020-08-25 11:41 |  | 2020-09-15 11:40 | 2020-09-16 | 2020-09-04 18:09 | 2020-09-24 14:05 | CR0012881 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W38 | 2020-09 | 67 | 67 | 41.8553 | 9 | 2 | 2 | 0.07 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-08 | 0 | 0
154 | CR0012881 | CTASK0021466 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 2 | 2 | 2020-09-15 18:18 | 2020-09-14 10:18 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Deployment][CLT Internal] Enhancement for row editing in DG Application and auto notification flag in BKG Creation | 2020-08-04 15:08 | 2020-08-27 | 2020-08-24 16:12 | 2020-08-24 21:21 | 2020-08-25 11:41 |  | 2020-09-15 11:40 | 2020-09-16 | 2020-09-04 18:09 | 2020-09-24 14:05 | CR0012881 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W38 | 2020-09 | 67 | 67 | 41.8553 | 9 | 2 | 2 | 0.07 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-08 | 0 | 0
155 | CR0012701 | CTASK0020893 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 40 | 40 | 2020-07-24 16:48 | 2020-07-13 16:47 | Container | Service Management | Booking/Documentation | Manifest | Korea | Manifest Transmit | [Development-Testing] Amend mapping of goods description in Manifest F/F | 2020-07-06 18:32 | 2020-08-01 | 2020-07-24 15:04 | 2020-07-24 16:40 | 2020-07-27 13:57 |  | 2020-08-04 13:56 | 2020-07-29 09:30 | 2020-07-27 14:53 | 2020-08-28 13:00 | CR0012701 | Service ManagementBooking/DocumentationManifestKoreaManifest Transmit | OPUS-BKG-MFT-A | 2020-W32 | 2020-08 | 56 | 56 | 28.8081 | 3 | 1 | 1 | 0.08 | 193506 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 30 | 0 | 1.25 | 2020-07 | 0 | 0
156 | CR0012701 | CTASK0020803 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2020-06-24 15:42 | 2020-06-19 15:42 | Container | Service Management | Booking/Documentation | Manifest | Korea | Manifest Transmit | [Analytics] Amend mapping of goods description in Manifest F/F | 2020-07-06 18:32 | 2020-08-01 | 2020-07-24 15:04 | 2020-07-24 16:40 | 2020-07-27 13:57 |  | 2020-08-04 13:56 | 2020-07-29 09:30 | 2020-07-27 14:53 | 2020-08-28 13:00 | CR0012701 | Service ManagementBooking/DocumentationManifestKoreaManifest Transmit | OPUS-BKG-MFT-A | 2020-W32 | 2020-08 | 56 | 56 | 28.8081 | 3 | 1 | 1 | 0.08 | 193506 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 30 | 0 | 1.25 | 2020-07 | 0 | 0
157 | CR0012701 | CTASK0021502 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2020-07-29 13:00 | 2020-07-27 13:00 | Container | Service Management | Booking/Documentation | Manifest | Korea | Manifest Transmit | [Deployment] Korea Manifest - Amend mapping of goods description in Manifest F/F | 2020-07-06 18:32 | 2020-08-01 | 2020-07-24 15:04 | 2020-07-24 16:40 | 2020-07-27 13:57 |  | 2020-08-04 13:56 | 2020-07-29 09:30 | 2020-07-27 14:53 | 2020-08-28 13:00 | CR0012701 | Service ManagementBooking/DocumentationManifestKoreaManifest Transmit | OPUS-BKG-MFT-A | 2020-W32 | 2020-08 | 56 | 56 | 28.8081 | 3 | 1 | 1 | 0.08 | 193506 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 30 | 0 | 1.25 | 2020-07 | 0 | 0
158 | CR0013800 | CTASK0026433 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2021-04-17 01:05 | 2021-04-15 02:05 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] OPUS Standby Booking Detail - dynamic change 'TEU' to 'BOX' Allocation when RF Flag is Y | 2021-04-12 17:42 | 2021-05-06 | 2021-04-19 18:31 | 2021-06-14 13:27 | 2021-06-14 14:27 |  | 2021-06-22 10:00 | 2021-06-22 10:00 | 2021-06-16 09:06 | 2021-07-22 14:00 | CR0013800 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W25 | 2021-06 | 4 | 4 | 70.6792 | 5 | 1 | 1 | 0 | 153106 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.22951 | 0.13043 | 2021-04 | 0 | 0
159 | CR0013800 | CTASK0026434 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2021-04-17 01:06 | 2021-04-15 02:06 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] OPUS Standby Booking Detail - dynamic change 'TEU' to 'BOX' Allocation when RF Flag is Y | 2021-04-12 17:42 | 2021-05-06 | 2021-04-19 18:31 | 2021-06-14 13:27 | 2021-06-14 14:27 |  | 2021-06-22 10:00 | 2021-06-22 10:00 | 2021-06-16 09:06 | 2021-07-22 14:00 | CR0013800 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W25 | 2021-06 | 4 | 4 | 70.6792 | 5 | 1 | 1 | 0 | 153106 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.22951 | 0.13043 | 2021-04 | 0 | 0
160 | CR0013800 | CTASK0026425 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Documentation] OPUS Standby Booking Detail - dynamic change 'TEU' to 'BOX' Allocation when RF Flag is Y | 2021-04-12 17:42 | 2021-05-06 | 2021-04-19 18:31 | 2021-06-14 13:27 | 2021-06-14 14:27 |  | 2021-06-22 10:00 | 2021-06-22 10:00 | 2021-06-16 09:06 | 2021-07-22 14:00 | CR0013800 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W25 | 2021-06 | 4 | 4 | 70.6792 | 5 | 1 | 1 | 0 | 153106 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.22951 | 0.13043 | 2021-04 | 0 | 0
161 | CR0013800 | CTASK0026432 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2021-04-13 01:01 | 2021-04-12 02:00 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Desgin] OPUS Standby Booking Detail - dynamic change 'TEU' to 'BOX' Allocation when RF Flag is Y | 2021-04-12 17:42 | 2021-05-06 | 2021-04-19 18:31 | 2021-06-14 13:27 | 2021-06-14 14:27 |  | 2021-06-22 10:00 | 2021-06-22 10:00 | 2021-06-16 09:06 | 2021-07-22 14:00 | CR0013800 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W25 | 2021-06 | 4 | 4 | 70.6792 | 5 | 1 | 1 | 0 | 153106 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.22951 | 0.13043 | 2021-04 | 0 | 0
162 | CR0013800 | CTASK0026435 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2021-07-01 01:07 | 2021-06-01 02:07 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] OPUS Standby Booking Detail - dynamic change 'TEU' to 'BOX' Allocation when RF Flag is Y | 2021-04-12 17:42 | 2021-05-06 | 2021-04-19 18:31 | 2021-06-14 13:27 | 2021-06-14 14:27 |  | 2021-06-22 10:00 | 2021-06-22 10:00 | 2021-06-16 09:06 | 2021-07-22 14:00 | CR0013800 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W25 | 2021-06 | 4 | 4 | 70.6792 | 5 | 1 | 1 | 0 | 153106 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.22951 | 0.13043 | 2021-04 | 0 | 0
163 | CR0010906 | CTASK0018268 | Closed | OPUS-BKG-RPT | Thai Nguyen Quoc | 3 | 4 | 2020-02-11 | 2020-02-07 15:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | NA *DOC* Enhance Charge Remarks pop-up to assist Revenue Audit process (CSVC/EXP DOC) | 2019-05-15 08:03 | 2019-07-19 08:03 | 2019-07-18 15:30 | 2020-02-04 04:15 | 2020-02-28 17:35 |  | 2020-03-17 10:00 | 2020-03-17 09:00 | 2020-03-13 22:32 | 2020-04-16 13:00 | CR0010906 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2020-W12 | 2020-03 | 16 | 17 | 307.0811 | 2 | 2 | 1 | 0 | 193470 | 0.2 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 25 | 0 | 1.3333 | 2019-05 | 0 | 0
164 | CR0010906 | CTASK0018885 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 13 | 13 | 2020-03-17 10:50 | 2020-03-11 10:50 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [stg test + deployment] NA *DOC* Enhance Charge Remarks pop-up to assist Revenue Audit process (CSVC/EXP DOC) | 2019-05-15 08:03 | 2019-07-19 08:03 | 2019-07-18 15:30 | 2020-02-04 04:15 | 2020-02-28 17:35 |  | 2020-03-17 10:00 | 2020-03-17 09:00 | 2020-03-13 22:32 | 2020-04-16 13:00 | CR0010906 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2020-W12 | 2020-03 | 16 | 17 | 307.0811 | 2 | 2 | 1 | 0 | 193470 | 0.2 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 25 | 0 | 1.3333 | 2019-05 | 0 | 0
165 | CR0013219 | CTASK0023665 | Closed | OPUS-TES | Thai Nguyen | 26 | 20 | 2020-11-30 12:55 | 2020-11-18 12:55 | Container | Service Management | TML INV |  |  |  | [Internal] TES agreement - apply expiry date | 2020-12-10 10:56 | 2021-01-22 10:55 | 2020-12-30 11:05 | 2021-04-01 14:02 | 2021-04-07 12:01 |  | 2021-04-13 12:00 | 2021-04-13 11:30 | 2021-04-08 11:36 | 2021-05-14 14:00 | CR0013219 | Service ManagementTML INV | OPUS-TES | 2021-W15 | 2021-04 | 31 | 25 | 124.0447 | 2 | 1 | 1 | 0.01 | 173249 | 2.2 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 27 | 0 | 0.5 | 2020-12 | 0 | 0
166 | CR0013219 | CTASK0026215 | Closed | OPUS-TES | Thai Nguyen | 5 | 5 | 2021-05-01 01:00 | 2021-04-01 01:00 | Container | Service Management | TML INV |  |  |  | [202104] [Internal] TES agreement - apply expiry date | 2020-12-10 10:56 | 2021-01-22 10:55 | 2020-12-30 11:05 | 2021-04-01 14:02 | 2021-04-07 12:01 |  | 2021-04-13 12:00 | 2021-04-13 11:30 | 2021-04-08 11:36 | 2021-05-14 14:00 | CR0013219 | Service ManagementTML INV | OPUS-TES | 2021-W15 | 2021-04 | 31 | 25 | 124.0447 | 2 | 1 | 1 | 0.01 | 173249 | 2.2 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 27 | 0 | 0.5 | 2020-12 | 0 | 0
167 | CR0012280 | CTASK0020508 | Closed | OPUS-OPF | Tuan Pham Huu | 40 | 40 | 2020-06-12 17:28 | 2020-06-01 17:28 | Container | Vessel Operation | Operation & PFMC | Setup | TDR/RDR |  | [CLV]User Management for Opus Stowage | 2020-04-07 16:59 | 2020-04-14 17:57 | 2020-04-14 14:57 | 2020-06-18 13:34 | 2020-07-16 13:22 |  | 2020-07-16 13:22 | 2020-07-21 10:14 | 2020-07-16 16:16 | 2020-08-21 13:00 | CR0012280 | Vessel OperationOperation & PFMCSetupTDR/RDR | OPUS-OPF | 2020-W29 | 2020-07 | 57 | 57 | 99.8495 | 2 | 1 | 2 | 0.02 | 193523 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0 | 2020-04 | 0 | 0
168 | CR0012280 | CTASK0020507 | Closed | OPUS-OPF | Thuan Tran | 17 | 17 | 2020-06-12 17:26 | 2020-06-01 17:26 | Container | Vessel Operation | Operation & PFMC | Setup | TDR/RDR |  | [CLV]User Management for Opus Stowage | 2020-04-07 16:59 | 2020-04-14 17:57 | 2020-04-14 14:57 | 2020-06-18 13:34 | 2020-07-16 13:22 |  | 2020-07-16 13:22 | 2020-07-21 10:14 | 2020-07-16 16:16 | 2020-08-21 13:00 | CR0012280 | Vessel OperationOperation & PFMCSetupTDR/RDR | OPUS-OPF | 2020-W29 | 2020-07 | 57 | 57 | 99.8495 | 2 | 1 | 2 | 0.02 | 183423 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0 | 2020-04 | 0 | 0
169 | CR0011660 | CTASK0017998 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 254 | 254 | 2020-05-13 09:35 | 2020-01-18 10:34 | Container | Service Management | Booking/Documentation | Manifest |  |  | HKG Manifest | 2020-02-07 18:36 | 2020-05-23 | 2020-05-22 13:26 | 2021-01-11 15:17 | 2021-06-09 13:30 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-25 10:10 | 2021-07-29 14:00 | CR0011660 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 363 | 352 | 507.6417 | 4 | 2 | 2 | 0.03 | 193506 | 0.7 | 1 | 0 | 1 | 4 | 1 | 5 | 16 | 53 | 1.1212 | 0.85714 | 2020-02 | 1 | 1
170 | CR0011660 | CTASK0018102 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 73 | 73 | 2020-04-21 19:00 | 2020-01-30 10:30 | Container | Service Management | Booking/Documentation | Manifest |  |  | HKG Manifest | 2020-02-07 18:36 | 2020-05-23 | 2020-05-22 13:26 | 2021-01-11 15:17 | 2021-06-09 13:30 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-25 10:10 | 2021-07-29 14:00 | CR0011660 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 363 | 352 | 507.6417 | 4 | 2 | 2 | 0.03 | 193470 | 0.9 | 1 | 0 | 1 | 4 | 1 | 5 | 16 | 53 | 0.36842 | 1.3333 | 2020-02 | 1 | 1
171 | CR0011660 | CTASK0027276 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 16 | 5 | 2021-06-02 23:00 | 2021-05-31 10:30 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Deployment] HKG Manifest | 2020-02-07 18:36 | 2020-05-23 | 2020-05-22 13:26 | 2021-01-11 15:17 | 2021-06-09 13:30 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-25 10:10 | 2021-07-29 14:00 | CR0011660 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 363 | 352 | 507.6417 | 4 | 2 | 2 | 0.03 | 193470 | 0.9 | 1 | 0 | 1 | 4 | 1 | 5 | 16 | 53 | 0.36842 | 1.3333 | 2020-02 | 1 | 1
172 | CR0011660 | CTASK0021275 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 20 | 20 | 2020-08-31 15:00 | 2020-07-10 15:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Development-Testing]HK Manifest(Fix Bug) | 2020-02-07 18:36 | 2020-05-23 | 2020-05-22 13:26 | 2021-01-11 15:17 | 2021-06-09 13:30 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-25 10:10 | 2021-07-29 14:00 | CR0011660 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 363 | 352 | 507.6417 | 4 | 2 | 2 | 0.03 | 193506 | 0.7 | 1 | 0 | 1 | 4 | 1 | 5 | 16 | 53 | 1.1212 | 0.85714 | 2020-02 | 1 | 1
173 | CR0013147 | CTASK0022894 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2020-10-31 19:20 | 2020-10-06 19:20 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] [CLT Internal] GDN has been added into constraints since CR0012145 but this change requires the additional modification on auto escalation logic to align the logic. | 2020-10-19 11:17 | 2020-11-26 | 2020-11-25 11:31 | 2020-11-27 15:03 | 2020-11-27 16:38 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2020-11-27 16:50 | 2021-02-18 14:00 | CR0013147 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W3 | 2021-01 | 45 | 47 | 91.9465 | 5 | 1 | 2 | 0.02 | 193503 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.33333 | 0.28571 | 2020-10 | 0 | 0
174 | CR0013147 | CTASK0022917 | Closed | OPUS-BKG-M | Loc Tran | 16 | 16 | 2020-10-31 17:10 | 2020-10-12 17:10 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] [CLT Internal] GDN has been added into constraints since CR0012145 but this change requires the additional modification on auto escalation logic to align the logic. | 2020-10-19 11:17 | 2020-11-26 | 2020-11-25 11:31 | 2020-11-27 15:03 | 2020-11-27 16:38 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2020-11-27 16:50 | 2021-02-18 14:00 | CR0013147 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W3 | 2021-01 | 45 | 47 | 91.9465 | 5 | 1 | 2 | 0.02 | 193503 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.33333 | 0.28571 | 2020-10 | 0 | 0
175 | CR0013147 | CTASK0022920 | Closed | OPUS-BKG-M | Loc Tran | 14 | 16 | 2020-11-30 19:21 | 2020-10-21 19:21 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] [CLT Internal] GDN has been added into constraints since CR0012145 but this change requires the additional modification on auto escalation logic to align the logic. | 2020-10-19 11:17 | 2020-11-26 | 2020-11-25 11:31 | 2020-11-27 15:03 | 2020-11-27 16:38 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2020-11-27 16:50 | 2021-02-18 14:00 | CR0013147 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W3 | 2021-01 | 45 | 47 | 91.9465 | 5 | 1 | 2 | 0.02 | 193503 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.33333 | 0.28571 | 2020-10 | 0 | 0
176 | CR0013147 | CTASK0022807 | Closed | OPUS-BKG-M | Kieu Le | 3 | 3 | 2020-10-03 01:30 | 2020-10-01 02:29 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] [CLT Internal] GDN has been added into constraints since CR0012145 but this change requires the additional modification on auto escalation logic to align the logic. | 2020-10-19 11:17 | 2020-11-26 | 2020-11-25 11:31 | 2020-11-27 15:03 | 2020-11-27 16:38 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2020-11-27 16:50 | 2021-02-18 14:00 | CR0013147 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W3 | 2021-01 | 45 | 47 | 91.9465 | 5 | 1 | 2 | 0.02 | 153106 | 2.1 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.22951 | 0.13043 | 2020-10 | 0 | 0
177 | CR0013147 | CTASK0022922 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-01-19 19:33 | 2021-01-11 19:33 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] [CLT Internal] GDN has been added into constraints since CR0012145 but this change requires the additional modification on auto escalation logic to align the logic. | 2020-10-19 11:17 | 2020-11-26 | 2020-11-25 11:31 | 2020-11-27 15:03 | 2020-11-27 16:38 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2020-11-27 16:50 | 2021-02-18 14:00 | CR0013147 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W3 | 2021-01 | 45 | 47 | 91.9465 | 5 | 1 | 2 | 0.02 | 193503 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.33333 | 0.28571 | 2020-10 | 0 | 0
178 | CR0013083 | CTASK0022583 | Closed | OPUS-SCO | Nguyen Ha Vi | 120 | 120 | 2020-12-31 17:37 | 2020-12-01 17:37 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Vi Nguyen][DEC][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 203664 | 0.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.8182 | 1.2857 | 2020-09 | 8 | 1
179 | CR0013083 | CTASK0022566 | Closed | OPUS-SCO | Chuong Ta | 82 | 80 | 2020-10-31 15:30 | 2020-10-01 15:30 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Chuong Ta][OCT][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183379 | 1.5 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.32 | 0.38462 | 2020-09 | 8 | 1
180 | CR0013083 | CTASK0022578 | Closed | OPUS-SCO | Mohamed Hary | 100 | 100 | 2020-12-31 16:24 | 2020-12-01 16:24 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Hary][December] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193489 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.72727 | 0.63636 | 2020-09 | 8 | 1
181 | CR0013083 | CTASK0022570 | Closed | OPUS-SCO | Cuong Tran Hung | 50 | 50 | 2020-09-30 15:52 | 2020-09-21 15:52 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [CuongTran][September] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193530 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.2308 | 1.2222 | 2020-09 | 8 | 1
182 | CR0013083 | CTASK0022599 | Closed | OPUS-SCO | Lien Le | 142 | 140 | 2020-11-30 20:35 | 2020-11-01 20:35 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Lien Le][November] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193441 | 1.5 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.42308 | 1.2222 | 2020-09 | 8 | 1
183 | CR0013083 | CTASK0022571 | Closed | OPUS-SCO | Cuong Tran Hung | 130 | 130 | 2020-10-31 15:54 | 2020-10-01 15:54 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [CuongTran][October] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193530 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.2308 | 1.2222 | 2020-09 | 8 | 1
184 | CR0013083 | CTASK0022576 | Closed | OPUS-SCO | Mohamed Hary | 80 | 80 | 2020-10-31 16:19 | 2020-10-01 16:19 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Hary][October] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193489 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.72727 | 0.63636 | 2020-09 | 8 | 1
185 | CR0013083 | CTASK0022569 | Closed | OPUS-SCO | Chuong Ta | 1 | 1 | 2021-01-28 16:35 | 2021-01-01 16:35 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Chuong Ta][JAN][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183379 | 1.5 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.32 | 0.38462 | 2020-09 | 8 | 1
186 | CR0013083 | CTASK0022573 | Closed | OPUS-SCO | Cuong Tran Hung | 150 | 150 | 2020-12-31 15:58 | 2020-12-01 15:58 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [CuongTran][December] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193530 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.2308 | 1.2222 | 2020-09 | 8 | 1
187 | CR0013083 | CTASK0022567 | Closed | OPUS-SCO | Chuong Ta | 86 | 80 | 2020-11-30 16:32 | 2020-11-01 16:32 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Chuong Ta][NOV][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183379 | 1.5 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.32 | 0.38462 | 2020-09 | 8 | 1
188 | CR0013083 | CTASK0022580 | Closed | OPUS-SCO | Nguyen Ha Vi | 60 | 60 | 2020-09-30 16:29 | 2020-09-21 16:29 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Vi Nguyen][SEP][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 203664 | 0.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.8182 | 1.2857 | 2020-09 | 8 | 1
189 | CR0013083 | CTASK0022589 | Closed | OPUS-SCO | Hang To | 80 | 80 | 2020-11-30 18:32 | 2020-11-01 18:32 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [HangTo][November] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183344 | 1.4 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 2.1111 | 2.4286 | 2020-09 | 8 | 1
190 | CR0013083 | CTASK0022565 | Closed | OPUS-SCO | Chuong Ta | 32 | 30 | 2020-09-30 15:24 | 2020-09-21 15:24 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Chuong Ta][SEP][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183379 | 1.5 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.32 | 0.38462 | 2020-09 | 8 | 1
191 | CR0013083 | CTASK0022577 | Closed | OPUS-SCO | Mohamed Hary | 80 | 80 | 2020-11-30 16:22 | 2020-11-01 16:22 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Hary][November] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193489 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.72727 | 0.63636 | 2020-09 | 8 | 1
192 | CR0013083 | CTASK0022581 | Closed | OPUS-SCO | Nguyen Ha Vi | 100 | 100 | 2020-10-31 16:33 | 2020-10-01 16:32 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Vi Nguyen][OCT][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 203664 | 0.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.8182 | 1.2857 | 2020-09 | 8 | 1
193 | CR0013083 | CTASK0022579 | Closed | OPUS-SCO | Mohamed Hary | 1 | 1 | 2021-01-31 16:25 | 2021-01-01 16:25 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Hary][January] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193489 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.72727 | 0.63636 | 2020-09 | 8 | 1
194 | CR0013083 | CTASK0022586 | Closed | OPUS-SCO | Hang To | 20 | 20 | 2020-09-30 17:28 | 2020-09-01 17:28 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [HangTo][September] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183344 | 1.4 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 2.1111 | 2.4286 | 2020-09 | 8 | 1
195 | CR0013083 | CTASK0022574 | Closed | OPUS-SCO | Cuong Tran Hung | 1 | 1 | 2021-01-29 16:03 | 2021-01-01 16:03 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [CuongTran][January] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193530 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.2308 | 1.2222 | 2020-09 | 8 | 1
196 | CR0013083 | CTASK0022598 | Closed | OPUS-SCO | Lien Le | 135 | 135 | 2020-10-31 19:33 | 2020-10-01 19:33 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Lien Le][October] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193441 | 1.5 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.42308 | 1.2222 | 2020-09 | 8 | 1
197 | CR0013083 | CTASK0022590 | Closed | OPUS-SCO | Hang To | 120 | 120 | 2020-12-31 18:33 | 2020-12-01 18:33 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [HangTo][December] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183344 | 1.4 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 2.1111 | 2.4286 | 2020-09 | 8 | 1
198 | CR0013083 | CTASK0022582 | Closed | OPUS-SCO | Nguyen Ha Vi | 100 | 100 | 2020-11-30 17:36 | 2020-11-01 17:36 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Vi Nguyen][NOV][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 203664 | 0.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.8182 | 1.2857 | 2020-09 | 8 | 1
199 | CR0013083 | CTASK0022600 | Closed | OPUS-SCO | Lien Le | 147 | 145 | 2020-12-31 20:40 | 2020-12-01 20:39 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Lien Le][December] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193441 | 1.5 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.42308 | 1.2222 | 2020-09 | 8 | 1
200 | CR0013083 | CTASK0022591 | Closed | OPUS-SCO | Hang To | 1 | 1 | 2021-01-31 18:34 | 2021-01-01 18:34 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [HangTo][January] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183344 | 1.4 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 2.1111 | 2.4286 | 2020-09 | 8 | 1
201 | CR0013083 | CTASK0022575 | Closed | OPUS-SCO | Mohamed Hary | 40 | 40 | 2020-09-30 16:12 | 2020-09-01 16:12 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Hary][September] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193489 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.72727 | 0.63636 | 2020-09 | 8 | 1
202 | CR0013083 | CTASK0022572 | Closed | OPUS-SCO | Cuong Tran Hung | 130 | 130 | 2020-11-30 15:56 | 2020-11-01 15:56 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [CuongTran][November] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193530 | 1.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.2308 | 1.2222 | 2020-09 | 8 | 1
203 | CR0013083 | CTASK0022601 | Closed | OPUS-SCO | Lien Le | 1 | 1 | 2021-01-28 20:41 | 2021-01-01 20:40 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Lien Le][January] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 193441 | 1.5 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.42308 | 1.2222 | 2020-09 | 8 | 1
204 | CR0013083 | CTASK0022588 | Closed | OPUS-SCO | Hang To | 80 | 80 | 2020-10-31 17:31 | 2020-10-01 17:31 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [HangTo][October] NA CLEAR Implementation | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183344 | 1.4 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 2.1111 | 2.4286 | 2020-09 | 8 | 1
205 | CR0013083 | CTASK0022568 | Closed | OPUS-SCO | Chuong Ta | 110 | 110 | 2020-12-31 16:34 | 2020-12-01 16:33 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Chuong Ta][DEC][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 183379 | 1.5 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 0.32 | 0.38462 | 2020-09 | 8 | 1
206 | CR0013083 | CTASK0022585 | Closed | OPUS-SCO | Nguyen Ha Vi | 1 | 1 | 2021-01-29 17:39 | 2021-01-01 17:39 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Vi Nguyen][JAN][NA CLEAR Implementation] | 2020-09-23 08:57 | 2020-12-14 08:52 | 2020-12-08 17:16 | 2020-12-09 08:12 | 2020-12-09 08:59 |  | 2020-12-28 09:00 | 2020-12-28 10:00 | 2020-12-23 17:51 | 2021-01-27 14:00 | CR0013083 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 2174 | 2160 | 96.0021 | 29 | 1 | 6 | 0.94 | 203664 | 0.3 | 3 | 8 | 0 | 4 | 2 | 2 | 9 | 30 | 1.8182 | 1.2857 | 2020-09 | 8 | 1
207 | CR0010811 | CTASK0011411 | Closed | OPUS-TES | Thai Nguyen | 20 | 20 | 2019-01-24 19:00 | 2019-01-15 16:00 | Container | Service Management | TML INV | Invoice |  |  | GHQ - Disallow stevedore related auto cost code from being invoiced thru manual/semi-auto calculation method | 2019-01-16 18:26 | 2019-01-23 18:24 | 2019-01-18 17:40 | 2019-01-22 12:59 | 2019-01-24 16:24 |  | 2019-02-01 16:23 | 2019-02-01 13:44 | 2019-02-12 13:45 | 2019-02-14 15:50 | CR0010811 | Service ManagementTML INVInvoice | OPUS-TES | 2019-W5 | 2019-02 | 20 | 20 | 15.915 | 1 | 1 | 1 | 0.05 | 173249 | 0.3 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0.6 | 2019-01 | 0 | 0
208 | CR0011995 | CTASK0017298 | Closed | OPUS-TPB | Manh Nguyen | 1 | 1 |  |  | Container | Service Management | A/R Invoice |  |  |  | [Actual] Change in company name / ONE India for all invoices | 2019-11-28 17:26 | 2019-12-06 17:25 | 2019-11-29 12:23 | 2019-12-04 12:08 | 2019-12-10 10:52 |  | 2019-12-10 10:48 | 2019-12-10 11:23 | 2019-12-10 11:09 | 2019-12-10 11:31 | CR0011995 | Service ManagementA/R Invoice | OPUS-INV | 2019-W50 | 2019-12 | 0 | 0 | 11.7239 | 1 | 1 | 1 | 0 | 153138 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 18 | 0 | 0.25 | 2019-11 | 0 | 0
209 | CR0013555 | CTASK0024909 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-02-26 17:17 | 2021-02-01 02:16 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Development] Asia - Opus_Portcast API Connection - Add Dominant Flag to the conditions (Ref: CR0011895) | 2021-02-03 09:11 | 2021-02-25 | 2021-02-22 15:21 | 2021-02-23 14:33 | 2021-02-23 15:40 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-02-23 15:52 | 2021-04-08 14:00 | CR0013555 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W10 | 2021-03 | 21 | 21 | 34.034 | 4 | 1 | 1 | 0.03 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 46 | 0.22951 | 0.13043 | 2021-02 | 0 | 0
210 | CR0013555 | CTASK0024902 | Closed | OPUS-BKG-M | Kieu Le | 3 | 3 | 2021-01-29 13:13 | 2021-01-25 13:13 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Design] Asia - Opus_Portcast API Connection - Add Dominant Flag to the conditions (Ref: CR0011895) | 2021-02-03 09:11 | 2021-02-25 | 2021-02-22 15:21 | 2021-02-23 14:33 | 2021-02-23 15:40 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-02-23 15:52 | 2021-04-08 14:00 | CR0013555 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W10 | 2021-03 | 21 | 21 | 34.034 | 4 | 1 | 1 | 0.03 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 46 | 0.22951 | 0.13043 | 2021-02 | 0 | 0
211 | CR0013555 | CTASK0024913 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-03-31 17:19 | 2021-03-01 02:19 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Deployment] Asia - Opus_Portcast API Connection - Add Dominant Flag to the conditions (Ref: CR0011895) | 2021-02-03 09:11 | 2021-02-25 | 2021-02-22 15:21 | 2021-02-23 14:33 | 2021-02-23 15:40 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-02-23 15:52 | 2021-04-08 14:00 | CR0013555 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W10 | 2021-03 | 21 | 21 | 34.034 | 4 | 1 | 1 | 0.03 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 46 | 0.22951 | 0.13043 | 2021-02 | 0 | 0
212 | CR0013555 | CTASK0024911 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-02-26 17:18 | 2021-02-01 17:18 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Testing] Asia - Opus_Portcast API Connection - Add Dominant Flag to the conditions (Ref: CR0011895) | 2021-02-03 09:11 | 2021-02-25 | 2021-02-22 15:21 | 2021-02-23 14:33 | 2021-02-23 15:40 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-02-23 15:52 | 2021-04-08 14:00 | CR0013555 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W10 | 2021-03 | 21 | 21 | 34.034 | 4 | 1 | 1 | 0.03 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 46 | 0.22951 | 0.13043 | 2021-02 | 0 | 0
213 | CR0013477 | CTASK0025876 | Closed | OPUS-BKG-EBKG | Vinh Tran | 2 | 2 | 2021-03-16 02:00 | 2021-03-15 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] Remove "TAB" character in default "Reject Reason" in OPUS | 2021-03-25 13:14 | 2021-04-07 | 2021-04-05 15:20 | 2021-05-07 14:45 | 2021-05-07 15:22 |  | 2021-05-12 10:00 | 2021-05-12 10:00 | 2021-05-10 09:24 | 2021-06-12 14:00 | CR0013477 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W19 | 2021-05 | 22 | 18 | 47.865 | 4 | 2 | 2 | 0.02 | 193525 | 1.8 | 2 | 0 | 0 | 1 | 1 | 1 | 6 | 28 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
214 | CR0013477 | CTASK0025875 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] Remove "TAB" character in default "Reject Reason" in OPUS | 2021-03-25 13:14 | 2021-04-07 | 2021-04-05 15:20 | 2021-05-07 14:45 | 2021-05-07 15:22 |  | 2021-05-12 10:00 | 2021-05-12 10:00 | 2021-05-10 09:24 | 2021-06-12 14:00 | CR0013477 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W19 | 2021-05 | 22 | 18 | 47.865 | 4 | 2 | 2 | 0.02 | 193470 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 6 | 28 | 0.36842 | 0.11111 | 2021-03 | 0 | 0
215 | CR0013477 | CTASK0025878 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 12 | 8 | 2021-04-02 23:00 | 2021-03-25 10:30 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] Remove "TAB" character in default "Reject Reason" in OPUS | 2021-03-25 13:14 | 2021-04-07 | 2021-04-05 15:20 | 2021-05-07 14:45 | 2021-05-07 15:22 |  | 2021-05-12 10:00 | 2021-05-12 10:00 | 2021-05-10 09:24 | 2021-06-12 14:00 | CR0013477 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W19 | 2021-05 | 22 | 18 | 47.865 | 4 | 2 | 2 | 0.02 | 193470 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 6 | 28 | 0.36842 | 0.11111 | 2021-03 | 0 | 0
216 | CR0013477 | CTASK0025879 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2021-05-04 23:30 | 2021-05-07 10:30 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] Remove "TAB" character in default "Reject Reason" in OPUS | 2021-03-25 13:14 | 2021-04-07 | 2021-04-05 15:20 | 2021-05-07 14:45 | 2021-05-07 15:22 |  | 2021-05-12 10:00 | 2021-05-12 10:00 | 2021-05-10 09:24 | 2021-06-12 14:00 | CR0013477 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W19 | 2021-05 | 22 | 18 | 47.865 | 4 | 2 | 2 | 0.02 | 193470 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 6 | 28 | 0.36842 | 0.11111 | 2021-03 | 0 | 0
217 | CR0013569 | CTASK0025623 | Closed | OPUS-TPB | Manh Nguyen | 50 | 48 | 2021-04-01 01:00 | 2021-03-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [202103] Asia *TPB* Dynamic QR code on Invoices with effect 1st April 2021 (TPB) | 2021-02-24 17:24 | 2021-04-05 22:00 | 2021-04-05 15:07 | 2021-04-06 15:39 | 2021-04-08 12:14 |  | 2021-04-13 12:00 | 2021-04-13 11:30 | 2021-04-08 13:02 | 2021-04-19 11:06 | CR0013569 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W15 | 2021-04 | 102 | 83 | 47.7748 | 3 | 1 | 1 | 0.07 | 153138 | 2.4 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 27 | 0 | 0.16667 | 2021-02 | 0 | 0
218 | CR0013569 | CTASK0025056 | Closed | OPUS-TPB | Manh Nguyen | 15 | 15 | 2021-02-27 01:00 | 2021-02-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [202102] Asia *TPB* Dynamic QR code on Invoices with effect 1st April 2021 (TPB) | 2021-02-24 17:24 | 2021-04-05 22:00 | 2021-04-05 15:07 | 2021-04-06 15:39 | 2021-04-08 12:14 |  | 2021-04-13 12:00 | 2021-04-13 11:30 | 2021-04-08 13:02 | 2021-04-19 11:06 | CR0013569 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W15 | 2021-04 | 102 | 83 | 47.7748 | 3 | 1 | 1 | 0.07 | 153138 | 2.4 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 27 | 0 | 0.16667 | 2021-02 | 0 | 0
219 | CR0013569 | CTASK0026224 | Closed | OPUS-TPB | Manh Nguyen | 37 | 20 | 2021-05-01 01:00 | 2021-04-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [202104] Asia *TPB* Dynamic QR code on Invoices with effect 1st April 2021 (TPB) | 2021-02-24 17:24 | 2021-04-05 22:00 | 2021-04-05 15:07 | 2021-04-06 15:39 | 2021-04-08 12:14 |  | 2021-04-13 12:00 | 2021-04-13 11:30 | 2021-04-08 13:02 | 2021-04-19 11:06 | CR0013569 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W15 | 2021-04 | 102 | 83 | 47.7748 | 3 | 1 | 1 | 0.07 | 153138 | 2.4 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 27 | 0 | 0.16667 | 2021-02 | 0 | 0
220 | CR0010829 | CTASK0021956 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 4 | 4 | 2020-08-25 19:30 | 2020-08-19 11:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Deployment] *ESA-JPN* JP129 change OPUS to send Manifest (MFR/CMF) for Revenue Empty Container BLs | 2020-07-09 17:11 | 2020-07-18 | 2020-07-16 16:29 | 2020-08-18 17:12 | 2020-08-20 10:18 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-20 15:14 | 2020-09-24 13:00 | CR0010829 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2020-W35 | 2020-08 | 12 | 12 | 46.7009 | 2 | 1 | 1 | 0.01 | 173280 | 1.6 | 0 | 0 | 0 | 1 | 1 | 1 | 12 | 30 | 0 | 0.18519 | 2020-07 | 0 | 0
221 | CR0010829 | CTASK0021116 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 8 | 8 | 2020-07-10 19:30 | 2020-07-01 11:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Development + Deployment + Testing] *ESA-JPN* JP129 change OPUS to send Manifest (MFR/CMF) for Revenue Empty Container BLs | 2020-07-09 17:11 | 2020-07-18 | 2020-07-16 16:29 | 2020-08-18 17:12 | 2020-08-20 10:18 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-20 15:14 | 2020-09-24 13:00 | CR0010829 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2020-W35 | 2020-08 | 12 | 12 | 46.7009 | 2 | 1 | 1 | 0.01 | 173280 | 1.6 | 0 | 0 | 0 | 1 | 1 | 1 | 12 | 30 | 0 | 0.18519 | 2020-07 | 0 | 0
222 | CR0012243 | CTASK0019891 | Closed | OPUS-DOM | Giang Nguyen Hoang | 10 | 10 | 2020-05-22 16:57 | 2020-04-28 16:57 | DOM Web Portal | IMC | EQ Match | Booking Activity |  |  | NA*DOM*Domestic Portal* Request to reactivate booking if status is expired and CP event is received for container against the booking | 2020-04-28 17:18 | 2020-06-30 21:00 | 2020-06-19 15:36 | 2020-07-14 22:27 | 2020-07-24 09:25 |  | 2020-08-04 11:00 | 2020-08-04 11:00 | 2020-07-24 22:34 | 2020-09-04 13:00 | CR0012243 | IMCEQ MatchBooking Activity | OPUS-DOM | 2020-W32 | 2020-08 | 19 | 20 | 97.7374 | 2 | 1 | 2 | 0.01 | 183440 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0 | 2020-04 | 0 | 0
223 | CR0012243 | CTASK0019890 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 9 | 10 | 2020-05-22 16:56 | 2020-04-28 16:56 | DOM Web Portal | IMC | EQ Match | Booking Activity |  |  | NA*DOM*Domestic Portal* Request to reactivate booking if status is expired and CP event is received for container against the booking | 2020-04-28 17:18 | 2020-06-30 21:00 | 2020-06-19 15:36 | 2020-07-14 22:27 | 2020-07-24 09:25 |  | 2020-08-04 11:00 | 2020-08-04 11:00 | 2020-07-24 22:34 | 2020-09-04 13:00 | CR0012243 | IMCEQ MatchBooking Activity | OPUS-DOM | 2020-W32 | 2020-08 | 19 | 20 | 97.7374 | 2 | 1 | 2 | 0.01 | 183432 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0 | 2020-04 | 0 | 0
224 | CR0013396 | CTASK0024175 | Closed | OPUS-BKG-CHG | Nam Nguyen | 6 | 6 | 2020-12-16 20:46 | 2020-12-14 20:46 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [CLT Internal] to enhance the auto-rating popup for stability of surcharge rating | 2021-01-06 11:54 | 2021-01-28 | 2021-01-27 13:58 | 2021-02-18 09:24 | 2021-02-18 11:53 |  | 2021-03-09 10:00 | 2021-03-09 09:40 | 2021-03-03 18:16 | 2021-04-08 14:00 | CR0013396 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W10 | 2021-03 | 50 | 50 | 61.9209 | 2 | 1 | 1 | 0.03 | 123048 | 2.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 46 | 0 | 0.047619 | 2021-01 | 0 | 0
225 | CR0013396 | CTASK0024176 | Closed | OPUS-BKG-CHG | Nam Nguyen | 44 | 44 | 2021-01-15 20:31 | 2021-01-04 20:31 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [CLT Internal] to enhance the auto-rating popup for stability of surcharge rating | 2021-01-06 11:54 | 2021-01-28 | 2021-01-27 13:58 | 2021-02-18 09:24 | 2021-02-18 11:53 |  | 2021-03-09 10:00 | 2021-03-09 09:40 | 2021-03-03 18:16 | 2021-04-08 14:00 | CR0013396 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W10 | 2021-03 | 50 | 50 | 61.9209 | 2 | 1 | 1 | 0.03 | 123048 | 2.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 46 | 0 | 0.047619 | 2021-01 | 0 | 0
226 | CR0012712 | CTASK0021317 | Closed | OPUS-SCO | Chuong Ta | 10 | 10 | 2020-08-31 10:02 | 2020-08-01 10:02 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [August][Chuong Ta] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 183379 | 1.4 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 0.38462 | 2020-08 | 9 | 1
227 | CR0012712 | CTASK0021360 | Closed | OPUS-SCO | Hang To | 60 | 60 | 2020-10-01 09:25 | 2020-09-01 09:25 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [September][Hang] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 183344 | 1.3 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 2.4286 | 2020-08 | 9 | 1
228 | CR0012712 | CTASK0021361 | Closed | OPUS-SCO | Hang To | 1 | 1 | 2020-10-31 09:26 | 2020-10-01 09:26 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [October][Hang] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 183344 | 1.3 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 2.4286 | 2020-08 | 9 | 1
229 | CR0012712 | CTASK0021363 | Closed | OPUS-SCO | Mohamed Hary | 1 | 1 | 2020-10-31 09:28 | 2020-10-01 09:28 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [October][Hary Mohamed] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 193489 | 1.2 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 0.63636 | 2020-08 | 9 | 1
230 | CR0012712 | CTASK0021107 | Closed | OPUS-SCO | Hang To | 84 | 81 | 2020-07-31 16:20 | 2020-07-08 16:20 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [July][Hang] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 183344 | 1.3 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 2.4286 | 2020-08 | 9 | 1
231 | CR0012712 | CTASK0021314 | Closed | OPUS-SCO | Mohamed Hary | 20 | 20 | 2020-08-31 09:57 | 2020-08-01 09:57 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [August][Hary Mohamed] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 193489 | 1.2 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 0.63636 | 2020-08 | 9 | 1
232 | CR0012712 | CTASK0021364 | Closed | OPUS-SCO | Dinh Cong Tuan | 60 | 60 | 2020-09-30 09:30 | 2020-09-01 09:30 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [September][Tuan Dinh] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 193510 | 1.2 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 0 | 2020-08 | 9 | 1
233 | CR0012712 | CTASK0021359 | Closed | OPUS-SCO | Hang To | 70 | 69 | 2020-08-31 09:24 | 2020-08-01 09:24 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [August][Hang] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 183344 | 1.3 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 2.4286 | 2020-08 | 9 | 1
234 | CR0012712 | CTASK0021315 | Closed | OPUS-SCO | Dinh Cong Tuan | 20 | 20 | 2020-08-31 10:00 | 2020-08-01 10:00 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [August][Tuan Dinh] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 193510 | 1.2 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 0 | 2020-08 | 9 | 1
235 | CR0012712 | CTASK0021318 | Closed | OPUS-SCO | Lien Le | 14 | 14 | 2020-08-31 10:03 | 2020-08-01 10:03 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [August][Lien Le] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 193441 | 1.4 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 1.2222 | 2020-08 | 9 | 1
236 | CR0012712 | CTASK0021365 | Closed | OPUS-SCO | Dinh Cong Tuan | 1 | 1 | 2020-10-31 09:31 | 2020-10-01 09:31 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [October][Tuan Dinh] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 193510 | 1.2 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 0 | 2020-08 | 9 | 1
237 | CR0012712 | CTASK0021362 | Closed | OPUS-SCO | Mohamed Hary | 40 | 40 | 2020-09-30 09:28 | 2020-09-01 09:28 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Dispute Management |  | [September][Hary Mohamed] EUA - Dispute Management Improvements [CR1] | 2020-08-20 16:41 | 2020-09-30 16:40 | 2020-09-17 21:46 | 2020-12-23 10:13 | 2020-12-23 10:41 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:47 | 2021-01-19 20:47 | CR0012712 | Statement ManagementStatement Account ReceivableDispute ManagerDispute Management | OPUS-SAR | 2020-W53 | 2020-12 | 378 | 374 | 129.7217 | 12 | 1 | 5 | 0.12 | 193489 | 1.2 | 1 | 9 | 0 | 4 | 2 | 2 | 9 | 30 | 0 | 0.63636 | 2020-08 | 9 | 1
238 | CR0011435 | CTASK0016964 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 126 | 59 | 2019-12-16 13:00 | 2019-10-31 15:30 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | (SAS_AU) Cargo release : We require a copy of the EU Cargo Release D/O menu for use in AU so that Electronic Delivery orders can be emailed to customers | 2019-12-09 16:07 | 2020-01-03 13:12 | 2020-01-02 11:03 | 2020-02-03 14:50 | 2020-02-04 15:59 |  | 2020-02-11 10:59 | 2020-02-11 17:47 | 2020-02-04 16:02 | 2020-02-17 11:32 | CR0011435 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2020-W7 | 2020-02 | 138 | 71 | 63.7858 | 2 | 1 | 1 | 0.05 | 173280 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 13 | 0 | 0 | 2019-12 | 0 | 0
239 | CR0011435 | CTASK0018245 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 12 | 12 |  |  | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | (SAS_AU) Cargo release : We require a copy of the EU Cargo Release D/O menu for use in AU so that Electronic Delivery orders can be emailed to customers | 2019-12-09 16:07 | 2020-01-03 13:12 | 2020-01-02 11:03 | 2020-02-03 14:50 | 2020-02-04 15:59 |  | 2020-02-11 10:59 | 2020-02-11 17:47 | 2020-02-04 16:02 | 2020-02-17 11:32 | CR0011435 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2020-W7 | 2020-02 | 138 | 71 | 63.7858 | 2 | 1 | 1 | 0.05 | 173280 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 13 | 0 | 0 | 2019-12 | 0 | 0
240 | CR0012090 | CTASK0019188 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 36 | 36 | 2020-04-25 12:33 | 2020-04-14 12:33 | Container | Service Management | Booking/Documentation | Booking | Booking | Container Information [Alt+4] | [Development/Testing] NA-Booking/Doc-Create COP Comment/history visibility in Booking Creation/Inquiry and Inbound CS USA/Inbound CS -Phase 2 of CR0011520 | 2020-03-30 17:15 | 2020-04-30 17:15 | 2020-04-27 15:03 | 2020-06-02 15:32 | 2020-06-05 11:36 |  | 2020-06-16 11:35 | 2020-06-16 09:52 | 2020-06-05 23:53 | 2020-07-16 13:00 | CR0012090 | Service ManagementBooking/DocumentationBookingBookingContainer Information [Alt+4] | OPUS-BKG-OB | 2020-W25 | 2020-06 | 102 | 101 | 77.764 | 6 | 2 | 2 | 0.05 | 193506 | 0.8 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 29 | 0 | 0.85714 | 2020-03 | 0 | 0
241 | CR0012090 | CTASK0020655 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 6 | 6 | 2020-06-16 19:09 | 2020-06-15 19:09 | Container | Service Management | Booking/Documentation | Booking | Booking | Container Information [Alt+4] | [Deployment] NA-Booking/Doc-Create COP Comment/history visibility in Booking Creation/Inquiry and Inbound CS USA/Inbound CS -Phase 2 of CR0011520 | 2020-03-30 17:15 | 2020-04-30 17:15 | 2020-04-27 15:03 | 2020-06-02 15:32 | 2020-06-05 11:36 |  | 2020-06-16 11:35 | 2020-06-16 09:52 | 2020-06-05 23:53 | 2020-07-16 13:00 | CR0012090 | Service ManagementBooking/DocumentationBookingBookingContainer Information [Alt+4] | OPUS-BKG-OB | 2020-W25 | 2020-06 | 102 | 101 | 77.764 | 6 | 2 | 2 | 0.05 | 193506 | 0.8 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 29 | 0 | 0.85714 | 2020-03 | 0 | 0
242 | CR0012090 | CTASK0019169 | Closed | OPUS-BKG-OB | Nam Nguyen | 38 | 37 | 2020-04-17 15:33 | 2020-03-31 15:33 | Container | Service Management | Booking/Documentation | Booking | Booking | Container Information [Alt+4] | [Development & Testing] NA-Booking/Doc-Create COP Comment/history visibility in Booking Creation/Inquiry and Inbound CS USA/Inbound CS -Phase 2 of CR0011520 | 2020-03-30 17:15 | 2020-04-30 17:15 | 2020-04-27 15:03 | 2020-06-02 15:32 | 2020-06-05 11:36 |  | 2020-06-16 11:35 | 2020-06-16 09:52 | 2020-06-05 23:53 | 2020-07-16 13:00 | CR0012090 | Service ManagementBooking/DocumentationBookingBookingContainer Information [Alt+4] | OPUS-BKG-OB | 2020-W25 | 2020-06 | 102 | 101 | 77.764 | 6 | 2 | 2 | 0.05 | 123048 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 29 | 0 | 0.46154 | 2020-03 | 0 | 0
243 | CR0012090 | CTASK0019135 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 4 | 4 | 2020-03-26 15:17 | 2020-03-20 15:17 | Container | Service Management | Booking/Documentation | Booking | Booking | Container Information [Alt+4] | [Analysis] NA-Booking/Doc-Create COP Comment/history visibility in Booking Creation/Inquiry and Inbound CS USA/Inbound CS -Phase 2 of CR0011520 | 2020-03-30 17:15 | 2020-04-30 17:15 | 2020-04-27 15:03 | 2020-06-02 15:32 | 2020-06-05 11:36 |  | 2020-06-16 11:35 | 2020-06-16 09:52 | 2020-06-05 23:53 | 2020-07-16 13:00 | CR0012090 | Service ManagementBooking/DocumentationBookingBookingContainer Information [Alt+4] | OPUS-BKG-OB | 2020-W25 | 2020-06 | 102 | 101 | 77.764 | 6 | 2 | 2 | 0.05 | 193506 | 0.8 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 29 | 0 | 0.85714 | 2020-03 | 0 | 0
244 | CR0012090 | CTASK0019119 | Closed | OPUS-BKG-OB | Nam Nguyen | 12 | 12 | 2020-03-24 19:32 | 2020-03-23 19:32 | Container | Service Management | Booking/Documentation | Booking | Booking | Container Information [Alt+4] | [Analysis] NA-Booking/Doc-Create COP Comment/history visibility in Booking Creation/Inquiry and Inbound CS USA/Inbound CS -Phase 2 of CR0011520 | 2020-03-30 17:15 | 2020-04-30 17:15 | 2020-04-27 15:03 | 2020-06-02 15:32 | 2020-06-05 11:36 |  | 2020-06-16 11:35 | 2020-06-16 09:52 | 2020-06-05 23:53 | 2020-07-16 13:00 | CR0012090 | Service ManagementBooking/DocumentationBookingBookingContainer Information [Alt+4] | OPUS-BKG-OB | 2020-W25 | 2020-06 | 102 | 101 | 77.764 | 6 | 2 | 2 | 0.05 | 123048 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 29 | 0 | 0.46154 | 2020-03 | 0 | 0
245 | CR0012090 | CTASK0019170 | Closed | OPUS-BKG-OB | Nam Nguyen | 6 | 6 | 2020-06-08 18:08 | 2020-06-05 18:08 | Container | Service Management | Booking/Documentation | Booking | Booking | Container Information [Alt+4] | [Deployment] NA-Booking/Doc-Create COP Comment/history visibility in Booking Creation/Inquiry and Inbound CS USA/Inbound CS -Phase 2 of CR0011520 | 2020-03-30 17:15 | 2020-04-30 17:15 | 2020-04-27 15:03 | 2020-06-02 15:32 | 2020-06-05 11:36 |  | 2020-06-16 11:35 | 2020-06-16 09:52 | 2020-06-05 23:53 | 2020-07-16 13:00 | CR0012090 | Service ManagementBooking/DocumentationBookingBookingContainer Information [Alt+4] | OPUS-BKG-OB | 2020-W25 | 2020-06 | 102 | 101 | 77.764 | 6 | 2 | 2 | 0.05 | 123048 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 29 | 0 | 0.46154 | 2020-03 | 0 | 0
246 | CR0013528 | CTASK0025530 | Closed | OPUS-FLT | Tran Anh Duy | 20 | 20 | 2021-02-12 13:43 | 2021-01-29 13:43 | Container | Support & Admin | Fleet Management | Slip | Monthly Hire Accrual |  | [CLT-PC] Development FLT screen to trace the outstanding contract | 2021-02-17 12:56 | 2021-03-03 20:00 | 2021-03-03 11:09 | 2021-07-26 18:15 | 2021-07-27 10:37 |  | 2021-08-03 09:00 | 2021-08-03 09:00 | 2021-07-30 10:32 | 2021-08-10 14:00 | CR0013528 | Support & AdminFleet ManagementSlipMonthly Hire Accrual | OPUS-FLT | 2021-W31 | 2021-08 | 40 | 40 | 166.8364 | 3 | 1 | 2 | 0.01 | 193516 | 1.9 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 22 | 0 | 0 | 2021-02 | 0 | 0
247 | CR0013528 | CTASK0024805 | Closed | OPUS-FLT | Hieu Vu | 20 | 20 | 2021-02-12 13:43 | 2021-01-29 13:43 | Container | Support & Admin | Fleet Management | Slip | Monthly Hire Accrual |  | [CLT-PC] Development FLT screen to trace the outstanding contract | 2021-02-17 12:56 | 2021-03-03 20:00 | 2021-03-03 11:09 | 2021-07-26 18:15 | 2021-07-27 10:37 |  | 2021-08-03 09:00 | 2021-08-03 09:00 | 2021-07-30 10:32 | 2021-08-10 14:00 | CR0013528 | Support & AdminFleet ManagementSlipMonthly Hire Accrual | OPUS-FLT | 2021-W31 | 2021-08 | 40 | 40 | 166.8364 | 3 | 1 | 2 | 0.01 | 183375 | 2.4 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 22 | 0.076923 | 0 | 2021-02 | 0 | 0
248 | CR0013528 | CTASK0024807 | Closed | OPUS-FLT | Tran Anh Duy | 1 | 1 |  |  | Container | Support & Admin | Fleet Management | Slip | Monthly Hire Accrual |  | [Documentation] Development FLT screen to trace the outstanding contract | 2021-02-17 12:56 | 2021-03-03 20:00 | 2021-03-03 11:09 | 2021-07-26 18:15 | 2021-07-27 10:37 |  | 2021-08-03 09:00 | 2021-08-03 09:00 | 2021-07-30 10:32 | 2021-08-10 14:00 | CR0013528 | Support & AdminFleet ManagementSlipMonthly Hire Accrual | OPUS-FLT | 2021-W31 | 2021-08 | 40 | 40 | 166.8364 | 3 | 1 | 2 | 0.01 | 193516 | 1.9 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 22 | 0 | 0 | 2021-02 | 0 | 0
249 | CR0012497 | CTASK0019417 | Closed | OPUS-SCG | Pham Khanh Van | 60 | 60 |  |  | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | [CLV] Change MSC EDI Logic in Opus | 2020-04-08 16:59 | 2020-04-10 16:59 | 2020-04-09 09:24 | 2020-05-13 17:40 | 2020-05-13 17:49 |  | 2020-05-19 09:30 | 2020-05-19 09:41 | 2020-05-15 13:40 | 2020-06-20 13:00 | CR0012497 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2020-W21 | 2020-05 | 60 | 60 | 40.688 | 1 | 1 | 1 | 0.06 | 193477 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 26 | 0 | 0 | 2020-04 | 0 | 0
250 | CR0011770 | CTASK0016795 | Closed | OPUS-BKG-M | Thien Lai | 28 | 32 | 2019-11-22 16:55 | 2019-11-11 16:55 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | NA *Standby* Add Escalation Date to Date type drop down menu in Standby Booking Status Report Screen | 2019-11-06 10:50 | 2019-12-03 | 2019-11-18 16:27 | 2019-11-28 06:41 | 2019-11-28 12:47 | 2019-11-18 16:28 | 2019-12-10 12:47 | 2019-12-10 09:30 | 2019-12-03 01:01 | 2019-12-16 23:44 | CR0011770 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2019-W50 | 2019-12 | 38 | 32 | 34.081 | 2 | 1 | 1 | 0.04 | 193567 | 0.3 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 18 | 0 | 0.52941 | 2019-11 | 0 | 0
251 | CR0011770 | CTASK0016774 | Closed | OPUS-BKG-M | Thien Lai | 10 | 10 |  |  | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Estimated] NA *Standby* Add Escalation Date to Date type drop down menu in Standby Booking Status Report Screen | 2019-11-06 10:50 | 2019-12-03 | 2019-11-18 16:27 | 2019-11-28 06:41 | 2019-11-28 12:47 | 2019-11-18 16:28 | 2019-12-10 12:47 | 2019-12-10 09:30 | 2019-12-03 01:01 | 2019-12-16 23:44 | CR0011770 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2019-W50 | 2019-12 | 38 | 32 | 34.081 | 2 | 1 | 1 | 0.04 | 193567 | 0.3 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 18 | 0 | 0.52941 | 2019-11 | 0 | 0
252 | CR0012528 | CTASK0019641 | Closed | OPUS-BKG-M | Loc Tran | 7 | 6 | 2020-05-16 02:00 | 2020-05-07 19:44 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] AS - OPUS Container - Add validation to check Receiver ID before sending a 301 EDI | 2020-05-07 13:15 | 2020-06-25 | 2020-06-18 03:57 | 2020-06-22 18:15 | 2020-07-30 09:25 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:26 | 2020-08-04 12:36 | CR0012528 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W32 | 2020-08 | 30 | 33 | 88.8649 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.36364 | 2020-05 | 0 | 0
253 | CR0012528 | CTASK0019600 | Closed | OPUS-BKG-M | Loc Tran | 15 | 15 | 2020-04-18 02:00 | 2020-04-14 10:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] AS - OPUS Container - Add validation to check Receiver ID before sending a 301 EDI | 2020-05-07 13:15 | 2020-06-25 | 2020-06-18 03:57 | 2020-06-22 18:15 | 2020-07-30 09:25 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:26 | 2020-08-04 12:36 | CR0012528 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W32 | 2020-08 | 30 | 33 | 88.8649 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.36364 | 2020-05 | 0 | 0
254 | CR0012528 | CTASK0019638 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-05-16 02:00 | 2020-05-07 15:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] AS - OPUS Container - Add validation to check Receiver ID before sending a 301 EDI | 2020-05-07 13:15 | 2020-06-25 | 2020-06-18 03:57 | 2020-06-22 18:15 | 2020-07-30 09:25 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:26 | 2020-08-04 12:36 | CR0012528 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W32 | 2020-08 | 30 | 33 | 88.8649 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.36364 | 2020-05 | 0 | 0
255 | CR0012528 | CTASK0020482 | Closed | OPUS-BKG-M | Loc Tran | 2 | 2 | 2020-06-05 19:24 | 2020-06-01 19:24 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] AS - OPUS Container - Add validation to check Receiver ID before sending a 301 EDI | 2020-05-07 13:15 | 2020-06-25 | 2020-06-18 03:57 | 2020-06-22 18:15 | 2020-07-30 09:25 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:26 | 2020-08-04 12:36 | CR0012528 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W32 | 2020-08 | 30 | 33 | 88.8649 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.36364 | 2020-05 | 0 | 0
256 | CR0012528 | CTASK0019643 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2020-08-31 18:45 | 2020-08-01 18:45 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] AS - OPUS Container - Add validation to check Receiver ID before sending a 301 EDI | 2020-05-07 13:15 | 2020-06-25 | 2020-06-18 03:57 | 2020-06-22 18:15 | 2020-07-30 09:25 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:26 | 2020-08-04 12:36 | CR0012528 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W32 | 2020-08 | 30 | 33 | 88.8649 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.36364 | 2020-05 | 0 | 0
257 | CR0013753 | CTASK0026053 | Closed | OPUS-SCG | Lanh Le | 8 | 11 | 2021-04-07 11:06 | 2021-03-23 11:06 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [Documentation][CLT Internal] Enhancement to enables cancellation through EDI for VVD that have already been canceled | 2021-03-24 13:17 | 2021-04-07 19:30 | 2021-04-06 09:14 | 2021-04-14 10:15 | 2021-04-15 13:08 |  | 2021-04-27 10:08 | 2021-04-27 11:21 | 2021-04-19 16:28 | 2021-05-27 14:00 | CR0013753 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W17 | 2021-04 | 27 | 29 | 33.8681 | 3 | 1 | 2 | 0.04 | 183422 | 2.4 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0 | 0 | 2021-03 | 0 | 0
258 | CR0013753 | CTASK0026055 | Closed | OPUS-SCG | Tu Nguyen | 9 | 8 | 2021-04-06 11:08 | 2021-04-01 11:08 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [CLV][CLT Internal] Enhancement to enables cancellation through EDI for VVD that have already been canceled | 2021-03-24 13:17 | 2021-04-07 19:30 | 2021-04-06 09:14 | 2021-04-14 10:15 | 2021-04-15 13:08 |  | 2021-04-27 10:08 | 2021-04-27 11:21 | 2021-04-19 16:28 | 2021-05-27 14:00 | CR0013753 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W17 | 2021-04 | 27 | 29 | 33.8681 | 3 | 1 | 2 | 0.04 | 123045 | 2.5 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0 | 0 | 2021-03 | 0 | 0
259 | CR0013753 | CTASK0026054 | Closed | OPUS-SCG | Lanh Le | 10 | 10 | 2021-04-02 11:08 | 2021-03-25 11:08 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [CLV][CLT Internal] Enhancement to enables cancellation through EDI for VVD that have already been canceled | 2021-03-24 13:17 | 2021-04-07 19:30 | 2021-04-06 09:14 | 2021-04-14 10:15 | 2021-04-15 13:08 |  | 2021-04-27 10:08 | 2021-04-27 11:21 | 2021-04-19 16:28 | 2021-05-27 14:00 | CR0013753 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W17 | 2021-04 | 27 | 29 | 33.8681 | 3 | 1 | 2 | 0.04 | 183422 | 2.4 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0 | 0 | 2021-03 | 0 | 0
260 | CR0012353 | CTASK0018803 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 12 | 12 | 2020-03-26 12:00 | 2020-03-09 09:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [CLT Internal] NA *DOC* Inquiry on pop-up received when Issuing Received For Shipment BL | 2020-03-11 15:39 | 2020-03-18 | 2020-03-16 15:38 | 2020-03-20 11:00 | 2020-03-20 11:36 |  | 2020-03-31 10:00 | 2020-03-31 10:00 | 2020-03-25 16:30 | 2020-04-30 13:00 | CR0012353 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W14 | 2020-03 | 12 | 12 | 19.7649 | 1 | 1 | 1 | 0.03 | 193512 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 25 | 0 | 0.5 | 2020-03 | 0 | 0
261 | CR0011261 | CTASK0012671 | Closed | OPUS-MGS | Tien Le | 58 | 44 | 2019-04-24 16:24 | 2019-04-12 16:24 | [6 empty] | [CHS]Chrome v74 patch & CLP(Common Library Patch) v4.4 | 2019-04-22 12:59 | 2019-04-26 12:59 | 2019-04-23 09:50 | 2019-04-24 14:33 | 2019-04-24 14:35 |  | 2019-04-26 10:00 | 2019-04-25 18:00 | 2019-04-26 18:00 | 2019-05-27 13:07 | CR0011261 |  | OPUS-MGS | 2019-W17 | 2019-04 | 268 | 108 | 3.8754 | 7 | 5 | 5 | 1.16 | 173286 | 0.6 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
262 | CR0011261 | CTASK0012684 | Closed | OPUS-PRI | Nhien Nguyen | 20 | 20 | 2019-04-23 19:03 | 2019-04-15 19:03 | [6 empty] | [PRI] Chrome74v & CLP 4.4 TEST | 2019-04-22 12:59 | 2019-04-26 12:59 | 2019-04-23 09:50 | 2019-04-24 14:33 | 2019-04-24 14:35 |  | 2019-04-26 10:00 | 2019-04-25 18:00 | 2019-04-26 18:00 | 2019-05-27 13:07 | CR0011261 |  | OPUS-PRI | 2019-W17 | 2019-04 | 268 | 108 | 3.8754 | 7 | 5 | 5 | 1.16 | 183364 | 0.6 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
263 | CR0011261 | CTASK0012669 | Closed | OPUS-MGS | Tuyen Truong | 30 | 44 | 2019-04-24 16:19 | 2019-04-12 16:19 | [6 empty] | [MGS]Chrome v74 patch & CLP(Common Library Patch) v4.4 | 2019-04-22 12:59 | 2019-04-26 12:59 | 2019-04-23 09:50 | 2019-04-24 14:33 | 2019-04-24 14:35 |  | 2019-04-26 10:00 | 2019-04-25 18:00 | 2019-04-26 18:00 | 2019-05-27 13:07 | CR0011261 |  | OPUS-MGS | 2019-W17 | 2019-04 | 268 | 108 | 3.8754 | 7 | 5 | 5 | 1.16 | 173255 | 0.6 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
264 | CR0011261 | CTASK0012708 | Closed | OPUS-BKG-RPT | Nhan Le | 40 | 40 | [8 empty] | [BKG-RPT] Chrome74v & CLP 4.4 TEST | 2019-04-22 12:59 | 2019-04-26 12:59 | 2019-04-23 09:50 | 2019-04-24 14:33 | 2019-04-24 14:35 |  | 2019-04-26 10:00 | 2019-04-25 18:00 | 2019-04-26 18:00 | 2019-05-27 13:07 | CR0011261 |  | OPUS-BKG-RPT | 2019-W17 | 2019-04 | 268 | 108 | 3.8754 | 7 | 5 | 5 | 1.16 | 183353 | 0.6 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
265 | CR0011261 | CTASK0012703 | Closed | OPUS-BKG-M | Kieu Le | 40 | 40 | [8 empty] | [BKG-M] Chrome74v & CLP 4.4 TEST | 2019-04-22 12:59 | 2019-04-26 12:59 | 2019-04-23 09:50 | 2019-04-24 14:33 | 2019-04-24 14:35 |  | 2019-04-26 10:00 | 2019-04-25 18:00 | 2019-04-26 18:00 | 2019-05-27 13:07 | CR0011261 |  | OPUS-BKG-M | 2019-W17 | 2019-04 | 268 | 108 | 3.8754 | 7 | 5 | 5 | 1.16 | 153106 | 0.6 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
266 | CR0011261 | CTASK0012734 | Closed | OPUS-BKG-OB | Nhan Le | 40 | 40 | [8 empty] | [BKG-OPT] Chrome74v & CLP 4.4 TEST | 2019-04-22 12:59 | 2019-04-26 12:59 | 2019-04-23 09:50 | 2019-04-24 14:33 | 2019-04-24 14:35 |  | 2019-04-26 10:00 | 2019-04-25 18:00 | 2019-04-26 18:00 | 2019-05-27 13:07 | CR0011261 |  | OPUS-BKG-OB | 2019-W17 | 2019-04 | 268 | 108 | 3.8754 | 7 | 5 | 5 | 1.16 | 183353 | 0.6 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
267 | CR0011261 | CTASK0012707 | Closed | OPUS-BKG-OB | Kieu Le | 40 | 40 | [8 empty] | [BKG-OB] Chrome74v & CLP 4.4 TEST | 2019-04-22 12:59 | 2019-04-26 12:59 | 2019-04-23 09:50 | 2019-04-24 14:33 | 2019-04-24 14:35 |  | 2019-04-26 10:00 | 2019-04-25 18:00 | 2019-04-26 18:00 | 2019-05-27 13:07 | CR0011261 |  | OPUS-BKG-OB | 2019-W17 | 2019-04 | 268 | 108 | 3.8754 | 7 | 5 | 5 | 1.16 | 153106 | 0.6 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
268 | CR0012986 | CTASK0022355 | Closed | OPUS-MGS | Tuyen Truong | 24 | 24 | 2021-03-12 23:00 | 2021-02-01 09:00 | Container | Equipment Management | M.G. Set | Inventory | General Inventory |  | [Documentation] NA * MGS* General Inventory - Add Remarks Column in the 'General Inventory' Screen | 2021-02-18 10:51 | 2021-03-06 01:00 | 2021-03-05 19:55 | 2021-03-16 09:27 | 2021-03-17 16:13 |  | 2021-03-30 10:30 | 2021-03-30 10:30 | 2021-03-18 10:45 | 2021-04-29 14:00 | CR0012986 | Equipment ManagementM.G. SetInventoryGeneral Inventory | OPUS-MGS | 2021-W13 | 2021-03 | 95 | 88 | 39.9855 | 2 | 1 | 2 | 0.09 | 173255 | 2.4 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0 | 0 | 2021-02 | 0 | 0
269 | CR0012986 | CTASK0022359 | Closed | OPUS-MGS | Tien Le | 71 | 64 | 2021-03-12 23:00 | 2021-02-01 09:00 | Container | Equipment Management | M.G. Set | Inventory | General Inventory |  | NA * MGS* General Inventory - Add Remarks Column in the 'General Inventory' Screen | 2021-02-18 10:51 | 2021-03-06 01:00 | 2021-03-05 19:55 | 2021-03-16 09:27 | 2021-03-17 16:13 |  | 2021-03-30 10:30 | 2021-03-30 10:30 | 2021-03-18 10:45 | 2021-04-29 14:00 | CR0012986 | Equipment ManagementM.G. SetInventoryGeneral Inventory | OPUS-MGS | 2021-W13 | 2021-03 | 95 | 88 | 39.9855 | 2 | 1 | 2 | 0.09 | 173286 | 2.4 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0 | 0 | 2021-02 | 0 | 0
270 | CR0013706 | CTASK0026050 | Closed | OPUS-CHS | Tuyen Truong | 47 | 60 | 2021-04-17 01:00 | 2021-04-01 10:00 | Container | Equipment Management | Chassis | Movement | General Chassis Movement Inquiry |  | [CLT Internal] Performance Improvement on batch job for EDI:CHSHIP | 2021-06-09 13:45 | 2021-06-11 01:00 | 2021-06-09 15:41 | 2021-06-23 17:25 | 2021-06-23 17:48 |  | 2021-06-29 11:00 | 2021-06-29 11:00 | 2021-06-24 13:07 | 2021-07-29 14:00 | CR0013706 | Equipment ManagementChassisMovementGeneral Chassis Movement Inquiry | OPUS-CHS | 2021-W26 | 2021-06 | 67 | 80 | 19.8852 | 2 | 1 | 1 | 0.17 | 173255 | 2.7 | 0 | 0 | 0 | 1 | 1 | 1 | 16 | 53 | 0 | 0 | 2021-06 | 0 | 0
271 | CR0013706 | CTASK0026048 | Closed | OPUS-CHS | Tuyen Truong | 20 | 20 | 2021-04-01 01:59 | 2021-03-23 10:00 | Container | Equipment Management | Chassis | Movement | General Chassis Movement Inquiry |  | [Documentation][CLT Internal] Performance Improvement on batch job for EDI:CHSHIP | 2021-06-09 13:45 | 2021-06-11 01:00 | 2021-06-09 15:41 | 2021-06-23 17:25 | 2021-06-23 17:48 |  | 2021-06-29 11:00 | 2021-06-29 11:00 | 2021-06-24 13:07 | 2021-07-29 14:00 | CR0013706 | Equipment ManagementChassisMovementGeneral Chassis Movement Inquiry | OPUS-CHS | 2021-W26 | 2021-06 | 67 | 80 | 19.8852 | 2 | 1 | 1 | 0.17 | 173255 | 2.7 | 0 | 0 | 0 | 1 | 1 | 1 | 16 | 53 | 0 | 0 | 2021-06 | 0 | 0
272 | CR0013445 | CTASK0024623 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-01-29 15:57 | 2021-01-12 15:57 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] Enable 'Firm Standby Status' in Standby Status Report for EUA | 2021-01-15 08:59 | 2021-02-11 02:00 | 2021-02-02 13:23 | 2021-02-10 14:15 | 2021-02-10 14:41 |  | 2021-03-09 19:00 | 2021-03-09 10:00 | 2021-02-18 15:23 | 2021-04-08 14:00 | CR0013445 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W10 | 2021-03 | 34 | 34 | 53.4175 | 5 | 1 | 1 | 0.03 | 153106 | 2.3 | 2 | 0 | 0 | 1 | 1 | 2 | 7 | 46 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
273 | CR0013445 | CTASK0024613 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-01-29 12:48 | 2021-01-11 12:48 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] Enable 'Firm Standby Status' in Standby Status Report for EUA | 2021-01-15 08:59 | 2021-02-11 02:00 | 2021-02-02 13:23 | 2021-02-10 14:15 | 2021-02-10 14:41 |  | 2021-03-09 19:00 | 2021-03-09 10:00 | 2021-02-18 15:23 | 2021-04-08 14:00 | CR0013445 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W10 | 2021-03 | 34 | 34 | 53.4175 | 5 | 1 | 1 | 0.03 | 153106 | 2.3 | 2 | 0 | 0 | 1 | 1 | 2 | 7 | 46 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
274 | CR0013445 | CTASK0024626 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-02-26 16:01 | 2021-02-01 16:01 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] Enable 'Firm Standby Status' in Standby Status Report for EUA | 2021-01-15 08:59 | 2021-02-11 02:00 | 2021-02-02 13:23 | 2021-02-10 14:15 | 2021-02-10 14:41 |  | 2021-03-09 19:00 | 2021-03-09 10:00 | 2021-02-18 15:23 | 2021-04-08 14:00 | CR0013445 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W10 | 2021-03 | 34 | 34 | 53.4175 | 5 | 1 | 1 | 0.03 | 153106 | 2.3 | 2 | 0 | 0 | 1 | 1 | 2 | 7 | 46 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
275 | CR0013445 | CTASK0024625 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-01-29 15:58 | 2021-01-12 15:58 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] Enable 'Firm Standby Status' in Standby Status Report for EUA | 2021-01-15 08:59 | 2021-02-11 02:00 | 2021-02-02 13:23 | 2021-02-10 14:15 | 2021-02-10 14:41 |  | 2021-03-09 19:00 | 2021-03-09 10:00 | 2021-02-18 15:23 | 2021-04-08 14:00 | CR0013445 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W10 | 2021-03 | 34 | 34 | 53.4175 | 5 | 1 | 1 | 0.03 | 153106 | 2.3 | 2 | 0 | 0 | 1 | 1 | 2 | 7 | 46 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
276 | CR0013445 | CTASK0024628 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-03-31 16:05 | 2021-03-01 02:05 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] Enable 'Firm Standby Status' in Standby Status Report for EUA | 2021-01-15 08:59 | 2021-02-11 02:00 | 2021-02-02 13:23 | 2021-02-10 14:15 | 2021-02-10 14:41 |  | 2021-03-09 19:00 | 2021-03-09 10:00 | 2021-02-18 15:23 | 2021-04-08 14:00 | CR0013445 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W10 | 2021-03 | 34 | 34 | 53.4175 | 5 | 1 | 1 | 0.03 | 153106 | 2.3 | 2 | 0 | 0 | 1 | 1 | 2 | 7 | 46 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
277 | CR0012804 | CTASK0023085 | Closed | OPUS-CTM | Tran Le | 4 | 4 |  |  | S/W | WAS |  |  |  |  | Weblogic Upgrade - CTM/DMT | 2020-07-27 09:12 | 2020-12-14 09:11 | 2020-12-10 10:29 |  | 2020-12-10 10:32 |  | 2020-11-22 10:32 | 2020-11-22 10:34 | 2020-12-10 10:33 | 2020-12-18 15:02 | CR0012804 | WAS | OPUS-CTM | 2020-W47 | 2020-11 | 88 | 98 | 118.0553 | 7 | 6 | 7 | 0.03 | 193501 | 0.8 | 0 | 0 | 0 | 1 | 3 | 2 | 6 | 16 | 0 | 0 | 2020-07 | 0 | 0
278 | CR0012804 | CTASK0023122 | Closed | OPUS-TES | Thai Nguyen | 14 | 30 |  |  | S/W | WAS |  |  |  |  | CR for Weblogic Upgrade. (TES/TPB) | 2020-07-27 09:12 | 2020-12-14 09:11 | 2020-12-10 10:29 |  | 2020-12-10 10:32 |  | 2020-11-22 10:32 | 2020-11-22 10:34 | 2020-12-10 10:33 | 2020-12-18 15:02 | CR0012804 | WAS | OPUS-TES | 2020-W47 | 2020-11 | 88 | 98 | 118.0553 | 7 | 6 | 7 | 0.03 | 173249 | 1.8 | 0 | 0 | 0 | 1 | 3 | 2 | 6 | 16 | 0 | 2 | 2020-07 | 0 | 0
279 | CR0012804 | CTASK0022722 | Closed | OPUS-PRI | Man Hoang | 18 | 18 | 2020-09-28 13:38 | 2020-09-24 13:37 | S/W | WAS |  |  |  |  | PROD, SCM Source compare - PRI | 2020-07-27 09:12 | 2020-12-14 09:11 | 2020-12-10 10:29 |  | 2020-12-10 10:32 |  | 2020-11-22 10:32 | 2020-11-22 10:34 | 2020-12-10 10:33 | 2020-12-18 15:02 | CR0012804 | WAS | OPUS-PRI | 2020-W47 | 2020-11 | 88 | 98 | 118.0553 | 7 | 6 | 7 | 0.03 | 183431 | 1.7 | 0 | 0 | 0 | 1 | 3 | 2 | 6 | 16 | 0 | 0.66667 | 2020-07 | 0 | 0
280 | CR0012804 | CTASK0022510 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 6 | 4 | 2020-09-18 13:00 | 2020-09-17 13:00 | S/W | WAS |  |  |  |  | Request to create CR for Weblogic Upgrade. - BKG Manifest | 2020-07-27 09:12 | 2020-12-14 09:11 | 2020-12-10 10:29 |  | 2020-12-10 10:32 |  | 2020-11-22 10:32 | 2020-11-22 10:34 | 2020-12-10 10:33 | 2020-12-18 15:02 | CR0012804 | WAS | OPUS-BKG-MFT-A | 2020-W47 | 2020-11 | 88 | 98 | 118.0553 | 7 | 6 | 7 | 0.03 | 193506 | 1.2 | 0 | 0 | 0 | 1 | 3 | 2 | 6 | 16 | 0 | 1.25 | 2020-07 | 0 | 0
281 | CR0012804 | CTASK0023012 | Closed | OPUS-CHS | Tien Le | 4 | 4 | 2020-10-16 17:00 | 2020-10-12 08:00 | S/W | WAS |  |  |  |  | PROD, SCM Source compare - CHS | 2020-07-27 09:12 | 2020-12-14 09:11 | 2020-12-10 10:29 |  | 2020-12-10 10:32 |  | 2020-11-22 10:32 | 2020-11-22 10:34 | 2020-12-10 10:33 | 2020-12-18 15:02 | CR0012804 | WAS | OPUS-CHS | 2020-W47 | 2020-11 | 88 | 98 | 118.0553 | 7 | 6 | 7 | 0.03 | 173286 | 1.8 | 0 | 0 | 0 | 1 | 3 | 2 | 6 | 16 | 0 | 0 | 2020-07 | 0 | 0
282 | CR0012804 | CTASK0022723 | Closed | OPUS-ACM | Huynh Tuan Khanh | 30 | 30 | 2020-09-28 13:39 | 2020-09-25 13:39 | S/W | WAS |  |  |  |  | PROD, SCM Source compare - ACM | 2020-07-27 09:12 | 2020-12-14 09:11 | 2020-12-10 10:29 |  | 2020-12-10 10:32 |  | 2020-11-22 10:32 | 2020-11-22 10:34 | 2020-12-10 10:33 | 2020-12-18 15:02 | CR0012804 | WAS | OPUS-ACM | 2020-W47 | 2020-11 | 88 | 98 | 118.0553 | 7 | 6 | 7 | 0.03 | 193499 | 1.2 | 0 | 0 | 0 | 1 | 3 | 2 | 6 | 16 | 0 | 0 | 2020-07 | 0 | 0
283 | CR0012804 | CTASK0022724 | Closed | OPUS-PRI | Nhien Nguyen | 12 | 12 | 2020-09-28 13:40 | 2020-09-24 13:40 | S/W | WAS |  |  |  |  | PROD, SCM Source compare - PRI | 2020-07-27 09:12 | 2020-12-14 09:11 | 2020-12-10 10:29 |  | 2020-12-10 10:32 |  | 2020-11-22 10:32 | 2020-11-22 10:34 | 2020-12-10 10:33 | 2020-12-18 15:02 | CR0012804 | WAS | OPUS-PRI | 2020-W47 | 2020-11 | 88 | 98 | 118.0553 | 7 | 6 | 7 | 0.03 | 183364 | 1.8 | 0 | 0 | 0 | 1 | 3 | 2 | 6 | 16 | 0 | 0 | 2020-07 | 0 | 0
284 | CR0012816 | CTASK0021271 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 26 | 26 | 2020-08-31 14:09 | 2020-08-01 14:09 | Container | Service Management | Trans S/O | Work Order |  |  | (HM) EUA Vend All transport operators - Change extract of W/O (sur)charges to JOEDI application file | 2020-08-12 14:29 | 2020-09-11 21:00 | 2020-08-24 14:01 | 2020-08-31 21:03 | 2020-09-01 14:57 |  | 2020-09-08 11:00 | 2020-09-08 10:00 | 2020-09-03 09:30 | 2020-10-08 13:00 | CR0012816 | Service ManagementTrans S/OWork Order | OPUS-TRS | 2020-W37 | 2020-09 | 52 | 52 | 26.855 | 2 | 1 | 2 | 0.08 | 183432 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0 | 2020-08 | 0 | 0
285 | CR0012816 | CTASK0021272 | Closed | OPUS-TRS | Giang Nguyen Hoang | 26 | 26 | 2020-08-31 14:09 | 2020-08-01 14:09 | Container | Service Management | Trans S/O | Work Order |  |  | (HM) EUA Vend All transport operators - Change extract of W/O (sur)charges to JOEDI application file | 2020-08-12 14:29 | 2020-09-11 21:00 | 2020-08-24 14:01 | 2020-08-31 21:03 | 2020-09-01 14:57 |  | 2020-09-08 11:00 | 2020-09-08 10:00 | 2020-09-03 09:30 | 2020-10-08 13:00 | CR0012816 | Service ManagementTrans S/OWork Order | OPUS-TRS | 2020-W37 | 2020-09 | 52 | 52 | 26.855 | 2 | 1 | 2 | 0.08 | 183440 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0 | 2020-08 | 0 | 0
286 | CR0012864 | CTASK0022206 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2020-09-08 13:00 | 2020-09-01 13:00 | Container | Service Management | Booking/Documentation | Manifest | Indonesia |  | [Production] Indonesia Customs Manifest Excel Download - Missing field information mapping for Description of Goods | 2020-08-12 10:11 | 2020-08-21 | 2020-08-19 13:46 | 2020-08-27 13:51 | 2020-08-27 17:49 |  | 2020-09-08 10:00 | 2020-09-08 09:30 | 2020-08-27 17:53 | 2020-10-08 13:00 | CR0012864 | Service ManagementBooking/DocumentationManifestIndonesia | OPUS-BKG-MFT-A | 2020-W37 | 2020-09 | 34 | 34 | 26.9923 | 3 | 1 | 1 | 0.05 | 193506 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-08 | 0 | 0
287 | CR0012864 | CTASK0021342 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2020-07-23 13:00 | 2020-07-20 13:00 | Container | Service Management | Booking/Documentation | Manifest | Indonesia |  | [Analytics] Indonesia Customs Manifest Excel Download - Missing field information mapping for Description of Goods | 2020-08-12 10:11 | 2020-08-21 | 2020-08-19 13:46 | 2020-08-27 13:51 | 2020-08-27 17:49 |  | 2020-09-08 10:00 | 2020-09-08 09:30 | 2020-08-27 17:53 | 2020-10-08 13:00 | CR0012864 | Service ManagementBooking/DocumentationManifestIndonesia | OPUS-BKG-MFT-A | 2020-W37 | 2020-09 | 34 | 34 | 26.9923 | 3 | 1 | 1 | 0.05 | 193506 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-08 | 0 | 0
288 | CR0012864 | CTASK0021533 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 18 | 18 | 2020-08-07 13:00 | 2020-08-03 13:00 | Container | Service Management | Booking/Documentation | Manifest | Indonesia |  | [Development - Testing] Indonesia Customs Manifest Excel Download - Missing field information mapping for Description of Goods | 2020-08-12 10:11 | 2020-08-21 | 2020-08-19 13:46 | 2020-08-27 13:51 | 2020-08-27 17:49 |  | 2020-09-08 10:00 | 2020-09-08 09:30 | 2020-08-27 17:53 | 2020-10-08 13:00 | CR0012864 | Service ManagementBooking/DocumentationManifestIndonesia | OPUS-BKG-MFT-A | 2020-W37 | 2020-09 | 34 | 34 | 26.9923 | 3 | 1 | 1 | 0.05 | 193506 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-08 | 0 | 0
289 | CR0010408 | CTASK0014527 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | Create new copy element (temperature) in booking copy function | 2019-05-28 14:26 | 2019-07-08 20:38 | 2019-06-10 11:06 | 2019-08-19 17:57 | 2019-08-19 18:20 | 2019-06-10 11:08 | 2019-08-27 18:20 | 2019-08-27 10:59 | 2019-08-19 18:28 | 2019-09-03 10:28 | CR0010408 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W35 | 2019-08 | 16 | 0 | 91.1625 | 1 | 1 | 1 | 0 | 153106 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 6 | 0 | 0 | 2019-05 | 0 | 0
290 | CR0013492 | CTASK0025707 | Closed | OPUS-DMT | Cuong Nguyen | 2 | 2 | 2021-04-30 20:00 | 2021-04-19 08:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK3] CLV_Analysis_Pair Test | 2021-04-13 14:05 | 2021-04-30 20:00 | 2021-04-27 11:39 | 2021-06-28 10:09 | 2021-07-09 04:06 |  | 2021-07-20 10:00 | 2021-07-20 09:54 | 2021-07-09 09:08 | 2021-07-29 14:00 | CR0013492 | Service ManagementDemurrage/Detention | OPUS-DMT | 2021-W29 | 2021-07 | 2 | 2 | 97.8298 | 1 | 1 | 1 | 0 | 193529 | 1.9 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 28 | 0 | 0.058824 | 2021-04 | 0 | 0
291 | CR0011750 | CTASK0024818 | Closed | OPUS-SCE | VInh Bui | 25 | 25 | 2021-01-31 17:41 | 2021-01-01 17:40 | Container | Service Management | SCEM | Visibility | Customer EDI Monitoring |  | VVD got changed but'VE' or 'AG' event was not triggered for BN: CMBV11641400 / CNTR: TCKU4615257 | 2020-01-30 13:18 | 2020-02-07 14:27 | 2020-02-07 14:00 | 2021-01-15 10:46 | 2021-01-16 05:05 |  | 2021-01-27 | 2021-01-26 11:31 | 2021-01-21 16:58 | 2021-02-23 14:12 | CR0011750 | Service ManagementSCEMVisibilityCustomer EDI Monitoring | OPUS-SCE | 2021-W4 | 2021-01 | 88 | 25 | 362.446 | 3 | 1 | 3 | 0 | 193469 | 0.3 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 40 | 0 | 0 | 2020-01 | 0 | 0
292 | CR0011750 | CTASK0017833 | Closed | OPUS-SCE | Thanh Tran Ngoc | 60 | 60 |  |  | Container | Service Management | SCEM | Visibility | Customer EDI Monitoring |  | [Actual] VVD got changed but'VE' or 'AG' event was not triggered for BN: CMBV11641400 / CNTR: TCKU4615257 | 2020-01-30 13:18 | 2020-02-07 14:27 | 2020-02-07 14:00 | 2021-01-15 10:46 | 2021-01-16 05:05 |  | 2021-01-27 | 2021-01-26 11:31 | 2021-01-21 16:58 | 2021-02-23 14:12 | CR0011750 | Service ManagementSCEMVisibilityCustomer EDI Monitoring | OPUS-SCE | 2021-W4 | 2021-01 | 88 | 25 | 362.446 | 3 | 1 | 3 | 0 | 193478 | 0.3 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 40 | 0 | 0 | 2020-01 | 0 | 0
293 | CR0011750 | CTASK0024887 | Closed | OPUS-SCE | Son Nguyen The | 3 | 3 | 2021-01-31 15:50 | 2021-01-01 15:50 | Container | Service Management | SCEM | Visibility | Customer EDI Monitoring |  | VVD got changed but'VE' or 'AG' event was not triggered for BN: CMBV11641400 / CNTR: TCKU4615257 | 2020-01-30 13:18 | 2020-02-07 14:27 | 2020-02-07 14:00 | 2021-01-15 10:46 | 2021-01-16 05:05 |  | 2021-01-27 | 2021-01-26 11:31 | 2021-01-21 16:58 | 2021-02-23 14:12 | CR0011750 | Service ManagementSCEMVisibilityCustomer EDI Monitoring | OPUS-SCE | 2021-W4 | 2021-01 | 88 | 25 | 362.446 | 3 | 1 | 3 | 0 | 193531 | 0.3 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 40 | 0 | 0 | 2020-01 | 0 | 0
294 | CR0012753 | CTASK0021765 | Closed | OPUS-OPF | Tuan Pham Huu | 115 | 115 | 2020-10-30 13:33 | 2020-08-24 13:33 | Container | Vessel Operation |  |  |  |  | [CLV] OPUS Enhancement to manage Coprar EDI from Partners | 2020-07-27 16:02 | 2020-10-30 16:02 | 2020-10-28 17:51 | 2020-12-03 13:08 | 2020-12-03 13:10 |  | 2020-12-08 12:10 | 2020-12-08 11:33 | 2020-12-03 13:29 | 2021-01-14 14:00 | CR0012753 | Vessel Operation | OPUS-OPF | 2020-W50 | 2020-12 | 343 | 370 | 133.8389 | 4 | 1 | 4 | 0.12 | 193523 | 1.2 | 0 | 0 | 0 | 4 | 2 | 2 | 3 | 30 | 0 | 0 | 2020-07 | 0 | 0
295 | CR0012753 | CTASK0021764 | Closed | OPUS-OPF | Toai Phan | 112 | 135 | 2020-10-30 13:33 | 2020-08-24 13:33 | Container | Vessel Operation |  |  |  |  | [CLV] OPUS Enhancement to manage Coprar EDI from Partners | 2020-07-27 16:02 | 2020-10-30 16:02 | 2020-10-28 17:51 | 2020-12-03 13:08 | 2020-12-03 13:10 |  | 2020-12-08 12:10 | 2020-12-08 11:33 | 2020-12-03 13:29 | 2021-01-14 14:00 | CR0012753 | Vessel Operation | OPUS-OPF | 2020-W50 | 2020-12 | 343 | 370 | 133.8389 | 4 | 1 | 4 | 0.12 | 183427 | 1.7 | 0 | 0 | 0 | 4 | 2 | 2 | 3 | 30 | 0 | 2 | 2020-07 | 0 | 0
296 | CR0012753 | CTASK0021763 | Closed | OPUS-OPF | Linh Nguyen | 66 | 70 | 2020-11-01 13:33 | 2020-08-24 13:33 | Container | Vessel Operation |  |  |  |  | [CLV] OPUS Enhancement to manage Coprar EDI from Partners | 2020-07-27 16:02 | 2020-10-30 16:02 | 2020-10-28 17:51 | 2020-12-03 13:08 | 2020-12-03 13:10 |  | 2020-12-08 12:10 | 2020-12-08 11:33 | 2020-12-03 13:29 | 2021-01-14 14:00 | CR0012753 | Vessel Operation | OPUS-OPF | 2020-W50 | 2020-12 | 343 | 370 | 133.8389 | 4 | 1 | 4 | 0.12 | 193464 | 1.4 | 0 | 0 | 0 | 4 | 2 | 2 | 3 | 30 | 0 | 0 | 2020-07 | 0 | 0
297 | CR0012753 | CTASK0021075 | Closed | OPUS-OPF | Thuan Tran | 50 | 50 | 2020-10-30 13:33 | 2020-08-24 13:33 | Container | Vessel Operation |  |  |  |  | [CLV] OPUS Enhancement to manage Coprar EDI from Partners | 2020-07-27 16:02 | 2020-10-30 16:02 | 2020-10-28 17:51 | 2020-12-03 13:08 | 2020-12-03 13:10 |  | 2020-12-08 12:10 | 2020-12-08 11:33 | 2020-12-03 13:29 | 2021-01-14 14:00 | CR0012753 | Vessel Operation | OPUS-OPF | 2020-W50 | 2020-12 | 343 | 370 | 133.8389 | 4 | 1 | 4 | 0.12 | 183423 | 1.7 | 0 | 0 | 0 | 4 | 2 | 2 | 3 | 30 | 0 | 0 | 2020-07 | 0 | 0
298 | CR0013925 | CTASK0027094 | Closed | OPUS-DMT | Cuong Nguyen | 33 | 37 | 2021-06-18 20:00 | 2021-05-12 08:00 | Container | Service Management | Demurrage/Detention | F/T Adjustment | DAR - After Booking |  | [CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2021-05-31 10:03 | 2021-06-18 20:00 | 2021-06-18 14:52 | 2021-06-23 09:19 | 2021-06-23 09:44 |  | 2021-07-06 10:00 | 2021-07-06 09:54 | 2021-06-24 14:42 | 2021-07-06 13:38 | CR0013925 | Service ManagementDemurrage/DetentionF/T AdjustmentDAR - After Booking | OPUS-DMT | 2021-W27 | 2021-07 | 33 | 37 | 35.9976 | 1 | 1 | 1 | 0.04 | 193529 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0.11538 | 0.22222 | 2021-05 | 0 | 0
299 | CR0013499 | CTASK0024703 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-04-29 19:21 | 2021-04-26 11:21 | Container | Service Management | Booking/Documentation | Booking | Work With Bookings |  | [Testing] [CLT Internal] Search Field Layout Enhancement on Work With Booking | 2021-04-12 10:46 | 2021-05-06 | 2021-04-29 18:18 | 2021-05-06 17:57 | 2021-05-06 18:27 |  | 2021-05-18 10:00 | 2021-05-18 11:00 | 2021-05-07 09:04 | 2021-06-17 14:00 | CR0013499 | Service ManagementBooking/DocumentationBookingWork With Bookings | OPUS-BKG-M | 2021-W20 | 2021-05 | 40 | 40 | 35.9677 | 5 | 1 | 1 | 0.05 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
300 | CR0013499 | CTASK0024702 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 20 | 20 | 2021-04-17 02:00 | 2021-04-12 10:51 | Container | Service Management | Booking/Documentation | Booking | Work With Bookings |  | [Development] [CLT Internal] Search Field Layout Enhancement on Work With Booking | 2021-04-12 10:46 | 2021-05-06 | 2021-04-29 18:18 | 2021-05-06 17:57 | 2021-05-06 18:27 |  | 2021-05-18 10:00 | 2021-05-18 11:00 | 2021-05-07 09:04 | 2021-06-17 14:00 | CR0013499 | Service ManagementBooking/DocumentationBookingWork With Bookings | OPUS-BKG-M | 2021-W20 | 2021-05 | 40 | 40 | 35.9677 | 5 | 1 | 1 | 0.05 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
301 | CR0013499 | CTASK0024677 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 12 | 12 | 2021-01-15 09:26 | 2021-01-13 01:26 | Container | Service Management | Booking/Documentation | Booking | Work With Bookings |  | [Design] [CLT Internal] Search Field Layout Enhancement on Work With Booking | 2021-04-12 10:46 | 2021-05-06 | 2021-04-29 18:18 | 2021-05-06 17:57 | 2021-05-06 18:27 |  | 2021-05-18 10:00 | 2021-05-18 11:00 | 2021-05-07 09:04 | 2021-06-17 14:00 | CR0013499 | Service ManagementBooking/DocumentationBookingWork With Bookings | OPUS-BKG-M | 2021-W20 | 2021-05 | 40 | 40 | 35.9677 | 5 | 1 | 1 | 0.05 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
302 | CR0013499 | CTASK0024704 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-05-14 14:51 | 2021-05-13 10:51 | Container | Service Management | Booking/Documentation | Booking | Work With Bookings |  | [Deployment][CLT Internal] Search Field Layout Enhancement on Work With Booking | 2021-04-12 10:46 | 2021-05-06 | 2021-04-29 18:18 | 2021-05-06 17:57 | 2021-05-06 18:27 |  | 2021-05-18 10:00 | 2021-05-18 11:00 | 2021-05-07 09:04 | 2021-06-17 14:00 | CR0013499 | Service ManagementBooking/DocumentationBookingWork With Bookings | OPUS-BKG-M | 2021-W20 | 2021-05 | 40 | 40 | 35.9677 | 5 | 1 | 1 | 0.05 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
303 | CR0013499 | CTASK0024701 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Booking | Work With Bookings |  | [Document][CLT Internal] Search Field Layout Enhancement on Work With Booking | 2021-04-12 10:46 | 2021-05-06 | 2021-04-29 18:18 | 2021-05-06 17:57 | 2021-05-06 18:27 |  | 2021-05-18 10:00 | 2021-05-18 11:00 | 2021-05-07 09:04 | 2021-06-17 14:00 | CR0013499 | Service ManagementBooking/DocumentationBookingWork With Bookings | OPUS-BKG-M | 2021-W20 | 2021-05 | 40 | 40 | 35.9677 | 5 | 1 | 1 | 0.05 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
304 | CR0013493 | CTASK0026066 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 2 | 2 | 2021-03-30 02:00 | 2021-03-23 02:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [PROD]Trinidad y Tobago Manifest - Additional enhancement / OPUS User Interface (related to CR0010433 / ECR0000415 ) | 2021-02-19 17:23 | 2021-03-05 | 2021-03-03 18:35 | 2021-03-19 16:51 | 2021-03-22 16:18 |  | 2021-03-30 10:00 | 2021-03-31 | 2021-03-23 11:20 | 2021-04-29 14:00 | CR0013493 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W13 | 2021-03 | 45 | 42 | 38.6925 | 3 | 1 | 1 | 0.05 | 193506 | 1.7 | 2 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 1.1212 | 1.25 | 2021-02 | 0 | 0
305 | CR0013493 | CTASK0025115 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 4 | 4 | 2021-02-03 02:00 | 2021-02-01 02:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Analysis]Trinidad y Tobago Manifest - Additional enhancement / OPUS User Interface (related to CR0010433 / ECR0000415 ) | 2021-02-19 17:23 | 2021-03-05 | 2021-03-03 18:35 | 2021-03-19 16:51 | 2021-03-22 16:18 |  | 2021-03-30 10:00 | 2021-03-31 | 2021-03-23 11:20 | 2021-04-29 14:00 | CR0013493 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W13 | 2021-03 | 45 | 42 | 38.6925 | 3 | 1 | 1 | 0.05 | 193506 | 1.7 | 2 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 1.1212 | 1.25 | 2021-02 | 0 | 0
306 | CR0013493 | CTASK0025231 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 39 | 36 | 2021-02-26 02:00 | 2021-02-01 02:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Dev-Test]Trinidad y Tobago Manifest - Additional enhancement / OPUS User Interface (related to CR0010433 / ECR0000415 ) | 2021-02-19 17:23 | 2021-03-05 | 2021-03-03 18:35 | 2021-03-19 16:51 | 2021-03-22 16:18 |  | 2021-03-30 10:00 | 2021-03-31 | 2021-03-23 11:20 | 2021-04-29 14:00 | CR0013493 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W13 | 2021-03 | 45 | 42 | 38.6925 | 3 | 1 | 1 | 0.05 | 193506 | 1.7 | 2 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 1.1212 | 1.25 | 2021-02 | 0 | 0
307 | CR0012329 | CTASK0022287 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 | 2020-09-11 02:00 | 2020-09-03 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Freight Invoice (EDI) | [Analysis] Add "Contract Party" when send IFTMCS EDI to CargoSmart (SR0083131) - Only Flat File Change | 2021-01-20 16:48 | 2021-02-05 | 2021-02-04 16:33 | 2021-03-08 09:37 | 2021-03-08 13:25 |  | 2021-03-16 10:00 | 2021-03-16 10:00 | 2021-03-10 10:49 | 2021-04-15 14:00 | CR0012329 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Freight Invoice (EDI) | OPUS-BKG-OB | 2021-W11 | 2021-03 | 24 | 24 | 54.7169 | 3 | 1 | 1 | 0.02 | 193470 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.36842 | 0.17391 | 2021-01 | 0 | 0
308 | CR0012329 | CTASK0022307 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 12 | 12 | 2021-01-30 01:00 | 2021-01-21 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Freight Invoice (EDI) | [Development+Test] Add "Contract Party" when send IFTMCS EDI to CargoSmart (SR0083131) - Only Flat File Change | 2021-01-20 16:48 | 2021-02-05 | 2021-02-04 16:33 | 2021-03-08 09:37 | 2021-03-08 13:25 |  | 2021-03-16 10:00 | 2021-03-16 10:00 | 2021-03-10 10:49 | 2021-04-15 14:00 | CR0012329 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Freight Invoice (EDI) | OPUS-BKG-OB | 2021-W11 | 2021-03 | 24 | 24 | 54.7169 | 3 | 1 | 1 | 0.02 | 193470 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.36842 | 0.17391 | 2021-01 | 0 | 0
309 | CR0012329 | CTASK0025866 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2021-03-15 23:00 | 2021-03-08 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Freight Invoice (EDI) | [Deployment] Add "Contract Party" when send IFTMCS EDI to CargoSmart (SR0083131) - Only Flat File Change | 2021-01-20 16:48 | 2021-02-05 | 2021-02-04 16:33 | 2021-03-08 09:37 | 2021-03-08 13:25 |  | 2021-03-16 10:00 | 2021-03-16 10:00 | 2021-03-10 10:49 | 2021-04-15 14:00 | CR0012329 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Freight Invoice (EDI) | OPUS-BKG-OB | 2021-W11 | 2021-03 | 24 | 24 | 54.7169 | 3 | 1 | 1 | 0.02 | 193470 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.36842 | 0.17391 | 2021-01 | 0 | 0
310 | CR0013032 | CTASK0022753 | Closed | OPUS-SPC | Linh Nguyen | 60 | 60 | 2020-12-01 13:47 | 2020-10-16 13:47 | Container | Sales Management | Space Control |  |  |  | [CLT Internal] [SPC - Add validation logic of bottleneck in case of Double calling port] | 2020-10-07 11:16 | 2020-11-13 11:16 | 2020-11-10 16:52 | 2021-05-21 09:36 | 2021-06-01 13:47 |  | 2021-06-09 13:46 | 2021-06-08 14:13 | 2021-06-03 11:43 | 2021-07-09 14:00 | CR0013032 | Sales ManagementSpace Control | OPUS-SPC | 2021-W23 | 2021-06 | 60 | 60 | 245.1044 | 1 | 1 | 1 | 0.01 | 193464 | 1.6 | 0 | 0 | 0 | 1 | 1 | 3 | 9 | 53 | 0 | 0 | 2020-10 | 0 | 0
311 | CR0012141 | CTASK0019963 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 21 | 19 | 2020-05-25 11:26 | 2020-05-06 11:26 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (US Office) | Manifest Details by B/L (US Office) | [Development+ Testing+ Deployment] NA VENDOR EDI - Mapping of IMDG Class in HMANIFEST to US Customs | 2020-05-12 11:18 | 2020-05-22 11:28 | 2020-05-18 10:20 | 2020-05-19 22:23 | 2020-05-20 09:41 |  | 2020-05-26 09:41 | 2020-05-26 09:41 | 2020-05-20 17:17 | 2020-06-09 18:03 | CR0012141 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (US Office)Manifest Details by B/L (US Office) | OPUS-BKG-MFT-M | 2020-W22 | 2020-05 | 21 | 19 | 13.9326 | 1 | 1 | 1 | 0.06 | 193512 | 0.9 | 0 | 0 | 1 | 1 | 1 | 1 | 8 | 26 | 0 | 0.5 | 2020-05 | 1 | 1
312 | CR0013287 | CTASK0023467 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 16 | 16 | 2020-12-08 02:00 | 2020-11-10 13:20 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [CLT Internal](SvEG) EUA EDI VEND : COPRAR transmission history screen | 2020-11-11 11:23 | 2020-12-01 | 2020-11-20 10:31 | 2020-11-26 19:30 | 2020-11-27 09:43 |  | 2020-12-08 10:00 | 2020-12-08 11:42 | 2020-11-27 13:27 | 2020-12-08 13:16 | CR0013287 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W50 | 2020-12 | 16 | 16 | 26.9428 | 1 | 1 | 1 | 0.02 | 193470 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 30 | 0 | 0.17391 | 2020-11 | 0 | 0
313 | CR0012974 | CTASK0022285 | Closed | OPUS-CTM | Tran Le | 19 | 32 |  |  | Container | Service Management | CNTR Movement |  |  |  | CTM logic correction | 2020-09-29 16:07 | 2020-10-13 16:04 | 2020-10-13 17:21 | 2020-11-13 13:09 | 2020-11-17 10:39 |  | 2020-12-01 11:00 | 2020-12-01 10:00 | 2020-11-19 09:15 | 2021-01-01 14:00 | CR0012974 | Service ManagementCNTR Movement | OPUS-CTM | 2020-W49 | 2020-12 | 19 | 32 | 62.7868 | 1 | 1 | 1 | 0.02 | 193501 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0 | 2020-09 | 0 | 0
314 | CR0011374 | CTASK0014492 | Closed | OPUS-TES | Thai Nguyen | 2 | 2 |  |  | Container | Service Management | TML INV | Invoice | CSR Creation | CSR Creation | (actual) [CLT Internal] Zero amount remove in CSR creation of TES | 2019-06-11 16:42 | 2019-07-19 22:35 | 2019-06-12 13:59 | 2019-06-21 12:16 | 2019-06-26 10:57 | 2019-06-13 13:34 | 2019-07-02 10:00 | 2019-07-03 09:00 | 2019-06-26 10:58 | 2019-08-11 23:48 | CR0011374 | Service ManagementTML INVInvoiceCSR CreationCSR Creation | OPUS-TES | 2019-W27 | 2019-07 | 18 | 0 | 20.7211 | 2 | 1 | 1 | 0 | 173249 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 7 | 0 | 0.6 | 2019-06 | 0 | 0
315 | CR0011374 | CTASK0014853 | Closed | OPUS-TES | Thai Nguyen | 16 | 16 |  |  | Container | Service Management | TML INV | Invoice | CSR Creation | CSR Creation | (actual) [CLT Internal] Zero amount remove in CSR creation of TES | 2019-06-11 16:42 | 2019-07-19 22:35 | 2019-06-12 13:59 | 2019-06-21 12:16 | 2019-06-26 10:57 | 2019-06-13 13:34 | 2019-07-02 10:00 | 2019-07-03 09:00 | 2019-06-26 10:58 | 2019-08-11 23:48 | CR0011374 | Service ManagementTML INVInvoiceCSR CreationCSR Creation | OPUS-TES | 2019-W27 | 2019-07 | 18 | 0 | 20.7211 | 2 | 1 | 1 | 0 | 173249 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 7 | 0 | 0.6 | 2019-06 | 0 | 0
316 | CR0013105 | CTASK0022910 | Closed | OPUS-BKG-OB | Nam Nguyen | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | B/L Issue [Alt+8] | [Development] eBL PDF generation function | 2020-11-03 18:21 | 2021-01-09 | 2021-01-07 16:57 | 2021-02-10 13:55 | 2021-02-19 17:10 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-02-25 09:52 | 2021-04-08 14:00 | CR0013105 | Service ManagementBooking/DocumentationOutbound DocB/L CreationB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W10 | 2021-03 | 0 | 0 | 125.6523 | 2 | 1 | 1 | 0 | 123048 | 2.1 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 46 | 0 | 0.047619 | 2020-11 | 0 | 0
317 | CR0013105 | CTASK0022911 | Closed | OPUS-BKG-OB | Nam Nguyen | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | B/L Issue [Alt+8] | [Test] eBL PDF generation function | 2020-11-03 18:21 | 2021-01-09 | 2021-01-07 16:57 | 2021-02-10 13:55 | 2021-02-19 17:10 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-02-25 09:52 | 2021-04-08 14:00 | CR0013105 | Service ManagementBooking/DocumentationOutbound DocB/L CreationB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W10 | 2021-03 | 0 | 0 | 125.6523 | 2 | 1 | 1 | 0 | 123048 | 2.1 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 46 | 0 | 0.047619 | 2020-11 | 0 | 0
318 | CR0012870 | CTASK0021554 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-01-28 19:08 | 2021-01-25 19:08 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] FIRM Date (GMT) and FIRM Date (Local) of Booking Status | 2020-08-25 13:21 | 2020-10-08 | 2020-10-06 17:50 | 2020-11-12 09:44 | 2020-11-12 11:18 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-19 13:16 | 2021-03-04 14:00 | CR0012870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 128 | 128 | 160.8601 | 5 | 1 | 2 | 0.03 | 193488 | 1.2 | 1 | 0 | 0 | 2 | 1 | 3 | 8 | 21 | 0.53659 | 0.28125 | 2020-08 | 0 | 0
319 | CR0012870 | CTASK0021508 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2020-08-01 01:35 | 2020-07-27 02:34 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] FIRM Date (GMT) and FIRM Date (Local) of Booking Status | 2020-08-25 13:21 | 2020-10-08 | 2020-10-06 17:50 | 2020-11-12 09:44 | 2020-11-12 11:18 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-19 13:16 | 2021-03-04 14:00 | CR0012870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 128 | 128 | 160.8601 | 5 | 1 | 2 | 0.03 | 153106 | 1.9 | 1 | 0 | 0 | 2 | 1 | 3 | 8 | 21 | 0.22951 | 0.4 | 2020-08 | 0 | 0
320 | CR0012870 | CTASK0021549 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 80 | 80 | 2020-09-21 18:30 | 2020-09-01 10:02 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] FIRM Date (GMT) and FIRM Date (Local) of Booking Status | 2020-08-25 13:21 | 2020-10-08 | 2020-10-06 17:50 | 2020-11-12 09:44 | 2020-11-12 11:18 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-19 13:16 | 2021-03-04 14:00 | CR0012870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 128 | 128 | 160.8601 | 5 | 1 | 2 | 0.03 | 193488 | 1.2 | 1 | 0 | 0 | 2 | 1 | 3 | 8 | 21 | 0.53659 | 0.28125 | 2020-08 | 0 | 0
321 | CR0012870 | CTASK0021552 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 14 | 14 | 2020-09-30 19:06 | 2020-09-21 19:06 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] FIRM Date (GMT) and FIRM Date (Local) of Booking Status | 2020-08-25 13:21 | 2020-10-08 | 2020-10-06 17:50 | 2020-11-12 09:44 | 2020-11-12 11:18 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-19 13:16 | 2021-03-04 14:00 | CR0012870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 128 | 128 | 160.8601 | 5 | 1 | 2 | 0.03 | 193488 | 1.2 | 1 | 0 | 0 | 2 | 1 | 3 | 8 | 21 | 0.53659 | 0.28125 | 2020-08 | 0 | 0
322 | CR0012870 | CTASK0022824 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 10 | 10 | 2020-10-05 19:15 | 2020-10-02 19:15 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] FIRM Date (GMT) and FIRM Date (Local) of Booking Status | 2020-08-25 13:21 | 2020-10-08 | 2020-10-06 17:50 | 2020-11-12 09:44 | 2020-11-12 11:18 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-19 13:16 | 2021-03-04 14:00 | CR0012870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 128 | 128 | 160.8601 | 5 | 1 | 2 | 0.03 | 193488 | 1.2 | 1 | 0 | 0 | 2 | 1 | 3 | 8 | 21 | 0.53659 | 0.28125 | 2020-08 | 0 | 0
323 | CR0013280 | CTASK0023986 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 24 | 24 | 2020-12-26 01:00 | 2020-12-14 10:34 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development]Global *EDI* FF Update 301/301U | 2020-12-23 10:35 | 2021-01-09 01:00 | 2021-01-08 16:07 | 2021-02-04 06:52 | 2021-02-05 10:15 |  | 2021-02-05 10:14 | 2021-03-02 10:00 | 2021-02-09 13:05 | 2021-04-01 14:00 | CR0013280 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 38 | 38 | 43.9854 | 4 | 1 | 1 | 0.04 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 21 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
324 | CR0013280 | CTASK0023930 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2020-12-02 18:28 | 2020-12-01 10:28 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design]Global *EDI* FF Update 301/301U | 2020-12-23 10:35 | 2021-01-09 01:00 | 2021-01-08 16:07 | 2021-02-04 06:52 | 2021-02-05 10:15 |  | 2021-02-05 10:14 | 2021-03-02 10:00 | 2021-02-09 13:05 | 2021-04-01 14:00 | CR0013280 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 38 | 38 | 43.9854 | 4 | 1 | 1 | 0.04 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 21 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
325 | CR0013280 | CTASK0023988 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-02-25 02:00 | 2021-02-22 10:58 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment]Global *EDI* FF Update 301/301U | 2020-12-23 10:35 | 2021-01-09 01:00 | 2021-01-08 16:07 | 2021-02-04 06:52 | 2021-02-05 10:15 |  | 2021-02-05 10:14 | 2021-03-02 10:00 | 2021-02-09 13:05 | 2021-04-01 14:00 | CR0013280 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 38 | 38 | 43.9854 | 4 | 1 | 1 | 0.04 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 21 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
326 | CR0013280 | CTASK0023987 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-01-06 19:57 | 2021-01-04 09:57 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing]Global *EDI* FF Update 301/301U | 2020-12-23 10:35 | 2021-01-09 01:00 | 2021-01-08 16:07 | 2021-02-04 06:52 | 2021-02-05 10:15 |  | 2021-02-05 10:14 | 2021-03-02 10:00 | 2021-02-09 13:05 | 2021-04-01 14:00 | CR0013280 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 38 | 38 | 43.9854 | 4 | 1 | 1 | 0.04 | 193488 | 1.5 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 21 | 0.53659 | 0.28125 | 2020-12 | 0 | 0
327 | CR0012202 | CTASK0023183 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 7 | 7 | 2020-10-30 19:30 | 2020-10-26 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (US Office) | P/MIB Generate | [Development+Testing+Deployment][CLT Internal] NA - BKG - Unable to cut an Inbond to the FTZ | 2020-11-04 09:16 | 2020-12-30 | 2020-12-22 12:59 | 2021-02-15 11:40 | 2021-03-17 15:43 |  | 2021-03-23 09:51 | 2021-03-23 09:50 | 2021-03-19 10:28 | 2021-04-22 14:00 | CR0012202 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (US Office)P/MIB Generate | OPUS-BKG-MFT-M | 2021-W12 | 2021-03 | 13 | 13 | 139.0241 | 2 | 1 | 1 | 0 | 173280 | 1.9 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 46 | 0 | 0.18519 | 2020-11 | 0 | 0
328 | CR0012202 | CTASK0025949 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 6 | 6 | 2021-03-22 19:30 | 2021-03-17 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (US Office) | P/MIB Generate | [Testing+Deployment][CLT Internal] NA - BKG - Unable to cut an Inbond to the FTZ | 2020-11-04 09:16 | 2020-12-30 | 2020-12-22 12:59 | 2021-02-15 11:40 | 2021-03-17 15:43 |  | 2021-03-23 09:51 | 2021-03-23 09:50 | 2021-03-19 10:28 | 2021-04-22 14:00 | CR0012202 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (US Office)P/MIB Generate | OPUS-BKG-MFT-M | 2021-W12 | 2021-03 | 13 | 13 | 139.0241 | 2 | 1 | 1 | 0 | 173280 | 1.9 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 46 | 0 | 0.18519 | 2020-11 | 0 | 0
329 | CR0013354 | CTASK0023875 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-01-29 12:13 | 2021-01-01 12:13 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] [CLT Internal] OOME Issue - Standby Booking Status Report | 2021-01-04 09:06 | 2021-01-28 02:00 | 2021-01-14 16:27 | 2021-01-27 14:22 | 2021-01-27 14:36 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-01-28 15:24 | 2021-03-11 14:00 | CR0013354 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W6 | 2021-02 | 19 | 19 | 36.0378 | 4 | 1 | 1 | 0.02 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
330 | CR0013354 | CTASK0023878 | Closed | OPUS-BKG-M | Kieu Le | 10 | 10 | 2021-01-29 12:15 | 2021-01-01 12:15 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] [CLT Internal] OOME Issue - Standby Booking Status Report | 2021-01-04 09:06 | 2021-01-28 02:00 | 2021-01-14 16:27 | 2021-01-27 14:22 | 2021-01-27 14:36 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-01-28 15:24 | 2021-03-11 14:00 | CR0013354 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W6 | 2021-02 | 19 | 19 | 36.0378 | 4 | 1 | 1 | 0.02 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
331 | CR0013354 | CTASK0023876 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-01-29 12:14 | 2021-01-01 12:14 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] [CLT Internal] OOME Issue - Standby Booking Status Report | 2021-01-04 09:06 | 2021-01-28 02:00 | 2021-01-14 16:27 | 2021-01-27 14:22 | 2021-01-27 14:36 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-01-28 15:24 | 2021-03-11 14:00 | CR0013354 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W6 | 2021-02 | 19 | 19 | 36.0378 | 4 | 1 | 1 | 0.02 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
332 | CR0013354 | CTASK0023880 | Closed | OPUS-BKG-M | Kieu Le | 3 | 3 | 2021-02-26 12:16 | 2021-02-01 12:16 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] [CLT Internal] OOME Issue - Standby Booking Status Report | 2021-01-04 09:06 | 2021-01-28 02:00 | 2021-01-14 16:27 | 2021-01-27 14:22 | 2021-01-27 14:36 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-01-28 15:24 | 2021-03-11 14:00 | CR0013354 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W6 | 2021-02 | 19 | 19 | 36.0378 | 4 | 1 | 1 | 0.02 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
333 | CR0013636 | CTASK0026583 | Closed | OPUS-ACM | Huynh Tuan Khanh | 80 | 80 | 2021-05-31 09:30 | 2021-04-20 09:30 | Container | Support & Admin | Agent Commission Management | Audit | FF Compensation Audit |  | NA Brokerage *ACM* Adding Delete Button | 2021-04-21 13:06 | 2021-05-31 20:05 | 2021-05-31 15:33 | 2021-06-18 09:10 | 2021-06-25 10:28 |  | 2021-06-29 10:28 | 2021-06-29 10:20 | 2021-06-25 13:34 | 2021-07-29 14:00 | CR0013636 | Support & AdminAgent Commission ManagementAuditFF Compensation Audit | OPUS-ACM | 2021-W26 | 2021-06 | 80 | 80 | 68.8904 | 1 | 1 | 1 | 0.05 | 193499 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0 | 0 | 2021-04 | 0 | 0
334 | CR0012554 | CTASK0019930 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 22 | 28 | 2020-05-07 19:30 | 2020-04-29 11:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Development + Testing + Deployment]Map "Description of Goods" in OPUS to KR manifest | 2020-05-12 10:20 | 2020-05-14 | 2020-05-12 14:20 | 2020-05-13 10:57 | 2020-05-13 16:04 |  | 2020-05-13 10:00 | 2020-05-14 09:40 | 2020-05-13 16:42 | 2020-06-13 13:00 | CR0012554 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2020-W20 | 2020-05 | 22 | 28 | 0.98595 | 1 | 1 | 1 | 1.18 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 26 | 0 | 0.18519 | 2020-05 | 0 | 0
335 | CR0012935 | CTASK0021963 | Closed | OPUS-BKG-OB | Nam Nguyen | 43 | 46 | 2020-11-06 20:46 | 2020-09-14 20:46 | Container | Service Management | Booking/Documentation | Setup | Internet BL Control Party Setup | Controlling Party Setup | [Development]Global "FTP" - Expeditors - Set up of new file naming rule | 2020-09-07 14:53 | 2020-09-30 | 2020-09-29 14:35 | 2020-11-07 15:04 | 2020-11-11 16:20 |  | 2020-12-01 10:00 | 2020-12-01 10:30 | 2020-11-24 17:09 | 2020-12-15 23:41 | CR0012935 | Service ManagementBooking/DocumentationSetupInternet BL Control Party SetupControlling Party Setup | OPUS-BKG-OB | 2020-W49 | 2020-12 | 53 | 56 | 84.7963 | 2 | 1 | 1 | 0.03 | 123048 | 1.9 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0.46154 | 2020-09 | 0 | 0
336 | CR0012935 | CTASK0022291 | Closed | OPUS-BKG-OB | Nam Nguyen | 10 | 10 | 2020-09-04 23:38 | 2020-09-03 23:38 | Container | Service Management | Booking/Documentation | Setup | Internet BL Control Party Setup | Controlling Party Setup | [Analysis] Global "FTP" - Expeditors - Set up of new file naming rule | 2020-09-07 14:53 | 2020-09-30 | 2020-09-29 14:35 | 2020-11-07 15:04 | 2020-11-11 16:20 |  | 2020-12-01 10:00 | 2020-12-01 10:30 | 2020-11-24 17:09 | 2020-12-15 23:41 | CR0012935 | Service ManagementBooking/DocumentationSetupInternet BL Control Party SetupControlling Party Setup | OPUS-BKG-OB | 2020-W49 | 2020-12 | 53 | 56 | 84.7963 | 2 | 1 | 1 | 0.03 | 123048 | 1.9 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0.46154 | 2020-09 | 0 | 0
337 | CR0012377 | CTASK0020401 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 30 | 30 | 2020-06-12 19:30 | 2020-06-01 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | [Development][More Request]- Customs Cargo List change to store Consrt.VVD and Container information | 2020-05-08 16:57 | 2020-05-28 | 2020-05-26 14:42 | 2020-07-07 11:22 | 2020-07-07 16:20 |  | 2020-07-14 10:00 | 2020-07-14 09:56 | 2020-07-09 18:49 | 2020-08-13 13:00 | CR0012377 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W29 | 2020-07 | 97 | 96 | 66.7106 | 4 | 1 | 1 | 0.06 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.18519 | 2020-05 | 0 | 0
338 | CR0012377 | CTASK0018867 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 6 | 6 | 2020-03-16 19:00 | 2020-03-11 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | [Estimation] Customs Cargo List change to store Consrt.VVD and Container information | 2020-05-08 16:57 | 2020-05-28 | 2020-05-26 14:42 | 2020-07-07 11:22 | 2020-07-07 16:20 |  | 2020-07-14 10:00 | 2020-07-14 09:56 | 2020-07-09 18:49 | 2020-08-13 13:00 | CR0012377 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W29 | 2020-07 | 97 | 96 | 66.7106 | 4 | 1 | 1 | 0.06 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.18519 | 2020-05 | 0 | 0
339 | CR0012377 | CTASK0021104 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 12 | 12 | 2020-07-13 19:30 | 2020-07-08 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | [Deployment] Customs Cargo List change to store Consrt.VVD and Container information | 2020-05-08 16:57 | 2020-05-28 | 2020-05-26 14:42 | 2020-07-07 11:22 | 2020-07-07 16:20 |  | 2020-07-14 10:00 | 2020-07-14 09:56 | 2020-07-09 18:49 | 2020-08-13 13:00 | CR0012377 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W29 | 2020-07 | 97 | 96 | 66.7106 | 4 | 1 | 1 | 0.06 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.18519 | 2020-05 | 0 | 0
340 | CR0012377 | CTASK0019194 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 49 | 48 | 2020-05-29 19:30 | 2020-03-26 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | [Development+Deploy+Testing] Customs Cargo List change to store Consrt.VVD and Container information | 2020-05-08 16:57 | 2020-05-28 | 2020-05-26 14:42 | 2020-07-07 11:22 | 2020-07-07 16:20 |  | 2020-07-14 10:00 | 2020-07-14 09:56 | 2020-07-09 18:49 | 2020-08-13 13:00 | CR0012377 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W29 | 2020-07 | 97 | 96 | 66.7106 | 4 | 1 | 1 | 0.06 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.18519 | 2020-05 | 0 | 0
341 | CR0013611 | CTASK0026197 | Closed | OPUS-TES | Thai Nguyen | 10 | 10 | 2021-05-01 01:00 | 2021-04-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202104] [CLT Internal] NA * TML INV * Conflicting messages received in Marine Terminal Invoice Creation | 2021-04-16 09:23 | 2021-06-30 22:00 | 2021-06-29 14:13 | 2021-07-01 11:24 | 2021-07-05 14:22 |  | 2021-07-13 12:30 | 2021-07-13 11:12 | 2021-07-06 08:41 | 2021-07-29 14:00 | CR0013611 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W28 | 2021-07 | 65 | 28 | 88.1299 | 4 | 1 | 1 | 0.01 | 173249 | 2.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0 | 0.5 | 2021-04 | 0 | 0
342 | CR0013611 | CTASK0027898 | Closed | OPUS-TES | Thai Nguyen | 3 | 3 | 2021-08-01 01:00 | 2021-07-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202107] [CLT Internal] NA * TML INV * Conflicting messages received in Marine Terminal Invoice Creation | 2021-04-16 09:23 | 2021-06-30 22:00 | 2021-06-29 14:13 | 2021-07-01 11:24 | 2021-07-05 14:22 |  | 2021-07-13 12:30 | 2021-07-13 11:12 | 2021-07-06 08:41 | 2021-07-29 14:00 | CR0013611 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W28 | 2021-07 | 65 | 28 | 88.1299 | 4 | 1 | 1 | 0.01 | 173249 | 2.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0 | 0.5 | 2021-04 | 0 | 0
343 | CR0013611 | CTASK0026819 | Closed | OPUS-TES | Thai Nguyen | 45 | 5 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202105] [CLT Internal] NA * TML INV * Conflicting messages received in Marine Terminal Invoice Creation | 2021-04-16 09:23 | 2021-06-30 22:00 | 2021-06-29 14:13 | 2021-07-01 11:24 | 2021-07-05 14:22 |  | 2021-07-13 12:30 | 2021-07-13 11:12 | 2021-07-06 08:41 | 2021-07-29 14:00 | CR0013611 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W28 | 2021-07 | 65 | 28 | 88.1299 | 4 | 1 | 1 | 0.01 | 173249 | 2.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0 | 0.5 | 2021-04 | 0 | 0
344 | CR0013611 | CTASK0027772 | Closed | OPUS-TES | Thai Nguyen | 10 | 10 | 2021-07-01 01:00 | 2021-06-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202106] [CLT Internal] NA * TML INV * Conflicting messages received in Marine Terminal Invoice Creation | 2021-04-16 09:23 | 2021-06-30 22:00 | 2021-06-29 14:13 | 2021-07-01 11:24 | 2021-07-05 14:22 |  | 2021-07-13 12:30 | 2021-07-13 11:12 | 2021-07-06 08:41 | 2021-07-29 14:00 | CR0013611 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W28 | 2021-07 | 65 | 28 | 88.1299 | 4 | 1 | 1 | 0.01 | 173249 | 2.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0 | 0.5 | 2021-04 | 0 | 0
345 | CR0013839 | CTASK0026676 | Closed | OPUS-SCG | Hieu Vu | 20 | 20 | 2021-06-04 11:10 | 2021-04-26 11:06 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Approved Details |  | [Documentation] Add VSL Opr Filter // Search By CNTR No // SPCL CGO Approved Details | 2021-05-04 10:41 | 2021-06-09 10:39 | 2021-05-24 17:51 | 2021-06-04 16:08 | 2021-06-04 17:14 |  | 2021-06-08 10:13 | 2021-06-08 09:53 | 2021-06-04 17:19 | 2021-07-08 14:00 | CR0013839 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Approved Details | OPUS-SCG | 2021-W23 | 2021-06 | 138 | 138 | 34.9808 | 2 | 1 | 1 | 0.16 | 183375 | 2.6 | 2 | 0 | 0 | 2 | 1 | 1 | 9 | 53 | 0.076923 | 0 | 2021-05 | 0 | 0
346 | CR0013839 | CTASK0026677 | Closed | OPUS-SCG | Hieu Vu | 118 | 118 | 2021-06-07 11:16 | 2021-04-27 11:16 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Approved Details |  | [CLV] Add VSL Opr Filter // Search By CNTR No // SPCL CGO Approved Details | 2021-05-04 10:41 | 2021-06-09 10:39 | 2021-05-24 17:51 | 2021-06-04 16:08 | 2021-06-04 17:14 |  | 2021-06-08 10:13 | 2021-06-08 09:53 | 2021-06-04 17:19 | 2021-07-08 14:00 | CR0013839 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Approved Details | OPUS-SCG | 2021-W23 | 2021-06 | 138 | 138 | 34.9808 | 2 | 1 | 1 | 0.16 | 183375 | 2.6 | 2 | 0 | 0 | 2 | 1 | 1 | 9 | 53 | 0.076923 | 0 | 2021-05 | 0 | 0
347 | CR0013598 | CTASK0025954 | Closed | OPUS-PRI | Ngan Nham | 32 | 32 | 2021-03-27 01:00 | 2021-03-18 01:00 | Data Integration | Customer |  |  |  |  | [Development] [ONE Force] [CRM] Two Way SYNC between Salesforce and OPUS / CR0010850 [CREATE API] | 2021-03-04 15:10 | 2021-03-27 01:00 | 2021-03-19 09:45 | 2021-05-20 13:01 | 2021-05-20 13:03 |  | 2021-05-25 13:00 | 2021-05-25 11:00 | 2021-05-20 13:08 | 2021-06-24 14:00 | CR0013598 | Customer | OPUS-PRI | 2021-W21 | 2021-05 | 32 | 40 | 81.9095 | 2 | 1 | 1 | 0.02 | 193461 | 2.3 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0 | 0 | 2021-03 | 0 | 0
348 | CR0013598 | CTASK0026994 | Closed | OPUS-PRI | Ngan Nham | 8 | 8 | 2021-06-01 01:00 | 2021-05-13 01:00 | Data Integration | Customer |  |  |  |  | [Development] modify the message | 2021-03-04 15:10 | 2021-03-27 01:00 | 2021-03-19 09:45 | 2021-05-20 13:01 | 2021-05-20 13:03 |  | 2021-05-25 13:00 | 2021-05-25 11:00 | 2021-05-20 13:08 | 2021-06-24 14:00 | CR0013598 | Customer | OPUS-PRI | 2021-W21 | 2021-05 | 32 | 40 | 81.9095 | 2 | 1 | 1 | 0.02 | 193461 | 2.3 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0 | 0 | 2021-03 | 0 | 0
349 | CR0011150 | CTASK0015352 | Closed | OPUS-BKG-MFT | Kieu Le | 34 | 34 |  |  | Container | Service Management | Booking/Documentation | Advance Manifest | Canada ACI (Origin Office) | Manifest Transmit (A6A) | NA - BKG - CBSA Customs Regulation - D3-1-1, item 36 & 37 | 2019-07-05 15:29 | 2019-10-31 15:58 | 2019-07-16 14:43 | 2019-07-17 04:49 | 2019-07-17 13:08 |  | 2019-07-23 09:30 | 2019-07-23 13:27 | 2019-07-18 04:23 | 2019-08-26 13:00 | CR0011150 | Service ManagementBooking/DocumentationAdvance ManifestCanada ACI (Origin Office)Manifest Transmit (A6A) | OPUS-BKG-MFT-M | 2019-W30 | 2019-07 | 34 | 0 | 17.7506 | 1 | 1 | 1 | 0 | 153106 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 2019-07 | 0 | 0
350 | CR0012216 | CTASK0020644 | Closed | OPUS-ACM | Huynh Tuan Khanh | 36 | 36 | 2020-07-31 12:54 | 2020-07-01 12:53 | Container | Support & Admin | Agent Commission Management | Agreement | FF Compensation Agreement Creation |  | [Dev][NA *ACM* Adding calulation settings on FF Compensation Agreement Creation module][Separated from Parent CTASK0020548] | 2021-03-15 14:25 | 2021-04-30 14:25 | 2021-04-30 09:48 | 2021-06-11 12:11 | 2021-06-24 10:09 |  | 2021-06-29 10:09 | 2021-06-29 10:20 | 2021-06-24 13:06 | 2021-07-29 14:00 | CR0012216 | Support & AdminAgent Commission ManagementAgreementFF Compensation Agreement Creation | OPUS-ACM | 2021-W26 | 2021-06 | 168 | 72 | 105.8222 | 5 | 1 | 2 | 0.03 | 193499 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0 | 0 | 2021-03 | 0 | 0
351 | CR0012216 | CTASK0020549 | Closed | OPUS-ACM | Nhien Nguyen | 2 | 2 | 2020-06-30 11:10 | 2020-06-01 11:10 | Container | Support & Admin | Agent Commission Management | Agreement | FF Compensation Agreement Creation |  | NA *ACM* Adding calulation settings on FF Compensation Agreement Creation module | 2021-03-15 14:25 | 2021-04-30 14:25 | 2021-04-30 09:48 | 2021-06-11 12:11 | 2021-06-24 10:09 |  | 2021-06-29 10:09 | 2021-06-29 10:20 | 2021-06-24 13:06 | 2021-07-29 14:00 | CR0012216 | Support & AdminAgent Commission ManagementAgreementFF Compensation Agreement Creation | OPUS-ACM | 2021-W26 | 2021-06 | 168 | 72 | 105.8222 | 5 | 1 | 2 | 0.03 | 183364 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0.54545 | 1.2 | 2021-03 | 0 | 0
352 | CR0012216 | CTASK0023675 | Closed | OPUS-ACM | Huynh Tuan Khanh | 70 | 70 | 2021-04-30 15:52 | 2021-03-15 15:52 | Container | Support & Admin | Agent Commission Management | Agreement | FF Compensation Agreement Creation |  | NA *ACM* Adding calulation settings on FF Compensation Agreement Creation module | 2021-03-15 14:25 | 2021-04-30 14:25 | 2021-04-30 09:48 | 2021-06-11 12:11 | 2021-06-24 10:09 |  | 2021-06-29 10:09 | 2021-06-29 10:20 | 2021-06-24 13:06 | 2021-07-29 14:00 | CR0012216 | Support & AdminAgent Commission ManagementAgreementFF Compensation Agreement Creation | OPUS-ACM | 2021-W26 | 2021-06 | 168 | 72 | 105.8222 | 5 | 1 | 2 | 0.03 | 193499 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0 | 0 | 2021-03 | 0 | 0
353 | CR0012216 | CTASK0020645 | Closed | OPUS-ACM | Nhien Nguyen | 14 | 14 | 2020-07-31 12:58 | 2020-07-01 12:58 | Container | Support & Admin | Agent Commission Management | Agreement | FF Compensation Agreement Creation |  | [Dev][NA *ACM* Adding calulation settings on FF Compensation Agreement Creation module][Separated from Parent CTASK0020549] | 2021-03-15 14:25 | 2021-04-30 14:25 | 2021-04-30 09:48 | 2021-06-11 12:11 | 2021-06-24 10:09 |  | 2021-06-29 10:09 | 2021-06-29 10:20 | 2021-06-24 13:06 | 2021-07-29 14:00 | CR0012216 | Support & AdminAgent Commission ManagementAgreementFF Compensation Agreement Creation | OPUS-ACM | 2021-W26 | 2021-06 | 168 | 72 | 105.8222 | 5 | 1 | 2 | 0.03 | 183364 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0.54545 | 1.2 | 2021-03 | 0 | 0
354 | CR0012216 | CTASK0020548 | Closed | OPUS-ACM | Huynh Tuan Khanh | 46 | 46 | 2020-06-30 11:09 | 2020-06-01 11:09 | Container | Support & Admin | Agent Commission Management | Agreement | FF Compensation Agreement Creation |  | NA *ACM* Adding calulation settings on FF Compensation Agreement Creation module | 2021-03-15 14:25 | 2021-04-30 14:25 | 2021-04-30 09:48 | 2021-06-11 12:11 | 2021-06-24 10:09 |  | 2021-06-29 10:09 | 2021-06-29 10:20 | 2021-06-24 13:06 | 2021-07-29 14:00 | CR0012216 | Support & AdminAgent Commission ManagementAgreementFF Compensation Agreement Creation | OPUS-ACM | 2021-W26 | 2021-06 | 168 | 72 | 105.8222 | 5 | 1 | 2 | 0.03 | 193499 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0 | 0 | 2021-03 | 0 | 0
355 | CR0013877 | CTASK0027577 | Implemented | OPUS-BKG-M | Loc Tran | 8 | 8 | 2021-06-30 10:16 | 2021-06-14 10:16 | Container | Service Management |  |  |  |  | [Design]Opus to send auto cancellation to ONE QUOTE (KT) bypassing AUTO EDI HOLD flag | 2021-06-16 10:55 | 2021-07-22 02:00 | 2021-07-20 13:40 | 2021-08-04 09:25 | 2021-08-04 09:34 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-08-12 16:04 |  | CR0013877 | Service Management | OPUS-BKG-M | 2021-W33 | 2021-08 | 65 | 59 | 61.962 | 4 | 1 | 1 | 0.04 | 193503 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 5 | 22 | 0.33333 | 0.28571 | 2021-06 | 0 | 0
356 | CR0013877 | CTASK0027580 | Implemented | OPUS-BKG-M | Loc Tran | 19 | 10 | 2021-07-31 18:10 | 2021-07-01 18:10 | Container | Service Management |  |  |  |  | [Testing]Opus to send auto cancellation to ONE QUOTE (KT) bypassing AUTO EDI HOLD flag | 2021-06-16 10:55 | 2021-07-22 02:00 | 2021-07-20 13:40 | 2021-08-04 09:25 | 2021-08-04 09:34 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-08-12 16:04 |  | CR0013877 | Service Management | OPUS-BKG-M | 2021-W33 | 2021-08 | 65 | 59 | 61.962 | 4 | 1 | 1 | 0.04 | 193503 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 5 | 22 | 0.33333 | 0.28571 | 2021-06 | 0 | 0
357 | CR0013877 | CTASK0027579 | Implemented | OPUS-BKG-M | Loc Tran | 34 | 37 | 2021-06-30 10:17 | 2021-06-16 10:17 | Container | Service Management |  |  |  |  | [Development]Opus to send auto cancellation to ONE QUOTE (KT) bypassing AUTO EDI HOLD flag | 2021-06-16 10:55 | 2021-07-22 02:00 | 2021-07-20 13:40 | 2021-08-04 09:25 | 2021-08-04 09:34 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-08-12 16:04 |  | CR0013877 | Service Management | OPUS-BKG-M | 2021-W33 | 2021-08 | 65 | 59 | 61.962 | 4 | 1 | 1 | 0.04 | 193503 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 5 | 22 | 0.33333 | 0.28571 | 2021-06 | 0 | 0
358 | CR0013877 | CTASK0027582 | Implemented | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-08-17 11:31 | 2021-08-09 11:31 | Container | Service Management |  |  |  |  | [Deployment]Opus to send auto cancellation to ONE QUOTE (KT) bypassing AUTO EDI HOLD flag | 2021-06-16 10:55 | 2021-07-22 02:00 | 2021-07-20 13:40 | 2021-08-04 09:25 | 2021-08-04 09:34 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-08-12 16:04 |  | CR0013877 | Service Management | OPUS-BKG-M | 2021-W33 | 2021-08 | 65 | 59 | 61.962 | 4 | 1 | 1 | 0.04 | 193503 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 5 | 22 | 0.33333 | 0.28571 | 2021-06 | 0 | 0
359 | CR0013508 | CTASK0025278 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-05-12 14:49 | 2021-05-11 10:48 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment]Modify the logic to populate VENT_NUM & VENT_CMH in COPARN's FF | 2021-04-07 21:42 | 2021-04-29 | 2021-04-28 09:54 | 2021-05-06 17:59 | 2021-05-06 18:21 |  | 2021-05-18 10:00 | 2021-05-18 11:00 | 2021-05-07 09:03 | 2021-06-17 14:00 | CR0013508 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W20 | 2021-05 | 32 | 32 | 40.5122 | 4 | 1 | 1 | 0.03 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
360 | CR0013508 | CTASK0025277 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-04-23 12:27 | 2021-04-22 12:27 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing]Modify the logic to populate VENT_NUM & VENT_CMH in COPARN's FF | 2021-04-07 21:42 | 2021-04-29 | 2021-04-28 09:54 | 2021-05-06 17:59 | 2021-05-06 18:21 |  | 2021-05-18 10:00 | 2021-05-18 11:00 | 2021-05-07 09:03 | 2021-06-17 14:00 | CR0013508 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W20 | 2021-05 | 32 | 32 | 40.5122 | 4 | 1 | 1 | 0.03 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
361 | CR0013508 | CTASK0025276 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 16 | 16 | 2021-04-10 02:00 | 2021-04-05 11:15 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development]Modify the logic to populate VENT_NUM & VENT_CMH in COPARN's FF | 2021-04-07 21:42 | 2021-04-29 | 2021-04-28 09:54 | 2021-05-06 17:59 | 2021-05-06 18:21 |  | 2021-05-18 10:00 | 2021-05-18 11:00 | 2021-05-07 09:03 | 2021-06-17 14:00 | CR0013508 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W20 | 2021-05 | 32 | 32 | 40.5122 | 4 | 1 | 1 | 0.03 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
362 | CR0013508 | CTASK0025220 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-02-09 12:32 | 2021-02-05 12:28 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design]Modify the logic to populate VENT_NUM & VENT_CMH in COPARN's FF | 2021-04-07 21:42 | 2021-04-29 | 2021-04-28 09:54 | 2021-05-06 17:59 | 2021-05-06 18:21 |  | 2021-05-18 10:00 | 2021-05-18 11:00 | 2021-05-07 09:03 | 2021-06-17 14:00 | CR0013508 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W20 | 2021-05 | 32 | 32 | 40.5122 | 4 | 1 | 1 | 0.03 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
363 | CR0012822 | CTASK0021144 | Closed | OPUS-BKG-M | Kieu Le | 10 | 12 | 2020-07-25 02:00 | 2020-07-20 02:24 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] [CLT Internal] Performance Improvement on Standby Booking Status Report. | 2020-07-16 13:50 | 2020-08-20 02:00 | 2020-08-13 10:01 | 2020-08-18 21:01 | 2020-08-19 13:12 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-19 13:13 | 2020-09-24 13:00 | CR0012822 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W35 | 2020-08 | 45 | 48 | 39.8401 | 4 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 1 | 1 | 1 | 1 | 12 | 30 | 0 | 0.4 | 2020-07 | 1 | 1
364 | CR0012822 | CTASK0021114 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2020-07-11 01:41 | 2020-07-06 02:41 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] [CLT Internal] Performance Improvement on Standby Booking Status Report. | 2020-07-16 13:50 | 2020-08-20 02:00 | 2020-08-13 10:01 | 2020-08-18 21:01 | 2020-08-19 13:12 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-19 13:13 | 2020-09-24 13:00 | CR0012822 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W35 | 2020-08 | 45 | 48 | 39.8401 | 4 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 1 | 1 | 1 | 1 | 12 | 30 | 0 | 0.4 | 2020-07 | 1 | 1
365 | CR0012822 | CTASK0021147 | Closed | OPUS-BKG-M | Kieu Le | 15 | 16 | 2020-07-25 01:25 | 2020-07-20 02:25 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] [CLT Internal] Performance Improvement on Standby Booking Status Report. | 2020-07-16 13:50 | 2020-08-20 02:00 | 2020-08-13 10:01 | 2020-08-18 21:01 | 2020-08-19 13:12 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-19 13:13 | 2020-09-24 13:00 | CR0012822 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W35 | 2020-08 | 45 | 48 | 39.8401 | 4 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 1 | 1 | 1 | 1 | 12 | 30 | 0 | 0.4 | 2020-07 | 1 | 1
366 | CR0012822 | CTASK0021149 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2020-08-31 18:58 | 2020-08-01 18:58 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] [CLT Internal] Performance Improvement on Standby Booking Status Report. | 2020-07-16 13:50 | 2020-08-20 02:00 | 2020-08-13 10:01 | 2020-08-18 21:01 | 2020-08-19 13:12 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-19 13:13 | 2020-09-24 13:00 | CR0012822 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W35 | 2020-08 | 45 | 48 | 39.8401 | 4 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 1 | 1 | 1 | 1 | 12 | 30 | 0 | 0.4 | 2020-07 | 1 | 1
367 | CR0011700 | CTASK0016408 | Closed | OPUS-BKG-M | Kieu Le | 78 | 80 | 2019-10-25 16:42 | 2019-09-30 16:42 | Container | Sales Management | Space Control |  |  |  | Asia - SPC - Standby Group SCRFA setup in Customer Constraint | 2019-10-04 11:51 | 2019-11-12 | 2019-11-11 18:00 | 2019-11-20 18:04 | 2019-11-21 11:34 |  | 2019-12-04 11:34 | 2019-12-03 15:49 | 2019-11-22 11:34 | 2019-12-23 14:33 | CR0011700 | Sales ManagementSpace Control | OPUS-SPC | 2019-W49 | 2019-12 | 78 | 80 | 60.9881 | 1 | 1 | 1 | 0.05 | 153106 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 18 | 0 | 0.4 | 2019-10 | 0 | 0
368 | CR0012324 | CTASK0018651 | Closed | OPUS-TRS | Giang Nguyen Hoang | 47 | 52 | 2020-04-30 10:35 | 2020-04-06 10:35 | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | NA *TRS* - New coulmn should be added in Railbill UI's to capture CAED # or CERS # (eComm - CR0012196) (OPUS -CR0012195) | 2020-04-06 10:33 | 2020-05-15 18:00 | 2020-04-22 14:29 | 2020-05-21 04:51 | 2020-05-21 10:44 |  | 2020-06-02 11:00 | 2020-06-02 10:23 | 2020-05-21 22:50 | 2020-06-09 00:53 | CR0012324 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2020-W23 | 2020-06 | 99 | 104 | 57.0186 | 2 | 1 | 2 | 0.08 | 183440 | 1.1 | 0 | 0 | 0 | 2 | 1 | 2 | 5 | 29 | 0 | 0 | 2020-04 | 0 | 0
369 | CR0012324 | CTASK0018650 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 52 | 52 | 2020-04-30 10:34 | 2020-04-06 10:34 | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | NA *TRS* - New coulmn should be added in Railbill UI's to capture CAED # or CERS # (eComm - CR0012196) (OPUS -CR0012195) | 2020-04-06 10:33 | 2020-05-15 18:00 | 2020-04-22 14:29 | 2020-05-21 04:51 | 2020-05-21 10:44 |  | 2020-06-02 11:00 | 2020-06-02 10:23 | 2020-05-21 22:50 | 2020-06-09 00:53 | CR0012324 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2020-W23 | 2020-06 | 99 | 104 | 57.0186 | 2 | 1 | 2 | 0.08 | 183432 | 1.1 | 0 | 0 | 0 | 2 | 1 | 2 | 5 | 29 | 0 | 0 | 2020-04 | 0 | 0
370 | CR0011043 | CTASK0014950 | Closed | OPUS-MNR | Tuyen Truong | 19 | 19 |  |  | Container | Equipment Management | M&R | Disposal | Invoice | Disposal Invoice Issue | [actual] EUA - M&R Disposal Invoice Lacking "ONE" co. Livery & automated BANK DETAILS. | 2019-06-25 13:21 | 2019-07-12 13:19 | 2019-07-02 11:13 | 2019-09-26 09:46 | 2019-09-30 10:10 |  | 2019-10-15 10:09 | 2019-10-08 10:52 | 2019-09-30 18:00 | 2019-11-10 14:00 | CR0011043 | Equipment ManagementM&RDisposalInvoiceDisposal Invoice Issue | OPUS-MNR | 2019-W42 | 2019-10 | 65 | 46 | 111.8663 | 3 | 1 | 1 | 0.02 | 173255 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-06 | 0 | 0
371 | CR0011043 | CTASK0015370 | Closed | OPUS-MNR | Tuyen Truong | 1 | 1 |  |  | Container | Equipment Management | M&R | Disposal | Invoice | Disposal Invoice Issue | [Documentation]EUA - M&R Disposal Invoice Lacking "ONE" co. Livery & automated BANK DETAILS. | 2019-06-25 13:21 | 2019-07-12 13:19 | 2019-07-02 11:13 | 2019-09-26 09:46 | 2019-09-30 10:10 |  | 2019-10-15 10:09 | 2019-10-08 10:52 | 2019-09-30 18:00 | 2019-11-10 14:00 | CR0011043 | Equipment ManagementM&RDisposalInvoiceDisposal Invoice Issue | OPUS-MNR | 2019-W42 | 2019-10 | 65 | 46 | 111.8663 | 3 | 1 | 1 | 0.02 | 173255 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-06 | 0 | 0
372 | CR0011043 | CTASK0015058 | Closed | OPUS-MNR | Tuyen Truong | 46 | 46 | 2019-07-12 07:54 | 2019-06-21 07:53 | Container | Equipment Management | M&R | Disposal | Invoice | Disposal Invoice Issue | [Initial]EUA - M&R Disposal Invoice Lacking "ONE" co. Livery & automated BANK DETAILS. | 2019-06-25 13:21 | 2019-07-12 13:19 | 2019-07-02 11:13 | 2019-09-26 09:46 | 2019-09-30 10:10 |  | 2019-10-15 10:09 | 2019-10-08 10:52 | 2019-09-30 18:00 | 2019-11-10 14:00 | CR0011043 | Equipment ManagementM&RDisposalInvoiceDisposal Invoice Issue | OPUS-MNR | 2019-W42 | 2019-10 | 65 | 46 | 111.8663 | 3 | 1 | 1 | 0.02 | 173255 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-06 | 0 | 0
373 | CR0013827 | CTASK0026978 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 22 | 22 | 2021-05-27 16:58 | 2021-05-10 09:58 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | US Cargo Release | [Development+ Testing+ Deployment] NA *EDI* VENDOR - TDC315 - Addition of OPUS Yard code in the Flat File | 2021-05-24 10:53 | 2021-06-30 23:53 | 2021-06-25 15:27 | 2021-07-01 10:25 | 2021-07-05 17:35 |  | 2021-07-13 17:34 | 2021-07-13 15:56 | 2021-07-06 08:40 | 2021-07-22 18:08 | CR0013827 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseUS Cargo Release | OPUS-BKG-IB | 2021-W28 | 2021-07 | 36 | 38 | 50.2781 | 3 | 1 | 1 | 0.03 | 193512 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0.2963 | 0.3125 | 2021-05 | 0 | 0
374 | CR0013827 | CTASK0026890 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 8 | 10 | 2021-05-10 16:29 | 2021-05-05 16:29 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | US Cargo Release | [Estimation] NA *EDI* VENDOR - TDC315 - Addition of OPUS Yard code in the Flat File | 2021-05-24 10:53 | 2021-06-30 23:53 | 2021-06-25 15:27 | 2021-07-01 10:25 | 2021-07-05 17:35 |  | 2021-07-13 17:34 | 2021-07-13 15:56 | 2021-07-06 08:40 | 2021-07-22 18:08 | CR0013827 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseUS Cargo Release | OPUS-BKG-IB | 2021-W28 | 2021-07 | 36 | 38 | 50.2781 | 3 | 1 | 1 | 0.03 | 193512 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0.2963 | 0.3125 | 2021-05 | 0 | 0
375 | CR0013827 | CTASK0027987 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 6 | 6 | 2021-07-06 18:31 | 2021-07-05 09:31 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | US Cargo Release | [Deployment] NA *EDI* VENDOR - TDC315 - Addition of OPUS Yard code in the Flat File | 2021-05-24 10:53 | 2021-06-30 23:53 | 2021-06-25 15:27 | 2021-07-01 10:25 | 2021-07-05 17:35 |  | 2021-07-13 17:34 | 2021-07-13 15:56 | 2021-07-06 08:40 | 2021-07-22 18:08 | CR0013827 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseUS Cargo Release | OPUS-BKG-IB | 2021-W28 | 2021-07 | 36 | 38 | 50.2781 | 3 | 1 | 1 | 0.03 | 193512 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0.2963 | 0.3125 | 2021-05 | 0 | 0
376 | CR0013924 | CTASK0026972 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] [CLT-Internal] LA - CSVC - System didn't update Empty pick up date when changing VVD/POL | 2021-05-25 08:50 | 2021-06-25 08:50 | 2021-06-22 13:25 | 2021-07-15 17:24 | 2021-07-16 14:56 |  | 2021-07-27 10:56 | 2021-07-27 10:56 | 2021-07-19 16:52 | 2021-08-03 14:00 | CR0013924 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W30 | 2021-07 | 24 | 26 | 63.0877 | 4 | 1 | 1 | 0.02 | 193525 | 2 | 1 | 0 | 0 | 1 | 1 | 2 | 7 | 28 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
377 | CR0013924 | CTASK0026971 | Closed | OPUS-BKG-EBKG | Vinh Tran | 13 | 16 |  |  | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] [CLT-Internal] LA - CSVC - System didn't update Empty pick up date when changing VVD/POL | 2021-05-25 08:50 | 2021-06-25 08:50 | 2021-06-22 13:25 | 2021-07-15 17:24 | 2021-07-16 14:56 |  | 2021-07-27 10:56 | 2021-07-27 10:56 | 2021-07-19 16:52 | 2021-08-03 14:00 | CR0013924 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W30 | 2021-07 | 24 | 26 | 63.0877 | 4 | 1 | 1 | 0.02 | 193525 | 2 | 1 | 0 | 0 | 1 | 1 | 2 | 7 | 28 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
378 | CR0013924 | CTASK0026969 | Closed | OPUS-BKG-EBKG | Vinh Tran | 2 | 2 | 2021-05-13 02:00 | 2021-05-12 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] [CLT-Internal] LA - CSVC - System didn't update Empty pick up date when changing VVD/POL | 2021-05-25 08:50 | 2021-06-25 08:50 | 2021-06-22 13:25 | 2021-07-15 17:24 | 2021-07-16 14:56 |  | 2021-07-27 10:56 | 2021-07-27 10:56 | 2021-07-19 16:52 | 2021-08-03 14:00 | CR0013924 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W30 | 2021-07 | 24 | 26 | 63.0877 | 4 | 1 | 1 | 0.02 | 193525 | 2 | 1 | 0 | 0 | 1 | 1 | 2 | 7 | 28 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
379 | CR0013924 | CTASK0026970 | Closed | OPUS-BKG-EBKG | Vinh Tran | 5 | 4 | 2021-07-23 02:00 | 2021-07-20 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deplopment] [CLT-Internal] LA - CSVC - System didn't update Empty pick up date when changing VVD/POL | 2021-05-25 08:50 | 2021-06-25 08:50 | 2021-06-22 13:25 | 2021-07-15 17:24 | 2021-07-16 14:56 |  | 2021-07-27 10:56 | 2021-07-27 10:56 | 2021-07-19 16:52 | 2021-08-03 14:00 | CR0013924 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W30 | 2021-07 | 24 | 26 | 63.0877 | 4 | 1 | 1 | 0.02 | 193525 | 2 | 1 | 0 | 0 | 1 | 1 | 2 | 7 | 28 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
380 | CR0013132 | CTASK0022829 | Closed | OPUS-SCE | Son Nguyen The | 12 | 12 |  |  | Container | Service Management | SCEM | Customer Order Plan |  |  | [Documentation][CLT Internal] OPUS Service enhancement for triggering NFD event | 2020-10-14 13:44 | 2020-10-22 19:14 | 2020-10-19 15:29 |  | 2020-10-19 15:36 |  | 2020-11-03 12:00 | 2020-11-03 12:00 | 2020-10-21 19:17 | 2020-12-19 14:00 | CR0013132 | Service ManagementSCEMCustomer Order Plan | OPUS-SCE | 2020-W45 | 2020-11 | 24 | 15 | 19.9275 | 2 | 1 | 1 | 0.03 | 193531 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0 | 2020-10 | 0 | 0
381 | CR0013132 | CTASK0023045 | Closed | OPUS-SCE | Son Nguyen The | 12 | 15 | 2020-10-31 17:00 | 2020-10-15 17:00 | Container | Service Management | SCEM | Customer Order Plan |  |  | [CLT Internal] OPUS Service enhancement for triggering NFD event | 2020-10-14 13:44 | 2020-10-22 19:14 | 2020-10-19 15:29 |  | 2020-10-19 15:36 |  | 2020-11-03 12:00 | 2020-11-03 12:00 | 2020-10-21 19:17 | 2020-12-19 14:00 | CR0013132 | Service ManagementSCEMCustomer Order Plan | OPUS-SCE | 2020-W45 | 2020-11 | 24 | 15 | 19.9275 | 2 | 1 | 1 | 0.03 | 193531 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0 | 2020-10 | 0 | 0
382 | CR0012490 | CTASK0019869 | Closed | OPUS-BKG-M | Thien Lai | 12 | 12 | 2020-05-02 00:30 | 2020-04-27 09:29 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Design] EUA - Add functionality to Group VVD Port Assign – Broken Routes | 2020-05-26 09:59 | 2020-06-18 | 2020-06-11 15:22 | 2020-08-20 20:50 | 2020-08-24 15:42 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-28 23:58 | 2020-10-08 13:00 | CR0012490 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2020-W37 | 2020-09 | 52 | 52 | 105.0008 | 5 | 1 | 1 | 0.02 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-05 | 0 | 0
383 | CR0012490 | CTASK0020911 | Closed | OPUS-BKG-M | Thien Lai | 6 | 6 | 2020-06-13 00:13 | 2020-06-01 09:13 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Development] EUA - Add functionality to Group VVD Port Assign – Broken Routes | 2020-05-26 09:59 | 2020-06-18 | 2020-06-11 15:22 | 2020-08-20 20:50 | 2020-08-24 15:42 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-28 23:58 | 2020-10-08 13:00 | CR0012490 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2020-W37 | 2020-09 | 52 | 52 | 105.0008 | 5 | 1 | 1 | 0.02 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-05 | 0 | 0
384 | CR0012490 | CTASK0019946 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-09-30 18:48 | 2020-09-01 18:48 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Deployment] EUA - Add functionality to Group VVD Port Assign – Broken Routes | 2020-05-26 09:59 | 2020-06-18 | 2020-06-11 15:22 | 2020-08-20 20:50 | 2020-08-24 15:42 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-28 23:58 | 2020-10-08 13:00 | CR0012490 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2020-W37 | 2020-09 | 52 | 52 | 105.0008 | 5 | 1 | 1 | 0.02 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-05 | 0 | 0
385 | CR0012490 | CTASK0019942 | Closed | OPUS-BKG-M | Thien Lai | 22 | 22 | 2020-05-31 22:20 | 2020-05-27 09:20 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Development] EUA - Add functionality to Group VVD Port Assign – Broken Routes | 2020-05-26 09:59 | 2020-06-18 | 2020-06-11 15:22 | 2020-08-20 20:50 | 2020-08-24 15:42 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-28 23:58 | 2020-10-08 13:00 | CR0012490 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2020-W37 | 2020-09 | 52 | 52 | 105.0008 | 5 | 1 | 1 | 0.02 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-05 | 0 | 0
386 | CR0012490 | CTASK0019944 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-07-04 22:01 | 2020-05-27 09:01 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Testing] EUA - Add functionality to Group VVD Port Assign – Broken Routes | 2020-05-26 09:59 | 2020-06-18 | 2020-06-11 15:22 | 2020-08-20 20:50 | 2020-08-24 15:42 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-28 23:58 | 2020-10-08 13:00 | CR0012490 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2020-W37 | 2020-09 | 52 | 52 | 105.0008 | 5 | 1 | 1 | 0.02 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-05 | 0 | 0
387 | CR0011919 | CTASK0018173 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 8 | 8 | 2020-02-29 18:00 | 2020-02-10 09:00 | Container | Service Management | Trans S/O | Service Order | Creation | Supplement | NEGO COLUMN ERROR - TEST AND PRODUCTION - BSIU2901197 | 2020-02-13 09:31 | 2020-02-29 18:00 | 2020-02-25 15:17 | 2020-03-19 17:46 | 2020-03-23 10:27 |  | 2020-03-31 11:00 | 2020-03-31 11:00 | 2020-03-23 11:04 | 2020-04-30 13:00 | CR0011919 | Service ManagementTrans S/OService OrderCreationSupplement | OPUS-TRS | 2020-W14 | 2020-03 | 16 | 16 | 47.0617 | 2 | 1 | 2 | 0.01 | 183432 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 25 | 0 | 0 | 2020-02 | 0 | 0
388 | CR0011919 | CTASK0018174 | Closed | OPUS-TRS | Giang Nguyen Hoang | 8 | 8 | 2020-02-29 18:00 | 2020-02-10 09:00 | Container | Service Management | Trans S/O | Service Order | Creation | Supplement | NEGO COLUMN ERROR - TEST AND PRODUCTION - BSIU2901197 | 2020-02-13 09:31 | 2020-02-29 18:00 | 2020-02-25 15:17 | 2020-03-19 17:46 | 2020-03-23 10:27 |  | 2020-03-31 11:00 | 2020-03-31 11:00 | 2020-03-23 11:04 | 2020-04-30 13:00 | CR0011919 | Service ManagementTrans S/OService OrderCreationSupplement | OPUS-TRS | 2020-W14 | 2020-03 | 16 | 16 | 47.0617 | 2 | 1 | 2 | 0.01 | 183440 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 25 | 0 | 0 | 2020-02 | 0 | 0
389 | CR0012526 | CTASK0020531 | Closed | OPUS-VSK | Thuan Tran | 20 | 20 | 2020-08-31 19:02 | 2020-07-01 19:02 | Container | Vessel Operation | Vessel Schedule | VSL SKD | VSL SKD Update | C/ SKD Update and Simulation | [CLV] VSK Logic Change | 2020-05-27 15:17 | 2020-08-21 15:16 | 2020-06-15 13:50 | 2020-08-26 14:07 | 2020-08-27 09:32 |  | 2020-09-08 10:00 | 2020-09-08 13:19 | 2020-09-02 16:11 | 2020-10-09 13:00 | CR0012526 | Vessel OperationVessel ScheduleVSL SKDVSL SKD UpdateC/ SKD Update and Simulation | OPUS-VSK | 2020-W37 | 2020-09 | 120 | 120 | 103.7797 | 3 | 1 | 3 | 0.05 | 183423 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-05 | 0 | 0
390 | CR0012526 | CTASK0020530 | Closed | OPUS-VSK | Toai Phan | 70 | 70 | 2020-07-15 18:59 | 2020-06-01 18:59 | Container | Vessel Operation | Vessel Schedule | VSL SKD | VSL SKD Update | C/ SKD Update and Simulation | [CLV] VSK Logic Change | 2020-05-27 15:17 | 2020-08-21 15:16 | 2020-06-15 13:50 | 2020-08-26 14:07 | 2020-08-27 09:32 |  | 2020-09-08 10:00 | 2020-09-08 13:19 | 2020-09-02 16:11 | 2020-10-09 13:00 | CR0012526 | Vessel OperationVessel ScheduleVSL SKDVSL SKD UpdateC/ SKD Update and Simulation | OPUS-VSK | 2020-W37 | 2020-09 | 120 | 120 | 103.7797 | 3 | 1 | 3 | 0.05 | 183427 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 36 | 0 | 2 | 2020-05 | 0 | 0
391 | CR0012526 | CTASK0021049 | Closed | OPUS-VSK | Tuan Pham Huu | 30 | 30 | 2020-09-30 12:54 | 2020-07-01 12:54 | Container | Vessel Operation | Vessel Schedule | VSL SKD | VSL SKD Update | C/ SKD Update and Simulation | [CLV] VSK Logic Change | 2020-05-27 15:17 | 2020-08-21 15:16 | 2020-06-15 13:50 | 2020-08-26 14:07 | 2020-08-27 09:32 |  | 2020-09-08 10:00 | 2020-09-08 13:19 | 2020-09-02 16:11 | 2020-10-09 13:00 | CR0012526 | Vessel OperationVessel ScheduleVSL SKDVSL SKD UpdateC/ SKD Update and Simulation | OPUS-VSK | 2020-W37 | 2020-09 | 120 | 120 | 103.7797 | 3 | 1 | 3 | 0.05 | 193523 | 1 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-05 | 0 | 0
392 | CR0013047 | CTASK0022326 | Closed | OPUS-BKG-M | Loc Tran | 16 | 16 | 2020-11-30 12:30 | 2020-11-01 12:30 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Design][CLT Internal] Limit special character for the special cargo remark | 2020-11-09 09:36 | 2020-12-03 | 2020-11-26 17:25 | 2020-12-08 15:13 | 2020-12-08 17:24 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2020-12-08 18:23 | 2021-02-25 14:00 | CR0013047 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W4 | 2021-01 | 20 | 20 | 78.0164 | 2 | 1 | 1 | 0.01 | 193503 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.33333 | 0.28571 | 2020-11 | 0 | 0
393 | CR0013047 | CTASK0024882 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-01-26 12:11 | 2021-01-18 12:11 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Deployment][CLT Internal] Limit special character for the special cargo remark | 2020-11-09 09:36 | 2020-12-03 | 2020-11-26 17:25 | 2020-12-08 15:13 | 2020-12-08 17:24 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2020-12-08 18:23 | 2021-02-25 14:00 | CR0013047 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W4 | 2021-01 | 20 | 20 | 78.0164 | 2 | 1 | 1 | 0.01 | 193503 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.33333 | 0.28571 | 2020-11 | 0 | 0
394 | CR0013051 | CTASK0023335 | Closed | OPUS-ACM | Huynh Tuan Khanh | 112 | 100 | 2020-11-30 15:56 | 2020-11-02 15:56 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Enhancement request] Customer Integration Screen - Auto Populate fields based on Location code & other logic | 2020-11-04 11:40 | 2020-11-30 20:39 | 2020-11-30 14:41 | 2020-12-23 10:06 | 2020-12-23 13:56 |  | 2020-12-29 13:56 | 2020-12-29 17:56 | 2020-12-23 17:45 | 2021-01-29 14:00 | CR0013051 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2020-W53 | 2020-12 | 112 | 100 | 55.0949 | 1 | 1 | 1 | 0.08 | 193499 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0 | 2020-11 | 0 | 0
395 | CR0011274 | CTASK0014852 | Closed | OPUS-TES | Thai Nguyen | 113 | 120 |  |  | Container | Service Management | TML INV |  |  |  | (actual) Update TES SVLDTM calculation logic after CR0010731 implementation | 2019-07-08 15:50 | 2019-08-23 20:00 | 2019-07-12 15:06 | 2019-08-15 18:33 | 2019-08-19 13:52 |  | 2019-08-27 09:00 | 2019-08-27 09:56 | 2019-09-03 09:56 | 2019-09-03 12:48 | CR0011274 | Service ManagementTML INV | OPUS-TES | 2019-W35 | 2019-08 | 113 | 120 | 49.7156 | 1 | 1 | 1 | 0.1 | 173249 | 0.8 | 0 | 0 | 0 | 2 | 1 | 1 | 4 | 6 | 0 | 0.6 | 2019-07 | 0 | 0
396 | CR0012297 | CTASK0018471 | Closed | OPUS-SCO | Lien Le | 142 | 142 |  |  | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Agent Manager |  | [Actual][CLV] EUA - CLEAR - Add field "No OTS" button to CAM so that emails can be assigned to customers with no OTS | 2020-03-03 10:40 | 2020-03-31 10:40 | 2020-03-06 10:34 | 2020-03-17 22:41 | 2020-03-18 10:53 |  | 2020-03-24 10:53 | 2020-03-24 10:11 | 2020-03-18 17:19 | 2020-04-23 13:00 | CR0012297 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Agent Manager | OPUS-SCO | 2020-W13 | 2020-03 | 142 | 0 | 21.0089 | 1 | 1 | 1 | 0 | 193441 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 25 | 0 | 0 | 2020-03 | 0 | 0
397 | CR0013406 | CTASK0024819 | Closed | OPUS-SCG | Trang Duy Thong | 60 | 60 | 2021-02-26 18:05 | 2021-01-25 18:05 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV]New SCMD // OPUS ENHANCEMENT REQUEST | 2021-02-03 11:06 | 2021-03-31 11:06 | 2021-03-17 11:40 | 2021-04-27 15:59 | 2021-04-27 16:40 |  | 2021-05-04 10:00 | 2021-05-04 16:39 | 2021-04-27 16:52 | 2021-06-03 14:00 | CR0013406 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2021-W18 | 2021-05 | 60 | 60 | 89.9538 | 1 | 1 | 1 | 0.03 | 193511 | 0.7 | 1 | 0 | 0 | 1 | 1 | 2 | 4 | 28 | 0.81818 | 0 | 2021-02 | 0 | 0
398 | CR0011864 | CTASK0016766 | Closed | OPUS-BKG-OB | Nam Nguyen | 31 | 30 | 2019-10-18 18:27 | 2019-10-16 18:27 | [6 empty] | [CLT Internal][License Service] Chrome v78 & CLP(Common Library Patch) v4.4 RD patch | 2019-10-18 14:11 | 2019-10-31 14:11 | 2019-10-22 13:51 | 2019-10-22 14:59 | 2019-10-22 14:59 |  | 2019-10-22 14:59 | 2019-10-22 09:18 | 2020-01-02 09:18 | 2020-02-01 14:00 | CR0011864 |  | OPUS-BKG-OB | 2019-W43 | 2019-10 | 83 | 54 | 4.0338 | 6 | 4 | 6 | 0.56 | 123048 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 10 | 0 | 0.46154 | 2019-10 | 0 | 0
399 | CR0011864 | CTASK0016787 | Closed | OPUS-PRI | Nhien Nguyen | 24 | 24 | [8 empty] | [CLT Internal][License Service] Chrome v78 & CLP(Common Library Patch) v4.4 RD patch | 2019-10-18 14:11 | 2019-10-31 14:11 | 2019-10-22 13:51 | 2019-10-22 14:59 | 2019-10-22 14:59 |  | 2019-10-22 14:59 | 2019-10-22 09:18 | 2020-01-02 09:18 | 2020-02-01 14:00 | CR0011864 |  | OPUS-PRI | 2019-W43 | 2019-10 | 83 | 54 | 4.0338 | 6 | 4 | 6 | 0.56 | 183364 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 10 | 0 | 0 | 2019-10 | 0 | 0
400 | CR0011864 | CTASK0016886 | Closed | OPUS-TRS | Giang Nguyen Hoang | 7 | 7 | [8 empty] | [CLT Internal][License Service] Chrome v78 & CLP(Common Library Patch) v4.4 RD patch | 2019-10-18 14:11 | 2019-10-31 14:11 | 2019-10-22 13:51 | 2019-10-22 14:59 | 2019-10-22 14:59 |  | 2019-10-22 14:59 | 2019-10-22 09:18 | 2020-01-02 09:18 | 2020-02-01 14:00 | CR0011864 |  | OPUS-TRS | 2019-W43 | 2019-10 | 83 | 54 | 4.0338 | 6 | 4 | 6 | 0.56 | 183440 | 0.6 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 10 | 0 | 0 | 2019-10 | 0 | 0
401 | CR0011864 | CTASK0016819 | Closed | OPUS-APR | Chuong Ta | 7 | 7 | [8 empty] | Chrome v78 & CLP(Common Library Patch) v4.4 RD patch | 2019-10-18 14:11 | 2019-10-31 14:11 | 2019-10-22 13:51 | 2019-10-22 14:59 | 2019-10-22 14:59 |  | 2019-10-22 14:59 | 2019-10-22 09:18 | 2020-01-02 09:18 | 2020-02-01 14:00 | CR0011864 |  | OPUS-APR | 2019-W43 | 2019-10 | 83 | 54 | 4.0338 | 6 | 4 | 6 | 0.56 | 183379 | 0.6 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 10 | 0 | 0 | 2019-10 | 0 | 0
402 | CR0011864 | CTASK0016884 | Closed | OPUS-TRS | Hieu Tran | 7 | 7 | [8 empty] | [CLT Internal][License Service] Chrome v78 & CLP(Common Library Patch) v4.4 RD patch | 2019-10-18 14:11 | 2019-10-31 14:11 | 2019-10-22 13:51 | 2019-10-22 14:59 | 2019-10-22 14:59 |  | 2019-10-22 14:59 | 2019-10-22 09:18 | 2020-01-02 09:18 | 2020-02-01 14:00 | CR0011864 |  | OPUS-TRS | 2019-W43 | 2019-10 | 83 | 54 | 4.0338 | 6 | 4 | 6 | 0.56 | 183400 | 1.1 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 10 | 0 | 0 | 2019-10 | 0 | 0
403 | CR0011864 | CTASK0016862 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 7 | 7 | [8 empty] | [CLT Internal][License Service] Chrome v78 & CLP(Common Library Patch) v4.4 RD patch | 2019-10-18 14:11 | 2019-10-31 14:11 | 2019-10-22 13:51 | 2019-10-22 14:59 | 2019-10-22 14:59 |  | 2019-10-22 14:59 | 2019-10-22 09:18 | 2020-01-02 09:18 | 2020-02-01 14:00 | CR0011864 |  | OPUS-TRS | 2019-W43 | 2019-10 | 83 | 54 | 4.0338 | 6 | 4 | 6 | 0.56 | 183432 | 0.6 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 10 | 0 | 0 | 2019-10 | 0 | 0
404 | CR0010296 | CTASK0017216 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 41 | 28 | 2019-11-29 17:44 | 2019-11-20 17:44 | Container | Service Management | Booking/Documentation | Advance Manifest | Canada ACI (Canada Office) | CRN Create | NA *CUST* CRN Create Screen Column Additions and Update of CRN Auto-Generate Logic | 2019-11-21 10:08 | 2020-03-31 10:20 | 2020-02-10 18:25 | 2020-02-28 00:31 | 2020-03-03 17:28 |  | 2020-03-10 17:28 | 2020-03-10 10:16 | 2020-03-06 01:30 | 2020-04-09 13:00 | CR0010296 | Service ManagementBooking/DocumentationAdvance ManifestCanada ACI (Canada Office)CRN Create | OPUS-BKG-MFT-M | 2020-W11 | 2020-03 | 41 | 28 | 110.3058 | 1 | 1 | 1 | 0.01 | 193506 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0.85714 | 2019-11 | 0 | 0
405 | CR0011987 | CTASK0017276 | Closed | OPUS-SCO | Hang To | 1 | 1 |  |  | Container | Statement Management | Statement Account Receivable |  |  |  | Change of logic of Onguard replacement project for cluster countries. | 2020-01-08 10:16 | 2020-01-14 10:16 | 2020-01-08 15:15 |  | 2020-01-08 15:16 |  | 2020-01-09 09:01 | 2020-01-09 12:24 | 2020-01-08 16:59 | 2020-02-08 14:00 | CR0011987 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W2 | 2020-01 | 0 | 0 | 0.94756 | 2 | 1 | 2 | 0 | 183344 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 10 | 0 | 0 | 2020-01 | 0 | 0
406 | CR0011987 | CTASK0017283 | Closed | OPUS-SCO | Chuong Ta | 1 | 1 |  |  | Container | Statement Management | Statement Account Receivable |  |  |  | Change of logic of Onguard replacement project for cluster countries. | 2020-01-08 10:16 | 2020-01-14 10:16 | 2020-01-08 15:15 |  | 2020-01-08 15:16 |  | 2020-01-09 09:01 | 2020-01-09 12:24 | 2020-01-08 16:59 | 2020-02-08 14:00 | CR0011987 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W2 | 2020-01 | 0 | 0 | 0.94756 | 2 | 1 | 2 | 0 | 183379 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 10 | 0 | 0 | 2020-01 | 0 | 0
407 | CR0011558 | CTASK0016135 | Closed | OPUS-BKG-M | Kieu Le | 24 | 24 | 2019-09-20 09:24 | 2019-09-09 09:24 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | NA Vendor EDI- Please have auto-request function for reefer cargo updates in OPUS to Automatically send EDI when Temperature changed in booking | 2019-09-25 17:30 | 2019-10-01 | 2019-09-30 17:10 | 2019-10-29 05:39 | 2019-10-29 11:03 |  | 2019-10-29 11:03 | 2019-11-05 11:34 | 2019-10-29 21:57 | 2019-11-05 22:04 | CR0011558 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2019-W44 | 2019-10 | 24 | 24 | 33.7311 | 1 | 1 | 1 | 0.03 | 153106 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 10 | 0 | 0 | 2019-09 | 0 | 0
408 | CR0011900 | CTASK0019285 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 16 | 16 | 2020-04-28 18:40 | 2020-03-31 11:40 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development]OPUS - Adding Company Name in the Booking Contact in the e-Booking Request Preview (CR0011348) | 2020-02-10 10:43 | 2020-03-17 | 2020-03-16 11:17 | 2020-05-06 09:33 | 2020-06-23 10:45 |  | 2020-06-30 10:00 | 2020-06-30 10:09 | 2020-06-23 11:20 | 2020-07-30 13:00 | CR0011900 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 93 | 92 | 140.9698 | 4 | 2 | 2 | 0.03 | 193488 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 2.1667 | 2020-02 | 0 | 0
409 | CR0011900 | CTASK0017567 | Closed | OPUS-BKG-M | Vinh Tran | 68 | 68 | 2020-03-07 | 2020-02-10 09:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Estimate] OPUS - Adding Company Name in the Booking Contact in the e-Booking Request Preview (CR0011348) | 2020-02-10 10:43 | 2020-03-17 | 2020-03-16 11:17 | 2020-05-06 09:33 | 2020-06-23 10:45 |  | 2020-06-30 10:00 | 2020-06-30 10:09 | 2020-06-23 11:20 | 2020-07-30 13:00 | CR0011900 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 93 | 92 | 140.9698 | 4 | 2 | 2 | 0.03 | 193525 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 0.45455 | 2020-02 | 0 | 0
410 | CR0011900 | CTASK0018864 | Closed | OPUS-BKG-M | Vinh Tran | 5 | 4 | 2020-06-24 02:00 | 2020-06-23 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] OPUS - Adding Company Name in the Booking Contact in the e-Booking Request Preview (CR0011348) | 2020-02-10 10:43 | 2020-03-17 | 2020-03-16 11:17 | 2020-05-06 09:33 | 2020-06-23 10:45 |  | 2020-06-30 10:00 | 2020-06-30 10:09 | 2020-06-23 11:20 | 2020-07-30 13:00 | CR0011900 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 93 | 92 | 140.9698 | 4 | 2 | 2 | 0.03 | 193525 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 0.45455 | 2020-02 | 0 | 0
411 | CR0011900 | CTASK0018863 | Closed | OPUS-BKG-M | Vinh Tran | 4 | 4 | 2020-03-11 02:00 | 2020-03-10 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] OPUS - Adding Company Name in the Booking Contact in the e-Booking Request Preview (CR0011348) | 2020-02-10 10:43 | 2020-03-17 | 2020-03-16 11:17 | 2020-05-06 09:33 | 2020-06-23 10:45 |  | 2020-06-30 10:00 | 2020-06-30 10:09 | 2020-06-23 11:20 | 2020-07-30 13:00 | CR0011900 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 93 | 92 | 140.9698 | 4 | 2 | 2 | 0.03 | 193525 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 0.45455 | 2020-02 | 0 | 0
412 | CR0012471 | CTASK0023039 | Closed | OPUS-SPC | Linh Nguyen | 98 | 100 | 2020-11-14 13:49 | 2020-10-11 13:48 | Container | Sales Management |  |  |  |  | Possibility to receive automatic notifications for chosen updates to the Master Constraints Table | 2020-10-27 16:45 | 2020-11-07 | 2020-11-06 16:19 | 2020-12-23 09:22 | 2020-12-23 13:34 |  | 2020-12-29 10:00 | 2020-12-29 10:00 | 2020-12-23 17:43 | 2021-01-28 14:00 | CR0012471 | Sales Management | OPUS-SPC | 2020-W53 | 2020-12 | 98 | 100 | 62.7191 | 1 | 1 | 1 | 0.07 | 193464 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0 | 2020-10 | 0 | 0
413 | CR0012507 | CTASK0019603 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 2 | 2 | 2020-07-03 12:22 | 2020-07-01 12:21 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment][CLT Internal] Auto Notification Enhancement in eBKG | 2020-04-29 10:51 | 2020-06-25 | 2020-05-29 14:26 | 2020-06-03 22:55 | 2020-07-01 15:07 |  | 2020-07-07 10:00 | 2020-07-07 10:00 | 2020-07-01 15:07 | 2020-08-06 13:00 | CR0012507 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W28 | 2020-07 | 41 | 41 | 68.9649 | 5 | 2 | 2 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 27 | 0 | 2.1667 | 2020-04 | 0 | 0
414 | CR0012507 | CTASK0019604 | Closed | OPUS-BKG-M | Vinh Tran | 4 | 4 | 2020-05-26 02:00 | 2020-05-25 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] [CLT Internal] Auto Notification Enhancement in eBKG | 2020-04-29 10:51 | 2020-06-25 | 2020-05-29 14:26 | 2020-06-03 22:55 | 2020-07-01 15:07 |  | 2020-07-07 10:00 | 2020-07-07 10:00 | 2020-07-01 15:07 | 2020-08-06 13:00 | CR0012507 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W28 | 2020-07 | 41 | 41 | 68.9649 | 5 | 2 | 2 | 0.02 | 193525 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 27 | 0 | 0.45455 | 2020-04 | 0 | 0
415 | CR0012507 | CTASK0019601 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 3 | 3 | 2020-05-08 14:28 | 2020-04-29 14:28 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] [CLT Internal] Auto Notification Enhancement in eBKG | 2020-04-29 10:51 | 2020-06-25 | 2020-05-29 14:26 | 2020-06-03 22:55 | 2020-07-01 15:07 |  | 2020-07-07 10:00 | 2020-07-07 10:00 | 2020-07-01 15:07 | 2020-08-06 13:00 | CR0012507 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W28 | 2020-07 | 41 | 41 | 68.9649 | 5 | 2 | 2 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 27 | 0 | 2.1667 | 2020-04 | 0 | 0
416 | CR0012507 | CTASK0019602 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 2 | 2 | 2020-05-07 18:46 | 2020-05-07 16:46 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] [CLT Internal] Auto Notification Enhancement in eBKG | 2020-04-29 10:51 | 2020-06-25 | 2020-05-29 14:26 | 2020-06-03 22:55 | 2020-07-01 15:07 |  | 2020-07-07 10:00 | 2020-07-07 10:00 | 2020-07-01 15:07 | 2020-08-06 13:00 | CR0012507 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W28 | 2020-07 | 41 | 41 | 68.9649 | 5 | 2 | 2 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 27 | 0 | 2.1667 | 2020-04 | 0 | 0
417 | CR0012507 | CTASK0019428 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 30 | 30 | 2020-04-13 18:26 | 2020-04-07 16:26 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] [CLT Internal] Auto Notification Enhancement in eBKG | 2020-04-29 10:51 | 2020-06-25 | 2020-05-29 14:26 | 2020-06-03 22:55 | 2020-07-01 15:07 |  | 2020-07-07 10:00 | 2020-07-07 10:00 | 2020-07-01 15:07 | 2020-08-06 13:00 | CR0012507 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W28 | 2020-07 | 41 | 41 | 68.9649 | 5 | 2 | 2 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 27 | 0 | 2.1667 | 2020-04 | 0 | 0
418 | CR0013385 | CTASK0025748 | Closed | OPUS-BKG-M | Kieu Le | 80 | 83 | 2021-03-31 22:00 | 2021-03-12 02:45 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] Better visibility why a booking reached a certain guidance , i.e. GD4 . | 2021-03-16 17:27 | 2021-04-29 02:00 | 2021-04-28 13:52 | 2021-07-16 13:24 | 2021-07-19 09:15 |  | 2021-08-03 10:00 | 2021-08-03 10:00 | 2021-07-21 17:06 | 2021-08-10 14:00 | CR0013385 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W31 | 2021-08 | 192 | 196 | 139.6897 | 6 | 1 | 1 | 0.06 | 153106 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 7 | 22 | 0.22951 | 0.13043 | 2021-03 | 0 | 0
419 | CR0013385 | CTASK0025751 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-07-30 15:52 | 2021-07-01 15:52 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] Better visibility why a booking reached a certain guidance , i.e. GD4 . | 2021-03-16 17:27 | 2021-04-29 02:00 | 2021-04-28 13:52 | 2021-07-16 13:24 | 2021-07-19 09:15 |  | 2021-08-03 10:00 | 2021-08-03 10:00 | 2021-07-21 17:06 | 2021-08-10 14:00 | CR0013385 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W31 | 2021-08 | 192 | 196 | 139.6897 | 6 | 1 | 1 | 0.06 | 153106 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 7 | 22 | 0.22951 | 0.13043 | 2021-03 | 0 | 0
420 | CR0013385 | CTASK0025892 | Closed | OPUS-BKG-M | Kieu Le | 52 | 52 | 2021-04-30 12:02 | 2021-04-01 02:01 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] Better visibility why a booking reached a certain guidance , i.e. GD4 . | 2021-03-16 17:27 | 2021-04-29 02:00 | 2021-04-28 13:52 | 2021-07-16 13:24 | 2021-07-19 09:15 |  | 2021-08-03 10:00 | 2021-08-03 10:00 | 2021-07-21 17:06 | 2021-08-10 14:00 | CR0013385 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W31 | 2021-08 | 192 | 196 | 139.6897 | 6 | 1 | 1 | 0.06 | 153106 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 7 | 22 | 0.22951 | 0.13043 | 2021-03 | 0 | 0
421 | CR0013385 | CTASK0025749 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-04-30 15:50 | 2021-04-01 15:50 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] Better visibility why a booking reached a certain guidance , i.e. GD4 . | 2021-03-16 17:27 | 2021-04-29 02:00 | 2021-04-28 13:52 | 2021-07-16 13:24 | 2021-07-19 09:15 |  | 2021-08-03 10:00 | 2021-08-03 10:00 | 2021-07-21 17:06 | 2021-08-10 14:00 | CR0013385 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W31 | 2021-08 | 192 | 196 | 139.6897 | 6 | 1 | 1 | 0.06 | 153106 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 7 | 22 | 0.22951 | 0.13043 | 2021-03 | 0 | 0
422 | CR0013385 | CTASK0027309 | Closed | OPUS-BKG-M | Kieu Le | 13 | 13 | 2021-06-11 17:10 | 2021-06-01 02:10 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Additional request] Better visibility why a booking reached a certain guidance , i.e. GD4 . | 2021-03-16 17:27 | 2021-04-29 02:00 | 2021-04-28 13:52 | 2021-07-16 13:24 | 2021-07-19 09:15 |  | 2021-08-03 10:00 | 2021-08-03 10:00 | 2021-07-21 17:06 | 2021-08-10 14:00 | CR0013385 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W31 | 2021-08 | 192 | 196 | 139.6897 | 6 | 1 | 1 | 0.06 | 153106 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 7 | 22 | 0.22951 | 0.13043 | 2021-03 | 0 | 0
423 | CR0013385 | CTASK0025747 | Closed | OPUS-BKG-M | Kieu Le | 15 | 16 | 2021-03-31 15:44 | 2021-03-09 15:44 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] Better visibility why a booking reached a certain guidance , i.e. GD4 . | 2021-03-16 17:27 | 2021-04-29 02:00 | 2021-04-28 13:52 | 2021-07-16 13:24 | 2021-07-19 09:15 |  | 2021-08-03 10:00 | 2021-08-03 10:00 | 2021-07-21 17:06 | 2021-08-10 14:00 | CR0013385 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W31 | 2021-08 | 192 | 196 | 139.6897 | 6 | 1 | 1 | 0.06 | 153106 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 7 | 22 | 0.22951 | 0.13043 | 2021-03 | 0 | 0
424 | CR0013235 | CTASK0023438 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 12 | 14 | 2020-11-30 16:40 | 2020-11-09 16:40 | Container | Service Management | Trans S/O |  |  |  | [202011] PARIS Phase Zero Roll out to Spain & Portugal | 2020-11-09 10:26 | 2020-11-27 21:00 | 2020-11-12 15:15 | 2020-11-18 10:01 | 2020-11-18 10:14 |  | 2020-12-01 10:00 | 2020-12-01 10:00 | 2020-11-19 09:17 | 2021-01-01 14:00 | CR0013235 | Service ManagementTrans S/O | OPUS-TRS | 2020-W49 | 2020-12 | 23 | 28 | 21.9817 | 2 | 1 | 2 | 0.05 | 183432 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 10 | 30 | 0 | 0 | 2020-11 | 0 | 0
425 | CR0013235 | CTASK0023439 | Closed | OPUS-TRS | Giang Nguyen Hoang | 11 | 14 | 2020-11-30 16:41 | 2020-11-09 16:41 | Container | Service Management | Trans S/O |  |  |  | [202011] PARIS Phase Zero Roll out to Spain & Portugal | 2020-11-09 10:26 | 2020-11-27 21:00 | 2020-11-12 15:15 | 2020-11-18 10:01 | 2020-11-18 10:14 |  | 2020-12-01 10:00 | 2020-12-01 10:00 | 2020-11-19 09:17 | 2021-01-01 14:00 | CR0013235 | Service ManagementTrans S/O | OPUS-TRS | 2020-W49 | 2020-12 | 23 | 28 | 21.9817 | 2 | 1 | 2 | 0.05 | 183440 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 10 | 30 | 0 | 0 | 2020-11 | 0 | 0
426 | CR0013594 | CTASK0025368 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 16 | 16 | 2021-02-26 19:30 | 2021-02-17 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Development+Testing+Deployment] Australia Impending Arrival - SEAIAR - Date/Time create column for GMT Date/Time | 2021-02-18 13:33 | 2021-03-31 13:42 | 2021-03-23 14:33 | 2021-03-24 18:16 | 2021-03-24 18:24 |  | 2021-03-30 09:40 | 2021-03-30 10:20 | 2021-03-25 14:05 | 2021-04-29 14:00 | CR0013594 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2021-W13 | 2021-03 | 20 | 26 | 39.8383 | 2 | 1 | 1 | 0.03 | 173280 | 2.2 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0.375 | 1 | 2021-02 | 0 | 0
427 | CR0013594 | CTASK0026081 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 4 | 10 | 2021-03-29 19:30 | 2021-03-25 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Deployment+Testing] Australia Impending Arrival - SEAIAR - Date/Time create column for GMT Date/Time | 2021-02-18 13:33 | 2021-03-31 13:42 | 2021-03-23 14:33 | 2021-03-24 18:16 | 2021-03-24 18:24 |  | 2021-03-30 09:40 | 2021-03-30 10:20 | 2021-03-25 14:05 | 2021-04-29 14:00 | CR0013594 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2021-W13 | 2021-03 | 20 | 26 | 39.8383 | 2 | 1 | 1 | 0.03 | 173280 | 2.2 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0.375 | 1 | 2021-02 | 0 | 0
428 | CR0011423 | CTASK0016046 | Closed | OPUS-TPB | Manh Nguyen | 21 | 21 |  |  | Container | Service Management | 3rd Party Billing | M/Data management | TPB Code Creation |  | [actual] Additional TPB codes to be added in 3rd Party Billing module | 2019-08-20 10:01 | 2019-09-30 10:01 | 2019-08-26 10:25 | 2019-08-28 22:44 | 2019-08-29 09:02 | 2019-08-26 10:26 | 2019-09-03 09:02 | 2019-09-03 09:47 | 2019-08-29 09:02 | 2019-10-03 13:00 | CR0011423 | Service Management3rd Party BillingM/Data managementTPB Code Creation | OPUS-TPB | 2019-W36 | 2019-09 | 21 | 0 | 13.9588 | 1 | 1 | 1 | 0 | 153138 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 6 | 0 | 0 | 2019-08 | 0 | 0
429 | CR0011601 | CTASK0016563 | Closed | OPUS-BKG-M | Kieu Le | 75 | 80 | 2019-11-01 16:46 | 2019-10-21 16:46 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | NA *CSVC* Inquiry about adding Time Zone to the Booking Request Date/Time pop-up | 2019-10-18 18:54 | 2019-11-19 | 2019-11-06 14:35 | 2020-01-22 23:29 | 2020-01-27 12:07 | 2019-11-06 14:36 | 2020-02-11 12:06 | 2020-02-11 12:12 | 2020-02-06 08:29 | 2020-03-12 13:00 | CR0011601 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W7 | 2020-02 | 75 | 80 | 115.7168 | 1 | 1 | 1 | 0.03 | 153106 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 13 | 0 | 0.4 | 2019-10 | 0 | 0
430 | CR0012527 | CTASK0019587 | Closed | OPUS-BKG-M | Loc Tran | 9 | 9 | 2020-05-01 02:00 | 2020-04-27 11:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Development] NA *DOC* FMC number field updates in BL screen | 2020-04-27 10:23 | 2020-05-21 02:00 | 2020-05-14 17:58 | 2020-06-24 02:34 | 2020-06-24 15:00 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:15 | 2020-08-13 13:00 | CR0012527 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W29 | 2020-07 | 37 | 36 | 77.9837 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.36364 | 2020-04 | 0 | 0
431 | CR0012527 | CTASK0019517 | Closed | OPUS-BKG-M | Loc Tran | 12 | 12 | 2020-04-16 02:00 | 2020-04-10 15:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Design] NA *DOC* FMC number field updates in BL screen | 2020-04-27 10:23 | 2020-05-21 02:00 | 2020-05-14 17:58 | 2020-06-24 02:34 | 2020-06-24 15:00 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:15 | 2020-08-13 13:00 | CR0012527 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W29 | 2020-07 | 37 | 36 | 77.9837 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.36364 | 2020-04 | 0 | 0
432 | CR0012527 | CTASK0019590 | Closed | OPUS-BKG-M | Loc Tran | 5 | 5 | 2020-05-01 02:00 | 2020-04-27 11:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Testing] NA *DOC* FMC number field updates in BL screen | 2020-04-27 10:23 | 2020-05-21 02:00 | 2020-05-14 17:58 | 2020-06-24 02:34 | 2020-06-24 15:00 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:15 | 2020-08-13 13:00 | CR0012527 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W29 | 2020-07 | 37 | 36 | 77.9837 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.36364 | 2020-04 | 0 | 0
433 | CR0012527 | CTASK0019591 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2020-07-14 13:11 | 2020-07-06 13:11 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Deployment] NA *DOC* FMC number field updates in BL screen | 2020-04-27 10:23 | 2020-05-21 02:00 | 2020-05-14 17:58 | 2020-06-24 02:34 | 2020-06-24 15:00 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:15 | 2020-08-13 13:00 | CR0012527 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W29 | 2020-07 | 37 | 36 | 77.9837 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.36364 | 2020-04 | 0 | 0
434 | CR0012527 | CTASK0020070 | Closed | OPUS-BKG-M | Loc Tran | 7 | 6 | 2020-05-16 02:00 | 2020-05-12 11:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Testing] NA *DOC* FMC number field updates in BL screen | 2020-04-27 10:23 | 2020-05-21 02:00 | 2020-05-14 17:58 | 2020-06-24 02:34 | 2020-06-24 15:00 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:15 | 2020-08-13 13:00 | CR0012527 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W29 | 2020-07 | 37 | 36 | 77.9837 | 5 | 1 | 1 | 0.02 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.36364 | 2020-04 | 0 | 0
435 | CR0013963 | CTASK0027257 | Closed | OPUS-CTM | Phu Nguyen Hoang | 1 | 1 |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | [Documentation] [CLT Internal] Change logic when Call Sign have many Vessels | 2021-05-26 15:10 | 2021-05-31 19:00 | 2021-05-31 15:30 | 2021-06-15 13:22 | 2021-06-15 13:34 |  | 2021-06-22 14:33 | 2021-06-22 17:00 | 2021-06-17 14:12 | 2021-07-23 14:00 | CR0013963 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2021-W25 | 2021-06 | 34 | 18 | 26.9745 | 2 | 1 | 1 | 0.03 | 193463 | 2.2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.16667 | 0 | 2021-05 | 0 | 0
436 | CR0013963 | CTASK0027035 | Closed | OPUS-CTM | Phu Nguyen Hoang | 34 | 18 |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | [CLT Internal] Change logic when Call Sign have many Vessels | 2021-05-26 15:10 | 2021-05-31 19:00 | 2021-05-31 15:30 | 2021-06-15 13:22 | 2021-06-15 13:34 |  | 2021-06-22 14:33 | 2021-06-22 17:00 | 2021-06-17 14:12 | 2021-07-23 14:00 | CR0013963 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2021-W25 | 2021-06 | 34 | 18 | 26.9745 | 2 | 1 | 1 | 0.03 | 193463 | 2.2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.16667 | 0 | 2021-05 | 0 | 0
437 | CR0011359 | CTASK0019637 | Closed | OPUS-DMT | Tran Le | 9 | 20 |  |  | Container | Service Management | Demurrage/Detention | Charge Generation |  |  | Investigate FS and UT, logic changes | 2019-12-17 17:59 | 2020-04-22 20:00 | 2020-04-16 15:07 | 2020-06-26 11:34 | 2020-07-09 09:56 |  | 2020-07-21 10:00 | 2020-07-21 09:55 | 2020-07-10 14:30 | 2020-08-20 13:00 | CR0011359 | Service ManagementDemurrage/DetentionCharge Generation | OPUS-DMT | 2020-W30 | 2020-07 | 24 | 40 | 216.6673 | 2 | 1 | 2 | 0.01 | 193501 | 0.2 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 27 | 0 | 0 | 2019-12 | 0 | 0
438 | CR0011359 | CTASK0019704 | Closed | OPUS-DMT | Phu Nguyen Hoang | 15 | 20 |  |  | Container | Service Management | Demurrage/Detention | Charge Generation |  |  | Investigate FS and UT | 2019-12-17 17:59 | 2020-04-22 20:00 | 2020-04-16 15:07 | 2020-06-26 11:34 | 2020-07-09 09:56 |  | 2020-07-21 10:00 | 2020-07-21 09:55 | 2020-07-10 14:30 | 2020-08-20 13:00 | CR0011359 | Service ManagementDemurrage/DetentionCharge Generation | OPUS-DMT | 2020-W30 | 2020-07 | 24 | 40 | 216.6673 | 2 | 1 | 2 | 0.01 | 193463 | 0.8 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 27 | 0 | 0 | 2019-12 | 0 | 0
439 | CR0011113 | CTASK0017606 | Closed | OPUS-PRI | Ngan Nham | 44 | 44 |  |  | Container | Sales Management | Pricing | RFA |  |  | EAS - PRI - Create Charge Conversion to default Pay-Term on Arbitrary | 2019-07-03 13:16 | 2019-09-30 12:30 | 2019-09-27 13:25 | 2020-03-03 22:07 | 2020-03-04 09:49 |  | 2020-03-10 11:49 | 2020-03-10 10:07 | 2020-03-05 23:06 | 2020-04-09 13:00 | CR0011113 | Sales ManagementPricingRFA | OPUS-PRI | 2020-W11 | 2020-03 | 44 | 0 | 250.9397 | 1 | 1 | 1 | 0 | 193461 | 0.6 | 0 | 0 | 0 | 1 | 1 | 3 | 7 | 25 | 0 | 0 | 2019-07 | 0 | 0
440 | CR0013270 | CTASK0024038 | Closed | OPUS-CHS | Tien Le | 24 | 20 | 2020-12-31 19:31 | 2020-12-21 10:01 | Container | Equipment Management | Chassis | Inventory | Inventory Inquiry | General Inventory Inquiry | [CLT Internal] NA * CGM * Why does General Inventory report chassis TAXZ428771 at a yard not listed in Movement Inquiry. | 2021-03-22 18:15 | 2021-04-30 02:00 | 2021-04-28 19:13 | 2021-04-30 09:03 | 2021-05-04 19:13 |  | 2021-05-12 02:00 | 2021-05-11 10:00 | 2021-05-05 22:56 | 2021-06-11 14:00 | CR0013270 | Equipment ManagementChassisInventoryInventory InquiryGeneral Inventory Inquiry | OPUS-CHS | 2021-W19 | 2021-05 | 101 | 98 | 50.3232 | 4 | 1 | 2 | 0.08 | 173286 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 6 | 28 | 0 | 0 | 2021-03 | 0 | 0
441 | CR0013270 | CTASK0024039 | Closed | OPUS-CHS | Tuyen Truong | 28 | 24 | 2021-01-29 19:34 | 2021-01-01 10:00 | Container | Equipment Management | Chassis | Inventory | Inventory Inquiry | General Inventory Inquiry | [CLT Internal] NA * CGM * Why does General Inventory report chassis TAXZ428771 at a yard not listed in Movement Inquiry. | 2021-03-22 18:15 | 2021-04-30 02:00 | 2021-04-28 19:13 | 2021-04-30 09:03 | 2021-05-04 19:13 |  | 2021-05-12 02:00 | 2021-05-11 10:00 | 2021-05-05 22:56 | 2021-06-11 14:00 | CR0013270 | Equipment ManagementChassisInventoryInventory InquiryGeneral Inventory Inquiry | OPUS-CHS | 2021-W19 | 2021-05 | 101 | 98 | 50.3232 | 4 | 1 | 2 | 0.08 | 173255 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 6 | 28 | 0 | 0 | 2021-03 | 0 | 0
442 | CR0013270 | CTASK0024036 | Closed | OPUS-CHS | Tuyen Truong | 21 | 26 | 2021-01-30 01:15 | 2020-12-21 10:00 | Container | Equipment Management | Chassis | Inventory | Inventory Inquiry | General Inventory Inquiry | [Documentation][CLT Internal] NA * CGM * Why does General Inventory report chassis TAXZ428771 at a yard not listed in Movement Inquiry. | 2021-03-22 18:15 | 2021-04-30 02:00 | 2021-04-28 19:13 | 2021-04-30 09:03 | 2021-05-04 19:13 |  | 2021-05-12 02:00 | 2021-05-11 10:00 | 2021-05-05 22:56 | 2021-06-11 14:00 | CR0013270 | Equipment ManagementChassisInventoryInventory InquiryGeneral Inventory Inquiry | OPUS-CHS | 2021-W19 | 2021-05 | 101 | 98 | 50.3232 | 4 | 1 | 2 | 0.08 | 173255 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 6 | 28 | 0 | 0 | 2021-03 | 0 | 0
443 | CR0013270 | CTASK0024040 | Closed | OPUS-CHS | Tien Le | 28 | 28 | 2021-01-29 19:36 | 2021-01-01 10:00 | Container | Equipment Management | Chassis | Inventory | Inventory Inquiry | General Inventory Inquiry | [CLT Internal] NA * CGM * Why does General Inventory report chassis TAXZ428771 at a yard not listed in Movement Inquiry. | 2021-03-22 18:15 | 2021-04-30 02:00 | 2021-04-28 19:13 | 2021-04-30 09:03 | 2021-05-04 19:13 |  | 2021-05-12 02:00 | 2021-05-11 10:00 | 2021-05-05 22:56 | 2021-06-11 14:00 | CR0013270 | Equipment ManagementChassisInventoryInventory InquiryGeneral Inventory Inquiry | OPUS-CHS | 2021-W19 | 2021-05 | 101 | 98 | 50.3232 | 4 | 1 | 2 | 0.08 | 173286 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 6 | 28 | 0 | 0 | 2021-03 | 0 | 0
444 | CR0013279 | CTASK0023782 | Closed | OPUS-SCG | Trang Duy Thong | 19 | 19 | 2020-12-11 18:11 | 2020-12-01 18:11 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [CLV] OPUS Enhancement Request - CNTR No Field Information - Change Background Color | 2020-11-30 18:13 | 2020-12-18 18:23 | 2020-12-18 13:50 | 2021-03-04 12:50 | 2021-03-05 13:48 |  | 2021-03-16 09:30 | 2021-03-16 09:30 | 2021-03-11 15:41 | 2021-04-16 14:00 | CR0013279 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W11 | 2021-03 | 74 | 75 | 105.6368 | 3 | 1 | 2 | 0.03 | 193511 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0 | 0 | 2020-11 | 0 | 0
445 | CR0013279 | CTASK0023781 | Closed | OPUS-SCG | Pham Khanh Van | 13 | 16 | 2020-12-18 11:44 | 2020-11-25 11:44 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [Documentation]OPUS Enhancement Request - CNTR No Field Information - Change Background Color | 2020-11-30 18:13 | 2020-12-18 18:23 | 2020-12-18 13:50 | 2021-03-04 12:50 | 2021-03-05 13:48 |  | 2021-03-16 09:30 | 2021-03-16 09:30 | 2021-03-11 15:41 | 2021-04-16 14:00 | CR0013279 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W11 | 2021-03 | 74 | 75 | 105.6368 | 3 | 1 | 2 | 0.03 | 193477 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0 | 0 | 2020-11 | 0 | 0
446 | CR0013279 | CTASK0023783 | Closed | OPUS-SCG | Pham Khanh Van | 42 | 40 | 2020-12-11 18:13 | 2020-12-01 18:13 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [CLV] OPUS Enhancement Request - CNTR No Field Information - Change Background Color | 2020-11-30 18:13 | 2020-12-18 18:23 | 2020-12-18 13:50 | 2021-03-04 12:50 | 2021-03-05 13:48 |  | 2021-03-16 09:30 | 2021-03-16 09:30 | 2021-03-11 15:41 | 2021-04-16 14:00 | CR0013279 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W11 | 2021-03 | 74 | 75 | 105.6368 | 3 | 1 | 2 | 0.03 | 193477 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0 | 0 | 2020-11 | 0 | 0
447 | CR0012708 | CTASK0021829 | Closed | OPUS-ACM | Huynh Tuan Khanh | 80 | 80 | 2020-09-30 13:08 | 2020-08-03 13:08 | Container | Support & Admin | Agent Commission Management | Agreement | FF Compensation Agreement Creation |  | NA *ACM * FF modules in OPUS backend calculation checking order change request | 2020-08-13 13:09 | 2020-10-09 13:09 | 2020-09-28 14:47 | 2020-10-05 17:21 | 2020-10-06 09:27 |  | 2020-10-13 09:27 | 2020-10-20 16:35 | 2020-10-12 11:39 | 2020-11-14 02:34 | CR0012708 | Support & AdminAgent Commission ManagementAgreementFF Compensation Agreement Creation | OPUS-ACM | 2020-W42 | 2020-10 | 80 | 80 | 60.8459 | 1 | 1 | 1 | 0.05 | 193499 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0 | 2020-08 | 0 | 0
448 | CR0013863 | CTASK0026854 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-05-08 02:00 | 2021-05-04 11:22 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Design] Global *EDI* - For Tradelens IFTMBC F/F, please change to obtain DEST_ETA information from VSK to PRD. | 2021-05-10 09:41 | 2021-05-29 02:00 | 2021-05-27 15:20 | 2021-06-03 10:34 | 2021-06-03 10:39 |  | 2021-06-08 10:00 | 2021-06-08 10:00 | 2021-06-03 11:37 | 2021-07-10 14:00 | CR0013863 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2021-W23 | 2021-06 | 34 | 34 | 29.0131 | 4 | 1 | 1 | 0.05 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 9 | 53 | 0.53659 | 0.28125 | 2021-05 | 0 | 0
449 | CR0013863 | CTASK0026875 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-05-28 19:29 | 2021-05-24 11:29 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Test]Global *EDI* - For Tradelens IFTMBC F/F, please change to obtain DEST_ETA information from VSK to PRD. | 2021-05-10 09:41 | 2021-05-29 02:00 | 2021-05-27 15:20 | 2021-06-03 10:34 | 2021-06-03 10:39 |  | 2021-06-08 10:00 | 2021-06-08 10:00 | 2021-06-03 11:37 | 2021-07-10 14:00 | CR0013863 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2021-W23 | 2021-06 | 34 | 34 | 29.0131 | 4 | 1 | 1 | 0.05 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 9 | 53 | 0.53659 | 0.28125 | 2021-05 | 0 | 0
450 | CR0013863 | CTASK0026876 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-06-02 18:58 | 2021-06-01 10:57 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Deployment]Global *EDI* - For Tradelens IFTMBC F/F, please change to obtain DEST_ETA information from VSK to PRD. | 2021-05-10 09:41 | 2021-05-29 02:00 | 2021-05-27 15:20 | 2021-06-03 10:34 | 2021-06-03 10:39 |  | 2021-06-08 10:00 | 2021-06-08 10:00 | 2021-06-03 11:37 | 2021-07-10 14:00 | CR0013863 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2021-W23 | 2021-06 | 34 | 34 | 29.0131 | 4 | 1 | 1 | 0.05 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 9 | 53 | 0.53659 | 0.28125 | 2021-05 | 0 | 0
451 | CR0013863 | CTASK0026874 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 16 | 16 | 2021-05-14 19:42 | 2021-05-10 10:42 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Development] Global *EDI* - For Tradelens IFTMBC F/F, please change to obtain DEST_ETA information from VSK to PRD. | 2021-05-10 09:41 | 2021-05-29 02:00 | 2021-05-27 15:20 | 2021-06-03 10:34 | 2021-06-03 10:39 |  | 2021-06-08 10:00 | 2021-06-08 10:00 | 2021-06-03 11:37 | 2021-07-10 14:00 | CR0013863 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2021-W23 | 2021-06 | 34 | 34 | 29.0131 | 4 | 1 | 1 | 0.05 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 9 | 53 | 0.53659 | 0.28125 | 2021-05 | 0 | 0
452 | CR0012875 | CTASK0021407 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 22 | 22 | 2021-01-15 10:54 | 2021-01-04 10:54 | Container | Service Management | Domestic | Accounting | Invoice |  | NA *DOM* Add Customer Ref Number to Email Subj Line for Invoices Issued | 2021-01-04 10:53 | 2021-01-15 21:00 | 2021-01-14 08:48 | 2021-01-28 17:36 | 2021-02-02 11:24 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-02-04 09:58 | 2021-03-12 14:00 | CR0012875 | Service ManagementDomesticAccountingInvoice | OPUS-DOM | 2021-W6 | 2021-02 | 40 | 44 | 35.963 | 2 | 1 | 2 | 0.05 | 183432 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0 | 0 | 2021-01 | 0 | 0
453 | CR0012875 | CTASK0021408 | Closed | OPUS-DOM | Giang Nguyen Hoang | 18 | 22 | 2021-01-15 10:54 | 2021-01-04 10:54 | Container | Service Management | Domestic | Accounting | Invoice |  | NA *DOM* Add Customer Ref Number to Email Subj Line for Invoices Issued | 2021-01-04 10:53 | 2021-01-15 21:00 | 2021-01-14 08:48 | 2021-01-28 17:36 | 2021-02-02 11:24 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-02-04 09:58 | 2021-03-12 14:00 | CR0012875 | Service ManagementDomesticAccountingInvoice | OPUS-DOM | 2021-W6 | 2021-02 | 40 | 44 | 35.963 | 2 | 1 | 2 | 0.05 | 183440 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0 | 0 | 2021-01 | 0 | 0
454 | CR0013012 | CTASK0022760 | Closed | OPUS-PRI | Nhien Nguyen | 10 | 10 | 2020-10-31 16:26 | 2020-10-01 16:26 | Container | Sales Management | Pricing | RFA | Proposal & Amendment | RFA Proposal & Amendment Creation | [Tiger] Retro filing logic (RFA) | 2020-09-28 17:30 | 2020-11-04 20:08 | 2020-11-04 17:34 | 2021-01-13 09:41 | 2021-01-13 10:09 |  | 2021-01-19 10:09 | 2021-01-19 09:54 | 2021-01-13 16:12 | 2021-02-18 14:00 | CR0013012 | Sales ManagementPricingRFAProposal & AmendmentRFA Proposal & Amendment Creation | OPUS-PRI | 2021-W3 | 2021-01 | 100 | 100 | 112.6932 | 2 | 1 | 2 | 0.04 | 183364 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-09 | 0 | 0
455 | CR0013012 | CTASK0022924 | Closed | OPUS-PRI | Man Hoang | 90 | 90 | 2020-11-30 17:27 | 2020-10-01 17:27 | Container | Sales Management | Pricing | RFA | Proposal & Amendment | RFA Proposal & Amendment Creation | [Tiger] Retro filing logic (RFA) | 2020-09-28 17:30 | 2020-11-04 20:08 | 2020-11-04 17:34 | 2021-01-13 09:41 | 2021-01-13 10:09 |  | 2021-01-19 10:09 | 2021-01-19 09:54 | 2021-01-13 16:12 | 2021-02-18 14:00 | CR0013012 | Sales ManagementPricingRFAProposal & AmendmentRFA Proposal & Amendment Creation | OPUS-PRI | 2021-W3 | 2021-01 | 100 | 100 | 112.6932 | 2 | 1 | 2 | 0.04 | 183431 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0 | 0.66667 | 2020-09 | 0 | 0
456 | CR0013002 | CTASK0021996 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 6 | 6 | 2020-08-31 19:30 | 2020-08-24 11:00 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | [Estimation + Development + Testing + Deployment][CLT Internal] (HBA) EUA EDI ¦ CUSTOMS MANIFEST for TNPA South Africa | 2020-08-27 10:42 | 2020-08-31 23:33 | 2020-08-27 16:36 | 2020-08-27 17:07 | 2020-08-27 17:09 |  | 2020-09-01 10:08 | 2020-09-01 10:16 | 2020-08-27 17:37 | 2020-10-01 13:00 | CR0013002 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W36 | 2020-09 | 6 | 6 | 4.9764 | 1 | 1 | 1 | 0.05 | 173280 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.18519 | 2020-08 | 0 | 0
457 | CR0011384 | CTASK0017973 | Closed | OPUS-TES | Manh Nguyen | 1 | 1 |  |  | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [Actual] Development of ONE version HIT/YICT eBilling | 2019-07-17 11:20 | 2019-10-15 23:00 | 2019-10-15 15:47 | 2021-02-18 11:35 | 2021-02-18 11:53 |  | 2021-02-23 09:30 | 2021-02-24 18:01 | 2021-02-22 10:23 | 2021-03-28 14:00 | CR0011384 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W8 | 2021-02 | 0 | 0 | 586.9233 | 2 | 1 | 2 | 0 | 153138 | 0.8 | 0 | 0 | 0 | 1 | 1 | 5 | 4 | 21 | 0 | 0 | 2019-07 | 0 | 0
458 | CR0011384 | CTASK0017972 | Closed | OPUS-TES | Thai Nguyen | 1 | 1 |  |  | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [Actual] Development of ONE version HIT/YICT eBilling | 2019-07-17 11:20 | 2019-10-15 23:00 | 2019-10-15 15:47 | 2021-02-18 11:35 | 2021-02-18 11:53 |  | 2021-02-23 09:30 | 2021-02-24 18:01 | 2021-02-22 10:23 | 2021-03-28 14:00 | CR0011384 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W8 | 2021-02 | 0 | 0 | 586.9233 | 2 | 1 | 2 | 0 | 173249 | 0.8 | 0 | 0 | 0 | 1 | 1 | 5 | 4 | 21 | 0 | 0.6 | 2019-07 | 0 | 0
459 | CR0013241 | CTASK0023897 | Closed | OPUS-PRI | Nhien Nguyen | 21 | 20 | 2020-12-31 17:08 | 2020-12-01 17:08 | Container | Sales Management | Pricing | Service Contract | S/C Creation | S/C Proposal & Amendment Draft Print | NA *PRI* Blocking SC Print for Initial and Requested status contracts | 2020-12-11 10:18 | 2020-12-31 20:18 | 2020-12-31 10:04 | 2021-02-23 12:55 | 2021-02-23 13:49 |  | 2021-03-02 13:49 | 2021-03-02 09:25 | 2021-02-23 14:00 | 2021-04-03 14:00 | CR0013241 | Sales ManagementPricingService ContractS/C CreationS/C Proposal & Amendment Draft Print | OPUS-PRI | 2021-W9 | 2021-03 | 21 | 20 | 81.1463 | 1 | 1 | 1 | 0.01 | 183364 | 2.2 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 1.2 | 2020-12 | 0 | 0
460 | CR0014021 | CTASK0027308 | Closed | OPUS-PRI | Ngan Nham | 16 | 16 | 2021-07-01 01:00 | 2021-06-01 01:00 | [6 empty] | [Development] [Kontainers] HEA application _ (2) | 2021-06-09 12:34 | 2021-06-26 01:00 | 2021-06-10 13:52 | 2021-06-11 11:38 | 2021-06-11 11:40 |  | 2021-06-15 12:00 | 2021-06-15 12:00 | 2021-06-11 16:33 | 2021-07-16 14:00 | CR0014021 |  | OPUS-PRI | 2021-W24 | 2021-06 | 16 | 16 | 5.9762 | 1 | 1 | 1 | 0.11 | 193461 | 2.5 | 0 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0 | 0 | 2021-06 | 0 | 0
461 | CR0012484 | CTASK0022666 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 24 | 24 | 2020-09-30 11:23 | 2020-09-24 11:23 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202009] NA *TRS* Work Order Issue - Lowest Truck Rate Verification Logic | 2020-09-23 17:21 | 2020-11-10 21:00 | 2020-11-06 15:57 | 2021-01-05 10:01 | 2021-01-05 13:15 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2021-01-07 10:35 | 2021-02-18 14:00 | CR0012484 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W3 | 2021-01 | 219 | 208 | 117.6934 | 4 | 1 | 2 | 0.07 | 183432 | 1.5 | 0 | 0 | 0 | 3 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-09 | 0 | 0
462 | CR0012484 | CTASK0022667 | Closed | OPUS-TRS | Giang Nguyen Hoang | 24 | 24 | 2020-09-30 11:24 | 2020-09-24 11:24 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202009] NA *TRS* Work Order Issue - Lowest Truck Rate Verification Logic | 2020-09-23 17:21 | 2020-11-10 21:00 | 2020-11-06 15:57 | 2021-01-05 10:01 | 2021-01-05 13:15 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2021-01-07 10:35 | 2021-02-18 14:00 | CR0012484 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W3 | 2021-01 | 219 | 208 | 117.6934 | 4 | 1 | 2 | 0.07 | 183440 | 1.5 | 0 | 0 | 0 | 3 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-09 | 0 | 0
463 | CR0012484 | CTASK0022669 | Closed | OPUS-TRS | Giang Nguyen Hoang | 77 | 80 | 2020-10-31 11:25 | 2020-10-01 11:25 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202010] NA *TRS* Work Order Issue - Lowest Truck Rate Verification Logic | 2020-09-23 17:21 | 2020-11-10 21:00 | 2020-11-06 15:57 | 2021-01-05 10:01 | 2021-01-05 13:15 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2021-01-07 10:35 | 2021-02-18 14:00 | CR0012484 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W3 | 2021-01 | 219 | 208 | 117.6934 | 4 | 1 | 2 | 0.07 | 183440 | 1.5 | 0 | 0 | 0 | 3 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-09 | 0 | 0
464 | CR0012484 | CTASK0022668 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 94 | 80 | 2020-10-31 11:24 | 2020-10-01 11:24 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202010] NA *TRS* Work Order Issue - Lowest Truck Rate Verification Logic | 2020-09-23 17:21 | 2020-11-10 21:00 | 2020-11-06 15:57 | 2021-01-05 10:01 | 2021-01-05 13:15 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2021-01-07 10:35 | 2021-02-18 14:00 | CR0012484 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W3 | 2021-01 | 219 | 208 | 117.6934 | 4 | 1 | 2 | 0.07 | 183432 | 1.5 | 0 | 0 | 0 | 3 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-09 | 0 | 0
465 | CR0012190 | CTASK0018525 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 45 | 45 | 2020-03-26 19:30 | 2020-02-24 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Development] AR - ARG Advance Manifest // Internal Transit Indicator column and Partial CNTR VL event date bug | 2020-03-26 16:25 | 2020-04-03 | 2020-04-02 18:48 | 2020-04-24 04:03 | 2020-05-11 13:22 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-15 22:43 | 2020-06-18 13:00 | CR0012190 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W21 | 2020-05 | 69 | 69 | 53.7324 | 4 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.18519 | 2020-03 | 0 | 0
466 | CR0012190 | CTASK0018482 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 8 | 8 | 2020-02-19 19:30 | 2020-02-17 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Estimation]AR - ARG Advance Manifest // Internal Transit Indicator column and Partial CNTR VL event date bug | 2020-03-26 16:25 | 2020-04-03 | 2020-04-02 18:48 | 2020-04-24 04:03 | 2020-05-11 13:22 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-15 22:43 | 2020-06-18 13:00 | CR0012190 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W21 | 2020-05 | 69 | 69 | 53.7324 | 4 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.18519 | 2020-03 | 0 | 0
467 | CR0012190 | CTASK0019784 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 12 | 12 | 2020-04-28 19:30 | 2020-04-22 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Development] AR - ARG Advance Manifest // Internal Transit Indicator column and Partial CNTR VL event date bug - Add more functions | 2020-03-26 16:25 | 2020-04-03 | 2020-04-02 18:48 | 2020-04-24 04:03 | 2020-05-11 13:22 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-15 22:43 | 2020-06-18 13:00 | CR0012190 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W21 | 2020-05 | 69 | 69 | 53.7324 | 4 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.18519 | 2020-03 | 0 | 0
468 | CR0012190 | CTASK0020152 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 4 | 4 | 2020-05-18 19:30 | 2020-05-12 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Deployment]AR - ARG Advance Manifest // Internal Transit Indicator column and Partial CNTR VL event date bug | 2020-03-26 16:25 | 2020-04-03 | 2020-04-02 18:48 | 2020-04-24 04:03 | 2020-05-11 13:22 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-15 22:43 | 2020-06-18 13:00 | CR0012190 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W21 | 2020-05 | 69 | 69 | 53.7324 | 4 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.18519 | 2020-03 | 0 | 0
469 | CR0011187 | CTASK0017474 | Closed | OPUS-TRS | Hieu Tran | 3 | 20 | 2020-01-10 18:00 | 2019-12-23 09:00 | Container | Service Management | Trans S/O | Work Order |  |  | NA * TRS * Enhancement to correct Transportation Status Logic | 2019-12-03 10:04 | 2020-01-31 18:00 | 2020-01-09 16:59 | 2020-04-21 17:34 | 2020-04-21 17:43 |  | 2020-04-28 11:00 | 2020-04-28 11:00 | 2020-04-22 02:17 | 2020-05-28 13:00 | CR0011187 | Service ManagementTrans S/OWork Order | OPUS-TRS | 2020-W18 | 2020-04 | 34 | 60 | 147.0388 | 3 | 1 | 3 | 0.02 | 183400 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0 | 2019-12 | 0 | 0
470 | CR0011187 | CTASK0017472 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 13 | 20 | 2020-01-10 18:00 | 2019-12-23 09:00 | Container | Service Management | Trans S/O | Work Order |  |  | NA * TRS * Enhancement to correct Transportation Status Logic | 2019-12-03 10:04 | 2020-01-31 18:00 | 2020-01-09 16:59 | 2020-04-21 17:34 | 2020-04-21 17:43 |  | 2020-04-28 11:00 | 2020-04-28 11:00 | 2020-04-22 02:17 | 2020-05-28 13:00 | CR0011187 | Service ManagementTrans S/OWork Order | OPUS-TRS | 2020-W18 | 2020-04 | 34 | 60 | 147.0388 | 3 | 1 | 3 | 0.02 | 183432 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0 | 2019-12 | 0 | 0
471 | CR0011187 | CTASK0017473 | Closed | OPUS-TRS | Giang Nguyen Hoang | 18 | 20 | 2020-01-10 18:00 | 2019-12-23 09:00 | Container | Service Management | Trans S/O | Work Order |  |  | NA * TRS * Enhancement to correct Transportation Status Logic | 2019-12-03 10:04 | 2020-01-31 18:00 | 2020-01-09 16:59 | 2020-04-21 17:34 | 2020-04-21 17:43 |  | 2020-04-28 11:00 | 2020-04-28 11:00 | 2020-04-22 02:17 | 2020-05-28 13:00 | CR0011187 | Service ManagementTrans S/OWork Order | OPUS-TRS | 2020-W18 | 2020-04 | 34 | 60 | 147.0388 | 3 | 1 | 3 | 0.02 | 183440 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0 | 2019-12 | 0 | 0
472 | CR0012370 | CTASK0020106 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 7 | 7 | 2020-05-20 10:27 | 2020-05-12 10:27 | Container | Service Management | Booking/Documentation | Manifest | Malaysia | Malaysia Customs Manifest | [PROD] Fix Missing POR Information in OPUS FF for Malaysia uCustoms Manifest | 2020-03-18 15:33 | 2020-04-18 | 2020-04-16 09:54 | 2020-05-08 12:11 | 2020-05-08 16:44 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-08 18:39 | 2020-06-18 13:00 | CR0012370 | Service ManagementBooking/DocumentationManifestMalaysiaMalaysia Customs Manifest | OPUS-BKG-MFT-A | 2020-W21 | 2020-05 | 63 | 63 | 61.769 | 4 | 1 | 1 | 0.04 | 193506 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.85714 | 2020-03 | 0 | 0
473 | CR0012370 | CTASK0018900 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 24 | 24 | 2020-04-03 18:35 | 2020-03-13 18:35 | Container | Service Management | Booking/Documentation | Manifest | Malaysia | Malaysia Customs Manifest | [Development] Fix Missing POR Information in OPUS FF for Malaysia uCustoms Manifest | 2020-03-18 15:33 | 2020-04-18 | 2020-04-16 09:54 | 2020-05-08 12:11 | 2020-05-08 16:44 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-08 18:39 | 2020-06-18 13:00 | CR0012370 | Service ManagementBooking/DocumentationManifestMalaysiaMalaysia Customs Manifest | OPUS-BKG-MFT-A | 2020-W21 | 2020-05 | 63 | 63 | 61.769 | 4 | 1 | 1 | 0.04 | 193506 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.85714 | 2020-03 | 0 | 0
474 | CR0012370 | CTASK0018908 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 24 | 24 | 2020-04-10 19:30 | 2020-04-03 11:00 | Container | Service Management | Booking/Documentation | Manifest | Malaysia | Malaysia Customs Manifest | [Test] Fix Missing POR Information in OPUS FF for Malaysia uCustoms Manifest | 2020-03-18 15:33 | 2020-04-18 | 2020-04-16 09:54 | 2020-05-08 12:11 | 2020-05-08 16:44 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-08 18:39 | 2020-06-18 13:00 | CR0012370 | Service ManagementBooking/DocumentationManifestMalaysiaMalaysia Customs Manifest | OPUS-BKG-MFT-A | 2020-W21 | 2020-05 | 63 | 63 | 61.769 | 4 | 1 | 1 | 0.04 | 193506 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.85714 | 2020-03 | 0 | 0
475 | CR0012370 | CTASK0018818 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2020-03-12 16:01 | 2020-03-09 16:01 | Container | Service Management | Booking/Documentation | Manifest | Malaysia | Malaysia Customs Manifest | [Analysis] Fix Missing POR Information in OPUS FF for Malaysia uCustoms Manifest | 2020-03-18 15:33 | 2020-04-18 | 2020-04-16 09:54 | 2020-05-08 12:11 | 2020-05-08 16:44 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-08 18:39 | 2020-06-18 13:00 | CR0012370 | Service ManagementBooking/DocumentationManifestMalaysiaMalaysia Customs Manifest | OPUS-BKG-MFT-A | 2020-W21 | 2020-05 | 63 | 63 | 61.769 | 4 | 1 | 1 | 0.04 | 193506 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.85714 | 2020-03 | 0 | 0
476 | CR0012525 | CTASK0020519 | Closed | OPUS-FLT | Tu Nguyen | 28 | 25 | 2020-06-12 11:53 | 2020-06-01 11:53 | Container | Support & Admin | Fleet Management |  |  |  | [FLT] Maintain FLT_ROU Interface data | 2020-04-27 15:50 | 2020-05-31 18:00 | 2020-05-19 17:16 | 2020-06-12 17:56 | 2020-06-22 16:17 |  | 2020-06-30 10:00 | 2020-06-30 10:00 | 2020-06-25 18:31 | 2020-07-31 13:00 | CR0012525 | Support & AdminFleet Management | OPUS-FLT | 2020-W27 | 2020-06 | 28 | 25 | 63.7566 | 1 | 1 | 1 | 0.02 | 123045 | 1.6 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 0 | 2020-04 | 0 | 0
477 | CR0013143 | CTASK0022959 | Closed | OPUS-BKG-M | Loc Tran | 32 | 32 | 2020-11-18 19:22 | 2020-10-26 19:22 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal] Add an internal page to proceed BKG Office Change as regular data correction job for GSD Handling. | 2020-10-27 09:06 | 2020-12-03 | 2020-11-25 14:38 | 2020-12-10 08:39 | 2020-12-10 13:32 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2020-12-10 15:00 | 2021-02-12 14:00 | CR0013143 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W2 | 2021-01 | 75 | 66 | 77.0377 | 5 | 1 | 2 | 0.04 | 193503 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0.33333 | 0.28571 | 2020-10 | 0 | 0
478 | CR0013143 | CTASK0022962 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-01-19 16:57 | 2021-01-04 16:57 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal] Add an internal page to proceed BKG Office Change as regular data correction job for GSD Handling. | 2020-10-27 09:06 | 2020-12-03 | 2020-11-25 14:38 | 2020-12-10 08:39 | 2020-12-10 13:32 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2020-12-10 15:00 | 2021-02-12 14:00 | CR0013143 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W2 | 2021-01 | 75 | 66 | 77.0377 | 5 | 1 | 2 | 0.04 | 193503 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0.33333 | 0.28571 | 2020-10 | 0 | 0
479 | CR0013143 | CTASK0022940 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal] Add an internal page to proceed BKG Office Change as regular data correction job for GSD Handling. | 2020-10-27 09:06 | 2020-12-03 | 2020-11-25 14:38 | 2020-12-10 08:39 | 2020-12-10 13:32 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2020-12-10 15:00 | 2021-02-12 14:00 | CR0013143 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W2 | 2021-01 | 75 | 66 | 77.0377 | 5 | 1 | 2 | 0.04 | 193503 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0.33333 | 0.28571 | 2020-10 | 0 | 0
480 | CR0013143 | CTASK0022817 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2020-10-02 18:30 | 2020-10-01 10:20 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal] Add an internal page to proceed BKG Office Change as regular data correction job for GSD Handling. | 2020-10-27 09:06 | 2020-12-03 | 2020-11-25 14:38 | 2020-12-10 08:39 | 2020-12-10 13:32 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2020-12-10 15:00 | 2021-02-12 14:00 | CR0013143 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W2 | 2021-01 | 75 | 66 | 77.0377 | 5 | 1 | 2 | 0.04 | 193488 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0.53659 | 0.28125 | 2020-10 | 0 | 0
481 | CR0013143 | CTASK0022960 | Closed | OPUS-BKG-M | Loc Tran | 25 | 16 | 2020-11-30 13:07 | 2020-11-09 13:07 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] Add an internal page to proceed BKG Office Change as regular data correction job for GSD Handling. | 2020-10-27 09:06 | 2020-12-03 | 2020-11-25 14:38 | 2020-12-10 08:39 | 2020-12-10 13:32 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2020-12-10 15:00 | 2021-02-12 14:00 | CR0013143 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W2 | 2021-01 | 75 | 66 | 77.0377 | 5 | 1 | 2 | 0.04 | 193503 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0.33333 | 0.28571 | 2020-10 | 0 | 0
482 | CR0011527 | CTASK0016009 | Closed | OPUS-BKG-M | Kieu Le | 39 | 16 | 2019-08-30 14:23 | 2019-08-19 14:23 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [CLT Internal] Enhancement of standby history in case of split and combine. | 2019-07-03 11:23 | 2019-09-24 | 2019-09-09 15:55 | 2019-09-09 15:56 | 2019-09-09 15:57 |  | 2019-09-17 10:00 | 2019-09-17 09:00 | 2019-09-17 16:35 | 2019-09-17 16:49 | CR0011527 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2019-W38 | 2019-09 | 39 | 16 | 75.9421 | 1 | 1 | 1 | 0.01 | 153106 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 6 | 0 | 0 | 2019-07 | 0 | 0
483 | CR0011624 | CTASK0016696 | Closed | OPUS-MNR | Tuyen Truong | 8 | 50 | 2019-11-29 11:45 | 2019-10-14 11:45 | Container | Equipment Management | M&R |  |  |  | [Initial Effort] GHQ - Improve MNR cost classification | 2019-10-29 12:54 | 2019-11-29 18:53 | 2019-11-29 17:43 | 2019-12-05 10:01 | 2020-01-09 09:44 |  | 2020-01-22 09:41 | 2020-01-14 19:07 | 2020-01-09 13:24 | 2020-01-28 11:32 | CR0011624 | Equipment ManagementM&R | OPUS-MNR | 2020-W4 | 2020-01 | 145 | 100 | 84.8663 | 2 | 1 | 2 | 0.05 | 173255 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 10 | 0 | 0 | 2019-10 | 0 | 0
484 | CR0011624 | CTASK0016697 | Closed | OPUS-MNR | Tien Le | 137 | 50 | 2019-11-29 11:51 | 2019-10-14 11:51 | Container | Equipment Management | M&R |  |  |  | [Initial Effort]GHQ - Improve MNR cost classification | 2019-10-29 12:54 | 2019-11-29 18:53 | 2019-11-29 17:43 | 2019-12-05 10:01 | 2020-01-09 09:44 |  | 2020-01-22 09:41 | 2020-01-14 19:07 | 2020-01-09 13:24 | 2020-01-28 11:32 | CR0011624 | Equipment ManagementM&R | OPUS-MNR | 2020-W4 | 2020-01 | 145 | 100 | 84.8663 | 2 | 1 | 2 | 0.05 | 173286 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 10 | 0 | 0 | 2019-10 | 0 | 0
485 | CR0013316 | CTASK0024388 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 40 | 40 | 2021-01-29 19:30 | 2021-01-04 11:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development+Testing+Deployment] NA *Customs* Import - CBSA Regulatory Change - Jan 01, 2021 effective Date (OPUS changes) | 2021-01-07 10:32 | 2021-02-01 | 2021-01-29 15:24 | 2021-05-27 18:10 | 2021-05-28 09:42 |  | 2021-06-08 09:40 | 2021-06-03 09:50 | 2021-05-28 14:03 | 2021-07-03 14:00 | CR0013316 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W23 | 2021-06 | 52 | 52 | 151.964 | 2 | 1 | 1 | 0.01 | 173280 | 2.1 | 2 | 0 | 0 | 1 | 1 | 3 | 9 | 53 | 0.375 | 1 | 2021-01 | 0 | 0
486 | CR0013316 | CTASK0027310 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 12 | 12 | 2021-06-03 19:30 | 2021-06-01 11:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing + Deploment ] NA *Customs* Import - CBSA Regulatory Change - Jan 01, 2021 effective Date (OPUS changes) | 2021-01-07 10:32 | 2021-02-01 | 2021-01-29 15:24 | 2021-05-27 18:10 | 2021-05-28 09:42 |  | 2021-06-08 09:40 | 2021-06-03 09:50 | 2021-05-28 14:03 | 2021-07-03 14:00 | CR0013316 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W23 | 2021-06 | 52 | 52 | 151.964 | 2 | 1 | 1 | 0.01 | 173280 | 2.1 | 2 | 0 | 0 | 1 | 1 | 3 | 9 | 53 | 0.375 | 1 | 2021-01 | 0 | 0
487 | CR0012634 | CTASK0020454 | Closed | OPUS-SCO | Cuong Tran Hung | 90 | 90 | 2020-06-30 19:39 | 2020-06-01 19:39 | Container | Statement Management | Statement Account Receivable |  |  |  | [before July][ACTUAL][CLV]EUA - Add ability to search for a specific customer [CR6] | 2020-06-25 10:11 | 2020-08-04 10:11 | 2020-07-03 18:05 | 2020-07-24 07:09 | 2020-07-24 08:37 |  | 2020-07-28 08:37 | 2020-07-28 10:00 | 2020-07-24 09:29 | 2020-08-28 13:00 | CR0012634 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 150 | 150 | 32.9349 | 3 | 1 | 1 | 0.19 | 193530 | 1.1 | 0 | 0 | 0 | 2 | 1 | 1 | 8 | 27 | 0 | 1.2222 | 2020-06 | 0 | 0
488 | CR0012634 | CTASK0021415 | Closed | OPUS-SCO | Cuong Tran Hung | 12 | 12 | 2020-07-04 13:05 | 2020-07-01 13:05 | Container | Statement Management | Statement Account Receivable |  |  |  | [July][ACTUAL][CLV]EUA - Add ability to search for a specific customer [CR6] | 2020-06-25 10:11 | 2020-08-04 10:11 | 2020-07-03 18:05 | 2020-07-24 07:09 | 2020-07-24 08:37 |  | 2020-07-28 08:37 | 2020-07-28 10:00 | 2020-07-24 09:29 | 2020-08-28 13:00 | CR0012634 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 150 | 150 | 32.9349 | 3 | 1 | 1 | 0.19 | 193530 | 1.1 | 0 | 0 | 0 | 2 | 1 | 1 | 8 | 27 | 0 | 1.2222 | 2020-06 | 0 | 0
489 | CR0012634 | CTASK0020154 | Closed | OPUS-SCO | Cuong Tran Hung | 48 | 48 | 2020-05-31 19:11 | 2020-05-18 19:11 | Container | Statement Management | Statement Account Receivable |  |  |  | [ACTUAL][CLV]EUA - Add ability to search for a specific customer [CR6] | 2020-06-25 10:11 | 2020-08-04 10:11 | 2020-07-03 18:05 | 2020-07-24 07:09 | 2020-07-24 08:37 |  | 2020-07-28 08:37 | 2020-07-28 10:00 | 2020-07-24 09:29 | 2020-08-28 13:00 | CR0012634 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 150 | 150 | 32.9349 | 3 | 1 | 1 | 0.19 | 193530 | 1.1 | 0 | 0 | 0 | 2 | 1 | 1 | 8 | 27 | 0 | 1.2222 | 2020-06 | 0 | 0
490 | CR0011752 | CTASK0025080 | Closed | OPUS-DOM | Giang Nguyen Hoang | 10 | 10 | 2021-02-26 11:28 | 2021-02-02 11:28 | Container | Service Management | Domestic |  |  |  | [202102] NA *Domestic* Adjust Detention Free time Clock | 2020-12-14 14:06 | 2020-12-31 21:00 | 2020-12-30 13:12 | 2021-02-08 11:48 | 2021-02-22 22:53 |  | 2021-03-02 10:00 | 2021-03-02 09:09 | 2021-02-23 13:57 | 2021-04-02 14:00 | CR0011752 | Service ManagementDomestic | OPUS-DOM | 2021-W9 | 2021-03 | 81 | 67 | 77.8291 | 4 | 1 | 2 | 0.04 | 183440 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 0 | 2020-12 | 0 | 0
491 | CR0011752 | CTASK0024149 | Closed | OPUS-DOM | Giang Nguyen Hoang | 30 | 30 | 2020-12-31 13:29 | 2020-12-14 13:29 | Container | Service Management | Domestic |  |  |  | [202012] NA *Domestic* Adjust Detention Free time Clock | 2020-12-14 14:06 | 2020-12-31 21:00 | 2020-12-30 13:12 | 2021-02-08 11:48 | 2021-02-22 22:53 |  | 2021-03-02 10:00 | 2021-03-02 09:09 | 2021-02-23 13:57 | 2021-04-02 14:00 | CR0011752 | Service ManagementDomestic | OPUS-DOM | 2021-W9 | 2021-03 | 81 | 67 | 77.8291 | 4 | 1 | 2 | 0.04 | 183440 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 0 | 2020-12 | 0 | 0
492 | CR0011752 | CTASK0016875 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 27 | 27 | 2020-12-31 23:00 | 2020-12-10 09:00 | Container | Service Management | Domestic |  |  |  | [202012] NA *Domestic* Adjust Detention Free time Clock | 2020-12-14 14:06 | 2020-12-31 21:00 | 2020-12-30 13:12 | 2021-02-08 11:48 | 2021-02-22 22:53 |  | 2021-03-02 10:00 | 2021-03-02 09:09 | 2021-02-23 13:57 | 2021-04-02 14:00 | CR0011752 | Service ManagementDomestic | OPUS-DOM | 2021-W9 | 2021-03 | 81 | 67 | 77.8291 | 4 | 1 | 2 | 0.04 | 183432 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 0 | 2020-12 | 0 | 0
493 | CR0011752 | CTASK0025079 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 14 | 14 | 2021-02-26 11:28 | 2021-02-02 11:28 | Container | Service Management | Domestic |  |  |  | [202102] NA *Domestic* Adjust Detention Free time Clock | 2020-12-14 14:06 | 2020-12-31 21:00 | 2020-12-30 13:12 | 2021-02-08 11:48 | 2021-02-22 22:53 |  | 2021-03-02 10:00 | 2021-03-02 09:09 | 2021-02-23 13:57 | 2021-04-02 14:00 | CR0011752 | Service ManagementDomestic | OPUS-DOM | 2021-W9 | 2021-03 | 81 | 67 | 77.8291 | 4 | 1 | 2 | 0.04 | 183432 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 0 | 2020-12 | 0 | 0
494 | CR0011348 | CTASK0019374 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 1 | 1 |  |  | eCommerce | Outbound | Booking | Booking Request |  |  | [Development]eComm - Add e-booking Party in eComm and Booking Contact name in OPUS for mapping | 2020-02-05 10:43 | 2020-03-16 23:00 | 2020-03-16 15:22 | 2020-05-20 11:41 | 2020-06-23 11:45 |  | 2020-06-30 18:00 | 2020-06-30 09:30 | 2020-06-26 11:42 | 2020-07-30 13:00 | CR0011348 | OutboundBookingBooking Request | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 0 | 0 | 146.3033 | 1 | 1 | 1 | 0 | 193488 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 2.1667 | 2020-02 | 0 | 0
495 | CR0012177 | CTASK0019342 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 16 | 16 | 2020-04-13 19:34 | 2020-04-01 19:34 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Development] AS - OPUS CONTAINER - Email Address Not Auto-Populating for A/N Send Function | 2020-04-24 15:40 | 2020-05-08 20:32 | 2020-05-08 13:52 | 2020-07-23 16:39 | 2020-07-27 17:58 |  | 2020-09-01 17:57 | 2020-09-01 10:22 | 2020-08-21 12:22 | 2020-10-09 13:00 | CR0012177 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2020-W36 | 2020-09 | 63 | 70 | 130.0952 | 6 | 2 | 2 | 0.02 | 193512 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.5 | 2020-04 | 0 | 0
496 | CR0012177 | CTASK0019519 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 12 | 16 | 2020-04-17 18:25 | 2020-04-13 18:24 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Testing] AS - OPUS CONTAINER - Email Address Not Auto-Populating for A/N Send Function | 2020-04-24 15:40 | 2020-05-08 20:32 | 2020-05-08 13:52 | 2020-07-23 16:39 | 2020-07-27 17:58 |  | 2020-09-01 17:57 | 2020-09-01 10:22 | 2020-08-21 12:22 | 2020-10-09 13:00 | CR0012177 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2020-W36 | 2020-09 | 63 | 70 | 130.0952 | 6 | 2 | 2 | 0.02 | 193512 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.5 | 2020-04 | 0 | 0
497 | CR0012177 | CTASK0021507 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 17 | 15 | 2020-08-28 17:20 | 2020-07-27 17:20 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Testing + Deployment] AS - OPUS CONTAINER - Email Address Not Auto-Populating for A/N Send Function | 2020-04-24 15:40 | 2020-05-08 20:32 | 2020-05-08 13:52 | 2020-07-23 16:39 | 2020-07-27 17:58 |  | 2020-09-01 17:57 | 2020-09-01 10:22 | 2020-08-21 12:22 | 2020-10-09 13:00 | CR0012177 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2020-W36 | 2020-09 | 63 | 70 | 130.0952 | 6 | 2 | 2 | 0.02 | 193512 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.5 | 2020-04 | 0 | 0
498 | CR0012177 | CTASK0019199 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 14 | 16 | 2020-03-31 19:22 | 2020-03-26 19:22 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Estimation] AS - OPUS CONTAINER - Email Address Not Auto-Populating for A/N Send Function | 2020-04-24 15:40 | 2020-05-08 20:32 | 2020-05-08 13:52 | 2020-07-23 16:39 | 2020-07-27 17:58 |  | 2020-09-01 17:57 | 2020-09-01 10:22 | 2020-08-21 12:22 | 2020-10-09 13:00 | CR0012177 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2020-W36 | 2020-09 | 63 | 70 | 130.0952 | 6 | 2 | 2 | 0.02 | 193512 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.5 | 2020-04 | 0 | 0
499 | CR0012177 | CTASK0019520 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 2 | 5 | 2020-04-30 18:27 | 2020-04-13 18:27 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Deployment] AS - OPUS CONTAINER - Email Address Not Auto-Populating for A/N Send Function | 2020-04-24 15:40 | 2020-05-08 20:32 | 2020-05-08 13:52 | 2020-07-23 16:39 | 2020-07-27 17:58 |  | 2020-09-01 17:57 | 2020-09-01 10:22 | 2020-08-21 12:22 | 2020-10-09 13:00 | CR0012177 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2020-W36 | 2020-09 | 63 | 70 | 130.0952 | 6 | 2 | 2 | 0.02 | 193512 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.5 | 2020-04 | 0 | 0
500 | CR0012177 | CTASK0019283 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 2 | 2 | 2020-03-31 19:30 | 2020-03-31 10:30 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Analyze] AS - OPUS CONTAINER - Email Address Not Auto-Populating for A/N Send Function | 2020-04-24 15:40 | 2020-05-08 20:32 | 2020-05-08 13:52 | 2020-07-23 16:39 | 2020-07-27 17:58 |  | 2020-09-01 17:57 | 2020-09-01 10:22 | 2020-08-21 12:22 | 2020-10-09 13:00 | CR0012177 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2020-W36 | 2020-09 | 63 | 70 | 130.0952 | 6 | 2 | 2 | 0.02 | 193470 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.17391 | 2020-04 | 0 | 0
501 | CR0012398 | CTASK0019019 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-04-17 20:00 | 2020-04-14 20:00 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Deployment][CLT Internal] AS- OPUS Container - Booking Receipt Notice (Fax/Email) (Customer Notification) | 2020-03-27 09:20 | 2020-04-22 09:19 | 2020-04-13 17:44 | 2020-04-14 10:44 | 2020-04-14 10:46 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-04-14 10:47 | 2020-04-21 16:30 | CR0012398 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W17 | 2020-04 | 16 | 16 | 25.0278 | 4 | 1 | 1 | 0.03 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 16 | 0 | 0.52941 | 2020-03 | 0 | 0
502 | CR0012398 | CTASK0019015 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-04-11 01:06 | 2020-04-06 09:06 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Development][CLT Internal] AS- OPUS Container - Booking Receipt Notice (Fax/Email) (Customer Notification) | 2020-03-27 09:20 | 2020-04-22 09:19 | 2020-04-13 17:44 | 2020-04-14 10:44 | 2020-04-14 10:46 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-04-14 10:47 | 2020-04-21 16:30 | CR0012398 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W17 | 2020-04 | 16 | 16 | 25.0278 | 4 | 1 | 1 | 0.03 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 16 | 0 | 0.52941 | 2020-03 | 0 | 0
503 | CR0012398 | CTASK0018997 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-03-17 23:24 | 2020-03-16 19:43 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Design][CLT Internal] AS- OPUS Container - Booking Receipt Notice (Fax/Email) (Customer Notification) | 2020-03-27 09:20 | 2020-04-22 09:19 | 2020-04-13 17:44 | 2020-04-14 10:44 | 2020-04-14 10:46 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-04-14 10:47 | 2020-04-21 16:30 | CR0012398 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W17 | 2020-04 | 16 | 16 | 25.0278 | 4 | 1 | 1 | 0.03 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 16 | 0 | 0.52941 | 2020-03 | 0 | 0
504 | CR0012398 | CTASK0019017 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-04-11 01:05 | 2020-04-06 09:05 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Testing][CLT Internal] AS- OPUS Container - Booking Receipt Notice (Fax/Email) (Customer Notification) | 2020-03-27 09:20 | 2020-04-22 09:19 | 2020-04-13 17:44 | 2020-04-14 10:44 | 2020-04-14 10:46 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-04-14 10:47 | 2020-04-21 16:30 | CR0012398 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W17 | 2020-04 | 16 | 16 | 25.0278 | 4 | 1 | 1 | 0.03 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 16 | 0 | 0.52941 | 2020-03 | 0 | 0
505 | CR0013640 | CTASK0025718 | Closed | OPUS-BKG-IB | Thuc Tran | 6 | 6 | 2021-03-08 19:30 | 2021-03-03 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | Cargo Release Creation | [Estimation] Service Management > Booking/Documentation > Inbound Doc > Cargo Release > Cargo Release Creation. - Email Address location update | 2021-03-30 13:26 | 2021-05-18 23:26 | 2021-05-18 17:01 | 2021-06-10 13:50 | 2021-06-14 16:54 |  | 2021-06-29 16:35 | 2021-06-29 11:22 | 2021-06-17 14:12 | 2021-07-29 14:00 | CR0013640 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseCargo Release Creation | OPUS-BKG-IB | 2021-W26 | 2021-06 | 45 | 45 | 91.1312 | 3 | 1 | 1 | 0.02 | 173280 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0.375 | 1 | 2021-03 | 0 | 0
506 | CR0013640 | CTASK0027694 | Closed | OPUS-BKG-IB | Thuc Tran | 10 | 10 | 2021-06-29 19:30 | 2021-06-15 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | Cargo Release Creation | [Testing + Deployment] Service Management > Booking/Documentation > Inbound Doc > Cargo Release > Cargo Release Creation. - Email Address location update | 2021-03-30 13:26 | 2021-05-18 23:26 | 2021-05-18 17:01 | 2021-06-10 13:50 | 2021-06-14 16:54 |  | 2021-06-29 16:35 | 2021-06-29 11:22 | 2021-06-17 14:12 | 2021-07-29 14:00 | CR0013640 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseCargo Release Creation | OPUS-BKG-IB | 2021-W26 | 2021-06 | 45 | 45 | 91.1312 | 3 | 1 | 1 | 0.02 | 173280 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0.375 | 1 | 2021-03 | 0 | 0
507 | CR0013640 | CTASK0026675 | Closed | OPUS-BKG-IB | Thuc Tran | 29 | 29 | 2021-05-03 11:10 | 2021-04-26 11:10 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | Cargo Release Creation | [Development+Testing+Deployment]Service Management > Booking/Documentation > Inbound Doc > Cargo Release > Cargo Release Creation. - Email Address location update | 2021-03-30 13:26 | 2021-05-18 23:26 | 2021-05-18 17:01 | 2021-06-10 13:50 | 2021-06-14 16:54 |  | 2021-06-29 16:35 | 2021-06-29 11:22 | 2021-06-17 14:12 | 2021-07-29 14:00 | CR0013640 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseCargo Release Creation | OPUS-BKG-IB | 2021-W26 | 2021-06 | 45 | 45 | 91.1312 | 3 | 1 | 1 | 0.02 | 173280 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0.375 | 1 | 2021-03 | 0 | 0
508 | CR0011225 | CTASK0017255 | Closed | OPUS-BKG-M | Vinh Tran | 2 | 2 | 2019-11-26 02:00 | 2019-11-25 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Estimate] Not to select FAK commodity in OOG/BB Cargo Application | 2019-11-29 11:55 | 2019-12-17 | 2019-12-16 16:57 | 2020-02-24 19:49 | 2020-02-26 11:33 | 2019-12-16 16:58 | 2020-07-07 10:00 | 2020-03-31 10:00 | 2020-03-16 16:06 | 2021-07-22 14:00 | CR0011225 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W28 | 2020-07 | 30 | 28 | 220.9198 | 3 | 1 | 1 | 0.01 | 193525 | 0.5 | 0 | 0 | 0 | 1 | 1 | 3 | 4 | 27 | 0 | 0.45455 | 2019-11 | 0 | 0
509 | CR0011225 | CTASK0020950 | Closed | OPUS-BKG-M | Vinh Tran | 4 | 4 | 2020-07-01 02:00 | 2020-06-30 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | Not to select FAK commodity in OOG/BB Cargo Application | 2019-11-29 11:55 | 2019-12-17 | 2019-12-16 16:57 | 2020-02-24 19:49 | 2020-02-26 11:33 | 2019-12-16 16:58 | 2020-07-07 10:00 | 2020-03-31 10:00 | 2020-03-16 16:06 | 2021-07-22 14:00 | CR0011225 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W28 | 2020-07 | 30 | 28 | 220.9198 | 3 | 1 | 1 | 0.01 | 193525 | 0.5 | 0 | 0 | 0 | 1 | 1 | 3 | 4 | 27 | 0 | 0.45455 | 2019-11 | 0 | 0
510 | CR0011225 | CTASK0016242 | Closed | OPUS-BKG-M | Vinh Tran | 24 | 24 | 2019-12-06 17:19 | 2019-12-02 17:18 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | Not to select FAK commodity in OOG/BB Cargo Application | 2019-11-29 11:55 | 2019-12-17 | 2019-12-16 16:57 | 2020-02-24 19:49 | 2020-02-26 11:33 | 2019-12-16 16:58 | 2020-07-07 10:00 | 2020-03-31 10:00 | 2020-03-16 16:06 | 2021-07-22 14:00 | CR0011225 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W28 | 2020-07 | 30 | 28 | 220.9198 | 3 | 1 | 1 | 0.01 | 193525 | 0.5 | 0 | 0 | 0 | 1 | 1 | 3 | 4 | 27 | 0 | 0.45455 | 2019-11 | 0 | 0
511 | CR0010331 | CTASK0018104 | Closed | OPUS-BKG-M | Loc Tran | 16 | 18 | 2020-01-03 19:00 | 2019-12-24 14:00 | Container | Service Management | Product Catalog |  |  |  | [Additional Development] PRD - Ability to set up DG constraint by IMDG class to disallow booking of only certain DG cargo. | 2019-05-17 11:21 | 2019-11-30 | 2019-11-29 16:02 | 2020-05-08 23:47 | 2020-05-25 14:27 |  | 2020-06-02 10:00 | 2020-06-02 10:30 | 2020-05-26 12:21 | 2020-07-02 13:00 | CR0010331 | Service ManagementProduct Catalog | OPUS-PRD | 2020-W23 | 2020-06 | 102 | 98 | 381.9439 | 3 | 2 | 3 | 0.01 | 193503 | -0.2 | 0 | 0 | 1 | 1 | 1 | 4 | 5 | 29 | 0 | 33 | 2019-05 | 1 | 1
512 | CR0010331 | CTASK0017394 | Closed | OPUS-PRI | Ngan Nham | 40 | 40 |  |  | Container | Service Management | Product Catalog |  |  |  | PRD - Ability to set up DG constraint by IMDG class to disallow booking of only certain DG cargo. | 2019-05-17 11:21 | 2019-11-30 | 2019-11-29 16:02 | 2020-05-08 23:47 | 2020-05-25 14:27 |  | 2020-06-02 10:00 | 2020-06-02 10:30 | 2020-05-26 12:21 | 2020-07-02 13:00 | CR0010331 | Service ManagementProduct Catalog | OPUS-PRD | 2020-W23 | 2020-06 | 102 | 98 | 381.9439 | 3 | 2 | 3 | 0.01 | 193461 | 0.5 | 0 | 0 | 1 | 1 | 1 | 4 | 5 | 29 | 0 | 0 | 2019-05 | 1 | 1
513 | CR0010331 | CTASK0017393 | Closed | OPUS-PRI | Nhien Nguyen | 46 | 40 |  |  | Container | Service Management | Product Catalog |  |  |  | PRD - Ability to set up DG constraint by IMDG class to disallow booking of only certain DG cargo. | 2019-05-17 11:21 | 2019-11-30 | 2019-11-29 16:02 | 2020-05-08 23:47 | 2020-05-25 14:27 |  | 2020-06-02 10:00 | 2020-06-02 10:30 | 2020-05-26 12:21 | 2020-07-02 13:00 | CR0010331 | Service ManagementProduct Catalog | OPUS-PRD | 2020-W23 | 2020-06 | 102 | 98 | 381.9439 | 3 | 2 | 3 | 0.01 | 183364 | 0.6 | 0 | 0 | 1 | 1 | 1 | 4 | 5 | 29 | 0 | 0 | 2019-05 | 1 | 1
514 | CR0013063 | CTASK0022455 | Closed | OPUS-BKG-IB | Thuc Tran | 41 | 41 | 2020-09-25 19:30 | 2020-09-14 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Development+Testing+Deployment] [Internal CR] Add user authority check before open full release popup in EU D/O screen | 2020-09-17 16:55 | 2020-09-29 23:19 | 2020-09-29 10:43 | 2020-10-15 11:49 | 2020-10-21 16:51 |  | 2020-10-27 15:42 | 2020-10-27 17:58 | 2020-10-22 09:39 | 2020-11-29 14:00 | CR0013063 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W44 | 2020-10 | 48 | 48 | 39.9493 | 2 | 1 | 1 | 0.05 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 20 | 0 | 0.18519 | 2020-09 | 0 | 0
515 | CR0013063 | CTASK0023118 | Closed | OPUS-BKG-IB | Thuc Tran | 7 | 7 | 2020-10-26 19:30 | 2020-10-21 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Testing+Deployment] [Internal CR] Add user authority check before open full release popup in EU D/O screen | 2020-09-17 16:55 | 2020-09-29 23:19 | 2020-09-29 10:43 | 2020-10-15 11:49 | 2020-10-21 16:51 |  | 2020-10-27 15:42 | 2020-10-27 17:58 | 2020-10-22 09:39 | 2020-11-29 14:00 | CR0013063 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W44 | 2020-10 | 48 | 48 | 39.9493 | 2 | 1 | 1 | 0.05 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 20 | 0 | 0.18519 | 2020-09 | 0 | 0
516 | CR0011615 | CTASK0018789 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 22 | 22 | 2020-03-31 18:00 | 2020-03-09 09:00 | Container | Service Management | Trans S/O | Code | USA Actual Customer Code Manage |  | NA * TRS * Actual Customer Code Manage - Use Notify Code when B/L type is Order | 2020-03-06 15:21 | 2020-03-31 18:00 | 2020-03-19 15:51 | 2020-05-14 01:04 | 2020-05-18 15:45 |  | 2020-05-26 11:00 | 2020-05-26 10:10 | 2020-05-20 02:45 | 2020-06-25 13:00 | CR0011615 | Service ManagementTrans S/OCodeUSA Actual Customer Code Manage | OPUS-TRS | 2020-W22 | 2020-05 | 44 | 44 | 80.8189 | 2 | 1 | 2 | 0.02 | 183432 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0 | 2020-03 | 0 | 0
517 | CR0011615 | CTASK0018790 | Closed | OPUS-TRS | Giang Nguyen Hoang | 22 | 22 | 2020-03-31 18:00 | 2020-03-09 09:00 | Container | Service Management | Trans S/O | Code | USA Actual Customer Code Manage |  | NA * TRS * Actual Customer Code Manage - Use Notify Code when B/L type is Order | 2020-03-06 15:21 | 2020-03-31 18:00 | 2020-03-19 15:51 | 2020-05-14 01:04 | 2020-05-18 15:45 |  | 2020-05-26 11:00 | 2020-05-26 10:10 | 2020-05-20 02:45 | 2020-06-25 13:00 | CR0011615 | Service ManagementTrans S/OCodeUSA Actual Customer Code Manage | OPUS-TRS | 2020-W22 | 2020-05 | 44 | 44 | 80.8189 | 2 | 1 | 2 | 0.02 | 183440 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0 | 2020-03 | 0 | 0
518 | CR0013595 | CTASK0025156 | Closed | OPUS-CTM | Tran Le | 8 | 36 |  |  | Container | Service Management | CNTR Movement | MVMT Inquiry | Auto-created Status Inquiry |  | CTM auto created event - LCC code query - Manage effort | 2021-02-08 13:21 | 2021-02-26 20:00 | 2021-02-09 11:05 | 2021-02-09 13:49 | 2021-02-09 13:54 |  | 2021-02-15 09:30 | 2021-02-15 10:00 | 2021-02-10 10:44 | 2021-03-16 11:12 | CR0013595 | Service ManagementCNTR MovementMVMT InquiryAuto-created Status Inquiry | OPUS-CTM | 2021-W7 | 2021-02 | 8 | 36 | 6.8393 | 1 | 1 | 1 | 0.22 | 193501 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 21 | 0 | 0.076923 | 2021-02 | 0 | 0
519 | CR0012317 | CTASK0019086 | Closed | OPUS-MDA | Nhat Phan Dinh Minh | 11 | 10 | 2020-04-30 18:00 | 2020-03-23 09:00 | Container | Biz Common | Master Data | Admin | MDA History Inquiry |  | EAS - MDA - Request Inquiry & Download History per MDA Code | 2020-03-23 10:31 | 2020-04-30 18:00 | 2020-03-30 13:34 | 2020-04-16 03:35 | 2020-04-22 12:11 |  | 2020-04-28 11:00 | 2020-04-28 11:00 | 2020-04-22 12:14 | 2020-05-28 13:00 | CR0012317 | Biz CommonMaster DataAdminMDA History Inquiry | OPUS-MDA | 2020-W18 | 2020-04 | 21 | 20 | 36.0205 | 2 | 1 | 2 | 0.02 | 183432 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0 | 2020-03 | 0 | 0
520 | CR0012317 | CTASK0019087 | Closed | OPUS-MDA | Giang Nguyen Hoang | 10 | 10 | 2020-04-30 18:00 | 2020-03-23 09:00 | Container | Biz Common | Master Data | Admin | MDA History Inquiry |  | EAS - MDA - Request Inquiry & Download History per MDA Code | 2020-03-23 10:31 | 2020-04-30 18:00 | 2020-03-30 13:34 | 2020-04-16 03:35 | 2020-04-22 12:11 |  | 2020-04-28 11:00 | 2020-04-28 11:00 | 2020-04-22 12:14 | 2020-05-28 13:00 | CR0012317 | Biz CommonMaster DataAdminMDA History Inquiry | OPUS-MDA | 2020-W18 | 2020-04 | 21 | 20 | 36.0205 | 2 | 1 | 2 | 0.02 | 183440 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0 | 2020-03 | 0 | 0
521 | CR0013022 | CTASK0022325 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 4 | 4 | 2020-09-09 13:00 | 2020-09-07 13:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Analytics][CLT internal] BKG- Rotterdam manifest , download function improvement | 2020-09-22 16:08 | 2020-09-30 | 2020-09-28 13:56 | 2020-10-15 16:53 | 2020-10-29 17:13 |  | 2020-11-03 10:00 | 2020-11-03 09:30 | 2020-10-29 17:42 | 2020-12-03 14:00 | CR0013022 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2020-W45 | 2020-11 | 32 | 32 | 41.7447 | 3 | 1 | 1 | 0.03 | 193506 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 1.25 | 2020-09 | 0 | 0
522 | CR0013022 | CTASK0023125 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 12 | 12 | 2020-11-10 02:00 | 2020-10-22 02:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Deployment][CLT internal] BKG- Rotterdam manifest , download function improvement | 2020-09-22 16:08 | 2020-09-30 | 2020-09-28 13:56 | 2020-10-15 16:53 | 2020-10-29 17:13 |  | 2020-11-03 10:00 | 2020-11-03 09:30 | 2020-10-29 17:42 | 2020-12-03 14:00 | CR0013022 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2020-W45 | 2020-11 | 32 | 32 | 41.7447 | 3 | 1 | 1 | 0.03 | 193506 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 1.25 | 2020-09 | 0 | 0
523 | CR0013022 | CTASK0022371 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 16 | 16 | 2020-09-30 13:00 | 2020-09-10 13:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Develop-Testing][CLT internal] BKG- Rotterdam manifest , download function improvement | 2020-09-22 16:08 | 2020-09-30 | 2020-09-28 13:56 | 2020-10-15 16:53 | 2020-10-29 17:13 |  | 2020-11-03 10:00 | 2020-11-03 09:30 | 2020-10-29 17:42 | 2020-12-03 14:00 | CR0013022 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2020-W45 | 2020-11 | 32 | 32 | 41.7447 | 3 | 1 | 1 | 0.03 | 193506 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 1.25 | 2020-09 | 0 | 0
524 | CR0013842 | CTASK0026403 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 31 | 42 | 2021-05-10 23:00 | 2021-04-09 10:30 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design + Development + Testing] [CLT Internal] 2 issues related to Cognos | 2021-04-27 09:20 | 2021-05-01 | 2021-04-28 09:56 | 2021-04-28 14:00 | 2021-04-28 14:33 |  | 2021-05-04 10:00 | 2021-05-04 10:00 | 2021-04-29 15:04 | 2021-06-03 14:00 | CR0013842 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W18 | 2021-05 | 31 | 52 | 7.028 | 2 | 1 | 2 | 0.31 | 193470 | 2.1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 28 | 0 | 0.11111 | 2021-04 | 0 | 0
525 | CR0013842 | CTASK0026390 | Closed | OPUS-BKG-OB | Nam Nguyen | 10 | 10 | 2021-05-07 15:48 | 2021-05-03 15:48 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design + Development + Testing] [CLT Internal] 2 issues related to Cognos | 2021-04-27 09:20 | 2021-05-01 | 2021-04-28 09:56 | 2021-04-28 14:00 | 2021-04-28 14:33 |  | 2021-05-04 10:00 | 2021-05-04 10:00 | 2021-04-29 15:04 | 2021-06-03 14:00 | CR0013842 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W18 | 2021-05 | 31 | 52 | 7.028 | 2 | 1 | 2 | 0.31 | 123048 | 2.6 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 28 | 0 | 0.047619 | 2021-04 | 0 | 0
526 | CR0012351 | CTASK0019632 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 4 | 4 | 2020-05-08 20:33 | 2020-05-07 10:32 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing]Please ccheck and advise if possible to match container sequence from eSI to container sequence in booking during eSI upload. | 2020-04-16 13:26 | 2020-05-21 | 2020-05-20 15:08 | 2020-11-13 07:10 | 2020-11-20 15:34 |  | 2021-01-12 11:00 | 2021-01-12 15:00 | 2021-01-04 10:50 | 2021-02-12 14:00 | CR0012351 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W2 | 2021-01 | 56 | 56 | 270.8984 | 4 | 1 | 1 | 0.01 | 193488 | 0.8 | 0 | 0 | 0 | 1 | 1 | 3 | 14 | 40 | 0 | 2.1667 | 2020-04 | 0 | 0
527 | CR0012351 | CTASK0019631 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 40 | 40 | 2020-04-29 16:26 | 2020-04-06 16:26 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development]Please ccheck and advise if possible to match container sequence from eSI to container sequence in booking during eSI upload. | 2020-04-16 13:26 | 2020-05-21 | 2020-05-20 15:08 | 2020-11-13 07:10 | 2020-11-20 15:34 |  | 2021-01-12 11:00 | 2021-01-12 15:00 | 2021-01-04 10:50 | 2021-02-12 14:00 | CR0012351 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W2 | 2021-01 | 56 | 56 | 270.8984 | 4 | 1 | 1 | 0.01 | 193488 | 0.8 | 0 | 0 | 0 | 1 | 1 | 3 | 14 | 40 | 0 | 2.1667 | 2020-04 | 0 | 0
528 | CR0012351 | CTASK0019331 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 8 | 8 | 2020-04-29 16:26 | 2020-04-06 16:26 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design]Please ccheck and advise if possible to match container sequence from eSI to container sequence in booking during eSI upload. | 2020-04-16 13:26 | 2020-05-21 | 2020-05-20 15:08 | 2020-11-13 07:10 | 2020-11-20 15:34 |  | 2021-01-12 11:00 | 2021-01-12 15:00 | 2021-01-04 10:50 | 2021-02-12 14:00 | CR0012351 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W2 | 2021-01 | 56 | 56 | 270.8984 | 4 | 1 | 1 | 0.01 | 193488 | 0.8 | 0 | 0 | 0 | 1 | 1 | 3 | 14 | 40 | 0 | 2.1667 | 2020-04 | 0 | 0
529 | CR0012351 | CTASK0019633 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 4 | 4 | 2020-12-25 18:55 | 2020-12-21 18:55 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment]Please ccheck and advise if possible to match container sequence from eSI to container sequence in booking during eSI upload. | 2020-04-16 13:26 | 2020-05-21 | 2020-05-20 15:08 | 2020-11-13 07:10 | 2020-11-20 15:34 |  | 2021-01-12 11:00 | 2021-01-12 15:00 | 2021-01-04 10:50 | 2021-02-12 14:00 | CR0012351 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W2 | 2021-01 | 56 | 56 | 270.8984 | 4 | 1 | 1 | 0.01 | 193488 | 0.8 | 0 | 0 | 0 | 1 | 1 | 3 | 14 | 40 | 0 | 2.1667 | 2020-04 | 0 | 0
530 | CR0012744 | CTASK0020843 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 2 | 2 | 2020-09-16 10:51 | 2020-09-15 10:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal]NA *BKG* Booking contact scroll bar will begin floating away when screen is sized to 80% or at 50% | 2020-08-04 11:18 | 2020-08-20 | 2020-08-18 11:25 | 2020-09-01 20:31 | 2020-09-03 10:03 |  | 2020-09-22 10:00 | 2020-09-22 10:00 | 2020-09-03 13:41 | 2020-09-22 10:32 | CR0012744 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W39 | 2020-09 | 19 | 19 | 48.9457 | 4 | 1 | 1 | 0.02 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 0.28125 | 2020-08 | 0 | 0
531 | CR0012744 | CTASK0020840 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 5 | 5 | 2020-06-24 18:31 | 2020-06-22 11:53 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal]NA *BKG* Booking contact scroll bar will begin floating away when screen is sized to 80% or at 50% | 2020-08-04 11:18 | 2020-08-20 | 2020-08-18 11:25 | 2020-09-01 20:31 | 2020-09-03 10:03 |  | 2020-09-22 10:00 | 2020-09-22 10:00 | 2020-09-03 13:41 | 2020-09-22 10:32 | CR0012744 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W39 | 2020-09 | 19 | 19 | 48.9457 | 4 | 1 | 1 | 0.02 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 0.28125 | 2020-08 | 0 | 0
532 | CR0012744 | CTASK0020842 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2020-07-31 18:53 | 2020-07-29 10:53 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal]NA *BKG* Booking contact scroll bar will begin floating away when screen is sized to 80% or at 50% | 2020-08-04 11:18 | 2020-08-20 | 2020-08-18 11:25 | 2020-09-01 20:31 | 2020-09-03 10:03 |  | 2020-09-22 10:00 | 2020-09-22 10:00 | 2020-09-03 13:41 | 2020-09-22 10:32 | CR0012744 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W39 | 2020-09 | 19 | 19 | 48.9457 | 4 | 1 | 1 | 0.02 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 0.28125 | 2020-08 | 0 | 0
533 | CR0012744 | CTASK0020841 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2020-07-31 18:51 | 2020-07-27 15:30 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal]NA *BKG* Booking contact scroll bar will begin floating away when screen is sized to 80% or at 50% | 2020-08-04 11:18 | 2020-08-20 | 2020-08-18 11:25 | 2020-09-01 20:31 | 2020-09-03 10:03 |  | 2020-09-22 10:00 | 2020-09-22 10:00 | 2020-09-03 13:41 | 2020-09-22 10:32 | CR0012744 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W39 | 2020-09 | 19 | 19 | 48.9457 | 4 | 1 | 1 | 0.02 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 0.28125 | 2020-08 | 0 | 0
534 | CR0013349 | CTASK0024017 | Closed | OPUS-BKG-M | Loc Tran | 40 | 45 | 2021-01-08 19:17 | 2020-12-04 19:17 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [CLT Internal] The performance enhancement of BRN generating query | 2020-12-18 15:21 | 2021-02-11 | 2021-02-09 13:47 | 2021-02-18 09:30 | 2021-03-03 10:05 |  | 2021-03-16 10:00 | 2021-03-16 08:48 | 2021-03-03 18:17 | 2021-04-16 14:00 | CR0013349 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W11 | 2021-03 | 40 | 45 | 87.777 | 1 | 1 | 1 | 0.02 | 193503 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.33333 | 0.28571 | 2020-12 | 0 | 0
535 | CR0011891 | CTASK0017627 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 |  |  | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Estimation] NA *Standby* Add BKG number to Standby Booking Detail Pop-up | 2020-01-31 17:28 | 2020-02-18 | 2020-02-07 14:57 | 2020-02-29 04:47 | 2020-03-02 12:24 |  | 2020-04-07 10:00 | 2020-04-07 10:00 | 2020-03-03 22:41 | 2020-04-08 04:57 | CR0011891 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W15 | 2020-04 | 10 | 8 | 66.6888 | 2 | 1 | 1 | 0 | 153106 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 16 | 0 | 0.4 | 2020-01 | 0 | 0
536 | CR0011891 | CTASK0017669 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-02-07 16:35 | 2020-02-03 16:35 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | NA *Standby* Add BKG number to Standby Booking Detail Pop-up | 2020-01-31 17:28 | 2020-02-18 | 2020-02-07 14:57 | 2020-02-29 04:47 | 2020-03-02 12:24 |  | 2020-04-07 10:00 | 2020-04-07 10:00 | 2020-03-03 22:41 | 2020-04-08 04:57 | CR0011891 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W15 | 2020-04 | 10 | 8 | 66.6888 | 2 | 1 | 1 | 0 | 153106 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 16 | 0 | 0.4 | 2020-01 | 0 | 0
537 | CR0014096 | CTASK0027727 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 38 | 38 | 2021-07-09 12:22 | 2021-06-28 12:22 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment]EUA CR - Regulatory Requirement - NXTPORT Secure Release Platform for BE Phase 2 Sprint 1 | 2021-06-29 09:58 | 2021-07-26 23:57 | 2021-07-26 17:07 | 2021-07-27 18:37 | 2021-07-28 11:11 |  | 2021-08-03 11:11 | 2021-08-03 11:42 | 2021-07-29 11:27 | 2021-08-10 14:00 | CR0014096 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W31 | 2021-08 | 38 | 38 | 35.0504 | 1 | 1 | 1 | 0.05 | 193512 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 7 | 22 | 0.2963 | 0.3125 | 2021-06 | 0 | 0
538 | CR0011480 | CTASK0015171 | Closed | OPUS-PSO | Hieu Vu | 16 | 16 |  |  | Container | Vessel Operation | Port Service Order | Report | Port Charge Invoice Summary |  | [Development] Data retrieval in Port Charge Invoice Summary screen | 2019-08-01 10:09 | 2019-08-16 17:38 | 2019-08-13 11:33 | 2019-08-14 15:38 | 2019-09-03 17:16 |  | 2019-08-27 11:00 | 2019-08-13 09:00 | 2019-09-03 18:11 | 2019-09-09 11:38 | CR0011480 | Vessel OperationPort Service OrderReportPort Charge Invoice Summary | OPUS-PSO | 2019-W35 | 2019-08 | 16 | 0 | 26.0356 | 1 | 1 | 1 | 0 | 183375 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 6 | 0 | 0 | 2019-08 | 0 | 0
539 | CR0013900 | CTASK0027176 | Closed | OPUS-DMT | Cuong Nguyen | 2 | 3 | 2021-06-11 20:00 | 2021-06-01 08:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK3] CLV_Pair Test | 2021-05-26 11:12 | 2021-06-11 20:00 | 2021-06-11 14:10 | 2021-07-21 10:01 | 2021-07-23 09:21 |  | 2021-08-03 10:00 | 2021-08-03 10:05 | 2021-07-26 09:13 | 2021-08-10 14:00 | CR0013900 | Service ManagementDemurrage/Detention | OPUS-DMT | 2021-W31 | 2021-08 | 2 | 3 | 68.95 | 1 | 1 | 1 | 0 | 193529 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 22 | 0 | 0.058824 | 2021-05 | 0 | 0
540 | CR0011207 | CTASK0013196 | Closed | OPUS-PRI | Nhien Nguyen | 10 | 10 | 2019-05-09 15:03 | 2019-05-09 10:02 | Container | Sales Management | Pricing | Code | Inquiry | Location Inquiry | [05/06 ~ 05/12] Show State Code & State Name in Location Inquiry result | 2019-05-08 14:14 | 2019-05-31 14:13 | 2019-05-10 17:17 | 2019-05-14 17:17 | 2019-05-15 10:16 |  | 2019-05-21 10:15 | 2019-05-21 12:15 | 2019-05-15 10:16 | 2019-06-20 13:00 | CR0011207 | Sales ManagementPricingCodeInquiryLocation Inquiry | OPUS-PRI | 2019-W21 | 2019-05 | 15 | 0 | 12.8346 | 2 | 1 | 1 | 0 | 183364 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 6 | 0 | 0 | 2019-05 | 0 | 0
541 | CR0011207 | CTASK0013746 | Closed | OPUS-PRI | Nhien Nguyen | 5 | 5 | 2019-05-21 17:22 | 2019-05-21 12:22 | Container | Sales Management | Pricing | Code | Inquiry | Location Inquiry | [05/21 ~ 05/26] [Populate State code and State name in Location Inquiry Result: Testing on STG and PROD environment] | 2019-05-08 14:14 | 2019-05-31 14:13 | 2019-05-10 17:17 | 2019-05-14 17:17 | 2019-05-15 10:16 |  | 2019-05-21 10:15 | 2019-05-21 12:15 | 2019-05-15 10:16 | 2019-06-20 13:00 | CR0011207 | Sales ManagementPricingCodeInquiryLocation Inquiry | OPUS-PRI | 2019-W21 | 2019-05 | 15 | 0 | 12.8346 | 2 | 1 | 1 | 0 | 183364 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 6 | 0 | 0 | 2019-05 | 0 | 0
542 | CR0013878 | CTASK0026635 | Implemented | OPUS-SCG | Lanh Le | 120 | 120 | 2021-06-30 11:47 | 2021-04-26 11:47 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval |  |  | DG EDI exchange with Samudera (SSL) | 2021-05-06 12:31 | 2021-06-25 12:31 | 2021-06-24 08:27 | 2021-08-04 15:06 | 2021-08-04 16:14 |  | 2021-08-10 10:14 | 2021-08-10 10:00 | 2021-08-05 17:43 |  | CR0013878 | Vessel OperationSpecial CargoSPCL CGO Approval | OPUS-SCG | 2021-W32 | 2021-08 | 120 | 120 | 95.905 | 1 | 1 | 1 | 0.05 | 183422 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 10 | 22 | 0 | 0 | 2021-05 | 0 | 0
543 | CR0012357 | CTASK0019337 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 | 2020-04-18 01:59 | 2020-04-13 02:59 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] Asia - SPC - Standby BKG User List - Modified Logic Request | 2020-04-06 11:44 | 2020-05-08 | 2020-04-29 09:58 | 2020-05-20 00:38 | 2020-05-22 11:18 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-05-22 13:20 | 2020-07-09 13:00 | CR0012357 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W24 | 2020-06 | 32 | 34 | 63.9276 | 4 | 1 | 1 | 0.02 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-04 | 0 | 0
544 | CR0012357 | CTASK0019117 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 | 2020-04-02 01:16 | 2020-03-23 10:15 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] Asia - SPC - Standby BKG User List - Modified Logic Request | 2020-04-06 11:44 | 2020-05-08 | 2020-04-29 09:58 | 2020-05-20 00:38 | 2020-05-22 11:18 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-05-22 13:20 | 2020-07-09 13:00 | CR0012357 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W24 | 2020-06 | 32 | 34 | 63.9276 | 4 | 1 | 1 | 0.02 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-04 | 0 | 0
545 | CR0012357 | CTASK0019341 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2020-06-10 01:29 | 2020-06-01 02:29 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] Asia - SPC - Standby BKG User List - Modified Logic Request | 2020-04-06 11:44 | 2020-05-08 | 2020-04-29 09:58 | 2020-05-20 00:38 | 2020-05-22 11:18 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-05-22 13:20 | 2020-07-09 13:00 | CR0012357 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W24 | 2020-06 | 32 | 34 | 63.9276 | 4 | 1 | 1 | 0.02 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-04 | 0 | 0
546 | CR0012357 | CTASK0019339 | Closed | OPUS-BKG-M | Kieu Le | 6 | 8 | 2020-04-18 01:06 | 2020-04-13 02:06 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] Asia - SPC - Standby BKG User List - Modified Logic Request | 2020-04-06 11:44 | 2020-05-08 | 2020-04-29 09:58 | 2020-05-20 00:38 | 2020-05-22 11:18 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-05-22 13:20 | 2020-07-09 13:00 | CR0012357 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W24 | 2020-06 | 32 | 34 | 63.9276 | 4 | 1 | 1 | 0.02 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-04 | 0 | 0
547 | CR0012205 | CTASK0018828 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 20 | 20 | 2020-03-31 18:05 | 2020-03-09 18:05 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [CLT Internal] Enhancement of ESM_BKG_0898 to prevent OOME | 2020-03-13 13:05 | 2020-04-30 | 2020-04-20 17:16 | 2020-04-22 01:31 | 2020-04-22 14:44 |  | 2020-04-28 10:00 | 2020-04-28 10:00 | 2020-04-22 14:44 | 2020-05-29 13:00 | CR0012205 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2020-W18 | 2020-04 | 73 | 69 | 45.8718 | 3 | 1 | 3 | 0.06 | 193488 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 2.1667 | 2020-03 | 0 | 0
548 | CR0012205 | CTASK0018113 | Closed | OPUS-BKG-M | Loc Tran | 47 | 47 | 2020-02-07 19:37 | 2020-01-30 10:00 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Design][CLT Internal] Enhancement of ESM_BKG_0898 to prevent OOME | 2020-03-13 13:05 | 2020-04-30 | 2020-04-20 17:16 | 2020-04-22 01:31 | 2020-04-22 14:44 |  | 2020-04-28 10:00 | 2020-04-28 10:00 | 2020-04-22 14:44 | 2020-05-29 13:00 | CR0012205 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2020-W18 | 2020-04 | 73 | 69 | 45.8718 | 3 | 1 | 3 | 0.06 | 193503 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0.36364 | 2020-03 | 0 | 0
549 | CR0012205 | CTASK0019685 | Closed | OPUS-BKG-M | Vinh Tran | 6 | 2 |  |  | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [CLT Internal] Enhancement of ESM_BKG_0898 to prevent OOME | 2020-03-13 13:05 | 2020-04-30 | 2020-04-20 17:16 | 2020-04-22 01:31 | 2020-04-22 14:44 |  | 2020-04-28 10:00 | 2020-04-28 10:00 | 2020-04-22 14:44 | 2020-05-29 13:00 | CR0012205 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2020-W18 | 2020-04 | 73 | 69 | 45.8718 | 3 | 1 | 3 | 0.06 | 193525 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0.45455 | 2020-03 | 0 | 0
550 | CR0011773 | CTASK0016450 | Closed | OPUS-BKG-M | Kieu Le | 9 | 24 | 2019-10-04 14:42 | 2019-09-23 14:42 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [CLT Internal] Booking History Performance Enhancement | 2019-10-04 11:52 | 2020-01-01 | 2019-12-23 16:56 | 2020-01-16 15:19 | 2020-01-16 15:45 |  | 2020-01-28 15:45 | 2020-01-28 11:23 | 2020-01-22 11:36 | 2020-02-27 14:00 | CR0011773 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W5 | 2020-01 | 9 | 24 | 116.162 | 1 | 1 | 1 | 0.01 | 153106 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 10 | 0 | 0.4 | 2019-10 | 0 | 0
551 | CR0011617 | CTASK0017523 | Closed | OPUS-TRS | Hieu Tran | 22 | 32 | 2019-12-27 18:00 | 2019-12-18 09:00 | Container | Service Management | Trans S/O | Service Order | Inquiry |  | NA * TRS * Add Columns for Frustate Date and Frustrate User ID | 2019-12-12 16:58 | 2020-01-31 18:00 | 2020-01-07 11:44 | 2020-01-23 16:58 | 2020-02-03 17:49 |  | 2020-02-11 11:00 | 2020-02-11 09:30 | 2020-02-04 01:25 | 2020-03-12 13:00 | CR0011617 | Service ManagementTrans S/OService OrderInquiry | OPUS-TRS | 2020-W7 | 2020-02 | 22 | 32 | 60.7517 | 1 | 1 | 1 | 0.02 | 183400 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 13 | 0 | 0 | 2019-12 | 0 | 0
552 | CR0012515 | CTASK0019829 | Closed | OPUS-MNR | Tuyen Truong | 22 | 25 | 2020-06-20 01:00 | 2020-06-02 11:00 | Container | Equipment Management | M&R | Repair | Invoice |  | [Documentation] NA *MNR* Update I/F file to Include new Acct Cost Center Code - US01RICEQ0 | 2020-06-01 17:25 | 2020-06-06 01:00 | 2020-06-05 15:14 | 2020-07-07 01:41 | 2020-07-08 13:25 |  | 2020-07-14 12:00 | 2020-07-14 11:00 | 2020-07-08 22:14 | 2020-08-13 13:00 | CR0012515 | Equipment ManagementM&RRepairInvoice | OPUS-MNR | 2020-W29 | 2020-07 | 22 | 25 | 42.7742 | 1 | 1 | 1 | 0.02 | 173255 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 27 | 0 | 0 | 2020-06 | 0 | 0
553 | CR0012917 | CTASK0021696 | Closed | OPUS-JOO | Thuan Tran | 40 | 40 | 2020-09-30 13:27 | 2020-08-24 13:27 | Container | Support & Admin | Joint Operation | CSR |  |  | [CLT Internal] CSR Approval validation | 2020-08-31 14:30 | 2020-11-30 14:29 | 2020-11-26 10:29 | 2021-01-04 13:21 | 2021-01-11 15:02 |  | 2021-01-22 15:02 | 2021-01-12 10:57 | 2021-01-15 09:13 | 2021-02-18 14:51 | CR0012917 | Support & AdminJoint OperationCSR | OPUS-JOO | 2021-W3 | 2021-01 | 120 | 120 | 144.0222 | 2 | 1 | 2 | 0.03 | 183423 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-08 | 0 | 0
554 | CR0012917 | CTASK0021695 | Closed | OPUS-JOO | Linh Nguyen | 80 | 80 | 2020-10-31 18:03 | 2020-08-24 18:03 | Container | Support & Admin | Joint Operation | CSR |  |  | [CLT Internal] CSR Approval validation | 2020-08-31 14:30 | 2020-11-30 14:29 | 2020-11-26 10:29 | 2021-01-04 13:21 | 2021-01-11 15:02 |  | 2021-01-22 15:02 | 2021-01-12 10:57 | 2021-01-15 09:13 | 2021-02-18 14:51 | CR0012917 | Support & AdminJoint OperationCSR | OPUS-JOO | 2021-W3 | 2021-01 | 120 | 120 | 144.0222 | 2 | 1 | 2 | 0.03 | 193464 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-08 | 0 | 0
555 | CR0011743 | CTASK0023160 | Closed | OPUS-SCE | VInh Bui | 33 | 30 | 2020-11-01 12:54 | 2020-10-02 12:54 | Container | Service Management | SCEM | Visibility | Customer EDI Monitoring |  | Create new 315 Message VBE to trigger using ETB in Coastal Vessel Schedule updates | 2020-01-30 09:20 | 2020-02-07 17:46 | 2020-02-07 14:03 | 2020-12-23 04:39 | 2021-01-16 05:09 |  | 2021-01-27 | 2021-01-26 11:31 | 2021-01-21 17:39 | 2021-02-23 14:11 | CR0011743 | Service ManagementSCEMVisibilityCustomer EDI Monitoring | OPUS-SCE | 2021-W4 | 2021-01 | 53 | 60 | 362.611 | 3 | 1 | 2 | 0.01 | 193469 | 0.3 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 40 | 0 | 0 | 2020-01 | 0 | 0
556 | CR0011743 | CTASK0023003 | Closed | OPUS-SCE | Son Nguyen The | 7 | 30 | 2020-10-31 16:05 | 2020-10-13 16:05 | Container | Service Management | SCEM | Visibility | Customer EDI Monitoring |  | Create new 315 Message VBE to trigger using ETB in Coastal Vessel Schedule updates | 2020-01-30 09:20 | 2020-02-07 17:46 | 2020-02-07 14:03 | 2020-12-23 04:39 | 2021-01-16 05:09 |  | 2021-01-27 | 2021-01-26 11:31 | 2021-01-21 17:39 | 2021-02-23 14:11 | CR0011743 | Service ManagementSCEMVisibilityCustomer EDI Monitoring | OPUS-SCE | 2021-W4 | 2021-01 | 53 | 60 | 362.611 | 3 | 1 | 2 | 0.01 | 193531 | 0.3 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 40 | 0 | 0 | 2020-01 | 0 | 0
557 | CR0011743 | CTASK0017994 | Closed | OPUS-SCE | VInh Bui | 13 | 13 |  |  | Container | Service Management | SCEM | Visibility | Customer EDI Monitoring |  | [ACTUAL]Create new 315 Message VBE to trigger using ETB in Coastal Vessel Schedule updates | 2020-01-30 09:20 | 2020-02-07 17:46 | 2020-02-07 14:03 | 2020-12-23 04:39 | 2021-01-16 05:09 |  | 2021-01-27 | 2021-01-26 11:31 | 2021-01-21 17:39 | 2021-02-23 14:11 | CR0011743 | Service ManagementSCEMVisibilityCustomer EDI Monitoring | OPUS-SCE | 2021-W4 | 2021-01 | 53 | 60 | 362.611 | 3 | 1 | 2 | 0.01 | 193469 | 0.3 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 40 | 0 | 0 | 2020-01 | 0 | 0
558 | CR0011036 | CTASK0012985 | Closed | OPUS-BKG-M | Kieu Le | 37 | 32 | 2019-09-06 10:52 | 2019-08-26 10:52 | Container | Vessel Operation | Special Cargo | IMDG | UN Number |  | Subsidiary hazards sequence change request as per IMDG | 2019-05-14 09:25 | 2019-09-17 | 2019-09-11 12:24 | 2019-09-18 14:56 | 2019-09-18 16:01 |  | 2019-09-23 09:30 | 2019-09-24 09:18 | 2019-09-19 12:42 | 2019-09-25 14:28 | CR0011036 | Vessel OperationSpecial CargoIMDGUN Number | OPUS-SCG | 2019-W39 | 2019-09 | 37 | 32 | 132.0033 | 1 | 1 | 1 | 0.01 | 153106 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 6 | 0 | 0 | 2019-05 | 0 | 0
559 | CR0013334 | CTASK0024005 | Closed | OPUS-SAP | Mohamed Hary | 8 | 8 | 2020-12-31 11:24 | 2020-12-04 11:24 | Container | Statement Management | Statement Account Payable | Invoices | Invoices Entry |  | [December][Mohamed Hary]Invoice Entry (STM_SAP_0010) - adding new field 'additional reference' for cargo commercial claim | 2020-12-07 16:18 | 2021-01-13 16:16 | 2021-01-12 16:30 | 2021-02-25 09:21 | 2021-02-25 09:26 |  | 2021-03-02 10:00 | 2021-03-02 17:03 | 2021-02-25 10:05 | 2021-04-05 14:00 | CR0013334 | Statement ManagementStatement Account PayableInvoicesInvoices Entry | OPUS-SAP | 2021-W9 | 2021-03 | 20 | 20 | 84.7376 | 2 | 1 | 2 | 0.01 | 193489 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.72727 | 0.63636 | 2020-12 | 0 | 0
560 | CR0013334 | CTASK0024532 | Closed | OPUS-SAP | Chuong Ta | 12 | 12 | 2021-01-31 12:16 | 2021-01-01 12:16 | Container | Statement Management | Statement Account Payable | Invoices | Invoices Entry |  | [January][Chuong Ta]Invoice Entry (STM_SAP_0010) - adding new field 'additional reference' for cargo commercial claim | 2020-12-07 16:18 | 2021-01-13 16:16 | 2021-01-12 16:30 | 2021-02-25 09:21 | 2021-02-25 09:26 |  | 2021-03-02 10:00 | 2021-03-02 17:03 | 2021-02-25 10:05 | 2021-04-05 14:00 | CR0013334 | Statement ManagementStatement Account PayableInvoicesInvoices Entry | OPUS-SAP | 2021-W9 | 2021-03 | 20 | 20 | 84.7376 | 2 | 1 | 2 | 0.01 | 183379 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.32 | 0.38462 | 2020-12 | 0 | 0
561 | CR0013472 | CTASK0024617 | Closed | OPUS-SCO | Nguyen Ha Vi | 54 | 54 | 2021-01-29 18:30 | 2021-01-11 09:30 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Vi Nguyen][JAN]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 203664 | 0.7 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 1.8182 | 1.2857 | 2021-02 | 0 | 0
562 | CR0013472 | CTASK0025943 | Closed | OPUS-SCO | Hang To | 12 | 10 | 2021-03-31 10:24 | 2021-03-18 10:24 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Hang To][MAR]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 183344 | 1.8 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 2.1111 | 2.4286 | 2021-02 | 0 | 0
563 | CR0013472 | CTASK0025912 | Closed | OPUS-SCO | Mohamed Hary | 10 | 10 | 2021-03-31 11:26 | 2021-03-17 11:26 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Mohamed Hary][MAR]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 193489 | 1.7 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 0.72727 | 0.63636 | 2021-02 | 0 | 0
564 | CR0013472 | CTASK0025910 | Closed | OPUS-SCO | Cuong Tran Hung | 10 | 10 | 2021-03-31 11:25 | 2021-03-17 11:25 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Cuong Tran Hung][Mar]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 193530 | 1.7 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 1.2308 | 1.2222 | 2021-02 | 0 | 0
565 | CR0013472 | CTASK0025088 | Closed | OPUS-SCO | Mohamed Hary | 40 | 40 | 2021-02-28 15:13 | 2021-02-02 15:13 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Mohamed Hary][FEB]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 193489 | 1.7 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 0.72727 | 0.63636 | 2021-02 | 0 | 0
566 | CR0013472 | CTASK0025090 | Closed | OPUS-SCO | Lien Le | 24 | 24 | 2021-02-28 15:15 | 2021-02-02 15:15 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Lien Le][FEB]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 193441 | 1.9 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 0.42308 | 1.2222 | 2021-02 | 0 | 0
567 | CR0013472 | CTASK0025913 | Closed | OPUS-SCO | Nguyen Ha Vi | 10 | 10 | 2021-03-31 11:27 | 2021-03-17 11:27 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Vi Nguyen][MAR]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 203664 | 0.7 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 1.8182 | 1.2857 | 2021-02 | 0 | 0
568 | CR0013472 | CTASK0025909 | Closed | OPUS-SCO | Chuong Ta | 10 | 10 | 2021-03-31 11:24 | 2021-03-17 11:24 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Chuong Ta][Mar]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 183379 | 1.9 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 0.32 | 0.38462 | 2021-02 | 0 | 0
569 | CR0013472 | CTASK0025438 | Closed | OPUS-SCO | Nguyen Ha Vi | 45 | 45 | 2021-02-26 13:18 | 2021-02-22 13:16 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Vi Nguyen][FEB]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 203664 | 0.7 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 1.8182 | 1.2857 | 2021-02 | 0 | 0
570 | CR0013472 | CTASK0025089 | Closed | OPUS-SCO | Cuong Tran Hung | 44 | 44 | 2021-02-28 15:14 | 2021-02-02 15:14 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Cuong Tran Hung][FEB]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 193530 | 1.7 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 1.2308 | 1.2222 | 2021-02 | 0 | 0
571 | CR0013472 | CTASK0025911 | Closed | OPUS-SCO | Lien Le | 11 | 10 | 2021-03-31 11:26 | 2021-03-17 11:26 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Lien Le][MAR]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 193441 | 1.9 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 0.42308 | 1.2222 | 2021-02 | 0 | 0
572 | CR0013472 | CTASK0025087 | Closed | OPUS-SCO | Chuong Ta | 55 | 55 | 2021-02-28 15:13 | 2021-02-02 15:13 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Chuong Ta][FEB]['Dispute' function expansion to B/L offices] | 2021-02-02 16:50 | 2021-03-23 16:48 | 2021-02-10 13:34 | 2021-03-26 09:02 | 2021-03-26 09:03 |  | 2021-03-30 10:00 | 2021-03-30 08:18 | 2021-03-26 09:14 | 2021-05-06 14:00 | CR0013472 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W13 | 2021-03 | 325 | 322 | 55.7156 | 12 | 1 | 6 | 0.24 | 183379 | 1.9 | 3 | 0 | 0 | 4 | 2 | 2 | 12 | 46 | 0.32 | 0.38462 | 2021-02 | 0 | 0
573 | CR0011608 | CTASK0021853 | Closed | OPUS-SCE | VInh Bui | 30 | 30 | 2020-09-01 12:19 | 2020-08-02 12:19 | Container | Biz Common | EDI Setup | Setup | Customer EDI - Detail Setup |  | Add Actual Customer to SUP and Add A/Customer (Actual Customer) to 315 FF | 2020-05-22 15:40 | 2020-05-29 15:39 | 2020-05-28 17:29 | 2020-08-12 11:41 | 2020-08-20 11:16 |  | 2020-09-02 01:00 | 2020-09-01 22:00 | 2020-08-21 10:58 | 2020-10-01 13:00 | CR0011608 | Biz CommonEDI SetupSetupCustomer EDI - Detail Setup | OPUS-SUP | 2020-W36 | 2020-09 | 60 | 60 | 102.3891 | 2 | 1 | 1 | 0.02 | 193469 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-05 | 0 | 0
574 | CR0011608 | CTASK0020802 | Closed | OPUS-SCE | VInh Bui | 30 | 30 | 2020-07-31 15:18 | 2020-07-01 15:17 | Container | Biz Common | EDI Setup | Setup | Customer EDI - Detail Setup |  | Add Actual Customer to SUP and Add A/Customer (Actual Customer) to 315 FF | 2020-05-22 15:40 | 2020-05-29 15:39 | 2020-05-28 17:29 | 2020-08-12 11:41 | 2020-08-20 11:16 |  | 2020-09-02 01:00 | 2020-09-01 22:00 | 2020-08-21 10:58 | 2020-10-01 13:00 | CR0011608 | Biz CommonEDI SetupSetupCustomer EDI - Detail Setup | OPUS-SUP | 2020-W36 | 2020-09 | 60 | 60 | 102.3891 | 2 | 1 | 1 | 0.02 | 193469 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-05 | 0 | 0
575 | CR0010299 | CTASK0024550 | Closed | OPUS-TRS | Giang Nguyen Hoang | 11 | 4 | 2021-01-31 11:21 | 2021-01-08 11:21 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202101] EUA - BKG _ TRO SCREEN TO VALIDATE SEQUENCE OF MULTI STOP APPOINTMENTS | 2021-01-07 16:01 | 2021-01-31 21:00 | 2021-01-14 10:42 | 2021-06-09 15:42 | 2021-06-15 09:48 |  | 2021-06-29 10:00 | 2021-06-29 09:52 | 2021-06-25 10:26 | 2021-07-29 14:00 | CR0010299 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W26 | 2021-06 | 18 | 8 | 172.7493 | 2 | 1 | 2 | 0 | 183440 | 1.8 | 0 | 0 | 0 | 1 | 1 | 3 | 16 | 53 | 0 | 0 | 2021-01 | 0 | 0
576 | CR0010299 | CTASK0024549 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 7 | 4 | 2021-01-31 11:21 | 2021-01-08 11:21 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202101] EUA - BKG _ TRO SCREEN TO VALIDATE SEQUENCE OF MULTI STOP APPOINTMENTS | 2021-01-07 16:01 | 2021-01-31 21:00 | 2021-01-14 10:42 | 2021-06-09 15:42 | 2021-06-15 09:48 |  | 2021-06-29 10:00 | 2021-06-29 09:52 | 2021-06-25 10:26 | 2021-07-29 14:00 | CR0010299 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W26 | 2021-06 | 18 | 8 | 172.7493 | 2 | 1 | 2 | 0 | 183432 | 1.8 | 0 | 0 | 0 | 1 | 1 | 3 | 16 | 53 | 0 | 0 | 2021-01 | 0 | 0
577 | CR0013267 | CTASK0023506 | Closed | OPUS-VSK | Thuan Tran | 9 | 9 | 2020-11-18 16:39 | 2020-11-16 16:38 | Container | Vessel Operation | Vessel Schedule | VSL SKD | VSL SKD Inquiry | VSL SKD Inquiry by Port | [CLV] OPUS Enhancement Request - To add last Port/ ETD | 2020-12-02 16:33 | 2020-12-11 16:32 | 2020-12-07 18:05 | 2020-12-09 11:50 | 2020-12-11 09:21 |  | 2020-12-22 09:21 | 2020-12-22 09:00 | 2020-12-17 17:34 | 2021-01-21 14:00 | CR0013267 | Vessel OperationVessel ScheduleVSL SKDVSL SKD InquiryVSL SKD Inquiry by Port | OPUS-VSK | 2020-W52 | 2020-12 | 9 | 9 | 19.7003 | 1 | 1 | 1 | 0.02 | 183423 | 2.1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 30 | 0 | 0 | 2020-12 | 0 | 0
578 | CR0012876 | CTASK0021869 | Closed | OPUS-BKG-CLLCDL | Thuc Tran | 8 | 8 | 2020-08-17 19:30 | 2020-08-14 11:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List |  | [Estimation](HM) *Opus FF* EUA Vend All terminals/COPRAR application file - Extract Sensitive Cargo indicator | 2020-08-31 13:05 | 2020-09-17 | 2020-09-15 14:21 | 2020-10-06 09:14 | 2020-11-11 11:15 |  | 2020-12-01 10:00 | 2020-12-01 10:00 | 2020-11-17 09:23 | 2020-12-31 14:00 | CR0012876 | Service ManagementBooking/DocumentationOperationLoading/Discharging List | OPUS-BKG-MFT-E | 2020-W49 | 2020-12 | 48 | 48 | 91.8718 | 3 | 1 | 1 | 0.02 | 173280 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0.18519 | 2020-08 | 0 | 0
579 | CR0012876 | CTASK0021941 | Closed | OPUS-BKG-CLLCDL | Thuc Tran | 34 | 34 | 2020-09-10 19:30 | 2020-08-27 11:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List |  | [Development + Testing + Deployment](HM) *Opus FF* EUA Vend All terminals/COPRAR application file - Extract Sensitive Cargo indicator | 2020-08-31 13:05 | 2020-09-17 | 2020-09-15 14:21 | 2020-10-06 09:14 | 2020-11-11 11:15 |  | 2020-12-01 10:00 | 2020-12-01 10:00 | 2020-11-17 09:23 | 2020-12-31 14:00 | CR0012876 | Service ManagementBooking/DocumentationOperationLoading/Discharging List | OPUS-BKG-MFT-E | 2020-W49 | 2020-12 | 48 | 48 | 91.8718 | 3 | 1 | 1 | 0.02 | 173280 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0.18519 | 2020-08 | 0 | 0
580 | CR0012876 | CTASK0023526 | Closed | OPUS-BKG-CLLCDL | Thuc Tran | 6 | 6 | 2020-11-20 19:30 | 2020-11-16 11:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List |  | [Deployment + Inspection](HM) *Opus FF* EUA Vend All terminals/COPRAR application file - Extract Sensitive Cargo indicator | 2020-08-31 13:05 | 2020-09-17 | 2020-09-15 14:21 | 2020-10-06 09:14 | 2020-11-11 11:15 |  | 2020-12-01 10:00 | 2020-12-01 10:00 | 2020-11-17 09:23 | 2020-12-31 14:00 | CR0012876 | Service ManagementBooking/DocumentationOperationLoading/Discharging List | OPUS-BKG-MFT-E | 2020-W49 | 2020-12 | 48 | 48 | 91.8718 | 3 | 1 | 1 | 0.02 | 173280 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0.18519 | 2020-08 | 0 | 0
581 | CR0012887 | CTASK0021597 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 32 | 32 | 2020-08-14 13:00 | 2020-08-10 13:00 | Container | Service Management | Booking/Documentation | Manifest | India |  | [Development - Testing] Asia *BKG/DOC* - SitPro & Firm Booking for India ( CR0010971) | 2020-08-12 10:12 | 2020-08-27 | 2020-08-25 16:50 | 2020-08-27 16:44 | 2020-08-27 17:50 |  | 2020-09-08 10:00 | 2020-09-08 09:30 | 2020-08-28 09:53 | 2020-10-09 13:00 | CR0012887 | Service ManagementBooking/DocumentationManifestIndia | OPUS-BKG-MFT-A | 2020-W37 | 2020-09 | 48 | 48 | 26.9917 | 3 | 1 | 1 | 0.07 | 193506 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-08 | 0 | 0
582 | CR0012887 | CTASK0022269 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2020-09-08 13:00 | 2020-09-03 13:00 | Container | Service Management | Booking/Documentation | Manifest | India |  | [Production]Asia *BKG/DOC* - SitPro & Firm Booking for India ( CR0010971) | 2020-08-12 10:12 | 2020-08-27 | 2020-08-25 16:50 | 2020-08-27 16:44 | 2020-08-27 17:50 |  | 2020-09-08 10:00 | 2020-09-08 09:30 | 2020-08-28 09:53 | 2020-10-09 13:00 | CR0012887 | Service ManagementBooking/DocumentationManifestIndia | OPUS-BKG-MFT-A | 2020-W37 | 2020-09 | 48 | 48 | 26.9917 | 3 | 1 | 1 | 0.07 | 193506 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-08 | 0 | 0
583 | CR0012887 | CTASK0021585 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2020-07-29 13:00 | 2020-07-28 13:00 | Container | Service Management | Booking/Documentation | Manifest | India |  | [Analytics] Asia *BKG/DOC* - SitPro & Firm Booking for India ( CR0010971) | 2020-08-12 10:12 | 2020-08-27 | 2020-08-25 16:50 | 2020-08-27 16:44 | 2020-08-27 17:50 |  | 2020-09-08 10:00 | 2020-09-08 09:30 | 2020-08-28 09:53 | 2020-10-09 13:00 | CR0012887 | Service ManagementBooking/DocumentationManifestIndia | OPUS-BKG-MFT-A | 2020-W37 | 2020-09 | 48 | 48 | 26.9917 | 3 | 1 | 1 | 0.07 | 193506 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-08 | 0 | 0
584 | CR0012239 | CTASK0018416 | Closed | OPUS-BKG-M | Loc Tran | 2 | 4 | 2020-03-06 17:17 | 2020-03-02 17:17 | [6 empty] | [Testing] Modify the condition of ECR0000358 (SR0081701) | 2020-02-21 01:30 | 2020-03-21 | 2020-03-19 12:49 | 2020-03-26 17:06 | 2020-03-26 17:22 |  | 2020-05-12 09:00 | 2020-05-12 10:00 | 2020-03-26 17:41 | 2020-06-11 13:00 | CR0012239 |  | OPUS-BKG-M | 2020-W20 | 2020-05 | 34 | 35 | 81.3126 | 4 | 1 | 1 | 0.02 | 193503 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.36364 | 2020-02 | 0 | 0
585 | CR0012239 | CTASK0018338 | Closed | OPUS-BKG-M | Loc Tran | 15 | 15 | 2020-02-14 18:00 | 2020-02-07 10:00 | [6 empty] | [Design] Modify the condition of ECR0000358 (SR0081701) | 2020-02-21 01:30 | 2020-03-21 | 2020-03-19 12:49 | 2020-03-26 17:06 | 2020-03-26 17:22 |  | 2020-05-12 09:00 | 2020-05-12 10:00 | 2020-03-26 17:41 | 2020-06-11 13:00 | CR0012239 |  | OPUS-BKG-M | 2020-W20 | 2020-05 | 34 | 35 | 81.3126 | 4 | 1 | 1 | 0.02 | 193503 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.36364 | 2020-02 | 0 | 0
586 | CR0012239 | CTASK0018421 | Closed | OPUS-BKG-M | Loc Tran | 3 | 2 | 2020-05-01 02:00 | 2020-04-28 11:00 | [6 empty] | [Deployment] Modify the condition of ECR0000358 (SR0081701) | 2020-02-21 01:30 | 2020-03-21 | 2020-03-19 12:49 | 2020-03-26 17:06 | 2020-03-26 17:22 |  | 2020-05-12 09:00 | 2020-05-12 10:00 | 2020-03-26 17:41 | 2020-06-11 13:00 | CR0012239 |  | OPUS-BKG-M | 2020-W20 | 2020-05 | 34 | 35 | 81.3126 | 4 | 1 | 1 | 0.02 | 193503 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.36364 | 2020-02 | 0 | 0
587 | CR0012239 | CTASK0018415 | Closed | OPUS-BKG-M | Loc Tran | 14 | 14 | 2020-02-28 17:14 | 2020-02-24 17:14 | [6 empty] | [Development] Modify the condition of ECR0000358 (SR0081701) | 2020-02-21 01:30 | 2020-03-21 | 2020-03-19 12:49 | 2020-03-26 17:06 | 2020-03-26 17:22 |  | 2020-05-12 09:00 | 2020-05-12 10:00 | 2020-03-26 17:41 | 2020-06-11 13:00 | CR0012239 |  | OPUS-BKG-M | 2020-W20 | 2020-05 | 34 | 35 | 81.3126 | 4 | 1 | 1 | 0.02 | 193503 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.36364 | 2020-02 | 0 | 0
588 | CR0011304 | CTASK0015549 | Closed | OPUS-BKG-OB | Kieu Le | 10 | 10 |  |  | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [CLT Internal] For RD database server, MRD files needs Prepared statement | 2019-09-03 17:54 | 2019-09-27 17:53 | 2019-09-03 17:55 | 2019-09-03 17:58 | 2019-09-03 18:00 |  | 2019-07-30 09:59 | 2019-07-30 09:01 | 2019-09-03 18:01 | 2019-10-04 13:00 | CR0011304 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2019-W31 | 2019-07 | 10 | 0 | -35.3295 | 1 | 1 | 1 | 0 | 153106 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 7 | 0 | 0 | 2019-09 | 0 | 0
589 | CR0012690 | CTASK0020826 | Closed | OPUS-SCO | Lien Le | 51 | 45 | 2020-07-31 18:46 | 2020-07-01 18:46 | Container | Statement Management | Statement Account Receivable |  |  |  | [Lien Le][Request to expand CLEAR system to be working at 3 SAS Invoice Offices(AU/AE/NZ) and all the other BL Offices] | 2020-06-17 17:24 | 2020-08-04 17:23 | 2020-07-01 13:36 | 2020-07-24 09:26 | 2020-07-24 09:32 |  | 2020-07-28 09:32 | 2020-07-28 10:00 | 2020-07-24 09:35 | 2020-08-28 13:00 | CR0012690 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 51 | 45 | 40.6723 | 1 | 1 | 1 | 0.05 | 193441 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 27 | 0 | 1.2222 | 2020-06 | 0 | 0
590 | CR0012882 | CTASK0022464 | Closed | OPUS-BKG-RPT | Nam Nguyen | 46 | 46 | 2020-11-04 00:35 | 2020-10-15 00:35 | Container | Service Management | Booking/Documentation | Report | VGM Dashboard |  | (SB) - EUA VEND EDI - VERMAS- UNIFEEDER - COP DETAIL - SP CANDIDATE - ENQUIRY | 2020-10-21 11:26 | 2020-11-14 | 2020-11-12 10:05 | 2020-11-27 15:08 | 2020-12-02 18:21 |  | 2021-01-05 10:00 | 2021-01-05 09:57 | 2020-12-03 13:32 | 2021-02-04 14:00 | CR0012882 | Service ManagementBooking/DocumentationReportVGM Dashboard | OPUS-BKG-RPT | 2021-W1 | 2021-01 | 46 | 46 | 75.9405 | 1 | 1 | 1 | 0.03 | 123048 | 2.1 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 40 | 0 | 0.047619 | 2020-10 | 0 | 0
591 | CR0011331 | CTASK0013596 | Closed | OPUS-MNR | Tien Le | 5 | 5 |  |  | Container | Equipment Management | M&R | Total Loss |  |  | [actual]GHQ MNR Total Loss - Align to keep historical record of all total loss request in MNR TLL regradless cancellation or deletion. | 2019-05-28 14:36 | 2019-06-14 14:35 | 2019-06-10 11:22 | 2019-10-14 15:57 | 2019-10-14 17:00 |  | 2019-10-29 16:59 | 2019-10-22 13:16 | 2019-10-15 17:20 | 2019-11-22 14:00 | CR0011331 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2019-W44 | 2019-10 | 68 | 10 | 154.0996 | 9 | 1 | 2 | 0 | 173286 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 10 | 0 | 0 | 2019-05 | 0 | 0
592 | CR0011331 | CTASK0013860 | Closed | OPUS-MNR | Tuyen Truong | 20 | 20 |  |  | Container | Equipment Management | M&R | Total Loss |  |  | [actual]GHQ MNR Total Loss - Align to keep historical record of all total loss request in MNR TLL regradless cancellation or deletion. | 2019-05-28 14:36 | 2019-06-14 14:35 | 2019-06-10 11:22 | 2019-10-14 15:57 | 2019-10-14 17:00 |  | 2019-10-29 16:59 | 2019-10-22 13:16 | 2019-10-15 17:20 | 2019-11-22 14:00 | CR0011331 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2019-W44 | 2019-10 | 68 | 10 | 154.0996 | 9 | 1 | 2 | 0 | 173255 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 10 | 0 | 0 | 2019-05 | 0 | 0
593 | CR0011331 | CTASK0013755 | Closed | OPUS-MNR | Tuyen Truong | 1 | 1 |  |  | Container | Equipment Management | M&R | Total Loss |  |  | [Documentation]GHQ MNR Total Loss - Align to keep historical record of all total loss request in MNR TLL regradless cancellation or deletion. | 2019-05-28 14:36 | 2019-06-14 14:35 | 2019-06-10 11:22 | 2019-10-14 15:57 | 2019-10-14 17:00 |  | 2019-10-29 16:59 | 2019-10-22 13:16 | 2019-10-15 17:20 | 2019-11-22 14:00 | CR0011331 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2019-W44 | 2019-10 | 68 | 10 | 154.0996 | 9 | 1 | 2 | 0 | 173255 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 10 | 0 | 0 | 2019-05 | 0 | 0
594 | CR0011331 | CTASK0014426 | Closed | OPUS-MNR | Tuyen Truong | 6 | 6 |  |  | Container | Equipment Management | M&R | Total Loss |  |  | [actual]GHQ MNR Total Loss - Align to keep historical record of all total loss request in MNR TLL regradless cancellation or deletion. | 2019-05-28 14:36 | 2019-06-14 14:35 | 2019-06-10 11:22 | 2019-10-14 15:57 | 2019-10-14 17:00 |  | 2019-10-29 16:59 | 2019-10-22 13:16 | 2019-10-15 17:20 | 2019-11-22 14:00 | CR0011331 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2019-W44 | 2019-10 | 68 | 10 | 154.0996 | 9 | 1 | 2 | 0 | 173255 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 10 | 0 | 0 | 2019-05 | 0 | 0
595 | CR0011331 | CTASK0013265 | Closed | OPUS-MNR | Tien Le | 1 | 1 |  |  | Container | Equipment Management | M&R | Total Loss |  |  | [actual]GHQ MNR Total Loss - Align to keep historical record of all total loss request in MNR TLL regradless cancellation or deletion. | 2019-05-28 14:36 | 2019-06-14 14:35 | 2019-06-10 11:22 | 2019-10-14 15:57 | 2019-10-14 17:00 |  | 2019-10-29 16:59 | 2019-10-22 13:16 | 2019-10-15 17:20 | 2019-11-22 14:00 | CR0011331 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2019-W44 | 2019-10 | 68 | 10 | 154.0996 | 9 | 1 | 2 | 0 | 173286 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 10 | 0 | 0 | 2019-05 | 0 | 0
596 | CR0011331 | CTASK0013595 | Closed | OPUS-MNR | Tuyen Truong | 20 | 20 | 2019-05-17 16:34 | 2019-05-13 16:33 | Container | Equipment Management | M&R | Total Loss |  |  | [actual]GHQ MNR Total Loss - Align to keep historical record of all total loss request in MNR TLL regradless cancellation or deletion. | 2019-05-28 14:36 | 2019-06-14 14:35 | 2019-06-10 11:22 | 2019-10-14 15:57 | 2019-10-14 17:00 |  | 2019-10-29 16:59 | 2019-10-22 13:16 | 2019-10-15 17:20 | 2019-11-22 14:00 | CR0011331 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2019-W44 | 2019-10 | 68 | 10 | 154.0996 | 9 | 1 | 2 | 0 | 173255 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 10 | 0 | 0 | 2019-05 | 0 | 0
597 | CR0011331 | CTASK0013753 | Closed | OPUS-MNR | Tien Le | 5 | 10 | 2019-06-14 14:02 | 2019-05-15 14:01 | Container | Equipment Management | M&R | Total Loss |  |  | [Initial]GHQ MNR Total Loss - Align to keep historical record of all total loss request in MNR TLL regradless cancellation or deletion. | 2019-05-28 14:36 | 2019-06-14 14:35 | 2019-06-10 11:22 | 2019-10-14 15:57 | 2019-10-14 17:00 |  | 2019-10-29 16:59 | 2019-10-22 13:16 | 2019-10-15 17:20 | 2019-11-22 14:00 | CR0011331 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2019-W44 | 2019-10 | 68 | 10 | 154.0996 | 9 | 1 | 2 | 0 | 173286 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 10 | 0 | 0 | 2019-05 | 0 | 0
598 | CR0011331 | CTASK0014275 | Closed | OPUS-MNR | Tuyen Truong | 3 | 3 |  |  | Container | Equipment Management | M&R | Total Loss |  |  | [actual] GHQ MNR Total Loss - Align to keep historical record of all total loss request in MNR TLL regradless cancellation or deletion. | 2019-05-28 14:36 | 2019-06-14 14:35 | 2019-06-10 11:22 | 2019-10-14 15:57 | 2019-10-14 17:00 |  | 2019-10-29 16:59 | 2019-10-22 13:16 | 2019-10-15 17:20 | 2019-11-22 14:00 | CR0011331 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2019-W44 | 2019-10 | 68 | 10 | 154.0996 | 9 | 1 | 2 | 0 | 173255 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 10 | 0 | 0 | 2019-05 | 0 | 0
599 | CR0011331 | CTASK0013263 | Closed | OPUS-MNR | Tuyen Truong | 9 | 9 |  |  | Container | Equipment Management | M&R | Total Loss |  |  | [actual]GHQ MNR Total Loss - Align to keep historical record of all total loss request in MNR TLL regradless cancellation or deletion. | 2019-05-28 14:36 | 2019-06-14 14:35 | 2019-06-10 11:22 | 2019-10-14 15:57 | 2019-10-14 17:00 |  | 2019-10-29 16:59 | 2019-10-22 13:16 | 2019-10-15 17:20 | 2019-11-22 14:00 | CR0011331 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2019-W44 | 2019-10 | 68 | 10 | 154.0996 | 9 | 1 | 2 | 0 | 173255 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 10 | 0 | 0 | 2019-05 | 0 | 0
600 | CR0012988 | CTASK0021966 | Closed | OPUS-SAP | Cuong Tran Hung | 12 | 12 | 2020-08-31 12:53 | 2020-08-20 12:53 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Agent Manager |  | [August][SAR][Cuong Tran Hung][SAR Customer Integration and Collection Agent Manager should be working when sub-office users log in] | 2020-08-20 15:26 | 2020-08-25 15:26 | 2020-08-21 09:04 | 2020-08-21 09:13 | 2020-08-21 09:15 |  | 2020-08-25 10:00 | 2020-08-25 10:17 | 2020-08-21 09:16 | 2020-09-24 13:00 | CR0012988 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Agent Manager | OPUS-SCO | 2020-W35 | 2020-08 | 44 | 44 | 4.7738 | 4 | 1 | 4 | 0.38 | 193530 | 1.2 | 2 | 0 | 0 | 1 | 2 | 1 | 12 | 30 | 0 | 1.2222 | 2020-08 | 0 | 0
601 | CR0012988 | CTASK0021965 | Closed | OPUS-SAP | Dinh Cong Tuan | 10 | 10 | 2020-08-31 12:52 | 2020-08-20 12:52 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Agent Manager |  | [August][SAR][Dinh Cong Tuan][SAR Customer Integration and Collection Agent Manager should be working when sub-office users log in] | 2020-08-20 15:26 | 2020-08-25 15:26 | 2020-08-21 09:04 | 2020-08-21 09:13 | 2020-08-21 09:15 |  | 2020-08-25 10:00 | 2020-08-25 10:17 | 2020-08-21 09:16 | 2020-09-24 13:00 | CR0012988 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Agent Manager | OPUS-SCO | 2020-W35 | 2020-08 | 44 | 44 | 4.7738 | 4 | 1 | 4 | 0.38 | 193510 | 1.2 | 2 | 0 | 0 | 1 | 2 | 1 | 12 | 30 | 0 | 0 | 2020-08 | 0 | 0
602 | CR0012988 | CTASK0021967 | Closed | OPUS-SAP | Hang To | 10 | 10 | 2020-08-31 12:53 | 2020-08-20 12:53 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Agent Manager |  | [August][SAR][Hang To][SAR Customer Integration and Collection Agent Manager should be working when sub-office users log in] | 2020-08-20 15:26 | 2020-08-25 15:26 | 2020-08-21 09:04 | 2020-08-21 09:13 | 2020-08-21 09:15 |  | 2020-08-25 10:00 | 2020-08-25 10:17 | 2020-08-21 09:16 | 2020-09-24 13:00 | CR0012988 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Agent Manager | OPUS-SCO | 2020-W35 | 2020-08 | 44 | 44 | 4.7738 | 4 | 1 | 4 | 0.38 | 183344 | 1.3 | 2 | 0 | 0 | 1 | 2 | 1 | 12 | 30 | 0 | 2.4286 | 2020-08 | 0 | 0
603 | CR0012988 | CTASK0021968 | Closed | OPUS-SAP | Mohamed Hary | 12 | 12 | 2020-08-31 12:54 | 2020-08-20 12:54 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Agent Manager |  | [August][SAR][Mohamed Hary][SAR Customer Integration and Collection Agent Manager should be working when sub-office users log in] | 2020-08-20 15:26 | 2020-08-25 15:26 | 2020-08-21 09:04 | 2020-08-21 09:13 | 2020-08-21 09:15 |  | 2020-08-25 10:00 | 2020-08-25 10:17 | 2020-08-21 09:16 | 2020-09-24 13:00 | CR0012988 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Agent Manager | OPUS-SCO | 2020-W35 | 2020-08 | 44 | 44 | 4.7738 | 4 | 1 | 4 | 0.38 | 193489 | 1.2 | 2 | 0 | 0 | 1 | 2 | 1 | 12 | 30 | 0 | 0.63636 | 2020-08 | 0 | 0
604 | CR0011024 | CTASK0019763 | Closed | OPUS-BKG-M | Vinh Tran | 2 | 2 | 2020-04-22 02:00 | 2020-04-21 02:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Development] Enable highlight fields with old and new value difference | 2019-07-23 08:30 | 2019-10-01 | 2019-09-30 09:30 | 2020-05-12 17:26 | 2020-05-19 13:28 |  | 2020-06-23 10:00 | 2020-06-23 10:17 | 2020-05-19 17:04 | 2020-07-23 13:00 | CR0011024 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 187 | 137 | 336.0628 | 8 | 2 | 3 | 0.02 | 193525 | 0.1 | 0 | 0 | 1 | 2 | 1 | 4 | 7 | 29 | 0 | 0.45455 | 2019-07 | 1 | 1
605 | CR0011024 | CTASK0017265 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Documentation] Enable highlight fields with old and new value difference | 2019-07-23 08:30 | 2019-10-01 | 2019-09-30 09:30 | 2020-05-12 17:26 | 2020-05-19 13:28 |  | 2020-06-23 10:00 | 2020-06-23 10:17 | 2020-05-19 17:04 | 2020-07-23 13:00 | CR0011024 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 187 | 137 | 336.0628 | 8 | 2 | 3 | 0.02 | 153106 | 0.8 | 0 | 0 | 1 | 2 | 1 | 4 | 7 | 29 | 0 | 0 | 2019-07 | 1 | 1
606 | CR0011024 | CTASK0020789 | Closed | OPUS-BKG-EBKG | Vinh Tran | 7 | 8 | 2020-06-23 02:00 | 2020-06-22 02:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | Enable highlight fields with old and new value difference | 2019-07-23 08:30 | 2019-10-01 | 2019-09-30 09:30 | 2020-05-12 17:26 | 2020-05-19 13:28 |  | 2020-06-23 10:00 | 2020-06-23 10:17 | 2020-05-19 17:04 | 2020-07-23 13:00 | CR0011024 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 187 | 137 | 336.0628 | 8 | 2 | 3 | 0.02 | 193525 | 0.1 | 0 | 0 | 1 | 2 | 1 | 4 | 7 | 29 | 0 | 0.45455 | 2019-07 | 1 | 1
607 | CR0011024 | CTASK0019101 | Closed | OPUS-BKG-M | Vinh Tran | 7 | 8 | 2020-03-21 02:00 | 2020-03-18 02:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Development] Enable highlight fields with old and new value difference | 2019-07-23 08:30 | 2019-10-01 | 2019-09-30 09:30 | 2020-05-12 17:26 | 2020-05-19 13:28 |  | 2020-06-23 10:00 | 2020-06-23 10:17 | 2020-05-19 17:04 | 2020-07-23 13:00 | CR0011024 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 187 | 137 | 336.0628 | 8 | 2 | 3 | 0.02 | 193525 | 0.1 | 0 | 0 | 1 | 2 | 1 | 4 | 7 | 29 | 0 | 0.45455 | 2019-07 | 1 | 1
608 | CR0011024 | CTASK0018239 | Closed | OPUS-BKG-M | Vinh Tran | 10 | 10 | 2020-02-06 02:00 | 2020-02-04 02:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | Enable highlight fields with old and new value difference | 2019-07-23 08:30 | 2019-10-01 | 2019-09-30 09:30 | 2020-05-12 17:26 | 2020-05-19 13:28 |  | 2020-06-23 10:00 | 2020-06-23 10:17 | 2020-05-19 17:04 | 2020-07-23 13:00 | CR0011024 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 187 | 137 | 336.0628 | 8 | 2 | 3 | 0.02 | 193525 | 0.1 | 0 | 0 | 1 | 2 | 1 | 4 | 7 | 29 | 0 | 0.45455 | 2019-07 | 1 | 1
609 | CR0011024 | CTASK0012419 | Closed | OPUS-BKG-EBKG | Kieu Le | 141 | 105 | 2019-08-16 10:32 | 2019-07-22 10:32 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | Enable highlight fields with old and new value difference | 2019-07-23 08:30 | 2019-10-01 | 2019-09-30 09:30 | 2020-05-12 17:26 | 2020-05-19 13:28 |  | 2020-06-23 10:00 | 2020-06-23 10:17 | 2020-05-19 17:04 | 2020-07-23 13:00 | CR0011024 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 187 | 137 | 336.0628 | 8 | 2 | 3 | 0.02 | 153106 | 0.8 | 0 | 0 | 1 | 2 | 1 | 4 | 7 | 29 | 0 | 0 | 2019-07 | 1 | 1
610 | CR0011024 | CTASK0019185 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 6 | 6 | 2020-03-24 18:05 | 2020-03-23 10:04 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | Enable highlight fields with old and new value difference | 2019-07-23 08:30 | 2019-10-01 | 2019-09-30 09:30 | 2020-05-12 17:26 | 2020-05-19 13:28 |  | 2020-06-23 10:00 | 2020-06-23 10:17 | 2020-05-19 17:04 | 2020-07-23 13:00 | CR0011024 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 187 | 137 | 336.0628 | 8 | 2 | 3 | 0.02 | 193488 | 0.1 | 0 | 0 | 1 | 2 | 1 | 4 | 7 | 29 | 0 | 2.1667 | 2019-07 | 1 | 1
611 | CR0011024 | CTASK0020591 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 8 | 8 | 2020-06-11 13:03 | 2020-06-08 13:02 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | Enable highlight fields with old and new value difference | 2019-07-23 08:30 | 2019-10-01 | 2019-09-30 09:30 | 2020-05-12 17:26 | 2020-05-19 13:28 |  | 2020-06-23 10:00 | 2020-06-23 10:17 | 2020-05-19 17:04 | 2020-07-23 13:00 | CR0011024 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 187 | 137 | 336.0628 | 8 | 2 | 3 | 0.02 | 193488 | 0.1 | 0 | 0 | 1 | 2 | 1 | 4 | 7 | 29 | 0 | 2.1667 | 2019-07 | 1 | 1
612 | CR0012715 | CTASK0021329 | Closed | OPUS-SCO | Hang To | 8 | 8 | 2020-08-31 10:32 | 2020-08-01 10:32 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [August][Hang To]EUA - Payment Request Letter Improvements [CR4] | 2020-08-20 16:42 | 2020-09-30 16:42 | 2020-09-04 15:32 | 2020-12-23 15:54 | 2020-12-23 16:06 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:54 | 2021-01-19 20:47 | CR0012715 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 91 | 83 | 129.7208 | 5 | 3 | 4 | 0.03 | 183344 | 1.3 | 1 | 3 | 0 | 1 | 2 | 2 | 9 | 30 | 0 | 2.4286 | 2020-08 | 3 | 1
613 | CR0012715 | CTASK0023833 | Closed | OPUS-DMT | Cuong Nguyen | 7 | 2 |  |  | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Documentation] EUA - Payment Request Letter Improvements [CR4] | 2020-08-20 16:42 | 2020-09-30 16:42 | 2020-09-04 15:32 | 2020-12-23 15:54 | 2020-12-23 16:06 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:54 | 2021-01-19 20:47 | CR0012715 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 91 | 83 | 129.7208 | 5 | 3 | 4 | 0.03 | 193529 | 1.2 | 1 | 3 | 0 | 1 | 2 | 2 | 9 | 30 | 0 | 0.058824 | 2020-08 | 3 | 1
614 | CR0012715 | CTASK0021327 | Closed | OPUS-SCO | Lien Le | 30 | 29 | 2020-08-31 10:30 | 2020-08-01 10:30 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [August][Lien Le]EUA - Payment Request Letter Improvements [CR4] | 2020-08-20 16:42 | 2020-09-30 16:42 | 2020-09-04 15:32 | 2020-12-23 15:54 | 2020-12-23 16:06 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:54 | 2021-01-19 20:47 | CR0012715 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 91 | 83 | 129.7208 | 5 | 3 | 4 | 0.03 | 193441 | 1.4 | 1 | 3 | 0 | 1 | 2 | 2 | 9 | 30 | 0 | 1.2222 | 2020-08 | 3 | 1
615 | CR0012715 | CTASK0021382 | Closed | OPUS-SCO | Lien Le | 20 | 20 | 2020-09-30 11:49 | 2020-09-01 11:49 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [September][Lien Le]EUA - Payment Request Letter Improvements [CR4] | 2020-08-20 16:42 | 2020-09-30 16:42 | 2020-09-04 15:32 | 2020-12-23 15:54 | 2020-12-23 16:06 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:54 | 2021-01-19 20:47 | CR0012715 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 91 | 83 | 129.7208 | 5 | 3 | 4 | 0.03 | 193441 | 1.4 | 1 | 3 | 0 | 1 | 2 | 2 | 9 | 30 | 0 | 1.2222 | 2020-08 | 3 | 1
616 | CR0012715 | CTASK0023758 | Closed | OPUS-TPB | Manh Nguyen | 26 | 24 | 2020-11-27 12:12 | 2020-11-24 12:12 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Actual]EUA - Payment Request Letter Improvements [CR4] | 2020-08-20 16:42 | 2020-09-30 16:42 | 2020-09-04 15:32 | 2020-12-23 15:54 | 2020-12-23 16:06 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:54 | 2021-01-19 20:47 | CR0012715 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2020-W53 | 2020-12 | 91 | 83 | 129.7208 | 5 | 3 | 4 | 0.03 | 153138 | 1.9 | 1 | 3 | 0 | 1 | 2 | 2 | 9 | 30 | 0 | 0.25 | 2020-08 | 3 | 1
617 | CR0013705 | CTASK0027901 | Closed | OPUS-TES | Thai Nguyen | 4 | 8 | 2021-08-01 01:00 | 2021-07-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202107][CLT Internal] WHY IS MASTER BOOKING NOT BEING PULLED OUT IN TES | 2021-04-05 15:34 | 2021-06-30 15:33 | 2021-06-28 16:30 | 2021-06-29 15:39 | 2021-06-30 10:00 |  | 2021-07-06 12:30 | 2021-07-06 11:33 | 2021-07-02 10:26 | 2021-07-29 14:00 | CR0013705 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W27 | 2021-07 | 61 | 82 | 91.8724 | 5 | 1 | 1 | 0.04 | 173249 | 2.5 | 0 | 0 | 1 | 1 | 1 | 2 | 8 | 28 | 0 | 0.5 | 2021-04 | 1 | 1
618 | CR0013705 | CTASK0027771 | Closed | OPUS-TES | Thai Nguyen | 4 | 4 | 2021-07-01 01:00 | 2021-06-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202106][CLT Internal] WHY IS MASTER BOOKING NOT BEING PULLED OUT IN TES | 2021-04-05 15:34 | 2021-06-30 15:33 | 2021-06-28 16:30 | 2021-06-29 15:39 | 2021-06-30 10:00 |  | 2021-07-06 12:30 | 2021-07-06 11:33 | 2021-07-02 10:26 | 2021-07-29 14:00 | CR0013705 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W27 | 2021-07 | 61 | 82 | 91.8724 | 5 | 1 | 1 | 0.04 | 173249 | 2.5 | 0 | 0 | 1 | 1 | 1 | 2 | 8 | 28 | 0 | 0.5 | 2021-04 | 1 | 1
619 | CR0013705 | CTASK0026203 | Closed | OPUS-TES | Thai Nguyen | 25 | 30 | 2021-05-01 01:00 | 2021-04-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202104][CLT Internal] WHY IS MASTER BOOKING NOT BEING PULLED OUT IN TES | 2021-04-05 15:34 | 2021-06-30 15:33 | 2021-06-28 16:30 | 2021-06-29 15:39 | 2021-06-30 10:00 |  | 2021-07-06 12:30 | 2021-07-06 11:33 | 2021-07-02 10:26 | 2021-07-29 14:00 | CR0013705 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W27 | 2021-07 | 61 | 82 | 91.8724 | 5 | 1 | 1 | 0.04 | 173249 | 2.5 | 0 | 0 | 1 | 1 | 1 | 2 | 8 | 28 | 0 | 0.5 | 2021-04 | 1 | 1
620 | CR0013705 | CTASK0025673 | Closed | OPUS-TES | Thai Nguyen | 16 | 20 | 2021-04-01 01:00 | 2021-03-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202103][CLT Internal] WHY IS MASTER BOOKING NOT BEING PULLED OUT IN TES | 2021-04-05 15:34 | 2021-06-30 15:33 | 2021-06-28 16:30 | 2021-06-29 15:39 | 2021-06-30 10:00 |  | 2021-07-06 12:30 | 2021-07-06 11:33 | 2021-07-02 10:26 | 2021-07-29 14:00 | CR0013705 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W27 | 2021-07 | 61 | 82 | 91.8724 | 5 | 1 | 1 | 0.04 | 173249 | 2.5 | 0 | 0 | 1 | 1 | 1 | 2 | 8 | 28 | 0 | 0.5 | 2021-04 | 1 | 1
621 | CR0013705 | CTASK0026821 | Closed | OPUS-TES | Thai Nguyen | 16 | 20 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202105][CLT Internal] WHY IS MASTER BOOKING NOT BEING PULLED OUT IN TES | 2021-04-05 15:34 | 2021-06-30 15:33 | 2021-06-28 16:30 | 2021-06-29 15:39 | 2021-06-30 10:00 |  | 2021-07-06 12:30 | 2021-07-06 11:33 | 2021-07-02 10:26 | 2021-07-29 14:00 | CR0013705 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W27 | 2021-07 | 61 | 82 | 91.8724 | 5 | 1 | 1 | 0.04 | 173249 | 2.5 | 0 | 0 | 1 | 1 | 1 | 2 | 8 | 28 | 0 | 0.5 | 2021-04 | 1 | 1
622 | CR0013846 | CTASK0026459 | Closed | OPUS-SCG | Trang Duy Thong | 8 | 8 | 2021-05-29 14:19 | 2021-05-10 14:19 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Approved Details |  | [Test] Pre-checking Enhancement - View Previous Action Pre-check Report | 2021-05-06 13:55 | 2021-06-11 13:54 | 2021-06-09 08:17 | 2021-06-30 16:44 | 2021-06-30 17:18 |  | 2021-07-06 10:17 | 2021-07-06 10:06 | 2021-07-01 11:42 | 2021-07-29 14:00 | CR0013846 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Approved Details | OPUS-SCG | 2021-W27 | 2021-07 | 0 | 8 | 60.8492 | 1 | 1 | 1 | 0.01 | 193511 | 0.9 | 1 | 0 | 1 | 1 | 1 | 2 | 8 | 28 | 0.81818 | 0 | 2021-05 | 1 | 1
623 | CR0011547 | CTASK0016335 | Closed | OPUS-SAP | Chuong Ta | 9 | 9 |  |  | Container | Statement Management | Statement Account Payable | Invoices | Invoice Slip Inquiry |  | [Actual] Asia *SAP* Statement Account Payable Invoice - To add download function | 2019-08-28 12:39 | 2019-09-30 12:39 | 2019-09-16 12:42 |  | 2019-09-16 12:43 |  | 2019-09-24 10:00 | 2019-09-24 09:27 | 2019-09-16 14:18 | 2019-09-25 12:11 | CR0011547 | Statement ManagementStatement Account PayableInvoicesInvoice Slip Inquiry | OPUS-SAP | 2019-W39 | 2019-09 | 9 | 0 | 26.8898 | 1 | 1 | 1 | 0 | 183379 | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 6 | 0 | 0 | 2019-08 | 0 | 0
624 | CR0012924 | CTASK0022300 | Closed | OPUS-DMT | Cuong Nguyen | 35 | 37 | 2020-12-11 20:00 | 2020-11-16 08:00 | Container | Service Management | Demurrage/Detention | Billing | Issued Invoice Inquiry |  | [CTASK2] CLV_Design_Development_Test_Deployment | 2020-12-01 13:19 | 2020-12-04 20:00 | 2020-12-03 16:07 | 2020-12-28 15:54 | 2020-12-28 16:55 |  | 2021-01-05 10:00 | 2021-01-05 09:57 | 2020-12-31 11:01 | 2021-01-06 16:27 | CR0012924 | Service ManagementDemurrage/DetentionBillingIssued Invoice Inquiry | OPUS-DMT | 2021-W1 | 2021-01 | 35 | 43 | 34.8618 | 2 | 1 | 2 | 0.05 | 193529 | 1.5 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 40 | 0.11538 | 0.058824 | 2020-12 | 0 | 0
625 | CR0012924 | CTASK0022301 | Closed | OPUS-DMT | Tran Le | 6 | 6 | 2020-12-11 20:00 | 2020-12-01 08:00 | Container | Service Management | Demurrage/Detention | Billing | Issued Invoice Inquiry |  | [CTASK3] CLT_Pair Test | 2020-12-01 13:19 | 2020-12-04 20:00 | 2020-12-03 16:07 | 2020-12-28 15:54 | 2020-12-28 16:55 |  | 2021-01-05 10:00 | 2021-01-05 09:57 | 2020-12-31 11:01 | 2021-01-06 16:27 | CR0012924 | Service ManagementDemurrage/DetentionBillingIssued Invoice Inquiry | OPUS-DMT | 2021-W1 | 2021-01 | 35 | 43 | 34.8618 | 2 | 1 | 2 | 0.05 | 193501 | 1.1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 40 | 0.052632 | 0.076923 | 2020-12 | 0 | 0
626 | CR0012199 | CTASK0018439 | Closed | OPUS-SCO | Lien Le | 579 | 100 | 2020-05-20 12:30 | 2020-03-11 12:30 | [6 empty] | [actual][CLV] Global expansion of DSO/CEI batch program and DSO/CEI Inquiry functions | 2020-02-12 16:00 | 2020-05-21 20:59 | 2020-04-22 10:51 | 2020-05-21 10:32 | 2020-05-21 10:36 |  | 2020-05-26 10:00 | 2020-05-26 11:12 | 2020-05-21 13:01 | 2020-06-25 13:00 | CR0012199 |  | OPUS-SCO | 2020-W22 | 2020-05 | 579 | 100 | 103.7501 | 1 | 1 | 1 | 0.04 | 193441 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0 | 2020-02 | 0 | 0
627 | CR0013731 | CTASK0026011 | Closed | OPUS-BKG-M | Loc Tran | 18 | 18 | 2021-04-30 16:54 | 2021-04-01 16:54 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Development][CLT Internal] Literal SQL Tuning on Special Cargo Manifest Report | 2021-04-07 21:44 | 2021-05-13 02:00 | 2021-05-11 09:27 | 2021-05-12 17:16 | 2021-06-03 17:50 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:36 | 2021-07-28 14:00 | CR0013731 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2021-W25 | 2021-06 | 58 | 52 | 80.5112 | 4 | 1 | 1 | 0.03 | 193503 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.33333 | 0.28571 | 2021-04 | 0 | 0
628 | CR0013731 | CTASK0026012 | Closed | OPUS-BKG-M | Loc Tran | 26 | 20 | 2021-04-30 18:59 | 2021-04-01 18:59 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Testing][CLT Internal] Literal SQL Tuning on Special Cargo Manifest Report | 2021-04-07 21:44 | 2021-05-13 02:00 | 2021-05-11 09:27 | 2021-05-12 17:16 | 2021-06-03 17:50 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:36 | 2021-07-28 14:00 | CR0013731 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2021-W25 | 2021-06 | 58 | 52 | 80.5112 | 4 | 1 | 1 | 0.03 | 193503 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.33333 | 0.28571 | 2021-04 | 0 | 0
629 | CR0013731 | CTASK0026013 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-06-30 14:00 | 2021-06-21 14:00 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Deployment][CLT Internal] Literal SQL Tuning on Special Cargo Manifest Report | 2021-04-07 21:44 | 2021-05-13 02:00 | 2021-05-11 09:27 | 2021-05-12 17:16 | 2021-06-03 17:50 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:36 | 2021-07-28 14:00 | CR0013731 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2021-W25 | 2021-06 | 58 | 52 | 80.5112 | 4 | 1 | 1 | 0.03 | 193503 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.33333 | 0.28571 | 2021-04 | 0 | 0
630 | CR0013731 | CTASK0025970 | Closed | OPUS-BKG-M | Loc Tran | 10 | 10 | 2021-03-31 17:07 | 2021-03-17 17:07 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Design][CLT Internal] Literal SQL Tuning on Special Cargo Manifest Report | 2021-04-07 21:44 | 2021-05-13 02:00 | 2021-05-11 09:27 | 2021-05-12 17:16 | 2021-06-03 17:50 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:36 | 2021-07-28 14:00 | CR0013731 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2021-W25 | 2021-06 | 58 | 52 | 80.5112 | 4 | 1 | 1 | 0.03 | 193503 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.33333 | 0.28571 | 2021-04 | 0 | 0
631 | CR0012637 | CTASK0021413 | Closed | OPUS-SCO | Hang To | 20 | 20 | 2020-07-31 11:49 | 2020-07-01 11:49 | Container | Statement Management | Statement Account Receivable |  |  |  | [July][Hang] Modifications of all CLEAR functions related to SAR customer sturcture change | 2020-06-04 14:07 | 2020-08-04 14:07 | 2020-07-07 14:39 | 2020-07-24 09:28 | 2020-07-24 09:31 |  | 2020-07-28 09:30 | 2020-07-28 10:00 | 2020-07-24 09:35 | 2020-08-28 13:00 | CR0012637 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 470 | 500 | 53.8078 | 8 | 1 | 5 | 0.39 | 183344 | 1.1 | 0 | 0 | 0 | 4 | 2 | 2 | 8 | 27 | 0 | 2.4286 | 2020-06 | 0 | 0
632 | CR0012637 | CTASK0020944 | Closed | OPUS-SCO | Mohamed Hary | 30 | 30 | 2020-07-31 14:34 | 2020-07-01 14:34 | Container | Statement Management | Statement Account Receivable |  |  |  | [July][Hary-development & test] Modifications of all CLEAR functions related to SAR customer sturcture change | 2020-06-04 14:07 | 2020-08-04 14:07 | 2020-07-07 14:39 | 2020-07-24 09:28 | 2020-07-24 09:31 |  | 2020-07-28 09:30 | 2020-07-28 10:00 | 2020-07-24 09:35 | 2020-08-28 13:00 | CR0012637 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 470 | 500 | 53.8078 | 8 | 1 | 5 | 0.39 | 193489 | 1 | 0 | 0 | 0 | 4 | 2 | 2 | 8 | 27 | 0 | 0.63636 | 2020-06 | 0 | 0
633 | CR0012637 | CTASK0020156 | Closed | OPUS-SCO | Hang To | 132 | 132 | 2020-07-07 19:25 | 2020-05-18 19:25 | Container | Statement Management | Statement Account Receivable |  |  |  | [before July][Hang] Modifications of all CLEAR functions related to SAR customer sturcture change | 2020-06-04 14:07 | 2020-08-04 14:07 | 2020-07-07 14:39 | 2020-07-24 09:28 | 2020-07-24 09:31 |  | 2020-07-28 09:30 | 2020-07-28 10:00 | 2020-07-24 09:35 | 2020-08-28 13:00 | CR0012637 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 470 | 500 | 53.8078 | 8 | 1 | 5 | 0.39 | 183344 | 1.1 | 0 | 0 | 0 | 4 | 2 | 2 | 8 | 27 | 0 | 2.4286 | 2020-06 | 0 | 0
634 | CR0012637 | CTASK0020823 | Closed | OPUS-SCO | Dinh Cong Tuan | 20 | 50 | 2020-06-30 18:41 | 2020-06-24 18:41 | Container | Statement Management | Statement Account Receivable |  |  |  | [Tuan-development & test] Modifications of all CLEAR functions related to SAR customer sturcture change | 2020-06-04 14:07 | 2020-08-04 14:07 | 2020-07-07 14:39 | 2020-07-24 09:28 | 2020-07-24 09:31 |  | 2020-07-28 09:30 | 2020-07-28 10:00 | 2020-07-24 09:35 | 2020-08-28 13:00 | CR0012637 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 470 | 500 | 53.8078 | 8 | 1 | 5 | 0.39 | 193510 | 1 | 0 | 0 | 0 | 4 | 2 | 2 | 8 | 27 | 0 | 0 | 2020-06 | 0 | 0
635 | CR0012637 | CTASK0020203 | Closed | OPUS-SCO | Lien Le | 159 | 159 | 2020-06-30 12:10 | 2020-05-18 12:10 | Container | Statement Management | Statement Account Receivable |  |  |  | [Before July]Modifications of all CLEAR functions related to SAR customer sturcture change | 2020-06-04 14:07 | 2020-08-04 14:07 | 2020-07-07 14:39 | 2020-07-24 09:28 | 2020-07-24 09:31 |  | 2020-07-28 09:30 | 2020-07-28 10:00 | 2020-07-24 09:35 | 2020-08-28 13:00 | CR0012637 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 470 | 500 | 53.8078 | 8 | 1 | 5 | 0.39 | 193441 | 1.2 | 0 | 0 | 0 | 4 | 2 | 2 | 8 | 27 | 0 | 1.2222 | 2020-06 | 0 | 0
636 | CR0012637 | CTASK0020824 | Closed | OPUS-SCO | Mohamed Hary | 20 | 20 | 2020-06-30 18:42 | 2020-06-24 18:42 | Container | Statement Management | Statement Account Receivable |  |  |  | [Hary-development & test] Modifications of all CLEAR functions related to SAR customer sturcture change | 2020-06-04 14:07 | 2020-08-04 14:07 | 2020-07-07 14:39 | 2020-07-24 09:28 | 2020-07-24 09:31 |  | 2020-07-28 09:30 | 2020-07-28 10:00 | 2020-07-24 09:35 | 2020-08-28 13:00 | CR0012637 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 470 | 500 | 53.8078 | 8 | 1 | 5 | 0.39 | 193489 | 1 | 0 | 0 | 0 | 4 | 2 | 2 | 8 | 27 | 0 | 0.63636 | 2020-06 | 0 | 0
637 | CR0012637 | CTASK0021412 | Closed | OPUS-SCO | Lien Le | 39 | 39 | 2020-07-31 11:43 | 2020-07-01 11:43 | Container | Statement Management | Statement Account Receivable |  |  |  | [July][Lien]Modifications of all CLEAR functions related to SAR customer sturcture change | 2020-06-04 14:07 | 2020-08-04 14:07 | 2020-07-07 14:39 | 2020-07-24 09:28 | 2020-07-24 09:31 |  | 2020-07-28 09:30 | 2020-07-28 10:00 | 2020-07-24 09:35 | 2020-08-28 13:00 | CR0012637 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 470 | 500 | 53.8078 | 8 | 1 | 5 | 0.39 | 193441 | 1.2 | 0 | 0 | 0 | 4 | 2 | 2 | 8 | 27 | 0 | 1.2222 | 2020-06 | 0 | 0
638 | CR0012637 | CTASK0020822 | Closed | OPUS-SCO | Chuong Ta | 50 | 50 | 2020-07-31 18:39 | 2020-07-01 18:39 | Container | Statement Management | Statement Account Receivable |  |  |  | [Chuong-development & test][July] Modifications of all CLEAR functions related to SAR customer sturcture change | 2020-06-04 14:07 | 2020-08-04 14:07 | 2020-07-07 14:39 | 2020-07-24 09:28 | 2020-07-24 09:31 |  | 2020-07-28 09:30 | 2020-07-28 10:00 | 2020-07-24 09:35 | 2020-08-28 13:00 | CR0012637 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W31 | 2020-07 | 470 | 500 | 53.8078 | 8 | 1 | 5 | 0.39 | 183379 | 1.2 | 0 | 0 | 0 | 4 | 2 | 2 | 8 | 27 | 0 | 0.38462 | 2020-06 | 0 | 0
639 | CR0011324 | CTASK0014964 | Closed | OPUS-PSO | Hieu Vu | 10 | 10 |  |  | Container | Vessel Operation | Vessel Schedule | VSL SKD | VSL SKD Inquiry | Long Range SKD Inquiry | CARA Interface : MDA/VSK Interface (Opus --> CARA) | 2019-06-13 09:45 | 2019-07-05 18:00 | 2019-07-09 13:20 |  | 2019-07-09 13:22 |  | 2019-07-16 10:00 | 2019-07-16 09:00 | 2019-07-09 16:07 | 2019-07-18 10:57 | CR0011324 | Vessel OperationVessel ScheduleVSL SKDVSL SKD InquiryLong Range SKD Inquiry | OPUS-VSK | 2019-W29 | 2019-07 | 10 | 0 | 33.0106 | 1 | 1 | 1 | 0 | 183375 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 2019-06 | 0 | 0
640 | CR0013371 | CTASK0026164 | Implemented | OPUS-BKG-OB | Nam Nguyen | 17 | 19 | 2021-05-21 17:07 | 2021-05-16 17:06 | Container | Service Management | Booking/Documentation | Report | Booking Container Report |  | [BKG-OB Nam Nguyen]NA *SPC* Booking Container Report downloaded data has incorrect total TEU per container data | 2021-05-06 08:01 | 2021-06-04 08:01 | 2021-06-01 09:54 | 2021-06-30 18:15 | 2021-07-12 08:55 |  | 2021-08-17 10:20 | 2021-08-17 10:32 | 2021-08-10 14:30 |  | CR0013371 | Service ManagementBooking/DocumentationReportBooking Container Report | OPUS-BKG-RPT | 2021-W33 | 2021-08 | 17 | 19 | 103.0969 | 1 | 1 | 1 | 0.01 | 123048 | 2.6 | 1 | 0 | 0 | 1 | 1 | 2 | 5 | 22 | 0.22222 | 0.047619 | 2021-05 | 0 | 0
641 | CR0013109 | CTASK0023546 | Closed | OPUS-DMT | Cuong Nguyen | 36 | 35 | 2021-01-08 20:00 | 2020-12-14 08:00 | Container | Service Management | Demurrage/Detention | A/R I/F |  |  | [CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2020-12-24 08:17 | 2021-01-22 20:00 | 2021-01-22 12:33 | 2021-03-19 10:13 | 2021-03-22 08:09 |  | 2021-03-30 10:00 | 2021-03-30 09:52 | 2021-03-22 17:08 | 2021-04-29 14:00 | CR0013109 | Service ManagementDemurrage/DetentionA/R I/F | OPUS-DMT | 2021-W13 | 2021-03 | 36 | 35 | 96.0718 | 1 | 1 | 1 | 0.02 | 193529 | 1.6 | 0 | 0 | 0 | 1 | 1 | 2 | 12 | 46 | 0 | 0.058824 | 2020-12 | 0 | 0
642 | CR0012242 | CTASK0022477 | Closed | OPUS-DOM | Giang Nguyen Hoang | 15 | 15 | 2020-09-30 14:40 | 2020-09-15 14:40 | DOM Web Portal | IMC | EQ Match | Booking Activity |  |  | NA * DOM * Add rail billing validations to Opus DOM and setup email notifications | 2020-09-15 11:28 | 2020-11-20 22:00 | 2020-11-16 15:06 | 2021-01-15 16:45 | 2021-01-19 13:30 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-21 16:59 | 2021-02-25 14:00 | CR0012242 | IMCEQ MatchBooking Activity | OPUS-DOM | 2021-W4 | 2021-01 | 0 | 30 | 132.9392 | 2 | 1 | 2 | 0.01 | 183440 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0 | 0 | 2020-09 | 0 | 0
643 | CR0012242 | CTASK0018488 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 15 | 15 | 2020-09-30 23:00 | 2020-09-15 09:00 | DOM Web Portal | IMC | EQ Match | Booking Activity |  |  | NA * DOM * Add rail billing validations to Opus DOM and setup email notifications | 2020-09-15 11:28 | 2020-11-20 22:00 | 2020-11-16 15:06 | 2021-01-15 16:45 | 2021-01-19 13:30 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-21 16:59 | 2021-02-25 14:00 | CR0012242 | IMCEQ MatchBooking Activity | OPUS-DOM | 2021-W4 | 2021-01 | 0 | 30 | 132.9392 | 2 | 1 | 2 | 0.01 | 183432 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0 | 0 | 2020-09 | 0 | 0
644 | CR0013720 | CTASK0026091 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 4 | 4 | 2021-03-30 02:00 | 2021-03-25 02:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [PROD]KOREA Local customs will be changed on 30th Mar, so the current auto-map by location should be changed from current code to new code. | 2021-03-16 17:58 | 2021-03-25 | 2021-03-23 16:32 | 2021-03-24 18:17 | 2021-03-25 09:35 |  | 2021-03-30 10:00 | 2021-03-30 10:00 | 2021-03-25 14:04 | 2021-04-29 14:00 | CR0013720 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W13 | 2021-03 | 18 | 18 | 13.6683 | 4 | 1 | 1 | 0.05 | 193506 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 1.1212 | 1.25 | 2021-03 | 0 | 0
645 | CR0013720 | CTASK0025903 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 4 | 4 | 2021-03-31 02:00 | 2021-03-17 02:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Test]KOREA Local customs will be changed on 30th Mar, so the current auto-map by location should be changed from current code to new code. | 2021-03-16 17:58 | 2021-03-25 | 2021-03-23 16:32 | 2021-03-24 18:17 | 2021-03-25 09:35 |  | 2021-03-30 10:00 | 2021-03-30 10:00 | 2021-03-25 14:04 | 2021-04-29 14:00 | CR0013720 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W13 | 2021-03 | 18 | 18 | 13.6683 | 4 | 1 | 1 | 0.05 | 193506 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 1.1212 | 1.25 | 2021-03 | 0 | 0
646 | CR0013720 | CTASK0025902 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2021-03-31 02:00 | 2021-03-17 02:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Dev-Deploy]KOREA Local customs will be changed on 30th Mar, so the current auto-map by location should be changed from current code to new code. | 2021-03-16 17:58 | 2021-03-25 | 2021-03-23 16:32 | 2021-03-24 18:17 | 2021-03-25 09:35 |  | 2021-03-30 10:00 | 2021-03-30 10:00 | 2021-03-25 14:04 | 2021-04-29 14:00 | CR0013720 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W13 | 2021-03 | 18 | 18 | 13.6683 | 4 | 1 | 1 | 0.05 | 193506 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 1.1212 | 1.25 | 2021-03 | 0 | 0
647 | CR0013720 | CTASK0025867 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 2 | 2 | 2021-03-16 02:00 | 2021-03-15 02:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Estimate]KOREA Local customs will be changed on 30th Mar, so the current auto-map by location should be changed from current code to new code. | 2021-03-16 17:58 | 2021-03-25 | 2021-03-23 16:32 | 2021-03-24 18:17 | 2021-03-25 09:35 |  | 2021-03-30 10:00 | 2021-03-30 10:00 | 2021-03-25 14:04 | 2021-04-29 14:00 | CR0013720 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W13 | 2021-03 | 18 | 18 | 13.6683 | 4 | 1 | 1 | 0.05 | 193506 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 1.1212 | 1.25 | 2021-03 | 0 | 0
648 | CR0013730 | CTASK0026252 | Closed | OPUS-BKG-IB | Thuc Tran | 22 | 22 | 2021-04-16 19:30 | 2021-04-01 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Development+Testing+Deployment] Issue // CR0013299 - CARGO RELEASE & EDI COREOR ENHANCEMENT // MX | 2021-03-25 09:48 | 2021-04-30 23:47 | 2021-04-30 10:06 | 2021-05-06 14:19 | 2021-05-13 16:14 |  | 2021-05-25 16:14 | 2021-05-25 10:52 | 2021-05-14 10:35 | 2021-06-24 14:00 | CR0013730 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W21 | 2021-05 | 36 | 36 | 61.2683 | 3 | 1 | 1 | 0.02 | 173280 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0.375 | 1 | 2021-03 | 0 | 0
649 | CR0013730 | CTASK0027057 | Closed | OPUS-BKG-IB | Thuc Tran | 10 | 10 | 2021-05-24 19:30 | 2021-05-14 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Deployment+Testing] Issue // CR0013299 - CARGO RELEASE & EDI COREOR ENHANCEMENT // MX | 2021-03-25 09:48 | 2021-04-30 23:47 | 2021-04-30 10:06 | 2021-05-06 14:19 | 2021-05-13 16:14 |  | 2021-05-25 16:14 | 2021-05-25 10:52 | 2021-05-14 10:35 | 2021-06-24 14:00 | CR0013730 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W21 | 2021-05 | 36 | 36 | 61.2683 | 3 | 1 | 1 | 0.02 | 173280 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0.375 | 1 | 2021-03 | 0 | 0
650 | CR0013730 | CTASK0025951 | Closed | OPUS-BKG-IB | Thuc Tran | 4 | 4 | 2021-03-22 19:30 | 2021-03-16 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Estimation] Issue // CR0013299 - CARGO RELEASE & EDI COREOR ENHANCEMENT // MX | 2021-03-25 09:48 | 2021-04-30 23:47 | 2021-04-30 10:06 | 2021-05-06 14:19 | 2021-05-13 16:14 |  | 2021-05-25 16:14 | 2021-05-25 10:52 | 2021-05-14 10:35 | 2021-06-24 14:00 | CR0013730 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W21 | 2021-05 | 36 | 36 | 61.2683 | 3 | 1 | 1 | 0.02 | 173280 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0.375 | 1 | 2021-03 | 0 | 0
651 | CR0011167 | CTASK0021157 | Closed | OPUS-DMT | Cuong Nguyen | 46 | 48 | 2020-08-31 20:00 | 2020-07-27 08:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK3] CLV_Analysis_Development_Test_Deployment | 2020-08-04 14:47 | 2020-08-31 20:00 | 2020-08-31 16:02 | 2020-10-20 10:44 | 2020-11-02 19:19 |  | 2020-11-10 10:00 | 2020-11-10 09:39 | 2020-11-03 08:36 | 2020-12-10 14:00 | CR0011167 | Service ManagementDemurrage/Detention | OPUS-DMT | 2020-W46 | 2020-11 | 46 | 48 | 97.8004 | 1 | 1 | 1 | 0.02 | 193529 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 16 | 0 | 0.058824 | 2020-08 | 0 | 0
652 | CR0012369 | CTASK0018825 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2020-05-20 01:57 | 2020-05-12 02:57 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment][CLT Internal] Booking initially didn't apply Standby validation and user performed Standby recalculation, but standby status remain as Blank even GD1 result from re-calculation. | 2020-03-13 12:55 | 2020-05-28 | 2020-04-22 17:02 | 2020-04-23 11:07 | 2020-05-12 09:18 |  | 2020-05-12 10:00 | 2020-05-19 10:00 | 2020-05-12 09:18 | 2020-05-19 11:22 | CR0012369 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W20 | 2020-05 | 29 | 29 | 59.8787 | 4 | 1 | 1 | 0.02 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.4 | 2020-03 | 0 | 0
653 | CR0012369 | CTASK0018820 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-03-20 19:20 | 2020-03-16 10:20 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development][CLT Internal] Booking initially didn't apply Standby validation and user performed Standby recalculation, but standby status remain as Blank even GD1 result from re-calculation. | 2020-03-13 12:55 | 2020-05-28 | 2020-04-22 17:02 | 2020-04-23 11:07 | 2020-05-12 09:18 |  | 2020-05-12 10:00 | 2020-05-19 10:00 | 2020-05-12 09:18 | 2020-05-19 11:22 | CR0012369 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W20 | 2020-05 | 29 | 29 | 59.8787 | 4 | 1 | 1 | 0.02 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.4 | 2020-03 | 0 | 0
654 | CR0012369 | CTASK0018821 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2020-03-20 19:22 | 2020-03-16 11:22 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing][CLT Internal] Booking initially didn't apply Standby validation and user performed Standby recalculation, but standby status remain as Blank even GD1 result from re-calculation. | 2020-03-13 12:55 | 2020-05-28 | 2020-04-22 17:02 | 2020-04-23 11:07 | 2020-05-12 09:18 |  | 2020-05-12 10:00 | 2020-05-19 10:00 | 2020-05-12 09:18 | 2020-05-19 11:22 | CR0012369 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W20 | 2020-05 | 29 | 29 | 59.8787 | 4 | 1 | 1 | 0.02 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.4 | 2020-03 | 0 | 0
655 | CR0012369 | CTASK0018817 | Closed | OPUS-BKG-M | Kieu Le | 3 | 3 | 2020-03-09 19:12 | 2020-03-09 11:12 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] [CLT Internal] Booking initially didn't apply Standby validation and user performed Standby recalculation, but standby status remain as Blank even GD1 result from re-calculation. | 2020-03-13 12:55 | 2020-05-28 | 2020-04-22 17:02 | 2020-04-23 11:07 | 2020-05-12 09:18 |  | 2020-05-12 10:00 | 2020-05-19 10:00 | 2020-05-12 09:18 | 2020-05-19 11:22 | CR0012369 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W20 | 2020-05 | 29 | 29 | 59.8787 | 4 | 1 | 1 | 0.02 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.4 | 2020-03 | 0 | 0
656 | CR0012836 | CTASK0021127 | Closed | OPUS-FLT | Tu Nguyen | 10 | 10 | 2020-07-24 18:00 | 2020-07-13 09:00 | Container | Support & Admin | Fleet Management | Setup | FLT Setup |  | [CLV][CLT Internal] Logic enhancement for monthly VVD assignment setup | 2020-07-15 11:07 | 2020-07-31 18:00 | 2020-07-22 16:17 | 2020-07-29 11:18 | 2020-07-29 13:30 |  | 2020-08-05 10:00 | 2020-08-04 11:15 | 2020-07-30 17:12 | 2020-09-04 13:00 | CR0012836 | Support & AdminFleet ManagementSetupFLT Setup | OPUS-FLT | 2020-W32 | 2020-08 | 10 | 10 | 20.9536 | 1 | 1 | 1 | 0.02 | 123045 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 30 | 0 | 0 | 2020-07 | 0 | 0
657 | CR0011051 | CTASK0014545 | Closed | OPUS-BKG-EBKG | Kieu Le | 3 | 3 |  |  | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | NA *BKG* Adding Additional Defaults for Bookings (CSVC/EXPORT) | 2019-06-03 09:25 | 2019-07-15 14:38 | 2019-06-10 17:05 | 2019-09-13 10:26 | 2019-09-16 09:24 |  | 2019-10-15 10:00 | 2019-10-15 12:36 | 2019-10-05 03:20 | 2019-11-07 06:30 | CR0011051 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2019-W42 | 2019-10 | 8 | 56 | 134.0246 | 3 | 2 | 1 | 0.02 | 153106 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-06 | 0 | 0
658 | CR0011051 | CTASK0014455 | Closed | OPUS-BKG-M | Kieu Le | 5 | 5 |  |  | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | NA *BKG* Adding Additional Defaults for Bookings (CSVC/EXPORT) | 2019-06-03 09:25 | 2019-07-15 14:38 | 2019-06-10 17:05 | 2019-09-13 10:26 | 2019-09-16 09:24 |  | 2019-10-15 10:00 | 2019-10-15 12:36 | 2019-10-05 03:20 | 2019-11-07 06:30 | CR0011051 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2019-W42 | 2019-10 | 8 | 56 | 134.0246 | 3 | 2 | 1 | 0.02 | 153106 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-06 | 0 | 0
659 | CR0011051 | CTASK0012494 | Closed | OPUS-BKG-M | Kieu Le | 56 | 56 | 2019-06-28 14:08 | 2019-06-03 14:08 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | NA *BKG* Adding Additional Defaults for Bookings (CSVC/EXPORT) | 2019-06-03 09:25 | 2019-07-15 14:38 | 2019-06-10 17:05 | 2019-09-13 10:26 | 2019-09-16 09:24 |  | 2019-10-15 10:00 | 2019-10-15 12:36 | 2019-10-05 03:20 | 2019-11-07 06:30 | CR0011051 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2019-W42 | 2019-10 | 8 | 56 | 134.0246 | 3 | 2 | 1 | 0.02 | 153106 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-06 | 0 | 0
660 | CR0012400 | CTASK0019560 | Closed | OPUS-TES | Thai Nguyen | 114 | 100 | 2020-08-31 13:14 | 2020-04-13 13:14 | Container | Service Management | TML INV |  |  |  | [Actual] GHQ - New TES Cost Code - TMOSOT | 2020-04-29 09:11 | 2020-05-22 09:10 | 2020-05-15 10:24 | 2020-10-19 18:22 | 2020-12-30 13:22 |  | 2020-10-20 17:10 | 2021-01-05 15:03 | 2020-12-31 09:38 | 2021-02-20 14:00 | CR0012400 | Service ManagementTML INV | OPUS-TES | 2020-W43 | 2020-10 | 114 | 100 | 174.333 | 1 | 1 | 1 | 0.02 | 173249 | 1.6 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 20 | 0 | 2 | 2020-04 | 0 | 0
661 | CR0011928 | CTASK0018724 | Closed | OPUS-BKG-M | Kieu Le | 5 | 5 | 2020-03-06 18:52 | 2020-03-04 18:52 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] NA *Standby* Standby status report Transshipment / Empty Pick Up search boxes and results - Standby Booking Status Report | 2020-02-06 11:35 | 2020-03-26 | 2020-03-23 16:09 | 2020-05-26 12:57 | 2020-05-27 17:40 |  | 2020-06-23 10:00 | 2020-06-16 10:00 | 2020-06-08 21:41 | 2020-06-26 23:55 | CR0011928 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W26 | 2020-06 | 53 | 52 | 137.9342 | 7 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
662 | CR0011928 | CTASK0019649 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2020-04-18 01:59 | 2020-04-15 02:09 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] NA *Standby* Standby status report Transshipment / Empty Pick Up search boxes and results - Standby Booking Status Report | 2020-02-06 11:35 | 2020-03-26 | 2020-03-23 16:09 | 2020-05-26 12:57 | 2020-05-27 17:40 |  | 2020-06-23 10:00 | 2020-06-16 10:00 | 2020-06-08 21:41 | 2020-06-26 23:55 | CR0011928 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W26 | 2020-06 | 53 | 52 | 137.9342 | 7 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
663 | CR0011928 | CTASK0017672 | Closed | OPUS-BKG-M | Kieu Le | 38 | 38 | 2020-02-21 16:51 | 2020-02-10 16:51 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] NA *Standby* Standby status report Transshipment / Empty Pick Up search boxes and results - Standby Booking Status Report | 2020-02-06 11:35 | 2020-03-26 | 2020-03-23 16:09 | 2020-05-26 12:57 | 2020-05-27 17:40 |  | 2020-06-23 10:00 | 2020-06-16 10:00 | 2020-06-08 21:41 | 2020-06-26 23:55 | CR0011928 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W26 | 2020-06 | 53 | 52 | 137.9342 | 7 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
664 | CR0011928 | CTASK0017646 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 |  |  | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Estimation] NA *Standby* Standby status report Transshipment / Empty Pick Up search boxes and results - Standby Booking Status Report | 2020-02-06 11:35 | 2020-03-26 | 2020-03-23 16:09 | 2020-05-26 12:57 | 2020-05-27 17:40 |  | 2020-06-23 10:00 | 2020-06-16 10:00 | 2020-06-08 21:41 | 2020-06-26 23:55 | CR0011928 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W26 | 2020-06 | 53 | 52 | 137.9342 | 7 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
665 | CR0011928 | CTASK0018723 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2020-03-04 15:25 | 2020-03-02 15:25 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] NA *Standby* Standby status report Transshipment / Empty Pick Up search boxes and results - Standby Booking Status Report | 2020-02-06 11:35 | 2020-03-26 | 2020-03-23 16:09 | 2020-05-26 12:57 | 2020-05-27 17:40 |  | 2020-06-23 10:00 | 2020-06-16 10:00 | 2020-06-08 21:41 | 2020-06-26 23:55 | CR0011928 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W26 | 2020-06 | 53 | 52 | 137.9342 | 7 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
666 | CR0011928 | CTASK0018725 | Closed | OPUS-BKG-M | Kieu Le | 3 | 4 | 2020-03-06 18:53 | 2020-03-04 18:53 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] NA *Standby* Standby status report Transshipment / Empty Pick Up search boxes and results - Standby Booking Status Report | 2020-02-06 11:35 | 2020-03-26 | 2020-03-23 16:09 | 2020-05-26 12:57 | 2020-05-27 17:40 |  | 2020-06-23 10:00 | 2020-06-16 10:00 | 2020-06-08 21:41 | 2020-06-26 23:55 | CR0011928 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W26 | 2020-06 | 53 | 52 | 137.9342 | 7 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
667 | CR0011928 | CTASK0018537 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2020-06-13 01:28 | 2020-06-09 02:28 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] NA *Standby* Standby status report Transshipment / Empty Pick Up search boxes and results - Standby Booking Status Report | 2020-02-06 11:35 | 2020-03-26 | 2020-03-23 16:09 | 2020-05-26 12:57 | 2020-05-27 17:40 |  | 2020-06-23 10:00 | 2020-06-16 10:00 | 2020-06-08 21:41 | 2020-06-26 23:55 | CR0011928 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W26 | 2020-06 | 53 | 52 | 137.9342 | 7 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
668 | CR0013364 | CTASK0023910 | Closed | OPUS-PRI | Ngan Nham | 40 | 40 | 2020-12-08 14:00 | 2020-12-01 14:00 | Container | Sales Management | Space Control |  |  |  | [Development] Asia - Creation of a new "BKG VIA" channel field with corresponding enhancements in BKG and SPC modules & add additional "Premium" service function | 2020-12-04 13:12 | 2020-12-12 | 2020-12-11 16:37 | 2020-12-23 09:43 | 2021-01-04 15:58 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2021-01-05 13:23 | 2021-02-12 14:00 | CR0013364 | Sales ManagementSpace Control | OPUS-SPC | 2021-W2 | 2021-01 | 40 | 40 | 38.8665 | 1 | 1 | 1 | 0.04 | 193461 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 14 | 40 | 0.125 | 0 | 2020-12 | 0 | 0
669 | CR0013202 | CTASK0023853 | Closed | OPUS-BKG-M | Thien Lai | 34 | 34 | 2020-12-31 17:26 | 2020-12-01 17:26 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] Add an internal Page to proceed Special Routing as regular correction job for GSD Handling. | 2020-11-13 09:46 | 2021-01-28 | 2021-01-22 13:19 | 2021-01-27 14:38 | 2021-01-27 14:53 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-28 15:25 | 2021-03-04 14:00 | CR0013202 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 119 | 120 | 81.0101 | 5 | 1 | 1 | 0.06 | 193567 | 1.3 | 1 | 0 | 0 | 2 | 1 | 2 | 8 | 21 | 0.5625 | 0.53333 | 2020-11 | 0 | 0
670 | CR0013202 | CTASK0023152 | Closed | OPUS-BKG-M | Thien Lai | 24 | 24 | 2020-11-10 18:40 | 2020-10-22 18:39 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal] Add an internal Page to proceed Special Routing as regular correction job for GSD Handling. | 2020-11-13 09:46 | 2021-01-28 | 2021-01-22 13:19 | 2021-01-27 14:38 | 2021-01-27 14:53 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-28 15:25 | 2021-03-04 14:00 | CR0013202 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 119 | 120 | 81.0101 | 5 | 1 | 1 | 0.06 | 193567 | 1.3 | 1 | 0 | 0 | 2 | 1 | 2 | 8 | 21 | 0.5625 | 0.53333 | 2020-11 | 0 | 0
671 | CR0013202 | CTASK0023480 | Closed | OPUS-BKG-M | Thien Lai | 24 | 24 | 2020-12-31 11:12 | 2020-12-01 11:12 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] Add an internal Page to proceed Special Routing as regular correction job for GSD Handling. | 2020-11-13 09:46 | 2021-01-28 | 2021-01-22 13:19 | 2021-01-27 14:38 | 2021-01-27 14:53 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-28 15:25 | 2021-03-04 14:00 | CR0013202 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 119 | 120 | 81.0101 | 5 | 1 | 1 | 0.06 | 193567 | 1.3 | 1 | 0 | 0 | 2 | 1 | 2 | 8 | 21 | 0.5625 | 0.53333 | 2020-11 | 0 | 0
672 | CR0013202 | CTASK0023478 | Closed | OPUS-BKG-M | Thien Lai | 30 | 30 | 2020-11-30 11:10 | 2020-11-16 11:10 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal] Add an internal Page to proceed Special Routing as regular correction job for GSD Handling. | 2020-11-13 09:46 | 2021-01-28 | 2021-01-22 13:19 | 2021-01-27 14:38 | 2021-01-27 14:53 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-28 15:25 | 2021-03-04 14:00 | CR0013202 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 119 | 120 | 81.0101 | 5 | 1 | 1 | 0.06 | 193567 | 1.3 | 1 | 0 | 0 | 2 | 1 | 2 | 8 | 21 | 0.5625 | 0.53333 | 2020-11 | 0 | 0
673 | CR0013202 | CTASK0023482 | Closed | OPUS-BKG-M | Thien Lai | 7 | 8 | 2021-01-31 11:12 | 2021-01-27 11:12 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal] Add an internal Page to proceed Special Routing as regular correction job for GSD Handling. | 2020-11-13 09:46 | 2021-01-28 | 2021-01-22 13:19 | 2021-01-27 14:38 | 2021-01-27 14:53 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-28 15:25 | 2021-03-04 14:00 | CR0013202 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W5 | 2021-02 | 119 | 120 | 81.0101 | 5 | 1 | 1 | 0.06 | 193567 | 1.3 | 1 | 0 | 0 | 2 | 1 | 2 | 8 | 21 | 0.5625 | 0.53333 | 2020-11 | 0 | 0
674 | CR0012596 | CTASK0020368 | Closed | OPUS-DMT | Cuong Nguyen | 9 | 8 | 2020-06-30 20:00 | 2020-06-22 08:00 | Container | Service Management | Demurrage/Detention |  |  |  | [Analysis+Development+Test+Deployment] Asia * DMT* DMT invoice to rename charge description for cancel shipment. | 2020-06-23 10:59 | 2020-07-22 20:00 | 2020-07-22 14:50 | 2020-08-13 02:04 | 2020-08-19 08:44 |  | 2020-08-25 10:00 | 2020-08-25 09:43 | 2020-08-19 09:49 | 2020-08-28 16:01 | CR0012596 | Service ManagementDemurrage/Detention | OPUS-DMT | 2020-W35 | 2020-08 | 9 | 8 | 62.9591 | 1 | 1 | 1 | 0.01 | 193529 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 12 | 30 | 0 | 0.058824 | 2020-06 | 0 | 0
675 | CR0011868 | CTASK0018638 | Closed | OPUS-BKG-M | Vinh Tran | 88 | 88 | 2020-03-28 02:00 | 2020-02-25 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] eComm suggestion - Saving column setting in eBooking and eSI process screen | 2020-02-26 17:53 | 2020-04-16 | 2020-04-14 17:03 | 2020-08-20 13:19 | 2020-08-31 14:27 |  | 2020-09-15 10:00 | 2020-09-15 10:40 | 2020-08-31 17:03 | 2020-10-15 13:00 | CR0011868 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W38 | 2020-09 | 132 | 128 | 201.6716 | 5 | 1 | 1 | 0.03 | 193525 | 0.7 | 0 | 0 | 0 | 2 | 1 | 3 | 9 | 36 | 0 | 0.45455 | 2020-02 | 0 | 0
676 | CR0011868 | CTASK0018639 | Closed | OPUS-BKG-M | Vinh Tran | 13 | 8 | 2020-04-04 02:00 | 2020-03-25 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] eComm suggestion - Saving column setting in eBooking and eSI process screen | 2020-02-26 17:53 | 2020-04-16 | 2020-04-14 17:03 | 2020-08-20 13:19 | 2020-08-31 14:27 |  | 2020-09-15 10:00 | 2020-09-15 10:40 | 2020-08-31 17:03 | 2020-10-15 13:00 | CR0011868 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W38 | 2020-09 | 132 | 128 | 201.6716 | 5 | 1 | 1 | 0.03 | 193525 | 0.7 | 0 | 0 | 0 | 2 | 1 | 3 | 9 | 36 | 0 | 0.45455 | 2020-02 | 0 | 0
677 | CR0011868 | CTASK0019547 | Closed | OPUS-BKG-M | Vinh Tran | 6 | 6 | 2020-04-14 02:00 | 2020-04-13 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] eComm suggestion - Saving column setting in eBooking and eSI process screen | 2020-02-26 17:53 | 2020-04-16 | 2020-04-14 17:03 | 2020-08-20 13:19 | 2020-08-31 14:27 |  | 2020-09-15 10:00 | 2020-09-15 10:40 | 2020-08-31 17:03 | 2020-10-15 13:00 | CR0011868 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W38 | 2020-09 | 132 | 128 | 201.6716 | 5 | 1 | 1 | 0.03 | 193525 | 0.7 | 0 | 0 | 0 | 2 | 1 | 3 | 9 | 36 | 0 | 0.45455 | 2020-02 | 0 | 0
678 | CR0011868 | CTASK0017295 | Closed | OPUS-BKG-M | Vinh Tran | 25 | 24 | 2020-05-01 10:10 | 2020-04-13 10:08 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] eComm suggestion - Saving column setting in eBooking and eSI process screen | 2020-02-26 17:53 | 2020-04-16 | 2020-04-14 17:03 | 2020-08-20 13:19 | 2020-08-31 14:27 |  | 2020-09-15 10:00 | 2020-09-15 10:40 | 2020-08-31 17:03 | 2020-10-15 13:00 | CR0011868 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W38 | 2020-09 | 132 | 128 | 201.6716 | 5 | 1 | 1 | 0.03 | 193525 | 0.7 | 0 | 0 | 0 | 2 | 1 | 3 | 9 | 36 | 0 | 0.45455 | 2020-02 | 0 | 0
679 | CR0011868 | CTASK0018640 | Closed | OPUS-BKG-M | Vinh Tran | 2 | 2 | 2020-10-01 18:48 | 2020-10-01 18:48 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] eComm suggestion - Saving column setting in eBooking and eSI process screen | 2020-02-26 17:53 | 2020-04-16 | 2020-04-14 17:03 | 2020-08-20 13:19 | 2020-08-31 14:27 |  | 2020-09-15 10:00 | 2020-09-15 10:40 | 2020-08-31 17:03 | 2020-10-15 13:00 | CR0011868 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W38 | 2020-09 | 132 | 128 | 201.6716 | 5 | 1 | 1 | 0.03 | 193525 | 0.7 | 0 | 0 | 0 | 2 | 1 | 3 | 9 | 36 | 0 | 0.45455 | 2020-02 | 0 | 0
680 | CR0013509 | CTASK0027422 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 20 | 20 | 2021-06-30 19:54 | 2021-06-01 19:54 | Container | Service Management | Booking/Documentation | Manifest |  |  | [PROD] Enhance on HONG KONG Manifest | 2021-02-19 17:22 | 2021-03-18 | 2021-03-17 11:44 | 2021-05-25 15:22 | 2021-06-09 13:28 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-10 14:24 | 2021-07-29 14:00 | CR0013509 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 57 | 58 | 129.6928 | 3 | 1 | 2 | 0.02 | 193606 | 1.3 | 3 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 4.25 | 2.25 | 2021-02 | 0 | 0
681 | CR0013509 | CTASK0025113 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 4 | 4 | 2021-02-04 02:00 | 2021-02-03 02:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Analytics]Enhance on HONG KONG Manifest | 2021-02-19 17:22 | 2021-03-18 | 2021-03-17 11:44 | 2021-05-25 15:22 | 2021-06-09 13:28 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-10 14:24 | 2021-07-29 14:00 | CR0013509 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 57 | 58 | 129.6928 | 3 | 1 | 2 | 0.02 | 193506 | 1.7 | 3 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 1.1212 | 1.25 | 2021-02 | 0 | 0
682 | CR0013509 | CTASK0025230 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 33 | 34 | 2021-03-31 02:00 | 2021-03-01 02:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Dev-Test]Enhance on HONG KONG Manifest | 2021-02-19 17:22 | 2021-03-18 | 2021-03-17 11:44 | 2021-05-25 15:22 | 2021-06-09 13:28 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-10 14:24 | 2021-07-29 14:00 | CR0013509 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 57 | 58 | 129.6928 | 3 | 1 | 2 | 0.02 | 193506 | 1.7 | 3 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 1.1212 | 1.25 | 2021-02 | 0 | 0
683 | CR0012356 | CTASK0023696 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 4 | 4 | 2020-12-15 02:00 | 2020-12-01 02:00 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare | DG Declare EDI Transmit | [Deployment] OPUS DG malfunction- data exchange between the modules | 2020-05-08 16:57 | 2020-09-03 | 2020-09-02 15:54 | 2020-11-11 18:55 | 2020-11-19 16:23 |  | 2020-12-15 10:00 | 2020-12-15 09:30 | 2020-12-10 10:03 | 2021-01-14 14:00 | CR0012356 | Service ManagementBooking/DocumentationOperationEU DG DeclareDG Declare EDI Transmit | OPUS-BKG-MFT-E | 2020-W51 | 2020-12 | 220 | 216 | 220.7102 | 6 | 1 | 1 | 0.04 | 193506 | 0.9 | 0 | 0 | 1 | 3 | 1 | 3 | 4 | 30 | 0 | 0.85714 | 2020-05 | 1 | 1
684 | CR0012356 | CTASK0022938 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 40 | 40 | 2020-10-23 13:00 | 2020-10-09 13:00 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare | DG Declare EDI Transmit | [Development-Testing] OPUS DG malfunction- data exchange between the modules (Change Require) | 2020-05-08 16:57 | 2020-09-03 | 2020-09-02 15:54 | 2020-11-11 18:55 | 2020-11-19 16:23 |  | 2020-12-15 10:00 | 2020-12-15 09:30 | 2020-12-10 10:03 | 2021-01-14 14:00 | CR0012356 | Service ManagementBooking/DocumentationOperationEU DG DeclareDG Declare EDI Transmit | OPUS-BKG-MFT-E | 2020-W51 | 2020-12 | 220 | 216 | 220.7102 | 6 | 1 | 1 | 0.04 | 193506 | 0.9 | 0 | 0 | 1 | 3 | 1 | 3 | 4 | 30 | 0 | 0.85714 | 2020-05 | 1 | 1
685 | CR0012356 | CTASK0019651 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 44 | 40 | 2020-06-27 10:33 | 2020-06-02 10:32 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare | DG Declare EDI Transmit | [Test] OPUS DG malfunction- data exchange between the modules | 2020-05-08 16:57 | 2020-09-03 | 2020-09-02 15:54 | 2020-11-11 18:55 | 2020-11-19 16:23 |  | 2020-12-15 10:00 | 2020-12-15 09:30 | 2020-12-10 10:03 | 2021-01-14 14:00 | CR0012356 | Service ManagementBooking/DocumentationOperationEU DG DeclareDG Declare EDI Transmit | OPUS-BKG-MFT-E | 2020-W51 | 2020-12 | 220 | 216 | 220.7102 | 6 | 1 | 1 | 0.04 | 193506 | 0.9 | 0 | 0 | 1 | 3 | 1 | 3 | 4 | 30 | 0 | 0.85714 | 2020-05 | 1 | 1
686 | CR0012356 | CTASK0020931 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 60 | 60 | 2020-08-31 19:00 | 2020-06-29 19:00 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare | DG Declare EDI Transmit | [Development-Testing] OPUS DG malfunction- data exchange between the modules (Change Require) | 2020-05-08 16:57 | 2020-09-03 | 2020-09-02 15:54 | 2020-11-11 18:55 | 2020-11-19 16:23 |  | 2020-12-15 10:00 | 2020-12-15 09:30 | 2020-12-10 10:03 | 2021-01-14 14:00 | CR0012356 | Service ManagementBooking/DocumentationOperationEU DG DeclareDG Declare EDI Transmit | OPUS-BKG-MFT-E | 2020-W51 | 2020-12 | 220 | 216 | 220.7102 | 6 | 1 | 1 | 0.04 | 193506 | 0.9 | 0 | 0 | 1 | 3 | 1 | 3 | 4 | 30 | 0 | 0.85714 | 2020-05 | 1 | 1
687 | CR0012356 | CTASK0019487 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 4 | 4 | 2020-04-13 16:42 | 2020-04-08 16:42 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare | DG Declare EDI Transmit | [Analysis]OPUS DG malfunction- data exchange between the modules | 2020-05-08 16:57 | 2020-09-03 | 2020-09-02 15:54 | 2020-11-11 18:55 | 2020-11-19 16:23 |  | 2020-12-15 10:00 | 2020-12-15 09:30 | 2020-12-10 10:03 | 2021-01-14 14:00 | CR0012356 | Service ManagementBooking/DocumentationOperationEU DG DeclareDG Declare EDI Transmit | OPUS-BKG-MFT-E | 2020-W51 | 2020-12 | 220 | 216 | 220.7102 | 6 | 1 | 1 | 0.04 | 193506 | 0.9 | 0 | 0 | 1 | 3 | 1 | 3 | 4 | 30 | 0 | 0.85714 | 2020-05 | 1 | 1
688 | CR0012356 | CTASK0019636 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 68 | 68 | 2020-06-27 10:33 | 2020-05-05 10:32 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare | DG Declare EDI Transmit | [Develop] OPUS DG malfunction- data exchange between the modules | 2020-05-08 16:57 | 2020-09-03 | 2020-09-02 15:54 | 2020-11-11 18:55 | 2020-11-19 16:23 |  | 2020-12-15 10:00 | 2020-12-15 09:30 | 2020-12-10 10:03 | 2021-01-14 14:00 | CR0012356 | Service ManagementBooking/DocumentationOperationEU DG DeclareDG Declare EDI Transmit | OPUS-BKG-MFT-E | 2020-W51 | 2020-12 | 220 | 216 | 220.7102 | 6 | 1 | 1 | 0.04 | 193506 | 0.9 | 0 | 0 | 1 | 3 | 1 | 3 | 4 | 30 | 0 | 0.85714 | 2020-05 | 1 | 1
689 | CR0012692 | CTASK0020381 | Closed | OPUS-PRD | Son Nguyen The | 23 | 44 | 2020-06-26 09:00 | 2020-05-29 09:00 | Container | Service Management | Product Catalog | Network Link (Ocean) | Ocean Route Management |  | GHQ - Ocean Route Transit Time Calculation logic correction | 2020-06-15 12:52 | 2020-06-19 18:00 | 2020-06-18 17:12 | 2020-06-25 10:08 | 2020-11-25 09:17 |  | 2020-12-01 10:00 | 2020-12-01 11:00 | 2020-11-26 13:24 | 2020-12-08 11:09 | CR0012692 | Service ManagementProduct CatalogNetwork Link (Ocean)Ocean Route Management | OPUS-PRD | 2020-W49 | 2020-12 | 23 | 44 | 168.8809 | 1 | 1 | 1 | 0.01 | 193531 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 10 | 30 | 0 | 0 | 2020-06 | 0 | 0
690 | CR0012309 | CTASK0019613 | Closed | OPUS-BKG-M | Loc Tran | 30 | 30 | 2020-04-25 02:00 | 2020-04-16 16:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Development] Additional Items for Customer Code Request Form - RPA BOT | 2020-04-16 13:15 | 2020-05-07 | 2020-05-06 14:51 | 2020-06-09 23:41 | 2020-06-09 23:54 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-10 16:14 | 2020-07-17 13:00 | CR0012309 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W25 | 2020-06 | 63 | 62 | 60.8645 | 5 | 1 | 1 | 0.04 | 193503 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.36364 | 2020-04 | 0 | 0
691 | CR0012309 | CTASK0019618 | Closed | OPUS-BKG-M | Loc Tran | 3 | 3 | 2020-06-12 12:09 | 2020-06-09 12:09 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Deployment] Additional Items for Customer Code Request Form - RPA BOT | 2020-04-16 13:15 | 2020-05-07 | 2020-05-06 14:51 | 2020-06-09 23:41 | 2020-06-09 23:54 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-10 16:14 | 2020-07-17 13:00 | CR0012309 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W25 | 2020-06 | 63 | 62 | 60.8645 | 5 | 1 | 1 | 0.04 | 193503 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.36364 | 2020-04 | 0 | 0
692 | CR0012309 | CTASK0018507 | Closed | OPUS-BKG-M | Loc Tran | 15 | 15 | 2020-02-27 18:00 | 2020-02-20 15:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Design] Additional Items for Customer Code Request Form - RPA BOT | 2020-04-16 13:15 | 2020-05-07 | 2020-05-06 14:51 | 2020-06-09 23:41 | 2020-06-09 23:54 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-10 16:14 | 2020-07-17 13:00 | CR0012309 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W25 | 2020-06 | 63 | 62 | 60.8645 | 5 | 1 | 1 | 0.04 | 193503 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.36364 | 2020-04 | 0 | 0
693 | CR0012309 | CTASK0020409 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-06-03 02:00 | 2020-06-01 11:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Development] Additional Items for Customer Code Request Form - RPA BOT | 2020-04-16 13:15 | 2020-05-07 | 2020-05-06 14:51 | 2020-06-09 23:41 | 2020-06-09 23:54 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-10 16:14 | 2020-07-17 13:00 | CR0012309 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W25 | 2020-06 | 63 | 62 | 60.8645 | 5 | 1 | 1 | 0.04 | 193503 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.36364 | 2020-04 | 0 | 0
694 | CR0012309 | CTASK0019616 | Closed | OPUS-BKG-M | Loc Tran | 9 | 8 | 2020-04-25 02:00 | 2020-04-17 11:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Customer Information [Alt+5] | [Testing] Additional Items for Customer Code Request Form - RPA BOT | 2020-04-16 13:15 | 2020-05-07 | 2020-05-06 14:51 | 2020-06-09 23:41 | 2020-06-09 23:54 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-10 16:14 | 2020-07-17 13:00 | CR0012309 | Service ManagementBooking/DocumentationOutbound DocB/L CreationCustomer Information [Alt+5] | OPUS-BKG-M | 2020-W25 | 2020-06 | 63 | 62 | 60.8645 | 5 | 1 | 1 | 0.04 | 193503 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.36364 | 2020-04 | 0 | 0
695 | CR0013254 | CTASK0024066 | Closed | OPUS-MNR | Tien Le | 40 | 40 | 2021-01-23 01:22 | 2021-01-01 10:21 | Container | Equipment Management | M&R |  |  |  | GHQ - New MNR Cost Code Creation | 2021-03-05 16:35 | 2021-03-19 19:30 | 2021-03-19 12:03 | 2021-03-29 09:26 | 2021-03-29 10:51 |  | 2021-03-31 10:00 | 2021-03-31 12:00 | 2021-03-30 10:39 | 2021-03-31 12:39 | CR0013254 | Equipment ManagementM&R | OPUS-MNR | 2021-W13 | 2021-03 | 69 | 70 | 25.726 | 3 | 2 | 2 | 0.11 | 173286 | 2.4 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0 | 0 | 2021-03 | 0 | 0
696 | CR0013254 | CTASK0025805 | Closed | OPUS-SAP | Chuong Ta | 10 | 10 | 2021-03-19 15:48 | 2021-03-11 15:48 | Container | Equipment Management | M&R |  |  |  | GHQ - New MNR Cost Code Creation | 2021-03-05 16:35 | 2021-03-19 19:30 | 2021-03-19 12:03 | 2021-03-29 09:26 | 2021-03-29 10:51 |  | 2021-03-31 10:00 | 2021-03-31 12:00 | 2021-03-30 10:39 | 2021-03-31 12:39 | CR0013254 | Equipment ManagementM&R | OPUS-MNR | 2021-W13 | 2021-03 | 69 | 70 | 25.726 | 3 | 2 | 2 | 0.11 | 183379 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0.32 | 0.38462 | 2021-03 | 0 | 0
697 | CR0013254 | CTASK0024065 | Closed | OPUS-MNR | Tien Le | 19 | 20 | 2021-01-01 01:20 | 2020-12-21 10:19 | Container | Equipment Management | M&R |  |  |  | [Documentation]GHQ - New MNR Cost Code Creation | 2021-03-05 16:35 | 2021-03-19 19:30 | 2021-03-19 12:03 | 2021-03-29 09:26 | 2021-03-29 10:51 |  | 2021-03-31 10:00 | 2021-03-31 12:00 | 2021-03-30 10:39 | 2021-03-31 12:39 | CR0013254 | Equipment ManagementM&R | OPUS-MNR | 2021-W13 | 2021-03 | 69 | 70 | 25.726 | 3 | 2 | 2 | 0.11 | 173286 | 2.4 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0 | 0 | 2021-03 | 0 | 0
698 | CR0011702 | CTASK0016433 | Closed | OPUS-BKG-M | Kieu Le | 103 | 104 | 2019-12-13 10:23 | 2019-11-25 10:23 | Container | Sales Management | Space Control | Allocation Control |  |  | OPUS SPC Standby - Adding Weight as constraint | 2019-11-05 12:29 | 2019-12-20 | 2019-12-20 00:07 | 2020-01-27 22:29 | 2020-02-05 17:48 |  | 2020-02-11 17:47 | 2020-02-12 09:47 | 2020-02-05 18:15 | 2020-03-12 13:00 | CR0011702 | Sales ManagementSpace ControlAllocation Control | OPUS-SPC | 2020-W7 | 2020-02 | 103 | 104 | 98.2211 | 1 | 1 | 1 | 0.04 | 153106 | 1.1 | 0 | 0 | 0 | 2 | 1 | 2 | 5 | 13 | 0 | 0.4 | 2019-11 | 0 | 0
699 | CR0010711 | CTASK0014273 | Closed | OPUS-BKG-M | Nhan Le | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | EUA BKG // L.OFC/Rep Assignment Logic | 2019-05-20 10:48 | 2019-06-17 18:43 | 2019-06-10 18:15 | 2019-07-25 17:51 | 2019-07-25 18:01 |  | 2019-07-30 10:00 | 2019-07-30 11:34 | 2019-07-26 16:03 | 2019-08-29 13:00 | CR0010711 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W31 | 2019-07 | 74 | 40 | 70.9666 | 5 | 1 | 2 | 0.02 | 183353 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-05 | 0 | 0
700 | CR0010711 | CTASK0013990 | Closed | OPUS-BKG-M | Nhan Le | 16 | 16 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | EUA BKG // L.OFC/Rep Assignment Logic | 2019-05-20 10:48 | 2019-06-17 18:43 | 2019-06-10 18:15 | 2019-07-25 17:51 | 2019-07-25 18:01 |  | 2019-07-30 10:00 | 2019-07-30 11:34 | 2019-07-26 16:03 | 2019-08-29 13:00 | CR0010711 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W31 | 2019-07 | 74 | 40 | 70.9666 | 5 | 1 | 2 | 0.02 | 183353 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-05 | 0 | 0
701 | CR0010711 | CTASK0012129 | Closed | OPUS-BKG-M | Kieu Le | 40 | 40 | 2019-05-31 14:49 | 2019-05-13 14:48 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | EUA BKG // L.OFC/Rep Assignment Logic | 2019-05-20 10:48 | 2019-06-17 18:43 | 2019-06-10 18:15 | 2019-07-25 17:51 | 2019-07-25 18:01 |  | 2019-07-30 10:00 | 2019-07-30 11:34 | 2019-07-26 16:03 | 2019-08-29 13:00 | CR0010711 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W31 | 2019-07 | 74 | 40 | 70.9666 | 5 | 1 | 2 | 0.02 | 153106 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-05 | 0 | 0
702 | CR0010711 | CTASK0015353 | Closed | OPUS-BKG-M | Nhan Le | 38 | 38 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | EUA BKG // L.OFC/Rep Assignment Logic | 2019-05-20 10:48 | 2019-06-17 18:43 | 2019-06-10 18:15 | 2019-07-25 17:51 | 2019-07-25 18:01 |  | 2019-07-30 10:00 | 2019-07-30 11:34 | 2019-07-26 16:03 | 2019-08-29 13:00 | CR0010711 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W31 | 2019-07 | 74 | 40 | 70.9666 | 5 | 1 | 2 | 0.02 | 183353 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-05 | 0 | 0
703 | CR0010711 | CTASK0014498 | Closed | OPUS-BKG-M | Nhan Le | 12 | 12 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | EUA BKG // L.OFC/Rep Assignment Logic | 2019-05-20 10:48 | 2019-06-17 18:43 | 2019-06-10 18:15 | 2019-07-25 17:51 | 2019-07-25 18:01 |  | 2019-07-30 10:00 | 2019-07-30 11:34 | 2019-07-26 16:03 | 2019-08-29 13:00 | CR0010711 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W31 | 2019-07 | 74 | 40 | 70.9666 | 5 | 1 | 2 | 0.02 | 183353 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-05 | 0 | 0
704 | CR0012431 | CTASK0019467 | Closed | OPUS-BKG-M | Loc Tran | 5 | 5 | 2020-08-31 18:42 | 2020-08-01 18:42 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] BKG_BOOKING missing update on default column such as UPD_DT, UPD_USR_ID | 2020-06-29 10:01 | 2020-07-23 | 2020-07-20 15:46 | 2020-07-23 08:41 | 2020-07-28 09:47 |  | 2020-08-11 10:00 | 2020-08-11 10:00 | 2020-08-07 11:36 | 2020-09-10 13:00 | CR0012431 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W33 | 2020-08 | 61 | 57 | 42.9996 | 5 | 1 | 1 | 0.06 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 30 | 0 | 0.36364 | 2020-06 | 0 | 0
705 | CR0012431 | CTASK0019200 | Closed | OPUS-BKG-M | Loc Tran | 30 | 30 | 2020-04-01 19:43 | 2020-03-26 19:43 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal] BKG_BOOKING missing update on default column such as UPD_DT, UPD_USR_ID | 2020-06-29 10:01 | 2020-07-23 | 2020-07-20 15:46 | 2020-07-23 08:41 | 2020-07-28 09:47 |  | 2020-08-11 10:00 | 2020-08-11 10:00 | 2020-08-07 11:36 | 2020-09-10 13:00 | CR0012431 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W33 | 2020-08 | 61 | 57 | 42.9996 | 5 | 1 | 1 | 0.06 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 30 | 0 | 0.36364 | 2020-06 | 0 | 0
706 | CR0012431 | CTASK0019463 | Closed | OPUS-BKG-M | Loc Tran | 10 | 10 | 2020-07-06 18:27 | 2020-06-29 18:27 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] BKG_BOOKING missing update on default column such as UPD_DT, UPD_USR_ID | 2020-06-29 10:01 | 2020-07-23 | 2020-07-20 15:46 | 2020-07-23 08:41 | 2020-07-28 09:47 |  | 2020-08-11 10:00 | 2020-08-11 10:00 | 2020-08-07 11:36 | 2020-09-10 13:00 | CR0012431 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W33 | 2020-08 | 61 | 57 | 42.9996 | 5 | 1 | 1 | 0.06 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 30 | 0 | 0.36364 | 2020-06 | 0 | 0
707 | CR0012431 | CTASK0019464 | Closed | OPUS-BKG-M | Loc Tran | 10 | 10 | 2020-07-07 19:31 | 2020-07-01 19:31 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] BKG_BOOKING missing update on default column such as UPD_DT, UPD_USR_ID | 2020-06-29 10:01 | 2020-07-23 | 2020-07-20 15:46 | 2020-07-23 08:41 | 2020-07-28 09:47 |  | 2020-08-11 10:00 | 2020-08-11 10:00 | 2020-08-07 11:36 | 2020-09-10 13:00 | CR0012431 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W33 | 2020-08 | 61 | 57 | 42.9996 | 5 | 1 | 1 | 0.06 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 30 | 0 | 0.36364 | 2020-06 | 0 | 0
708 | CR0012431 | CTASK0021304 | Closed | OPUS-BKG-M | Loc Tran | 6 | 2 | 2020-07-21 19:38 | 2020-07-14 19:38 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Pair Testing] [CLT Internal] BKG_BOOKING missing update on default column such as UPD_DT, UPD_USR_ID | 2020-06-29 10:01 | 2020-07-23 | 2020-07-20 15:46 | 2020-07-23 08:41 | 2020-07-28 09:47 |  | 2020-08-11 10:00 | 2020-08-11 10:00 | 2020-08-07 11:36 | 2020-09-10 13:00 | CR0012431 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W33 | 2020-08 | 61 | 57 | 42.9996 | 5 | 1 | 1 | 0.06 | 193503 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 30 | 0 | 0.36364 | 2020-06 | 0 | 0
709 | CR0013851 | CTASK0027565 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 31 | 29 | 2021-07-02 10:32 | 2021-06-14 10:31 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Development+ Testing+ Deployment] LA - MX Cargo Release - EDI to declare weight of the commodity by the container | 2021-06-15 11:15 | 2021-07-09 23:14 | 2021-07-07 17:29 | 2021-07-09 10:11 | 2021-07-12 10:50 |  | 2021-07-20 10:47 | 2021-07-20 12:57 | 2021-07-14 15:42 | 2021-07-29 14:00 | CR0013851 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W29 | 2021-07 | 31 | 29 | 34.9807 | 1 | 1 | 1 | 0.03 | 193512 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 28 | 0.2963 | 0.3125 | 2021-06 | 0 | 0
710 | CR0013756 | CTASK0026869 | Closed | OPUS-SCO | Chuong Ta | 23 | 22 | 2021-05-31 09:34 | 2021-05-07 09:34 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Chuong Ta][MAY 2021]LA ADDITIIONAL FILTER OPTION IN DISPUTE MANAGEMENT AND INFO IN OTS UI | 2021-05-07 16:23 | 2021-06-30 16:22 | 2021-05-24 10:02 | 2021-06-23 09:10 | 2021-06-23 09:16 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-23 16:35 | 2021-07-29 14:00 | CR0013756 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W26 | 2021-06 | 41 | 40 | 52.7341 | 3 | 1 | 3 | 0.03 | 183379 | 2.2 | 2 | 2 | 0 | 1 | 1 | 2 | 16 | 53 | 0.32 | 0.375 | 2021-05 | 2 | 1
711 | CR0013756 | CTASK0026870 | Closed | OPUS-SCO | Nguyen Ha Vi | 10 | 10 | 2021-05-31 09:35 | 2021-05-07 09:35 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Vi Nguyen][MAY 2021]LA ADDITIIONAL FILTER OPTION IN DISPUTE MANAGEMENT AND INFO IN OTS UI | 2021-05-07 16:23 | 2021-06-30 16:22 | 2021-05-24 10:02 | 2021-06-23 09:10 | 2021-06-23 09:16 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-23 16:35 | 2021-07-29 14:00 | CR0013756 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W26 | 2021-06 | 41 | 40 | 52.7341 | 3 | 1 | 3 | 0.03 | 203664 | 0.9 | 2 | 2 | 0 | 1 | 1 | 2 | 16 | 53 | 1.8182 | 1.2857 | 2021-05 | 2 | 1
712 | CR0013756 | CTASK0026872 | Closed | OPUS-SCO | Lien Le | 8 | 8 | 2021-05-31 09:39 | 2021-05-07 09:39 | Container | Statement Management | Statement Account Receivable | Dispute Manager |  |  | [Lien Le][MAY 2021]LA ADDITIIONAL FILTER OPTION IN DISPUTE MANAGEMENT AND INFO IN OTS UI | 2021-05-07 16:23 | 2021-06-30 16:22 | 2021-05-24 10:02 | 2021-06-23 09:10 | 2021-06-23 09:16 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-23 16:35 | 2021-07-29 14:00 | CR0013756 | Statement ManagementStatement Account ReceivableDispute Manager | OPUS-SCO | 2021-W26 | 2021-06 | 41 | 40 | 52.7341 | 3 | 1 | 3 | 0.03 | 193441 | 2.2 | 2 | 2 | 0 | 1 | 1 | 2 | 16 | 53 | 0.42308 | 0 | 2021-05 | 2 | 1
713 | CR0011616 | CTASK0017107 | Closed | OPUS-BKG-M | Thien Lai | 12 | 12 |  |  | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Estimate] NA *BKG* Issue with Auto EDI Hold and Standby | 2019-12-05 18:45 | 2020-01-07 | 2020-01-06 12:05 | 2020-01-30 05:15 | 2020-02-07 11:52 | 2020-01-06 12:08 | 2020-02-18 11:52 | 2020-02-18 11:14 | 2020-02-12 23:12 | 2020-02-25 01:36 | CR0011616 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W8 | 2020-02 | 43 | 36 | 74.7131 | 3 | 1 | 1 | 0.02 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 13 | 0 | 0.52941 | 2019-12 | 0 | 0
714 | CR0011616 | CTASK0017134 | Closed | OPUS-BKG-M | Thien Lai | 29 | 34 | 2019-12-20 13:49 | 2019-12-09 13:49 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | NA *BKG* Issue with Auto EDI Hold and Standby | 2019-12-05 18:45 | 2020-01-07 | 2020-01-06 12:05 | 2020-01-30 05:15 | 2020-02-07 11:52 | 2020-01-06 12:08 | 2020-02-18 11:52 | 2020-02-18 11:14 | 2020-02-12 23:12 | 2020-02-25 01:36 | CR0011616 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W8 | 2020-02 | 43 | 36 | 74.7131 | 3 | 1 | 1 | 0.02 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 13 | 0 | 0.52941 | 2019-12 | 0 | 0
715 | CR0011616 | CTASK0018569 | Closed | OPUS-BKG-M | Thien Lai | 2 | 2 | 2020-02-11 17:49 | 2020-02-07 17:49 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] NA *BKG* Issue with Auto EDI Hold and Standby | 2019-12-05 18:45 | 2020-01-07 | 2020-01-06 12:05 | 2020-01-30 05:15 | 2020-02-07 11:52 | 2020-01-06 12:08 | 2020-02-18 11:52 | 2020-02-18 11:14 | 2020-02-12 23:12 | 2020-02-25 01:36 | CR0011616 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W8 | 2020-02 | 43 | 36 | 74.7131 | 3 | 1 | 1 | 0.02 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 13 | 0 | 0.52941 | 2019-12 | 0 | 0
716 | CR0013056 | CTASK0026008 | Closed | OPUS-DMT | Cuong Nguyen | 99 | 130 | 2021-05-07 20:00 | 2021-03-29 09:00 | Container | Service Management | Demurrage/Detention | Billing | Invoice Creation & Issue |  | [CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2021-03-23 08:26 | 2021-05-07 20:00 | 2021-05-04 13:49 | 2021-06-01 09:27 | 2021-06-01 11:12 |  | 2021-06-29 10:00 | 2021-06-29 09:59 | 2021-06-01 13:53 | 2021-07-23 13:45 | CR0013056 | Service ManagementDemurrage/DetentionBillingInvoice Creation & Issue | OPUS-DMT | 2021-W26 | 2021-06 | 99 | 130 | 98.0653 | 1 | 1 | 1 | 0.06 | 193529 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 16 | 53 | 0.11538 | 0.058824 | 2021-03 | 0 | 0
717 | CR0010651 | CTASK0025028 | Closed | OPUS-SCO | Lien Le | 24 | 24 | 2021-01-31 16:49 | 2021-01-10 16:49 | Container | Service Management | A/R Invoice | Invoice Inquiry | Invoice Inquiry by B/L No |  | [Lien Le] modify CLEAR PRL | 2019-04-22 15:28 | 2019-05-31 15:28 | 2019-05-09 17:03 | 2021-04-23 00:33 | 2021-04-28 14:49 |  | 2021-05-04 10:00 | 2021-05-18 09:15 | 2021-04-30 13:44 | 2021-06-24 14:00 | CR0010651 | Service ManagementA/R InvoiceInvoice InquiryInvoice Inquiry by B/L No | OPUS-INV | 2021-W18 | 2021-05 | 24 | 24 | 742.7719 | 1 | 1 | 1 | 0 | 193441 | 0.1 | 2 | 0 | 0 | 1 | 1 | 5 | 4 | 28 | 0.42308 | 0 | 2019-04 | 0 | 0
718 | CR0011772 | CTASK0024068 | Closed | OPUS-BKG-M | Kieu Le | 15 | 15 | 2020-12-31 17:46 | 2020-12-01 17:46 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Testing] Mapping Data Source Change (Coparn 301F) FTX Segment Yard : JPTYO03 + JPYOK04 Receiver ID: MOTKT + YOKMO | 2020-03-23 09:14 | 2020-12-31 | 2020-12-30 13:26 | 2021-01-22 13:52 | 2021-01-22 14:13 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-22 17:59 | 2021-03-04 14:00 | CR0011772 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2021-W5 | 2021-02 | 30 | 30 | 316.0316 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 1 | 0 | 0 | 1 | 1 | 4 | 8 | 21 | 0.22951 | 0.4 | 2020-03 | 0 | 0
719 | CR0011772 | CTASK0019050 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2020-03-27 18:47 | 2020-03-23 18:47 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Development] Mapping Data Source Change (Coparn 301F) FTX Segment Yard : JPTYO03 + JPYOK04 Receiver ID: MOTKT + YOKMO | 2020-03-23 09:14 | 2020-12-31 | 2020-12-30 13:26 | 2021-01-22 13:52 | 2021-01-22 14:13 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-22 17:59 | 2021-03-04 14:00 | CR0011772 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2021-W5 | 2021-02 | 30 | 30 | 316.0316 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 1 | 0 | 0 | 1 | 1 | 4 | 8 | 21 | 0.22951 | 0.4 | 2020-03 | 0 | 0
720 | CR0011772 | CTASK0019051 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2020-04-17 18:49 | 2020-03-23 18:49 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Testing] Mapping Data Source Change (Coparn 301F) FTX Segment Yard : JPTYO03 + JPYOK04 Receiver ID: MOTKT + YOKMO | 2020-03-23 09:14 | 2020-12-31 | 2020-12-30 13:26 | 2021-01-22 13:52 | 2021-01-22 14:13 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-22 17:59 | 2021-03-04 14:00 | CR0011772 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2021-W5 | 2021-02 | 30 | 30 | 316.0316 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 1 | 0 | 0 | 1 | 1 | 4 | 8 | 21 | 0.22951 | 0.4 | 2020-03 | 0 | 0
721 | CR0011772 | CTASK0018901 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-03-16 19:45 | 2020-03-11 19:45 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Design] Mapping Data Source Change (Coparn 301F) FTX Segment Yard : JPTYO03 + JPYOK04 Receiver ID: MOTKT + YOKMO | 2020-03-23 09:14 | 2020-12-31 | 2020-12-30 13:26 | 2021-01-22 13:52 | 2021-01-22 14:13 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-22 17:59 | 2021-03-04 14:00 | CR0011772 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2021-W5 | 2021-02 | 30 | 30 | 316.0316 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 1 | 0 | 0 | 1 | 1 | 4 | 8 | 21 | 0.22951 | 0.4 | 2020-03 | 0 | 0
722 | CR0011772 | CTASK0019055 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-02-26 18:53 | 2021-02-01 02:53 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Deployment] Mapping Data Source Change (Coparn 301F) FTX Segment Yard : JPTYO03 + JPYOK04 Receiver ID: MOTKT + YOKMO | 2020-03-23 09:14 | 2020-12-31 | 2020-12-30 13:26 | 2021-01-22 13:52 | 2021-01-22 14:13 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-22 17:59 | 2021-03-04 14:00 | CR0011772 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2021-W5 | 2021-02 | 30 | 30 | 316.0316 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 1 | 0 | 0 | 1 | 1 | 4 | 8 | 21 | 0.22951 | 0.4 | 2020-03 | 0 | 0
723 | CR0012339 | CTASK0020986 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 8 | 8 | 2020-07-06 19:30 | 2020-07-01 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | US Cargo Release | [Deployment] NA *EDI* Vendor - Request for Change Request - Enhance TDC315 Flat File with required flags. | 2020-04-24 15:31 | 2020-06-05 20:31 | 2020-06-05 16:38 | 2020-06-25 21:47 | 2020-06-26 14:33 |  | 2020-07-07 14:32 | 2020-07-07 10:46 | 2020-06-26 16:12 | 2020-07-08 21:35 | CR0012339 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseUS Cargo Release | OPUS-BKG-IB | 2020-W28 | 2020-07 | 76 | 76 | 73.9584 | 3 | 1 | 1 | 0.04 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 27 | 0 | 0.18519 | 2020-04 | 0 | 0
724 | CR0012339 | CTASK0019456 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 60 | 60 | 2020-04-30 19:00 | 2020-04-09 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | US Cargo Release | [Development+Testing+Deployment] NA *EDI* Vendor - Request for Change Request - Enhance TDC315 Flat File with required flags. | 2020-04-24 15:31 | 2020-06-05 20:31 | 2020-06-05 16:38 | 2020-06-25 21:47 | 2020-06-26 14:33 |  | 2020-07-07 14:32 | 2020-07-07 10:46 | 2020-06-26 16:12 | 2020-07-08 21:35 | CR0012339 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseUS Cargo Release | OPUS-BKG-IB | 2020-W28 | 2020-07 | 76 | 76 | 73.9584 | 3 | 1 | 1 | 0.04 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 27 | 0 | 0.18519 | 2020-04 | 0 | 0
725 | CR0012339 | CTASK0019455 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 8 | 8 | 2020-04-08 19:30 | 2020-04-07 17:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | US Cargo Release | [Estimation] NA *EDI* Vendor - Request for Change Request - Enhance TDC315 Flat File with required flags. | 2020-04-24 15:31 | 2020-06-05 20:31 | 2020-06-05 16:38 | 2020-06-25 21:47 | 2020-06-26 14:33 |  | 2020-07-07 14:32 | 2020-07-07 10:46 | 2020-06-26 16:12 | 2020-07-08 21:35 | CR0012339 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseUS Cargo Release | OPUS-BKG-IB | 2020-W28 | 2020-07 | 76 | 76 | 73.9584 | 3 | 1 | 1 | 0.04 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 27 | 0 | 0.18519 | 2020-04 | 0 | 0
726 | CR0011986 | CTASK0017420 | Closed | OPUS-PRI | Nhien Nguyen | 8 | 10 |  |  | Container | Statement Management | Statement Account Receivable |  |  |  | EUA - Addition Columns and Search Criteria for Dispute Management Function | 2019-12-02 10:59 | 2019-12-31 10:59 | 2019-12-04 14:10 | 2019-12-05 18:30 | 2019-12-05 18:34 |  | 2019-12-10 18:33 | 2019-12-10 11:02 | 2019-12-05 19:10 | 2020-01-07 00:20 | CR0011986 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2019-W50 | 2019-12 | 8 | 10 | 8.315 | 1 | 1 | 1 | 0.05 | 183364 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 18 | 0 | 0 | 2019-12 | 0 | 0
727 | CR0012319 | CTASK0020153 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 4 | 4 | 2020-05-18 19:30 | 2020-05-12 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Deployment] AR - ARG Advance Manifest // new FROB XML method and EOV XML changes | 2020-03-18 15:33 | 2020-04-03 | 2020-04-01 18:55 | 2020-04-24 04:01 | 2020-05-11 13:21 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-15 23:10 | 2020-06-18 13:00 | CR0012319 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W21 | 2020-05 | 76 | 76 | 61.7685 | 3 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.18519 | 2020-03 | 0 | 0
728 | CR0012319 | CTASK0018704 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 6 | 6 | 2020-03-04 19:30 | 2020-03-02 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Estimation] AR - ARG Advance Manifest // new FROB XML method and EOV XML changes | 2020-03-18 15:33 | 2020-04-03 | 2020-04-01 18:55 | 2020-04-24 04:01 | 2020-05-11 13:21 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-15 23:10 | 2020-06-18 13:00 | CR0012319 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W21 | 2020-05 | 76 | 76 | 61.7685 | 3 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.18519 | 2020-03 | 0 | 0
729 | CR0012319 | CTASK0018747 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 66 | 66 | 2020-03-26 19:30 | 2020-03-05 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Development+Testing+Deployment]AR - ARG Advance Manifest // new FROB XML method and EOV XML changes | 2020-03-18 15:33 | 2020-04-03 | 2020-04-01 18:55 | 2020-04-24 04:01 | 2020-05-11 13:21 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-15 23:10 | 2020-06-18 13:00 | CR0012319 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W21 | 2020-05 | 76 | 76 | 61.7685 | 3 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.18519 | 2020-03 | 0 | 0
730 | CR0013503 | CTASK0024713 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-01-16 02:00 | 2021-01-15 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] [CLT Internal] GLOBAL *EDI* Request to check the APERAK EDI file sent to cargosmart. | 2021-01-20 11:17 | 2021-02-06 | 2021-02-04 11:47 | 2021-02-10 15:09 | 2021-02-10 15:14 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-10 15:16 | 2021-04-02 14:00 | CR0013503 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W9 | 2021-03 | 34 | 34 | 40.9463 | 4 | 1 | 1 | 0.03 | 193525 | 1.6 | 1 | 0 | 0 | 1 | 1 | 1 | 13 | 46 | 0.41667 | 0.47368 | 2021-01 | 0 | 0
731 | CR0013503 | CTASK0024714 | Closed | OPUS-BKG-EBKG | Vinh Tran | 6 | 6 | 2021-01-26 02:00 | 2021-01-25 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] [CLT Internal] GLOBAL *EDI* Request to check the APERAK EDI file sent to cargosmart. | 2021-01-20 11:17 | 2021-02-06 | 2021-02-04 11:47 | 2021-02-10 15:09 | 2021-02-10 15:14 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-10 15:16 | 2021-04-02 14:00 | CR0013503 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W9 | 2021-03 | 34 | 34 | 40.9463 | 4 | 1 | 1 | 0.03 | 193525 | 1.6 | 1 | 0 | 0 | 1 | 1 | 1 | 13 | 46 | 0.41667 | 0.47368 | 2021-01 | 0 | 0
732 | CR0013503 | CTASK0024715 | Closed | OPUS-BKG-EBKG | Vinh Tran | 20 | 20 | 2021-01-30 02:00 | 2021-01-25 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] [CLT Internal] GLOBAL *EDI* Request to check the APERAK EDI file sent to cargosmart. | 2021-01-20 11:17 | 2021-02-06 | 2021-02-04 11:47 | 2021-02-10 15:09 | 2021-02-10 15:14 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-10 15:16 | 2021-04-02 14:00 | CR0013503 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W9 | 2021-03 | 34 | 34 | 40.9463 | 4 | 1 | 1 | 0.03 | 193525 | 1.6 | 1 | 0 | 0 | 1 | 1 | 1 | 13 | 46 | 0.41667 | 0.47368 | 2021-01 | 0 | 0
733 | CR0013503 | CTASK0024716 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-02-27 02:00 | 2021-02-22 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] [CLT Internal] GLOBAL *EDI* Request to check the APERAK EDI file sent to cargosmart. | 2021-01-20 11:17 | 2021-02-06 | 2021-02-04 11:47 | 2021-02-10 15:09 | 2021-02-10 15:14 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-10 15:16 | 2021-04-02 14:00 | CR0013503 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W9 | 2021-03 | 34 | 34 | 40.9463 | 4 | 1 | 1 | 0.03 | 193525 | 1.6 | 1 | 0 | 0 | 1 | 1 | 1 | 13 | 46 | 0.41667 | 0.47368 | 2021-01 | 0 | 0
734 | CR0014013 | CTASK0027540 | Closed | OPUS-DOM | Giang Nguyen Hoang | 22 | 21 | 2021-06-30 13:30 | 2021-06-14 13:30 | Container | Service Management | Domestic | Accounting | Invoice |  | [202106] NA *DOM* Update to Invoice layout | 2021-06-14 13:22 | 2021-06-30 21:00 | 2021-06-22 14:15 | 2021-06-28 14:24 | 2021-06-29 08:56 |  | 2021-06-30 10:00 | 2021-07-01 10:50 | 2021-06-30 10:06 | 2021-07-29 14:00 | CR0014013 | Service ManagementDomesticAccountingInvoice | OPUS-DOM | 2021-W26 | 2021-06 | 44 | 42 | 15.8599 | 2 | 1 | 2 | 0.11 | 183440 | 2.3 | 0 | 0 | 0 | 1 | 1 | 1 | 16 | 53 | 0 | 0 | 2021-06 | 0 | 0
735 | CR0014013 | CTASK0027335 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 22 | 21 | 2021-06-30 11:12 | 2021-06-02 11:12 | Container | Service Management | Domestic | Accounting | Invoice |  | [202106] NA *DOM* Update to Invoice layout | 2021-06-14 13:22 | 2021-06-30 21:00 | 2021-06-22 14:15 | 2021-06-28 14:24 | 2021-06-29 08:56 |  | 2021-06-30 10:00 | 2021-07-01 10:50 | 2021-06-30 10:06 | 2021-07-29 14:00 | CR0014013 | Service ManagementDomesticAccountingInvoice | OPUS-DOM | 2021-W26 | 2021-06 | 44 | 42 | 15.8599 | 2 | 1 | 2 | 0.11 | 183432 | 2.3 | 0 | 0 | 0 | 1 | 1 | 1 | 16 | 53 | 0 | 0.22222 | 2021-06 | 0 | 0
736 | CR0010990 | CTASK0020028 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 14 | 14 | 2020-05-13 18:58 | 2020-05-11 18:58 | Container | Service Management | Booking/Documentation | Inbound Doc |  |  | [Estimation] EUA - BL and Vessel Name to be included in subject of documents sent to customers from OPUS | 2020-05-26 13:57 | 2020-06-30 22:56 | 2020-06-30 17:02 | 2020-08-19 10:28 | 2020-10-12 16:19 |  | 2020-10-27 16:19 | 2020-10-27 10:38 | 2020-10-21 16:52 | 2020-11-03 17:42 | CR0010990 | Service ManagementBooking/DocumentationInbound Doc | OPUS-BKG-IB | 2020-W44 | 2020-10 | 73 | 73 | 154.0982 | 3 | 1 | 1 | 0.02 | 193512 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 7 | 20 | 0 | 0.5 | 2020-05 | 0 | 0
737 | CR0010990 | CTASK0020386 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 39 | 39 | 2020-06-22 16:05 | 2020-06-01 16:05 | Container | Service Management | Booking/Documentation | Inbound Doc |  |  | [Development+ Testing+ Deployment]EUA - BL and Vessel Name to be included in subject of documents sent to customers from OPUS | 2020-05-26 13:57 | 2020-06-30 22:56 | 2020-06-30 17:02 | 2020-08-19 10:28 | 2020-10-12 16:19 |  | 2020-10-27 16:19 | 2020-10-27 10:38 | 2020-10-21 16:52 | 2020-11-03 17:42 | CR0010990 | Service ManagementBooking/DocumentationInbound Doc | OPUS-BKG-IB | 2020-W44 | 2020-10 | 73 | 73 | 154.0982 | 3 | 1 | 1 | 0.02 | 193512 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 7 | 20 | 0 | 0.5 | 2020-05 | 0 | 0
738 | CR0010990 | CTASK0020960 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 20 | 20 | 2020-07-08 11:52 | 2020-07-01 11:52 | Container | Service Management | Booking/Documentation | Inbound Doc |  |  | [Development+ Testing+ Deployment]EUA - BL and Vessel Name to be included in subject of documents sent to customers from OPUS | 2020-05-26 13:57 | 2020-06-30 22:56 | 2020-06-30 17:02 | 2020-08-19 10:28 | 2020-10-12 16:19 |  | 2020-10-27 16:19 | 2020-10-27 10:38 | 2020-10-21 16:52 | 2020-11-03 17:42 | CR0010990 | Service ManagementBooking/DocumentationInbound Doc | OPUS-BKG-IB | 2020-W44 | 2020-10 | 73 | 73 | 154.0982 | 3 | 1 | 1 | 0.02 | 193512 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 7 | 20 | 0 | 0.5 | 2020-05 | 0 | 0
739 | CR0012674 | CTASK0020780 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 15 | 15 | 2020-12-10 01:00 | 2020-11-18 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Revenue Audit |  | [Testing] Change of Revenue Audit UI | 2020-11-06 11:06 | 2020-12-05 | 2020-12-03 18:03 | 2021-03-15 09:18 | 2021-03-15 15:45 |  | 2021-03-30 10:00 | 2021-03-30 09:50 | 2021-03-16 09:14 | 2021-04-29 14:00 | CR0012674 | Service ManagementBooking/DocumentationOutbound DocRevenue Audit | OPUS-BKG-CHG | 2021-W13 | 2021-03 | 104 | 87 | 143.9538 | 4 | 1 | 1 | 0.03 | 193470 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 46 | 0.36842 | 0.17391 | 2020-11 | 0 | 0
740 | CR0012674 | CTASK0020779 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 47 | 43 | 2021-03-20 01:00 | 2020-11-03 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Revenue Audit |  | [Development] Change of Revenue Audit UI | 2020-11-06 11:06 | 2020-12-05 | 2020-12-03 18:03 | 2021-03-15 09:18 | 2021-03-15 15:45 |  | 2021-03-30 10:00 | 2021-03-30 09:50 | 2021-03-16 09:14 | 2021-04-29 14:00 | CR0012674 | Service ManagementBooking/DocumentationOutbound DocRevenue Audit | OPUS-BKG-CHG | 2021-W13 | 2021-03 | 104 | 87 | 143.9538 | 4 | 1 | 1 | 0.03 | 193470 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 46 | 0.36842 | 0.17391 | 2020-11 | 0 | 0
741 | CR0012674 | CTASK0020716 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 16 | 16 | 2020-08-05 19:30 | 2020-06-17 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Revenue Audit |  | [Estimation] Change of Revenue Audit UI | 2020-11-06 11:06 | 2020-12-05 | 2020-12-03 18:03 | 2021-03-15 09:18 | 2021-03-15 15:45 |  | 2021-03-30 10:00 | 2021-03-30 09:50 | 2021-03-16 09:14 | 2021-04-29 14:00 | CR0012674 | Service ManagementBooking/DocumentationOutbound DocRevenue Audit | OPUS-BKG-CHG | 2021-W13 | 2021-03 | 104 | 87 | 143.9538 | 4 | 1 | 1 | 0.03 | 193470 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 46 | 0.36842 | 0.17391 | 2020-11 | 0 | 0
742 | CR0012674 | CTASK0024393 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 26 | 13 | 2021-04-01 02:00 | 2021-03-09 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Revenue Audit |  | [Deployment] Change of Revenue Audit UI | 2020-11-06 11:06 | 2020-12-05 | 2020-12-03 18:03 | 2021-03-15 09:18 | 2021-03-15 15:45 |  | 2021-03-30 10:00 | 2021-03-30 09:50 | 2021-03-16 09:14 | 2021-04-29 14:00 | CR0012674 | Service ManagementBooking/DocumentationOutbound DocRevenue Audit | OPUS-BKG-CHG | 2021-W13 | 2021-03 | 104 | 87 | 143.9538 | 4 | 1 | 1 | 0.03 | 193470 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 46 | 0.36842 | 0.17391 | 2020-11 | 0 | 0
743 | CR0013871 | CTASK0027239 | Closed | OPUS-DMT | Cuong Nguyen | 34 | 75 | 2021-07-09 20:00 | 2021-05-24 08:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2021-06-22 13:08 | 2021-07-09 20:00 | 2021-07-07 12:59 | 2021-08-03 09:10 | 2021-08-03 09:27 |  | 2021-08-10 10:00 | 2021-08-10 09:56 | 2021-08-03 10:07 | 2021-08-12 10:07 | CR0013871 | Service ManagementDemurrage/Detention | OPUS-DMT | 2021-W32 | 2021-08 | 34 | 75 | 48.8697 | 1 | 1 | 1 | 0.06 | 193529 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 22 | 0.11538 | 0.22222 | 2021-06 | 0 | 0
744 | CR0013274 | CTASK0023569 | Closed | OPUS-BKG-M | Kieu Le | 1 | 10 | 2020-12-31 09:49 | 2020-11-16 09:49 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | To Develop Booking TAT Report on monthly basis directly in OPUS. | 2020-11-19 15:04 | 2021-01-01 | 2020-12-30 19:22 | 2021-02-10 14:08 | 2021-02-10 14:22 |  | 2021-04-13 10:00 | 2021-04-07 09:51 | 2021-02-18 09:16 | 2021-05-07 14:00 | CR0013274 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W15 | 2021-04 | 6 | 15 | 144.7887 | 2 | 1 | 2 | 0 | 153106 | 2.1 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 27 | 0 | 0.13043 | 2020-11 | 0 | 0
745 | CR0013274 | CTASK0026260 | Closed | OPUS-BKG-M | Loc Tran | 5 | 5 | 2021-04-30 12:28 | 2021-04-01 12:28 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | To Develop Booking TAT Report on monthly basis directly in OPUS. | 2020-11-19 15:04 | 2021-01-01 | 2020-12-30 19:22 | 2021-02-10 14:08 | 2021-02-10 14:22 |  | 2021-04-13 10:00 | 2021-04-07 09:51 | 2021-02-18 09:16 | 2021-05-07 14:00 | CR0013274 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W15 | 2021-04 | 6 | 15 | 144.7887 | 2 | 1 | 2 | 0 | 193503 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 27 | 0 | 0.28571 | 2020-11 | 0 | 0
746 | CR0010932 | CTASK0016063 | Closed | OPUS-BKG-M | Nam Nguyen | 48 | 25 | 2019-10-25 15:09 | 2019-10-14 15:09 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | GHQ SYM - Booking Cancel: Allow users to update remarks for booking cancellation | 2019-10-14 19:18 | 2019-11-12 | 2019-10-30 16:19 | 2019-11-28 09:45 | 2019-11-28 12:48 | 2019-10-30 16:19 | 2019-12-10 12:48 | 2019-12-10 09:30 | 2019-11-29 12:38 | 2020-01-10 14:00 | CR0010932 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W50 | 2019-12 | 48 | 25 | 56.7295 | 1 | 1 | 1 | 0.02 | 123048 | 1 | 0 | 0 | 1 | 1 | 1 | 2 | 8 | 18 | 0 | 0.46154 | 2019-10 | 1 | 1
747 | CR0013117 | CTASK0022993 | Closed | OPUS-PRI | Nhien Nguyen | 49 | 50 | 2020-10-31 16:58 | 2020-10-01 16:58 | Container | Sales Management | Pricing | Surcharge | Surcharge Creation |  | NA *PRI* (Tiger SDI) Add two surcharge attributes in Surcharge Creation/Inquiry | 2020-10-14 11:13 | 2020-10-31 11:13 | 2020-10-29 16:12 | 2020-11-20 16:14 | 2020-11-26 09:09 |  | 2020-12-01 09:09 | 2020-12-01 14:21 | 2020-11-27 09:21 | 2021-01-01 14:00 | CR0013117 | Sales ManagementPricingSurchargeSurcharge Creation | OPUS-PRI | 2020-W49 | 2020-12 | 49 | 50 | 47.9137 | 1 | 1 | 1 | 0.04 | 183364 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 10 | 30 | 0 | 1.2 | 2020-10 | 0 | 0
748 | CR0010335 | CTASK0015876 | Closed | OPUS-TES | Thai Nguyen | 92 | 92 |  |  | Container | Service Management | TML INV |  |  |  | [actual] TES Prepayment & Offset | 2019-05-07 10:52 | 2019-05-21 10:51 | 2019-05-21 09:01 | 2019-11-22 17:26 | 2019-11-25 13:18 |  | 2019-12-10 23:00 | 2019-12-10 10:44 | 2019-11-28 11:54 | 2019-12-10 19:29 | CR0010335 | Service ManagementTML INV | OPUS-TES | 2019-W50 | 2019-12 | 227 | 160 | 217.5054 | 7 | 1 | 2 | 0.03 | 173249 | 0.6 | 0 | 0 | 0 | 2 | 1 | 3 | 8 | 18 | 0 | 0.6 | 2019-05 | 0 | 0
749 | CR0010335 | CTASK0013982 | Closed | OPUS-TES | Thai Nguyen | 10 | 10 |  |  | Container | Service Management | TML INV |  |  |  | [actual] TES Prepayment & Offset | 2019-05-07 10:52 | 2019-05-21 10:51 | 2019-05-21 09:01 | 2019-11-22 17:26 | 2019-11-25 13:18 |  | 2019-12-10 23:00 | 2019-12-10 10:44 | 2019-11-28 11:54 | 2019-12-10 19:29 | CR0010335 | Service ManagementTML INV | OPUS-TES | 2019-W50 | 2019-12 | 227 | 160 | 217.5054 | 7 | 1 | 2 | 0.03 | 173249 | 0.6 | 0 | 0 | 0 | 2 | 1 | 3 | 8 | 18 | 0 | 0.6 | 2019-05 | 0 | 0
750 | CR0010335 | CTASK0012073 | Closed | OPUS-TES | Thai Nguyen | 160 | 160 | 2019-05-22 17:01 | 2019-03-26 17:01 | Container | Service Management | TML INV |  |  |  | TES Prepayment & Offset | 2019-05-07 10:52 | 2019-05-21 10:51 | 2019-05-21 09:01 | 2019-11-22 17:26 | 2019-11-25 13:18 |  | 2019-12-10 23:00 | 2019-12-10 10:44 | 2019-11-28 11:54 | 2019-12-10 19:29 | CR0010335 | Service ManagementTML INV | OPUS-TES | 2019-W50 | 2019-12 | 227 | 160 | 217.5054 | 7 | 1 | 2 | 0.03 | 173249 | 0.6 | 0 | 0 | 0 | 2 | 1 | 3 | 8 | 18 | 0 | 0.6 | 2019-05 | 0 | 0
751 | CR0010335 | CTASK0013672 | Closed | OPUS-TES | Manh Nguyen | 40 | 40 |  |  | Container | Service Management | TML INV |  |  |  | [actual]TES Prepayment & Offset | 2019-05-07 10:52 | 2019-05-21 10:51 | 2019-05-21 09:01 | 2019-11-22 17:26 | 2019-11-25 13:18 |  | 2019-12-10 23:00 | 2019-12-10 10:44 | 2019-11-28 11:54 | 2019-12-10 19:29 | CR0010335 | Service ManagementTML INV | OPUS-TES | 2019-W50 | 2019-12 | 227 | 160 | 217.5054 | 7 | 1 | 2 | 0.03 | 153138 | 0.6 | 0 | 0 | 0 | 2 | 1 | 3 | 8 | 18 | 0 | 0 | 2019-05 | 0 | 0
752 | CR0010335 | CTASK0013303 | Closed | OPUS-TES | Thai Nguyen | 40 | 40 |  |  | Container | Service Management | TML INV |  |  |  | [actual] TES Prepayment & Offset | 2019-05-07 10:52 | 2019-05-21 10:51 | 2019-05-21 09:01 | 2019-11-22 17:26 | 2019-11-25 13:18 |  | 2019-12-10 23:00 | 2019-12-10 10:44 | 2019-11-28 11:54 | 2019-12-10 19:29 | CR0010335 | Service ManagementTML INV | OPUS-TES | 2019-W50 | 2019-12 | 227 | 160 | 217.5054 | 7 | 1 | 2 | 0.03 | 173249 | 0.6 | 0 | 0 | 0 | 2 | 1 | 3 | 8 | 18 | 0 | 0.6 | 2019-05 | 0 | 0
753 | CR0010335 | CTASK0014268 | Closed | OPUS-TES | Thai Nguyen | 5 | 5 |  |  | Container | Service Management | TML INV |  |  |  | [actual] TES Prepayment & Offset | 2019-05-07 10:52 | 2019-05-21 10:51 | 2019-05-21 09:01 | 2019-11-22 17:26 | 2019-11-25 13:18 |  | 2019-12-10 23:00 | 2019-12-10 10:44 | 2019-11-28 11:54 | 2019-12-10 19:29 | CR0010335 | Service ManagementTML INV | OPUS-TES | 2019-W50 | 2019-12 | 227 | 160 | 217.5054 | 7 | 1 | 2 | 0.03 | 173249 | 0.6 | 0 | 0 | 0 | 2 | 1 | 3 | 8 | 18 | 0 | 0.6 | 2019-05 | 0 | 0
754 | CR0010335 | CTASK0013608 | Closed | OPUS-TES | Thai Nguyen | 40 | 40 |  |  | Container | Service Management | TML INV |  |  |  | [actual] TES Prepayment & Offset | 2019-05-07 10:52 | 2019-05-21 10:51 | 2019-05-21 09:01 | 2019-11-22 17:26 | 2019-11-25 13:18 |  | 2019-12-10 23:00 | 2019-12-10 10:44 | 2019-11-28 11:54 | 2019-12-10 19:29 | CR0010335 | Service ManagementTML INV | OPUS-TES | 2019-W50 | 2019-12 | 227 | 160 | 217.5054 | 7 | 1 | 2 | 0.03 | 173249 | 0.6 | 0 | 0 | 0 | 2 | 1 | 3 | 8 | 18 | 0 | 0.6 | 2019-05 | 0 | 0
755 | CR0011166 | CTASK0019801 | Closed | OPUS-BKG-CHG | Nam Nguyen | 51 | 51 | 2020-08-08 | 2020-06-29 09:00 | Container | Sales Management | Pricing |  |  |  | [Test + Deployment] EAS - PRI/BKG - Add <Pay Term>, <Pay Office> and <Payer Code> for Rate in S/C and RFA to support BKG Auto-rating | 2020-06-03 15:59 | 2020-07-21 23:00 | 2020-07-21 17:01 | 2021-01-27 09:31 | 2021-02-02 13:21 |  | 2021-02-16 13:22 | 2021-02-16 14:16 | 2021-02-02 16:16 | 2021-03-19 14:00 | CR0011166 | Sales ManagementPricing | OPUS-PRI | 2021-W7 | 2021-02 | 176 | 174 | 257.8906 | 5 | 2 | 2 | 0.03 | 123048 | 1.7 | 1 | 0 | 0 | 2 | 1 | 3 | 5 | 21 | 0.22222 | 0.46154 | 2020-06 | 0 | 0
756 | CR0011166 | CTASK0019684 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 6 | 6 | 2020-04-22 01:59 | 2020-04-17 19:22 | Container | Sales Management | Pricing |  |  |  | [Estimation] EAS - PRI/BKG - Add <Pay Term>, <Pay Office> and <Payer Code> for Rate in S/C and RFA to support BKG Auto-rating | 2020-06-03 15:59 | 2020-07-21 23:00 | 2020-07-21 17:01 | 2021-01-27 09:31 | 2021-02-02 13:21 |  | 2021-02-16 13:22 | 2021-02-16 14:16 | 2021-02-02 16:16 | 2021-03-19 14:00 | CR0011166 | Sales ManagementPricing | OPUS-PRI | 2021-W7 | 2021-02 | 176 | 174 | 257.8906 | 5 | 2 | 2 | 0.03 | 193470 | 1.2 | 1 | 0 | 0 | 2 | 1 | 3 | 5 | 21 | 0.36842 | 0.17391 | 2020-06 | 0 | 0
757 | CR0011166 | CTASK0025179 | Closed | OPUS-BKG-CHG | Nam Nguyen | 15 | 13 | 2021-02-19 19:02 | 2021-02-04 19:02 | Container | Sales Management | Pricing |  |  |  | [Test + Deployment] EAS - PRI/BKG - Add <Pay Term>, <Pay Office> and <Payer Code> for Rate in S/C and RFA to support BKG Auto-rating | 2020-06-03 15:59 | 2020-07-21 23:00 | 2020-07-21 17:01 | 2021-01-27 09:31 | 2021-02-02 13:21 |  | 2021-02-16 13:22 | 2021-02-16 14:16 | 2021-02-02 16:16 | 2021-03-19 14:00 | CR0011166 | Sales ManagementPricing | OPUS-PRI | 2021-W7 | 2021-02 | 176 | 174 | 257.8906 | 5 | 2 | 2 | 0.03 | 123048 | 1.7 | 1 | 0 | 0 | 2 | 1 | 3 | 5 | 21 | 0.22222 | 0.46154 | 2020-06 | 0 | 0
758 | CR0011166 | CTASK0019799 | Closed | OPUS-BKG-CHG | Nam Nguyen | 81 | 81 | 2020-07-01 | 2020-06-06 09:00 | Container | Sales Management | Pricing |  |  |  | [Development] EAS - PRI/BKG - Add <Pay Term>, <Pay Office> and <Payer Code> for Rate in S/C and RFA to support BKG Auto-rating | 2020-06-03 15:59 | 2020-07-21 23:00 | 2020-07-21 17:01 | 2021-01-27 09:31 | 2021-02-02 13:21 |  | 2021-02-16 13:22 | 2021-02-16 14:16 | 2021-02-02 16:16 | 2021-03-19 14:00 | CR0011166 | Sales ManagementPricing | OPUS-PRI | 2021-W7 | 2021-02 | 176 | 174 | 257.8906 | 5 | 2 | 2 | 0.03 | 123048 | 1.7 | 1 | 0 | 0 | 2 | 1 | 3 | 5 | 21 | 0.22222 | 0.46154 | 2020-06 | 0 | 0
759 | CR0011166 | CTASK0019624 | Closed | OPUS-BKG-CHG | Nam Nguyen | 23 | 23 | 2020-04-21 19:30 | 2020-04-15 19:30 | Container | Sales Management | Pricing |  |  |  | [Estimation] EAS - PRI/BKG - Add <Pay Term>, <Pay Office> and <Payer Code> for Rate in S/C and RFA to support BKG Auto-rating | 2020-06-03 15:59 | 2020-07-21 23:00 | 2020-07-21 17:01 | 2021-01-27 09:31 | 2021-02-02 13:21 |  | 2021-02-16 13:22 | 2021-02-16 14:16 | 2021-02-02 16:16 | 2021-03-19 14:00 | CR0011166 | Sales ManagementPricing | OPUS-PRI | 2021-W7 | 2021-02 | 176 | 174 | 257.8906 | 5 | 2 | 2 | 0.03 | 123048 | 1.7 | 1 | 0 | 0 | 2 | 1 | 3 | 5 | 21 | 0.22222 | 0.46154 | 2020-06 | 0 | 0
760 | CR0014034 | CTASK0027666 | Closed | OPUS-SCE | Tran Le | 17 | 17 |  |  | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [Documentation][SCE][CLT Internal] CA Rail logic | 2021-06-24 13:11 | 2021-07-09 21:43 | 2021-07-09 10:33 | 2021-07-12 15:16 | 2021-07-14 12:15 |  | 2021-07-27 10:00 | 2021-07-27 10:00 | 2021-07-14 15:42 | 2021-08-04 14:00 | CR0014034 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2021-W30 | 2021-07 | 17 | 17 | 32.8676 | 2 | 1 | 1 | 0.02 | 193501 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.052632 | 0.076923 | 2021-06 | 0 | 0
761 | CR0014034 | CTASK0027667 | Closed | OPUS-SCE | Tran Le | 17 | 17 |  |  | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [SCE][CLT Internal] CA Rail logic | 2021-06-24 13:11 | 2021-07-09 21:43 | 2021-07-09 10:33 | 2021-07-12 15:16 | 2021-07-14 12:15 |  | 2021-07-27 10:00 | 2021-07-27 10:00 | 2021-07-14 15:42 | 2021-08-04 14:00 | CR0014034 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2021-W30 | 2021-07 | 17 | 17 | 32.8676 | 2 | 1 | 1 | 0.02 | 193501 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.052632 | 0.076923 | 2021-06 | 0 | 0
762 | CR0013788 | CTASK0026612 | Closed | OPUS-DMT | Cuong Nguyen | 1 | 1 | 2021-05-14 20:00 | 2021-05-03 08:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK2] CLV_Pair Test | 2021-05-03 14:13 | 2021-05-14 20:00 | 2021-05-13 13:05 | 2021-07-26 10:24 | 2021-07-27 07:59 |  | 2021-08-03 10:00 | 2021-08-03 10:05 | 2021-07-28 09:22 | 2021-08-10 14:00 | CR0013788 | Service ManagementDemurrage/Detention | OPUS-DMT | 2021-W31 | 2021-08 | 1 | 1 | 91.8244 | 1 | 1 | 1 | 0 | 193529 | 1.9 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 22 | 0 | 0.058824 | 2021-05 | 0 | 0
763 | CR0013559 | CTASK0025130 | Closed | OPUS-BKG-M | Loc Tran | 15 | 15 | 2021-03-31 11:29 | 2021-03-11 11:29 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Development][CLT Internal] Prevent the errors of retrieving null that occurs in DG prchecking of the booking including CFR number. | 2021-03-16 17:25 | 2021-04-15 | 2021-04-12 16:46 | 2021-04-27 11:11 | 2021-04-27 14:39 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-27 16:00 | 2021-06-10 14:00 | CR0013559 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W19 | 2021-05 | 49 | 49 | 55.6913 | 4 | 1 | 1 | 0.04 | 193503 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 6 | 28 | 0.33333 | 0.28571 | 2021-03 | 0 | 0
764 | CR0013559 | CTASK0025131 | Closed | OPUS-BKG-M | Loc Tran | 15 | 15 | 2021-03-31 19:12 | 2021-03-22 19:12 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Testing][CLT Internal] Prevent the errors of retrieving null that occurs in DG prchecking of the booking including CFR number. | 2021-03-16 17:25 | 2021-04-15 | 2021-04-12 16:46 | 2021-04-27 11:11 | 2021-04-27 14:39 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-27 16:00 | 2021-06-10 14:00 | CR0013559 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W19 | 2021-05 | 49 | 49 | 55.6913 | 4 | 1 | 1 | 0.04 | 193503 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 6 | 28 | 0.33333 | 0.28571 | 2021-03 | 0 | 0
765 | CR0013559 | CTASK0024915 | Closed | OPUS-BKG-M | Loc Tran | 13 | 15 | 2021-02-22 12:45 | 2021-02-01 12:44 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Design][CLT Internal] Prevent the errors of retrieving null that occurs in DG prchecking of the booking including CFR number. | 2021-03-16 17:25 | 2021-04-15 | 2021-04-12 16:46 | 2021-04-27 11:11 | 2021-04-27 14:39 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-27 16:00 | 2021-06-10 14:00 | CR0013559 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W19 | 2021-05 | 49 | 49 | 55.6913 | 4 | 1 | 1 | 0.04 | 193503 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 6 | 28 | 0.33333 | 0.28571 | 2021-03 | 0 | 0
766 | CR0013559 | CTASK0025132 | Closed | OPUS-BKG-M | Loc Tran | 6 | 4 | 2021-05-12 18:39 | 2021-05-03 18:39 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Deployment][CLT Internal] Prevent the errors of retrieving null that occurs in DG prchecking of the booking including CFR number. | 2021-03-16 17:25 | 2021-04-15 | 2021-04-12 16:46 | 2021-04-27 11:11 | 2021-04-27 14:39 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-04-27 16:00 | 2021-06-10 14:00 | CR0013559 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W19 | 2021-05 | 49 | 49 | 55.6913 | 4 | 1 | 1 | 0.04 | 193503 | 1.7 | 1 | 0 | 0 | 1 | 1 | 2 | 6 | 28 | 0.33333 | 0.28571 | 2021-03 | 0 | 0
767 | CR0010976 | CTASK0014839 | Closed | OPUS-BKG-MFT | Nhan Le | 28 | 28 | 2019-06-14 19:49 | 2019-06-10 19:48 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | (HBA) EUA¦ New EU Manifest form for Spain and upload of customs relevant data from Excel document for Spain customs interface | 2019-04-08 13:58 | 2019-09-01 | 2019-07-03 10:43 | 2020-01-07 20:07 | 2020-03-18 17:07 |  | 2020-04-07 09:30 | 2020-07-07 10:02 | 2020-03-18 17:48 | 2020-08-06 13:00 | CR0010976 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W15 | 2020-04 | 124 | 0 | 364.8141 | 6 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 16 | 0 | 0 | 2019-04 | 0 | 0
768 | CR0010976 | CTASK0013651 | Closed | OPUS-BKG-MFT | Nhan Le | 20 | 20 | 2019-07-06 19:49 | 2019-07-02 19:49 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | (HBA) EUA¦ New EU Manifest form for Spain and upload of customs relevant data from Excel document for Spain customs interface | 2019-04-08 13:58 | 2019-09-01 | 2019-07-03 10:43 | 2020-01-07 20:07 | 2020-03-18 17:07 |  | 2020-04-07 09:30 | 2020-07-07 10:02 | 2020-03-18 17:48 | 2020-08-06 13:00 | CR0010976 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W15 | 2020-04 | 124 | 0 | 364.8141 | 6 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 16 | 0 | 0 | 2019-04 | 0 | 0
769 | CR0010976 | CTASK0013325 | Closed | OPUS-BKG-MFT | Nhan Le | 12 | 12 | 2019-06-14 19:49 | 2019-06-12 19:49 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | (HBA) EUA¦ New EU Manifest form for Spain and upload of customs relevant data from Excel document for Spain customs interface | 2019-04-08 13:58 | 2019-09-01 | 2019-07-03 10:43 | 2020-01-07 20:07 | 2020-03-18 17:07 |  | 2020-04-07 09:30 | 2020-07-07 10:02 | 2020-03-18 17:48 | 2020-08-06 13:00 | CR0010976 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W15 | 2020-04 | 124 | 0 | 364.8141 | 6 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 16 | 0 | 0 | 2019-04 | 0 | 0
770 | CR0010976 | CTASK0014274 | Closed | OPUS-BKG-MFT | Nhan Le | 8 | 8 | 2019-06-15 19:49 | 2019-06-15 19:49 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | (HBA) EUA¦ New EU Manifest form for Spain and upload of customs relevant data from Excel document for Spain customs interface | 2019-04-08 13:58 | 2019-09-01 | 2019-07-03 10:43 | 2020-01-07 20:07 | 2020-03-18 17:07 |  | 2020-04-07 09:30 | 2020-07-07 10:02 | 2020-03-18 17:48 | 2020-08-06 13:00 | CR0010976 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W15 | 2020-04 | 124 | 0 | 364.8141 | 6 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 16 | 0 | 0 | 2019-04 | 0 | 0
771 | CR0010976 | CTASK0012847 | Closed | OPUS-BKG-MFT | Nhan Le | 40 | 40 | 2019-06-29 19:49 | 2019-06-23 19:49 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | (HBA) EUA¦ New EU Manifest form for Spain and upload of customs relevant data from Excel document for Spain customs interface | 2019-04-08 13:58 | 2019-09-01 | 2019-07-03 10:43 | 2020-01-07 20:07 | 2020-03-18 17:07 |  | 2020-04-07 09:30 | 2020-07-07 10:02 | 2020-03-18 17:48 | 2020-08-06 13:00 | CR0010976 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W15 | 2020-04 | 124 | 0 | 364.8141 | 6 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 16 | 0 | 0 | 2019-04 | 0 | 0
772 | CR0010976 | CTASK0014500 | Closed | OPUS-BKG-MFT | Nhan Le | 16 | 16 | 2019-07-09 19:49 | 2019-07-06 19:49 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | (HBA) EUA¦ New EU Manifest form for Spain and upload of customs relevant data from Excel document for Spain customs interface | 2019-04-08 13:58 | 2019-09-01 | 2019-07-03 10:43 | 2020-01-07 20:07 | 2020-03-18 17:07 |  | 2020-04-07 09:30 | 2020-07-07 10:02 | 2020-03-18 17:48 | 2020-08-06 13:00 | CR0010976 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W15 | 2020-04 | 124 | 0 | 364.8141 | 6 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 16 | 0 | 0 | 2019-04 | 0 | 0
773 | CR0012144 | CTASK0019706 | Closed | OPUS-BKG-M | Vinh Tran | 67 | 56 | 2020-05-23 02:00 | 2020-04-22 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Development] EUA - TRO/O; TRO/I - Multi Container Copy / Appointment Search / Multi-stop / TRO Notice | 2020-04-13 09:13 | 2020-06-18 | 2020-06-17 17:05 | 2020-09-03 17:54 | 2020-09-04 14:32 |  | 2020-09-29 10:00 | 2020-09-28 09:43 | 2020-09-04 18:11 | 2020-10-28 13:00 | CR0012144 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2020-W40 | 2020-09 | 141 | 124 | 169.0328 | 3 | 1 | 1 | 0.03 | 193525 | 0.9 | 0 | 0 | 1 | 2 | 1 | 3 | 5 | 36 | 0 | 0.45455 | 2020-04 | 1 | 1
774 | CR0012144 | CTASK0019896 | Closed | OPUS-BKG-M | Vinh Tran | 8 | 8 | 2020-05-14 02:00 | 2020-05-06 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Testing] EUA - TRO/O; TRO/I - Multi Container Copy / Appointment Search / Multi-stop / TRO Notice | 2020-04-13 09:13 | 2020-06-18 | 2020-06-17 17:05 | 2020-09-03 17:54 | 2020-09-04 14:32 |  | 2020-09-29 10:00 | 2020-09-28 09:43 | 2020-09-04 18:11 | 2020-10-28 13:00 | CR0012144 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2020-W40 | 2020-09 | 141 | 124 | 169.0328 | 3 | 1 | 1 | 0.03 | 193525 | 0.9 | 0 | 0 | 1 | 2 | 1 | 3 | 5 | 36 | 0 | 0.45455 | 2020-04 | 1 | 1
775 | CR0012144 | CTASK0020499 | Closed | OPUS-BKG-M | Vinh Tran | 66 | 60 | 2020-06-13 02:00 | 2020-06-01 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Development] EUA - TRO/O; TRO/I - Multi Container Copy / Appointment Search / Multi-stop / TRO Notice | 2020-04-13 09:13 | 2020-06-18 | 2020-06-17 17:05 | 2020-09-03 17:54 | 2020-09-04 14:32 |  | 2020-09-29 10:00 | 2020-09-28 09:43 | 2020-09-04 18:11 | 2020-10-28 13:00 | CR0012144 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2020-W40 | 2020-09 | 141 | 124 | 169.0328 | 3 | 1 | 1 | 0.03 | 193525 | 0.9 | 0 | 0 | 1 | 2 | 1 | 3 | 5 | 36 | 0 | 0.45455 | 2020-04 | 1 | 1
776 | CR0013142 | CTASK0023517 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 4 | 4 | 2020-11-11 19:00 | 2020-11-09 11:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Estimation] Add Shipper's TAA No. in Korea Manifest EDI | 2020-11-24 11:22 | 2020-12-04 | 2020-12-02 18:09 | 2020-12-28 13:23 | 2021-01-04 17:57 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2021-01-04 18:05 | 2021-02-12 14:00 | CR0013142 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W2 | 2021-01 | 30 | 30 | 48.9429 | 3 | 1 | 1 | 0.03 | 173280 | 1.9 | 0 | 0 | 0 | 1 | 1 | 1 | 14 | 40 | 0 | 0.18519 | 2020-11 | 0 | 0
777 | CR0013142 | CTASK0024552 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 8 | 8 | 2021-01-08 19:30 | 2021-01-04 09:30 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Development +Deployment + Inspection]Add Shipper's TAA No. in Korea Manifest EDI | 2020-11-24 11:22 | 2020-12-04 | 2020-12-02 18:09 | 2020-12-28 13:23 | 2021-01-04 17:57 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2021-01-04 18:05 | 2021-02-12 14:00 | CR0013142 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W2 | 2021-01 | 30 | 30 | 48.9429 | 3 | 1 | 1 | 0.03 | 173280 | 1.9 | 0 | 0 | 0 | 1 | 1 | 1 | 14 | 40 | 0 | 0.18519 | 2020-11 | 0 | 0
778 | CR0013142 | CTASK0023555 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 18 | 18 | 2020-11-30 19:30 | 2020-11-16 11:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Development +Deployment + Inspection]Add Shipper's TAA No. in Korea Manifest EDI | 2020-11-24 11:22 | 2020-12-04 | 2020-12-02 18:09 | 2020-12-28 13:23 | 2021-01-04 17:57 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2021-01-04 18:05 | 2021-02-12 14:00 | CR0013142 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W2 | 2021-01 | 30 | 30 | 48.9429 | 3 | 1 | 1 | 0.03 | 173280 | 1.9 | 0 | 0 | 0 | 1 | 1 | 1 | 14 | 40 | 0 | 0.18519 | 2020-11 | 0 | 0
779 | CR0012374 | CTASK0019177 | Closed | OPUS-SCG | Pham Khanh Van | 72 | 72 |  |  | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] [CLT Internal] DG EDI exceptional case handling | 2020-03-26 09:39 | 2020-04-24 09:38 | 2020-04-22 14:41 | 2020-06-15 15:01 | 2020-06-16 10:33 |  | 2020-06-23 09:30 | 2020-06-23 13:38 | 2020-06-16 11:05 | 2020-07-24 13:00 | CR0012374 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W26 | 2020-06 | 72 | 72 | 88.9939 | 1 | 1 | 1 | 0.03 | 193477 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0 | 2020-03 | 0 | 0
780 | CR0011839 | CTASK0016925 | Closed | OPUS-BKG-M | Thien Lai | 57 | 30 | 2020-01-17 23:24 | 2020-01-06 18:13 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | Add "Quantity of Flat Rack" for Breakbulk Applications. | 2020-01-06 15:54 | 2020-02-14 15:53 | 2020-02-12 10:47 | 2020-02-17 13:12 | 2020-02-17 17:29 |  | 2020-03-10 07:30 | 2020-03-10 11:12 | 2020-02-28 23:37 | 2020-04-09 13:00 | CR0011839 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W11 | 2020-03 | 125 | 66 | 63.6497 | 5 | 2 | 2 | 0.04 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0.52941 | 2020-01 | 0 | 0
781 | CR0011839 | CTASK0018728 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-03-10 16:04 | 2020-03-02 16:04 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Deployment] Add "Quantity of Flat Rack" for Breakbulk Applications. | 2020-01-06 15:54 | 2020-02-14 15:53 | 2020-02-12 10:47 | 2020-02-17 13:12 | 2020-02-17 17:29 |  | 2020-03-10 07:30 | 2020-03-10 11:12 | 2020-02-28 23:37 | 2020-04-09 13:00 | CR0011839 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W11 | 2020-03 | 125 | 66 | 63.6497 | 5 | 2 | 2 | 0.04 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0.52941 | 2020-01 | 0 | 0
782 | CR0011839 | CTASK0018570 | Closed | OPUS-BKG-M | Thien Lai | 2 | 2 | 2020-02-13 17:52 | 2020-02-13 17:52 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Development] Add "Quantity of Flat Rack" for Breakbulk Applications. | 2020-01-06 15:54 | 2020-02-14 15:53 | 2020-02-12 10:47 | 2020-02-17 13:12 | 2020-02-17 17:29 |  | 2020-03-10 07:30 | 2020-03-10 11:12 | 2020-02-28 23:37 | 2020-04-09 13:00 | CR0011839 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W11 | 2020-03 | 125 | 66 | 63.6497 | 5 | 2 | 2 | 0.04 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0.52941 | 2020-01 | 0 | 0
783 | CR0011839 | CTASK0017786 | Closed | OPUS-SCG | Pham Khanh Van | 40 | 30 | 2020-02-14 13:29 | 2020-01-20 13:29 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [SCG-CLV] Add "Quantity of Flat Rack" for Breakbulk Applications. | 2020-01-06 15:54 | 2020-02-14 15:53 | 2020-02-12 10:47 | 2020-02-17 13:12 | 2020-02-17 17:29 |  | 2020-03-10 07:30 | 2020-03-10 11:12 | 2020-02-28 23:37 | 2020-04-09 13:00 | CR0011839 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W11 | 2020-03 | 125 | 66 | 63.6497 | 5 | 2 | 2 | 0.04 | 193477 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0 | 2020-01 | 0 | 0
784 | CR0011839 | CTASK0017602 | Closed | OPUS-BKG-M | Thien Lai | 22 | 22 |  |  | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Estimate] Add "Quantity of Flat Rack" for Breakbulk Applications. | 2020-01-06 15:54 | 2020-02-14 15:53 | 2020-02-12 10:47 | 2020-02-17 13:12 | 2020-02-17 17:29 |  | 2020-03-10 07:30 | 2020-03-10 11:12 | 2020-02-28 23:37 | 2020-04-09 13:00 | CR0011839 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W11 | 2020-03 | 125 | 66 | 63.6497 | 5 | 2 | 2 | 0.04 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0.52941 | 2020-01 | 0 | 0
785 | CR0011516 | CTASK0015886 | Closed | OPUS-TPB | Manh Nguyen | 20 | 20 |  |  | Container | Service Management | 3rd Party Billing | TPB Process | TPB Invoice Setting |  | (actual) Flexibility to control due date logic (by office) for third party billing invoices | 2019-08-06 10:22 | 2019-08-31 | 2019-08-08 17:35 | 2019-08-14 01:10 | 2019-08-14 08:52 |  | 2019-08-20 12:00 | 2019-08-20 09:59 | 2019-08-15 03:37 | 2019-09-19 13:00 | CR0011516 | Service Management3rd Party BillingTPB ProcessTPB Invoice Setting | OPUS-TPB | 2019-W34 | 2019-08 | 20 | 0 | 14.0678 | 1 | 1 | 1 | 0 | 153138 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 6 | 0 | 0 | 2019-08 | 0 | 0
786 | CR0010999 | CTASK0011943 | Closed | OPUS-TPB | Thai Nguyen | 20 | 20 | 2019-03-25 11:34 | 2019-03-14 11:33 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | Request to add new TPB code | 2019-03-19 12:55 | 2019-03-20 12:54 | 2019-03-20 17:59 | 2019-03-21 10:54 | 2019-03-21 10:58 | 2019-03-21 10:50 | 2019-03-22 10:57 | 2019-03-29 15:00 | 2019-03-22 10:47 | 2019-04-02 17:08 | CR0010999 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2019-W12 | 2019-03 | 20 | 20 | 2.9175 | 1 | 1 | 1 | 0.29 | 173249 | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0.6 | 2019-03 | 0 | 0
787 | CR0013615 | CTASK0025988 | Closed | OPUS-BKG-OB | Nam Nguyen | 10 | 10 | 2021-03-29 21:10 | 2021-03-22 21:10 | Container | Service Management | Booking/Documentation | Booking |  |  | [Design] EDI 301 Customer Flat File enhancement In Support of HazCheck and TradeLens , also booking confirmation API | 2021-04-08 13:12 | 2021-05-08 | 2021-05-07 14:07 | 2021-05-21 15:12 | 2021-05-24 16:56 |  | 2021-06-01 10:00 | 2021-06-01 10:00 | 2021-05-25 13:36 | 2021-07-01 14:00 | CR0013615 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W22 | 2021-06 | 120 | 114 | 53.8664 | 4 | 1 | 1 | 0.09 | 123048 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 6 | 53 | 0.22222 | 0.047619 | 2021-04 | 0 | 0
788 | CR0013615 | CTASK0026154 | Closed | OPUS-BKG-OB | Nam Nguyen | 74 | 72 | 2021-04-23 21:10 | 2021-04-05 21:10 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development] EDI 301 Customer Flat File enhancement In Support of HazCheck and TradeLens , also booking confirmation API | 2021-04-08 13:12 | 2021-05-08 | 2021-05-07 14:07 | 2021-05-21 15:12 | 2021-05-24 16:56 |  | 2021-06-01 10:00 | 2021-06-01 10:00 | 2021-05-25 13:36 | 2021-07-01 14:00 | CR0013615 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W22 | 2021-06 | 120 | 114 | 53.8664 | 4 | 1 | 1 | 0.09 | 123048 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 6 | 53 | 0.22222 | 0.047619 | 2021-04 | 0 | 0
789 | CR0013615 | CTASK0026155 | Closed | OPUS-BKG-OB | Nam Nguyen | 28 | 24 | 2021-05-22 21:10 | 2021-04-05 21:10 | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing]EDI 301 Customer Flat File enhancement In Support of HazCheck and TradeLens , also booking confirmation API | 2021-04-08 13:12 | 2021-05-08 | 2021-05-07 14:07 | 2021-05-21 15:12 | 2021-05-24 16:56 |  | 2021-06-01 10:00 | 2021-06-01 10:00 | 2021-05-25 13:36 | 2021-07-01 14:00 | CR0013615 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W22 | 2021-06 | 120 | 114 | 53.8664 | 4 | 1 | 1 | 0.09 | 123048 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 6 | 53 | 0.22222 | 0.047619 | 2021-04 | 0 | 0
790 | CR0013615 | CTASK0026156 | Closed | OPUS-BKG-OB | Nam Nguyen | 8 | 8 | 2021-06-01 01:29 | 2021-05-24 01:29 | Container | Service Management | Booking/Documentation | Booking |  |  | [Deployment] EDI 301 Customer Flat File enhancement In Support of HazCheck and TradeLens , also booking confirmation API | 2021-04-08 13:12 | 2021-05-08 | 2021-05-07 14:07 | 2021-05-21 15:12 | 2021-05-24 16:56 |  | 2021-06-01 10:00 | 2021-06-01 10:00 | 2021-05-25 13:36 | 2021-07-01 14:00 | CR0013615 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W22 | 2021-06 | 120 | 114 | 53.8664 | 4 | 1 | 1 | 0.09 | 123048 | 2.5 | 1 | 0 | 0 | 2 | 1 | 2 | 6 | 53 | 0.22222 | 0.047619 | 2021-04 | 0 | 0
791 | CR0011336 | CTASK0016359 | Closed | OPUS-BKG-MFT | Nam Nguyen | 22 | 22 |  |  | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | Sent Time & Received Time should be retain after BKG VVD change | 2019-10-22 10:52 | 2019-11-29 08:28 | 2019-11-19 16:56 | 2020-01-07 20:08 | 2020-02-10 15:02 |  | 2020-03-03 10:02 | 2020-03-03 08:28 | 2020-02-11 18:12 | 2020-04-03 13:00 | CR0011336 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W10 | 2020-03 | 22 | 0 | 132.9648 | 1 | 1 | 1 | 0 | 123048 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 25 | 0 | 0.46154 | 2019-10 | 0 | 0
792 | CR0012542 | CTASK0019823 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-09-30 18:47 | 2020-09-01 18:47 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Split | [Deployment][CLT Internal] Split is not available for booking that calls same port more than once. | 2020-07-21 18:11 | 2020-08-27 | 2020-08-19 18:02 | 2020-08-20 12:16 | 2020-08-21 09:07 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-08-21 09:07 | 2020-09-15 10:10 | CR0012542 | Service ManagementBooking/DocumentationBookingBookingBooking Split | OPUS-BKG-M | 2020-W38 | 2020-09 | 44 | 44 | 55.6592 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-07 | 0 | 0
793 | CR0012542 | CTASK0019705 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2020-04-25 00:55 | 2020-04-20 10:55 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Split | [Design][CLT Internal] Split is not available for booking that calls same port more than once. | 2020-07-21 18:11 | 2020-08-27 | 2020-08-19 18:02 | 2020-08-20 12:16 | 2020-08-21 09:07 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-08-21 09:07 | 2020-09-15 10:10 | CR0012542 | Service ManagementBooking/DocumentationBookingBookingBooking Split | OPUS-BKG-M | 2020-W38 | 2020-09 | 44 | 44 | 55.6592 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-07 | 0 | 0
794 | CR0012542 | CTASK0019821 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-07-29 18:46 | 2020-07-21 18:46 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Split | [Testing][CLT Internal] Split is not available for booking that calls same port more than once. | 2020-07-21 18:11 | 2020-08-27 | 2020-08-19 18:02 | 2020-08-20 12:16 | 2020-08-21 09:07 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-08-21 09:07 | 2020-09-15 10:10 | CR0012542 | Service ManagementBooking/DocumentationBookingBookingBooking Split | OPUS-BKG-M | 2020-W38 | 2020-09 | 44 | 44 | 55.6592 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-07 | 0 | 0
795 | CR0012542 | CTASK0019820 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-08-21 12:13 | 2020-08-10 09:14 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Split | [Testing][CLT Internal] Split is not available for booking that calls same port more than once. | 2020-07-21 18:11 | 2020-08-27 | 2020-08-19 18:02 | 2020-08-20 12:16 | 2020-08-21 09:07 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-08-21 09:07 | 2020-09-15 10:10 | CR0012542 | Service ManagementBooking/DocumentationBookingBookingBooking Split | OPUS-BKG-M | 2020-W38 | 2020-09 | 44 | 44 | 55.6592 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-07 | 0 | 0
796 | CR0012542 | CTASK0019819 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-07-29 18:46 | 2020-07-21 18:46 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Split | [Development][CLT Internal] Split is not available for booking that calls same port more than once. | 2020-07-21 18:11 | 2020-08-27 | 2020-08-19 18:02 | 2020-08-20 12:16 | 2020-08-21 09:07 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-08-21 09:07 | 2020-09-15 10:10 | CR0012542 | Service ManagementBooking/DocumentationBookingBookingBooking Split | OPUS-BKG-M | 2020-W38 | 2020-09 | 44 | 44 | 55.6592 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-07 | 0 | 0
797 | CR0011787 | CTASK0017011 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 40 | 16 | 2019-11-21 14:00 | 2019-11-06 19:09 | Container | Service Management | Booking/Documentation | Manifest | Panama |  | LA - SERVICE MANAGEMENT - PANAMA MANIFEST | 2019-11-20 11:17 | 2019-11-28 | 2019-11-25 14:07 | 2019-11-26 05:13 | 2019-11-28 10:32 |  | 2019-12-03 10:00 | 2019-12-03 10:24 | 2019-11-30 02:09 | 2019-12-05 01:19 | CR0011787 | Service ManagementBooking/DocumentationManifestPanama | OPUS-BKG-MFT-M | 2019-W49 | 2019-12 | 40 | 16 | 12.9467 | 1 | 1 | 1 | 0.05 | 173280 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 18 | 0 | 0 | 2019-11 | 0 | 0
798 | CR0012315 | CTASK0018623 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-05-22 19:55 | 2020-05-18 09:54 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Deployment][CLT Internal] Special Cargo Rider Enhancement (DG) | 2020-02-27 12:15 | 2020-04-02 | 2020-03-23 10:01 | 2020-03-23 10:22 | 2020-05-18 13:33 |  | 2020-05-26 10:00 | 2020-05-26 10:00 | 2020-05-18 13:33 | 2020-05-26 10:23 | CR0012315 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W22 | 2020-05 | 42 | 48 | 88.9066 | 4 | 1 | 1 | 0.02 | 193567 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.52941 | 2020-02 | 0 | 0
799 | CR0012315 | CTASK0018618 | Closed | OPUS-BKG-M | Thien Lai | 22 | 28 | 2020-03-06 12:46 | 2020-03-02 12:46 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Development][CLT Internal] Special Cargo Rider Enhancement (DG) | 2020-02-27 12:15 | 2020-04-02 | 2020-03-23 10:01 | 2020-03-23 10:22 | 2020-05-18 13:33 |  | 2020-05-26 10:00 | 2020-05-26 10:00 | 2020-05-18 13:33 | 2020-05-26 10:23 | CR0012315 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W22 | 2020-05 | 42 | 48 | 88.9066 | 4 | 1 | 1 | 0.02 | 193567 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.52941 | 2020-02 | 0 | 0
800 | CR0012315 | CTASK0018585 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-02-25 20:51 | 2020-02-25 10:51 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Design] [CLT Internal] Special Cargo Rider Enhancement (DG) | 2020-02-27 12:15 | 2020-04-02 | 2020-03-23 10:01 | 2020-03-23 10:22 | 2020-05-18 13:33 |  | 2020-05-26 10:00 | 2020-05-26 10:00 | 2020-05-18 13:33 | 2020-05-26 10:23 | CR0012315 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W22 | 2020-05 | 42 | 48 | 88.9066 | 4 | 1 | 1 | 0.02 | 193567 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.52941 | 2020-02 | 0 | 0
801 | CR0012315 | CTASK0018619 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-03-13 12:47 | 2020-03-09 12:47 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Testing][CLT Internal] Special Cargo Rider Enhancement (DG) | 2020-02-27 12:15 | 2020-04-02 | 2020-03-23 10:01 | 2020-03-23 10:22 | 2020-05-18 13:33 |  | 2020-05-26 10:00 | 2020-05-26 10:00 | 2020-05-18 13:33 | 2020-05-26 10:23 | CR0012315 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W22 | 2020-05 | 42 | 48 | 88.9066 | 4 | 1 | 1 | 0.02 | 193567 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.52941 | 2020-02 | 0 | 0
802 | CR0014004 | CTASK0027278 | Closed | OPUS-BKG-M | Loc Tran | 8 | 10 | 2021-07-01 02:00 | 2021-06-01 18:32 | Container | Service Management | Booking/Documentation | Booking | Compulsory Firm |  | [Testing][CLT Internal] EDI is not triggered once compulsory firm | 2021-06-03 10:20 | 2021-07-01 02:00 | 2021-06-22 16:15 | 2021-06-23 16:42 | 2021-06-23 16:59 |  | 2021-07-06 10:00 | 2021-07-06 10:00 | 2021-06-24 13:05 | 2021-07-29 14:00 | CR0014004 | Service ManagementBooking/DocumentationBookingCompulsory Firm | OPUS-BKG-M | 2021-W27 | 2021-07 | 35 | 37 | 32.9859 | 4 | 1 | 1 | 0.05 | 193503 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0.33333 | 0.28571 | 2021-06 | 0 | 0
803 | CR0014004 | CTASK0027250 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2021-06-01 02:00 | 2021-05-20 18:36 | Container | Service Management | Booking/Documentation | Booking | Compulsory Firm |  | [Design] [CLT Internal] EDI is not triggered once compulsory firm | 2021-06-03 10:20 | 2021-07-01 02:00 | 2021-06-22 16:15 | 2021-06-23 16:42 | 2021-06-23 16:59 |  | 2021-07-06 10:00 | 2021-07-06 10:00 | 2021-06-24 13:05 | 2021-07-29 14:00 | CR0014004 | Service ManagementBooking/DocumentationBookingCompulsory Firm | OPUS-BKG-M | 2021-W27 | 2021-07 | 35 | 37 | 32.9859 | 4 | 1 | 1 | 0.05 | 193503 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0.33333 | 0.28571 | 2021-06 | 0 | 0
804 | CR0014004 | CTASK0027280 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-06-30 13:51 | 2021-06-28 11:51 | Container | Service Management | Booking/Documentation | Booking | Compulsory Firm |  | [Deployment][CLT Internal] EDI is not triggered once compulsory firm | 2021-06-03 10:20 | 2021-07-01 02:00 | 2021-06-22 16:15 | 2021-06-23 16:42 | 2021-06-23 16:59 |  | 2021-07-06 10:00 | 2021-07-06 10:00 | 2021-06-24 13:05 | 2021-07-29 14:00 | CR0014004 | Service ManagementBooking/DocumentationBookingCompulsory Firm | OPUS-BKG-M | 2021-W27 | 2021-07 | 35 | 37 | 32.9859 | 4 | 1 | 1 | 0.05 | 193503 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0.33333 | 0.28571 | 2021-06 | 0 | 0
805 | CR0014004 | CTASK0027277 | Closed | OPUS-BKG-M | Loc Tran | 15 | 15 | 2021-07-01 02:00 | 2021-06-01 18:31 | Container | Service Management | Booking/Documentation | Booking | Compulsory Firm |  | [Development][CLT Internal] EDI is not triggered once compulsory firm | 2021-06-03 10:20 | 2021-07-01 02:00 | 2021-06-22 16:15 | 2021-06-23 16:42 | 2021-06-23 16:59 |  | 2021-07-06 10:00 | 2021-07-06 10:00 | 2021-06-24 13:05 | 2021-07-29 14:00 | CR0014004 | Service ManagementBooking/DocumentationBookingCompulsory Firm | OPUS-BKG-M | 2021-W27 | 2021-07 | 35 | 37 | 32.9859 | 4 | 1 | 1 | 0.05 | 193503 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0.33333 | 0.28571 | 2021-06 | 0 | 0
806 | CR0011151 | CTASK0017006 | Closed | OPUS-BKG-M | Thien Lai | 12 | 12 |  |  | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Estimate] NA *BKG* Customizable Customer Notification for Exports (CSVC/EXP DOC) | 2019-11-19 16:28 | 2019-12-24 | 2019-12-09 16:46 | 2020-02-08 04:03 | 2020-02-14 12:41 | 2019-12-09 16:47 | 2020-03-03 12:41 | 2020-03-03 10:00 | 2020-02-20 03:37 | 2020-04-02 13:00 | CR0011151 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W10 | 2020-03 | 78 | 78 | 104.8422 | 3 | 1 | 1 | 0.03 | 193567 | 0.3 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 25 | 0 | 0.52941 | 2019-11 | 0 | 0
807 | CR0011151 | CTASK0018575 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-03-03 19:29 | 2020-02-24 19:28 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Deployment] NA *BKG* Customizable Customer Notification for Exports (CSVC/EXP DOC) | 2019-11-19 16:28 | 2019-12-24 | 2019-12-09 16:46 | 2020-02-08 04:03 | 2020-02-14 12:41 | 2019-12-09 16:47 | 2020-03-03 12:41 | 2020-03-03 10:00 | 2020-02-20 03:37 | 2020-04-02 13:00 | CR0011151 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W10 | 2020-03 | 78 | 78 | 104.8422 | 3 | 1 | 1 | 0.03 | 193567 | 0.3 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 25 | 0 | 0.52941 | 2019-11 | 0 | 0
808 | CR0011151 | CTASK0017032 | Closed | OPUS-BKG-M | Thien Lai | 58 | 70 | 2019-12-06 16:07 | 2019-11-25 16:07 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | NA *BKG* Customizable Customer Notification for Exports (CSVC/EXP DOC) | 2019-11-19 16:28 | 2019-12-24 | 2019-12-09 16:46 | 2020-02-08 04:03 | 2020-02-14 12:41 | 2019-12-09 16:47 | 2020-03-03 12:41 | 2020-03-03 10:00 | 2020-02-20 03:37 | 2020-04-02 13:00 | CR0011151 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W10 | 2020-03 | 78 | 78 | 104.8422 | 3 | 1 | 1 | 0.03 | 193567 | 0.3 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 25 | 0 | 0.52941 | 2019-11 | 0 | 0
809 | CR0012295 | CTASK0019089 | Closed | OPUS-MDA | Giang Nguyen Hoang | 14 | 14 | 2020-04-30 18:00 | 2020-03-23 09:00 | Container | Biz Common | Master Data | Admin | Process Status |  | Prevent wrong approval on SINHO requests | 2020-03-23 10:31 | 2020-04-30 18:00 | 2020-04-06 17:58 | 2020-05-04 20:07 | 2020-05-07 14:16 |  | 2020-05-19 11:00 | 2020-05-19 10:31 | 2020-05-08 09:55 | 2020-06-18 13:00 | CR0012295 | Biz CommonMaster DataAdminProcess Status | OPUS-MDA | 2020-W21 | 2020-05 | 29 | 28 | 57.0202 | 2 | 1 | 2 | 0.02 | 183440 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0 | 2020-03 | 0 | 0
810 | CR0012295 | CTASK0019088 | Closed | OPUS-MDA | Nhat Phan Dinh Minh | 15 | 14 | 2020-04-30 18:00 | 2020-03-23 09:00 | Container | Biz Common | Master Data | Admin | Process Status |  | Prevent wrong approval on SINHO requests | 2020-03-23 10:31 | 2020-04-30 18:00 | 2020-04-06 17:58 | 2020-05-04 20:07 | 2020-05-07 14:16 |  | 2020-05-19 11:00 | 2020-05-19 10:31 | 2020-05-08 09:55 | 2020-06-18 13:00 | CR0012295 | Biz CommonMaster DataAdminProcess Status | OPUS-MDA | 2020-W21 | 2020-05 | 29 | 28 | 57.0202 | 2 | 1 | 2 | 0.02 | 183432 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0 | 2020-03 | 0 | 0
811 | CR0013463 | CTASK0024379 | Closed | OPUS-SCO | Cuong Tran Hung | 22 | 22 | 2021-01-31 20:28 | 2021-01-01 20:28 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [January][CLT Internal][Cuong Tran] NA CLEAR Additional Changes | 2020-12-30 13:38 | 2021-01-08 18:00 | 2021-01-07 16:44 | 2021-01-28 09:07 | 2021-01-28 15:08 |  | 2021-02-02 10:00 | 2021-02-02 13:57 | 2021-01-28 16:02 | 2021-03-04 14:00 | CR0013463 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2021-W5 | 2021-02 | 66 | 66 | 33.8488 | 2 | 1 | 2 | 0.08 | 193530 | 1.6 | 1 | 1 | 0 | 1 | 1 | 1 | 8 | 21 | 1.2308 | 1.2222 | 2020-12 | 1 | 1
812 | CR0013463 | CTASK0024378 | Closed | OPUS-SCO | Chuong Ta | 44 | 44 | 2021-01-31 20:27 | 2021-01-01 20:27 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [January][CLT Internal][Chuong Ta] NA CLEAR Additional Changes | 2020-12-30 13:38 | 2021-01-08 18:00 | 2021-01-07 16:44 | 2021-01-28 09:07 | 2021-01-28 15:08 |  | 2021-02-02 10:00 | 2021-02-02 13:57 | 2021-01-28 16:02 | 2021-03-04 14:00 | CR0013463 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2021-W5 | 2021-02 | 66 | 66 | 33.8488 | 2 | 1 | 2 | 0.08 | 183379 | 1.8 | 1 | 1 | 0 | 1 | 1 | 1 | 8 | 21 | 0.32 | 0.38462 | 2020-12 | 1 | 1
813 | CR0011132 | CTASK0019440 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 17 | 13 | 2020-04-10 01:59 | 2020-04-07 10:30 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI |  | [DEPLOYMENT] NA *BKG* Booking Remarks Hardcode setup (CSVC/EXP BOOKING) | 2019-08-08 15:18 | 2019-09-02 15:18 | 2019-08-30 11:21 | 2020-03-02 13:20 | 2020-03-02 13:38 |  | 2020-04-14 10:00 | 2020-04-14 10:00 | 2020-04-07 10:34 | 2020-05-14 13:00 | CR0011132 | Service ManagementBooking/DocumentationBookingFax/Email/EDI | OPUS-BKG-M | 2020-W16 | 2020-04 | 21 | 17 | 249.7793 | 2 | 2 | 2 | 0 | 193470 | 0.4 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 16 | 0 | 1.3333 | 2019-08 | 0 | 0
814 | CR0011132 | CTASK0018337 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-02-14 17:44 | 2020-02-12 17:44 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI |  | NA *BKG* Booking Remarks UI setup (CSVC/EXP BOOKING) | 2019-08-08 15:18 | 2019-09-02 15:18 | 2019-08-30 11:21 | 2020-03-02 13:20 | 2020-03-02 13:38 |  | 2020-04-14 10:00 | 2020-04-14 10:00 | 2020-04-07 10:34 | 2020-05-14 13:00 | CR0011132 | Service ManagementBooking/DocumentationBookingFax/Email/EDI | OPUS-BKG-M | 2020-W16 | 2020-04 | 21 | 17 | 249.7793 | 2 | 2 | 2 | 0 | 193567 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 16 | 0 | 0.52941 | 2019-08 | 0 | 0
815 | CR0012648 | CTASK0020412 | Closed | OPUS-PSO | Hieu Vu | 33 | 33 | 2020-06-12 17:53 | 2020-06-01 17:52 | Container | Vessel Operation | Port Service Order | Port Tariff |  |  | [Development] [CLT Internal] Open Cost code in approval office | 2020-08-26 10:38 | 2020-09-04 10:38 | 2020-09-03 10:14 | 2020-09-14 09:56 | 2020-09-16 15:09 |  | 2020-09-22 15:09 | 2020-09-22 15:39 | 2020-09-17 13:35 | 2020-10-25 13:00 | CR0012648 | Vessel OperationPort Service OrderPort Tariff | OPUS-PSO | 2020-W39 | 2020-09 | 75 | 75 | 27.1881 | 3 | 1 | 2 | 0.11 | 183375 | 1.9 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 0.125 | 2020-08 | 0 | 0
816 | CR0012648 | CTASK0020497 | Closed | OPUS-PSO | Hieu Vu | 10 | 10 | 2020-06-30 11:43 | 2020-06-01 11:43 | Container | Vessel Operation | Port Service Order | Port Tariff |  |  | [Analyze] [CLT Internal] Open Cost code in approval office | 2020-08-26 10:38 | 2020-09-04 10:38 | 2020-09-03 10:14 | 2020-09-14 09:56 | 2020-09-16 15:09 |  | 2020-09-22 15:09 | 2020-09-22 15:39 | 2020-09-17 13:35 | 2020-10-25 13:00 | CR0012648 | Vessel OperationPort Service OrderPort Tariff | OPUS-PSO | 2020-W39 | 2020-09 | 75 | 75 | 27.1881 | 3 | 1 | 2 | 0.11 | 183375 | 1.9 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 0.125 | 2020-08 | 0 | 0
817 | CR0012648 | CTASK0020498 | Closed | OPUS-PSO | Lanh Le | 32 | 32 | 2020-06-30 11:47 | 2020-06-01 11:46 | Container | Vessel Operation | Port Service Order | Port Tariff |  |  | [Development] [CLT Internal] Open Cost code in approval office | 2020-08-26 10:38 | 2020-09-04 10:38 | 2020-09-03 10:14 | 2020-09-14 09:56 | 2020-09-16 15:09 |  | 2020-09-22 15:09 | 2020-09-22 15:39 | 2020-09-17 13:35 | 2020-10-25 13:00 | CR0012648 | Vessel OperationPort Service OrderPort Tariff | OPUS-PSO | 2020-W39 | 2020-09 | 75 | 75 | 27.1881 | 3 | 1 | 2 | 0.11 | 183422 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 0 | 2020-08 | 0 | 0
818 | CR0013473 | CTASK0024631 | Closed | OPUS-DMT | Cuong Nguyen | 1 | 1 | 2021-01-22 20:00 | 2021-01-12 08:00 | Container | Service Management | Demurrage/Detention | Billing | Invoice Creation & Issue |  | [CTASK2] CLV_Pair Test | 2021-01-11 13:24 | 2021-01-22 20:00 | 2021-01-21 15:33 | 2021-01-23 08:31 | 2021-01-26 08:05 |  | 2021-02-02 10:00 | 2021-02-02 10:12 | 2021-01-26 10:47 | 2021-02-05 10:53 | CR0013473 | Service ManagementDemurrage/DetentionBillingInvoice Creation & Issue | OPUS-DMT | 2021-W5 | 2021-02 | 1 | 1 | 21.8585 | 1 | 1 | 1 | 0 | 193529 | 1.6 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 21 | 0 | 0.058824 | 2021-01 | 0 | 0
819 | CR0013401 | CTASK0024215 | Closed | OPUS-TPB | Manh Nguyen | 5 | 10 | [8 empty] | [TPB] RD server config change for PDF QR code | 2020-12-14 11:10 | 2020-12-15 12:01 | 2020-12-14 11:10 |  | 2020-12-14 11:11 |  | 2020-12-15 12:11 | 2020-12-15 11:22 | 2020-12-14 11:11 | 2021-04-24 14:00 | CR0013401 |  | OPUS-TPB | 2020-W51 | 2020-12 | 5 | 10 | 1.0421 | 1 | 1 | 1 | 0.4 | 153138 | 2.2 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 30 | 0 | 0.16667 | 2020-12 | 0 | 0
820 | CR0011109 | CTASK0012015 | Closed | OPUS-MNR | Tuyen Truong | 40 | 40 | 2019-04-02 19:00 | 2019-03-20 15:00 | Container | Equipment Management | M&R | Total Loss | Approval | Total Loss Approval | TLL DV invoice failed Biz com approval due to TLL containers attached to pre-booking | 2019-03-22 11:12 | 2019-03-26 15:00 | 2019-03-26 15:35 | 2019-03-27 18:56 | 2019-03-27 19:13 |  | 2019-03-29 15:00 | 2019-03-29 15:00 | 2019-03-27 19:18 | 2019-04-09 12:58 | CR0011109 | Equipment ManagementM&RTotal LossApprovalTotal Loss Approval | OPUS-MNR | 2019-W13 | 2019-03 | 40 | 40 | 7.1584 | 1 | 1 | 1 | 0.23 | 173255 | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 2019-03 | 0 | 0
821 | CR0013714 | CTASK0026019 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 1 | 1 | 2021-03-22 02:00 | 2021-03-22 02:00 | Container | Service Management | Booking/Documentation | Advance Manifest | China 24HR |  | [EST][CLT Internal] Mapping issue of CN24MNFST_XML | 2021-03-24 15:45 | 2021-04-02 | 2021-03-24 15:46 | 2021-05-04 16:47 | 2021-05-07 10:02 |  | 2021-05-18 10:00 | 2021-05-18 10:30 | 2021-05-07 13:15 | 2021-06-17 14:00 | CR0013714 | Service ManagementBooking/DocumentationAdvance ManifestChina 24HR | OPUS-BKG-MFT-A | 2021-W20 | 2021-05 | 5 | 5 | 54.7606 | 3 | 1 | 1 | 0 | 193506 | 1.8 | 2 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 1.1212 | 1.25 | 2021-03 | 0 | 0
822 | CR0013714 | CTASK0026006 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 2 | 2 | 2021-03-26 02:00 | 2021-03-23 02:00 | Container | Service Management | Booking/Documentation | Advance Manifest | China 24HR |  | [Dev][CLT Internal] Mapping issue of CN24MNFST_XML | 2021-03-24 15:45 | 2021-04-02 | 2021-03-24 15:46 | 2021-05-04 16:47 | 2021-05-07 10:02 |  | 2021-05-18 10:00 | 2021-05-18 10:30 | 2021-05-07 13:15 | 2021-06-17 14:00 | CR0013714 | Service ManagementBooking/DocumentationAdvance ManifestChina 24HR | OPUS-BKG-MFT-A | 2021-W20 | 2021-05 | 5 | 5 | 54.7606 | 3 | 1 | 1 | 0 | 193506 | 1.8 | 2 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 1.1212 | 1.25 | 2021-03 | 0 | 0
823 | CR0013714 | CTASK0027044 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 2 | 2 | 2021-05-18 02:00 | 2021-05-11 02:00 | Container | Service Management | Booking/Documentation | Advance Manifest | China 24HR |  | [PROD][CLT Internal] Mapping issue of CN24MNFST_XML | 2021-03-24 15:45 | 2021-04-02 | 2021-03-24 15:46 | 2021-05-04 16:47 | 2021-05-07 10:02 |  | 2021-05-18 10:00 | 2021-05-18 10:30 | 2021-05-07 13:15 | 2021-06-17 14:00 | CR0013714 | Service ManagementBooking/DocumentationAdvance ManifestChina 24HR | OPUS-BKG-MFT-A | 2021-W20 | 2021-05 | 5 | 5 | 54.7606 | 3 | 1 | 1 | 0 | 193506 | 1.8 | 2 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 1.1212 | 1.25 | 2021-03 | 0 | 0
824 | CR0012575 | CTASK0020212 | Closed | OPUS-BKG-OB | Nam Nguyen | 9 | 17 | 2020-06-30 18:23 | 2020-05-20 18:23 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Freight Invoice (EDI) | [Estimate] In Draft BL EDI, adding logic ':'(colon) to '--'(double dash) for for partner 'T100EX' | 2020-06-05 11:36 | 2020-07-01 | 2020-06-30 09:07 | 2020-07-09 10:06 | 2020-07-16 14:30 |  | 2020-08-11 11:00 | 2020-08-11 10:00 | 2020-08-01 14:02 | 2020-09-10 13:00 | CR0012575 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Freight Invoice (EDI) | OPUS-BKG-OB | 2020-W33 | 2020-08 | 41 | 49 | 66.9748 | 4 | 1 | 2 | 0.03 | 123048 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 30 | 0 | 0.46154 | 2020-06 | 0 | 0
825 | CR0012575 | CTASK0020211 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 2 | 2020-05-21 | 2020-05-20 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Freight Invoice (EDI) | [Analyze] In Draft BL EDI, adding logic ':'(colon) to '--'(double dash) for for partner 'T100EX' | 2020-06-05 11:36 | 2020-07-01 | 2020-06-30 09:07 | 2020-07-09 10:06 | 2020-07-16 14:30 |  | 2020-08-11 11:00 | 2020-08-11 10:00 | 2020-08-01 14:02 | 2020-09-10 13:00 | CR0012575 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Freight Invoice (EDI) | OPUS-BKG-OB | 2020-W33 | 2020-08 | 41 | 49 | 66.9748 | 4 | 1 | 2 | 0.03 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 30 | 0 | 0.17391 | 2020-06 | 0 | 0
826 | CR0012575 | CTASK0021727 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 2 | 4 | 2020-08-08 01:00 | 2020-08-06 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Freight Invoice (EDI) | [Deployment] In Draft BL EDI, adding logic ':'(colon) to '--'(double dash) for for partner 'T100EX' | 2020-06-05 11:36 | 2020-07-01 | 2020-06-30 09:07 | 2020-07-09 10:06 | 2020-07-16 14:30 |  | 2020-08-11 11:00 | 2020-08-11 10:00 | 2020-08-01 14:02 | 2020-09-10 13:00 | CR0012575 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Freight Invoice (EDI) | OPUS-BKG-OB | 2020-W33 | 2020-08 | 41 | 49 | 66.9748 | 4 | 1 | 2 | 0.03 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 30 | 0 | 0.17391 | 2020-06 | 0 | 0
827 | CR0012575 | CTASK0020725 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 26 | 26 | 2020-06-24 19:30 | 2020-06-18 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Freight Invoice (EDI) | [Develop] In Draft BL EDI, adding logic ':'(colon) to '--'(double dash) for for partner 'T100EX' | 2020-06-05 11:36 | 2020-07-01 | 2020-06-30 09:07 | 2020-07-09 10:06 | 2020-07-16 14:30 |  | 2020-08-11 11:00 | 2020-08-11 10:00 | 2020-08-01 14:02 | 2020-09-10 13:00 | CR0012575 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Freight Invoice (EDI) | OPUS-BKG-OB | 2020-W33 | 2020-08 | 41 | 49 | 66.9748 | 4 | 1 | 2 | 0.03 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 30 | 0 | 0.17391 | 2020-06 | 0 | 0
828 | CR0013037 | CTASK0022417 | Closed | OPUS-SCG | Tu Nguyen | 40 | 40 | 2020-10-31 09:51 | 2020-09-01 09:51 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | New DG EDI application with ZIM(SCG) | 2020-11-24 13:06 | 2021-03-20 | 2021-03-17 16:39 |  | 2021-03-17 16:41 |  | 2021-03-24 09:30 | 2021-03-24 10:00 | 2021-03-18 10:44 | 2021-04-23 14:00 | CR0013037 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2021-W12 | 2021-03 | 156 | 155 | 119.8502 | 2 | 1 | 2 | 0.05 | 123045 | 2.2 | 1 | 0 | 0 | 2 | 1 | 2 | 6 | 46 | 0 | 0 | 2020-11 | 0 | 0
829 | CR0013037 | CTASK0022416 | Closed | OPUS-SCG | Pham Khanh Van | 116 | 115 | 2020-10-31 09:54 | 2020-09-01 09:54 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | New DG EDI application with ZIM(SCG) | 2020-11-24 13:06 | 2021-03-20 | 2021-03-17 16:39 |  | 2021-03-17 16:41 |  | 2021-03-24 09:30 | 2021-03-24 10:00 | 2021-03-18 10:44 | 2021-04-23 14:00 | CR0013037 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2021-W12 | 2021-03 | 156 | 155 | 119.8502 | 2 | 1 | 2 | 0.05 | 193477 | 1.5 | 1 | 0 | 0 | 2 | 1 | 2 | 6 | 46 | 0 | 0 | 2020-11 | 0 | 0
830 | CR0013331 | CTASK0023835 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2020-12-31 15:14 | 2020-12-28 15:14 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] Wrong information shown in Booking History > Fax/EDI for Shipping Instruction | 2020-12-08 14:54 | 2021-01-21 02:00 | 2021-01-19 14:14 | 2021-01-27 14:28 | 2021-01-27 14:41 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-01-28 15:24 | 2021-03-11 14:00 | CR0013331 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W6 | 2021-02 | 36 | 36 | 62.7959 | 4 | 1 | 1 | 0.02 | 193567 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 4 | 21 | 0.5625 | 0.53333 | 2020-12 | 0 | 0
831 | CR0013331 | CTASK0023838 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2021-02-28 15:14 | 2021-02-01 15:14 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] Wrong information shown in Booking History > Fax/EDI for Shipping Instruction | 2020-12-08 14:54 | 2021-01-21 02:00 | 2021-01-19 14:14 | 2021-01-27 14:28 | 2021-01-27 14:41 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-01-28 15:24 | 2021-03-11 14:00 | CR0013331 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W6 | 2021-02 | 36 | 36 | 62.7959 | 4 | 1 | 1 | 0.02 | 193567 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 4 | 21 | 0.5625 | 0.53333 | 2020-12 | 0 | 0
832 | CR0013331 | CTASK0023830 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-11-30 13:40 | 2020-11-25 13:40 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] Wrong information shown in Booking History > Fax/EDI for Shipping Instruction | 2020-12-08 14:54 | 2021-01-21 02:00 | 2021-01-19 14:14 | 2021-01-27 14:28 | 2021-01-27 14:41 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-01-28 15:24 | 2021-03-11 14:00 | CR0013331 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W6 | 2021-02 | 36 | 36 | 62.7959 | 4 | 1 | 1 | 0.02 | 193567 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 4 | 21 | 0.5625 | 0.53333 | 2020-12 | 0 | 0
833 | CR0013331 | CTASK0023836 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-01-31 15:14 | 2021-01-01 15:14 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] Wrong information shown in Booking History > Fax/EDI for Shipping Instruction | 2020-12-08 14:54 | 2021-01-21 02:00 | 2021-01-19 14:14 | 2021-01-27 14:28 | 2021-01-27 14:41 |  | 2021-02-09 10:00 | 2021-02-09 10:00 | 2021-01-28 15:24 | 2021-03-11 14:00 | CR0013331 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W6 | 2021-02 | 36 | 36 | 62.7959 | 4 | 1 | 1 | 0.02 | 193567 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 4 | 21 | 0.5625 | 0.53333 | 2020-12 | 0 | 0
834 | CR0012264 | CTASK0019783 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 12 | 12 | 2020-04-27 19:30 | 2020-04-22 11:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Deployment] Add Shipper's SC/RFA number in Korea Manifest EDI for the purpose of empty container return management at CY/Terminal in Korea. | 2020-03-18 15:34 | 2020-04-10 | 2020-04-09 15:50 | 2020-04-16 18:52 | 2020-04-22 11:31 |  | 2020-04-28 10:00 | 2020-04-28 09:00 | 2020-04-23 10:11 | 2020-05-28 13:00 | CR0012264 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2020-W18 | 2020-04 | 46 | 46 | 40.7682 | 3 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0.18519 | 2020-03 | 0 | 0
835 | CR0012264 | CTASK0018852 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 30 | 30 | 2020-03-31 19:30 | 2020-03-11 11:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Development+Testing] Add Shipper's SC/RFA number in Korea Manifest EDI for the purpose of empty container return management at CY/Terminal in Korea. | 2020-03-18 15:34 | 2020-04-10 | 2020-04-09 15:50 | 2020-04-16 18:52 | 2020-04-22 11:31 |  | 2020-04-28 10:00 | 2020-04-28 09:00 | 2020-04-23 10:11 | 2020-05-28 13:00 | CR0012264 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2020-W18 | 2020-04 | 46 | 46 | 40.7682 | 3 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0.18519 | 2020-03 | 0 | 0
836 | CR0012264 | CTASK0018795 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 4 | 4 | 2020-03-09 19:30 | 2020-03-05 11:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Estimation] Add Shipper's SC/RFA number in Korea Manifest EDI for the purpose of empty container return management at CY/Terminal in Korea. | 2020-03-18 15:34 | 2020-04-10 | 2020-04-09 15:50 | 2020-04-16 18:52 | 2020-04-22 11:31 |  | 2020-04-28 10:00 | 2020-04-28 09:00 | 2020-04-23 10:11 | 2020-05-28 13:00 | CR0012264 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2020-W18 | 2020-04 | 46 | 46 | 40.7682 | 3 | 1 | 1 | 0.05 | 173280 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0.18519 | 2020-03 | 0 | 0
837 | CR0013077 | CTASK0022439 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 17 | 17 | 2020-09-24 01:59 | 2020-09-14 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Development + Testing][CLT Internal] C/A Confirm logic enhancement. | 2020-09-11 18:26 | 2020-09-26 01:59 | 2020-09-24 18:22 | 2020-10-15 11:23 | 2020-10-26 10:31 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-26 18:36 | 2020-12-04 14:00 | CR0013077 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W45 | 2020-11 | 33 | 36 | 52.6486 | 3 | 1 | 1 | 0.03 | 193470 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.17391 | 2020-09 | 0 | 0
838 | CR0013077 | CTASK0023187 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 11 | 2020-11-03 02:00 | 2020-10-26 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Deployment][CLT Internal] C/A Confirm logic enhancement. | 2020-09-11 18:26 | 2020-09-26 01:59 | 2020-09-24 18:22 | 2020-10-15 11:23 | 2020-10-26 10:31 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-26 18:36 | 2020-12-04 14:00 | CR0013077 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W45 | 2020-11 | 33 | 36 | 52.6486 | 3 | 1 | 1 | 0.03 | 193470 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.17391 | 2020-09 | 0 | 0
839 | CR0013077 | CTASK0022430 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 | 2020-09-12 02:00 | 2020-09-11 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Documentation & Analysis] [CLT Internal] C/A Confirm logic enhancement. | 2020-09-11 18:26 | 2020-09-26 01:59 | 2020-09-24 18:22 | 2020-10-15 11:23 | 2020-10-26 10:31 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-26 18:36 | 2020-12-04 14:00 | CR0013077 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W45 | 2020-11 | 33 | 36 | 52.6486 | 3 | 1 | 1 | 0.03 | 193470 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.17391 | 2020-09 | 0 | 0
840 | CR0014009 | CTASK0027766 | Closed | OPUS-DMT | Cuong Nguyen | 18 | 27 | 2021-07-30 20:00 | 2021-06-14 08:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2021-07-13 10:45 | 2021-07-16 20:00 | 2021-07-16 14:50 | 2021-07-28 15:24 | 2021-07-28 16:11 |  | 2021-08-10 20:00 | 2021-08-10 09:57 | 2021-08-03 09:18 | 2021-08-12 10:07 | CR0014009 | Service ManagementDemurrage/Detention | OPUS-DMT | 2021-W32 | 2021-08 | 18 | 27 | 28.3857 | 1 | 1 | 1 | 0.04 | 193529 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 22 | 0.11538 | 0.22222 | 2021-07 | 0 | 0
841 | CR0014057 | CTASK0027500 | Closed | OPUS-ACM | Huynh Tuan Khanh | 5 | 5 |  |  | Container | Support & Admin | Agent Commission Management |  |  |  | [CLT Internal] Change USD exchange rate when calculate ACM cost for COA | 2021-06-22 09:03 | 2021-06-30 09:03 | 2021-06-24 18:09 | 2021-06-25 13:14 | 2021-06-28 11:29 |  | 2021-07-09 11:28 | 2021-07-06 09:24 | 2021-06-30 10:02 | 2021-07-29 14:00 | CR0014057 | Support & AdminAgent Commission Management | OPUS-ACM | 2021-W27 | 2021-07 | 5 | 5 | 17.1007 | 1 | 1 | 1 | 0.01 | 193499 | 2.1 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0 | 0 | 2021-06 | 0 | 0
842 | CR0012472 | CTASK0019317 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 12 | 12 | 2020-04-03 19:30 | 2020-04-01 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | [Analysis] OPUS BOOKING: M&D Attachment Button - Enable after BDR with History and additional category | 2020-04-09 08:00 | 2020-04-22 08:00 | 2020-04-20 15:03 | 2020-04-24 21:27 | 2020-04-28 09:42 |  | 2020-05-07 10:01 | 2020-03-29 21:22 | 2020-04-28 10:12 | 2020-06-06 13:00 | CR0012472 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2020-W19 | 2020-05 | 27 | 27 | 28.0842 | 2 | 1 | 1 | 0.04 | 193470 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 26 | 0 | 0.17391 | 2020-04 | 0 | 0
843 | CR0012472 | CTASK0019379 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 15 | 15 | 2020-05-07 01:59 | 2020-04-06 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | OPUS BOOKING: M&D Attachment Button - Enable after BDR with History and additional category | 2020-04-09 08:00 | 2020-04-22 08:00 | 2020-04-20 15:03 | 2020-04-24 21:27 | 2020-04-28 09:42 |  | 2020-05-07 10:01 | 2020-03-29 21:22 | 2020-04-28 10:12 | 2020-06-06 13:00 | CR0012472 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2020-W19 | 2020-05 | 27 | 27 | 28.0842 | 2 | 1 | 1 | 0.04 | 193470 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 26 | 0 | 0.17391 | 2020-04 | 0 | 0
844 | CR0012739 | CTASK0021928 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 2 | 2 | 2020-08-12 20:05 | 2020-08-11 10:05 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Testing][CLT Internal] Empty Container Release Order OOME Issue Counter Measure | 2020-07-15 10:17 | 2020-08-20 | 2020-08-12 18:02 | 2020-08-12 21:55 | 2020-08-13 15:47 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-13 15:48 | 2020-09-01 10:13 | CR0012739 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2020-W36 | 2020-09 | 55 | 53 | 47.9879 | 5 | 1 | 1 | 0.05 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-07 | 0 | 0
845 | CR0012739 | CTASK0020629 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 17 | 17 | 2020-06-15 19:35 | 2020-06-11 11:35 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Design][CLT Internal] Empty Container Release Order OOME Issue Counter Measure | 2020-07-15 10:17 | 2020-08-20 | 2020-08-12 18:02 | 2020-08-12 21:55 | 2020-08-13 15:47 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-13 15:48 | 2020-09-01 10:13 | CR0012739 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2020-W36 | 2020-09 | 55 | 53 | 47.9879 | 5 | 1 | 1 | 0.05 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-07 | 0 | 0
846 | CR0012739 | CTASK0020695 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 4 | 2020-08-26 18:35 | 2020-08-21 10:00 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Deployment][CLT Internal] Empty Container Release Order OOME Issue Counter Measure | 2020-07-15 10:17 | 2020-08-20 | 2020-08-12 18:02 | 2020-08-12 21:55 | 2020-08-13 15:47 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-13 15:48 | 2020-09-01 10:13 | CR0012739 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2020-W36 | 2020-09 | 55 | 53 | 47.9879 | 5 | 1 | 1 | 0.05 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-07 | 0 | 0
847 | CR0012739 | CTASK0020693 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 26 | 26 | 2020-07-28 18:58 | 2020-07-15 11:58 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Development][CLT Internal] Empty Container Release Order OOME Issue Counter Measure | 2020-07-15 10:17 | 2020-08-20 | 2020-08-12 18:02 | 2020-08-12 21:55 | 2020-08-13 15:47 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-13 15:48 | 2020-09-01 10:13 | CR0012739 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2020-W36 | 2020-09 | 55 | 53 | 47.9879 | 5 | 1 | 1 | 0.05 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-07 | 0 | 0
848 | CR0012739 | CTASK0020694 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2020-07-27 18:36 | 2020-07-24 10:01 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Testing][CLT Internal] Empty Container Release Order OOME Issue Counter Measure | 2020-07-15 10:17 | 2020-08-20 | 2020-08-12 18:02 | 2020-08-12 21:55 | 2020-08-13 15:47 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-13 15:48 | 2020-09-01 10:13 | CR0012739 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2020-W36 | 2020-09 | 55 | 53 | 47.9879 | 5 | 1 | 1 | 0.05 | 193488 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.28125 | 2020-07 | 0 | 0
849 | CR0012746 | CTASK0021210 | Closed | OPUS-TPB | Manh Nguyen | 143 | 150 | 2021-01-29 08:44 | 2020-08-01 08:44 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [Actual] Additional logic in TPB module | 2020-10-15 11:57 | 2021-01-01 12:55 | 2020-12-03 13:44 | 2021-05-11 14:12 | 2021-05-17 17:25 |  | 2021-06-01 12:00 | 2021-06-01 10:57 | 2021-05-25 15:28 | 2021-07-01 14:00 | CR0012746 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2021-W22 | 2021-06 | 175 | 183 | 229.0022 | 5 | 2 | 2 | 0.03 | 153138 | 2 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 53 | 0 | 0.16667 | 2020-10 | 0 | 0
850 | CR0012746 | CTASK0026967 | Closed | OPUS-TES | Thai Nguyen | 1 | 1 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202105] Additional logic in TPB module | 2020-10-15 11:57 | 2021-01-01 12:55 | 2020-12-03 13:44 | 2021-05-11 14:12 | 2021-05-17 17:25 |  | 2021-06-01 12:00 | 2021-06-01 10:57 | 2021-05-25 15:28 | 2021-07-01 14:00 | CR0012746 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2021-W22 | 2021-06 | 175 | 183 | 229.0022 | 5 | 2 | 2 | 0.03 | 173249 | 2 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 53 | 0 | 0.5 | 2020-10 | 0 | 0
851 | CR0012746 | CTASK0021211 | Closed | OPUS-TPB | Thai Nguyen | 1 | 1 |  |  | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [Actual] Additional logic in TPB module | 2020-10-15 11:57 | 2021-01-01 12:55 | 2020-12-03 13:44 | 2021-05-11 14:12 | 2021-05-17 17:25 |  | 2021-06-01 12:00 | 2021-06-01 10:57 | 2021-05-25 15:28 | 2021-07-01 14:00 | CR0012746 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2021-W22 | 2021-06 | 175 | 183 | 229.0022 | 5 | 2 | 2 | 0.03 | 173249 | 2 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 53 | 0 | 0.5 | 2020-10 | 0 | 0
852 | CR0012746 | CTASK0027315 | Closed | OPUS-TPB | Manh Nguyen | 3 | 3 | 2021-07-01 01:00 | 2021-06-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202106] Additional logic in TPB module | 2020-10-15 11:57 | 2021-01-01 12:55 | 2020-12-03 13:44 | 2021-05-11 14:12 | 2021-05-17 17:25 |  | 2021-06-01 12:00 | 2021-06-01 10:57 | 2021-05-25 15:28 | 2021-07-01 14:00 | CR0012746 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2021-W22 | 2021-06 | 175 | 183 | 229.0022 | 5 | 2 | 2 | 0.03 | 153138 | 2 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 53 | 0 | 0.16667 | 2020-10 | 0 | 0
853 | CR0012746 | CTASK0026966 | Closed | OPUS-TPB | Manh Nguyen | 32 | 30 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202105] Additional logic in TPB module | 2020-10-15 11:57 | 2021-01-01 12:55 | 2020-12-03 13:44 | 2021-05-11 14:12 | 2021-05-17 17:25 |  | 2021-06-01 12:00 | 2021-06-01 10:57 | 2021-05-25 15:28 | 2021-07-01 14:00 | CR0012746 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2021-W22 | 2021-06 | 175 | 183 | 229.0022 | 5 | 2 | 2 | 0.03 | 153138 | 2 | 0 | 0 | 0 | 2 | 1 | 3 | 6 | 53 | 0 | 0.16667 | 2020-10 | 0 | 0
854 | CR0010680 | CTASK0012586 | Closed | OPUS-BKG-OB | Kieu Le | 28 | 28 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [~2019-04-19] Freight C/A approval | 2019-03-06 17:28 | 2019-03-16 | 2019-03-14 11:18 | 2019-05-03 18:23 | 2019-05-03 18:24 |  | 2019-05-09 10:00 | 2019-05-09 09:20 | 2019-05-08 17:43 | 2019-06-08 13:00 | CR0010680 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2019-W19 | 2019-05 | 46 | 0 | 63.6892 | 2 | 1 | 1 | 0 | 153106 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 6 | 0 | 0 | 2019-03 | 0 | 0
855 | CR0010680 | CTASK0013308 | Closed | OPUS-BKG-OB | Kieu Le | 18 | 18 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [~2019-05-10] Freight C/A approval | 2019-03-06 17:28 | 2019-03-16 | 2019-03-14 11:18 | 2019-05-03 18:23 | 2019-05-03 18:24 |  | 2019-05-09 10:00 | 2019-05-09 09:20 | 2019-05-08 17:43 | 2019-06-08 13:00 | CR0010680 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2019-W19 | 2019-05 | 46 | 0 | 63.6892 | 2 | 1 | 1 | 0 | 153106 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 6 | 0 | 0 | 2019-03 | 0 | 0
856 | CR0012656 | CTASK0020622 | Closed | OPUS-DOM | Giang Nguyen Hoang | 20 | 20 | 2020-06-26 15:44 | 2020-06-11 15:44 | DOM Web Portal | IMC | EQ Match | Booking Activity |  |  | (DOM) NA *DOM WEB PORTAL* Change Shipper Info. Address to a mandatory input in Web Rail billing UI | 2020-06-11 15:41 | 2020-07-03 21:00 | 2020-07-03 14:58 | 2020-07-09 06:07 | 2020-07-14 10:54 |  | 2020-07-21 11:00 | 2020-07-21 11:00 | 2020-07-14 22:55 | 2020-08-21 13:00 | CR0012656 | IMCEQ MatchBooking Activity | OPUS-DOM | 2020-W30 | 2020-07 | 39 | 40 | 39.8049 | 2 | 1 | 2 | 0.04 | 183440 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 27 | 0 | 0 | 2020-06 | 0 | 0
857 | CR0012656 | CTASK0020621 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 19 | 20 | 2020-06-26 15:43 | 2020-06-11 15:43 | DOM Web Portal | IMC | EQ Match | Booking Activity |  |  | (DOM) NA *DOM WEB PORTAL* Change Shipper Info. Address to a mandatory input in Web Rail billing UI | 2020-06-11 15:41 | 2020-07-03 21:00 | 2020-07-03 14:58 | 2020-07-09 06:07 | 2020-07-14 10:54 |  | 2020-07-21 11:00 | 2020-07-21 11:00 | 2020-07-14 22:55 | 2020-08-21 13:00 | CR0012656 | IMCEQ MatchBooking Activity | OPUS-DOM | 2020-W30 | 2020-07 | 39 | 40 | 39.8049 | 2 | 1 | 2 | 0.04 | 183432 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 27 | 0 | 0 | 2020-06 | 0 | 0
858 | CR0013573 | CTASK0026817 | Closed | OPUS-TES | Thai Nguyen | 17 | 20 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Off Dock CY Invoice Creation & Correction | [202105] [CLT Internal] AS - Opus Container - TES - Off Dock CY Invoice Creation & Correction | 2021-04-07 10:37 | 2021-07-01 | 2021-06-30 13:24 | 2021-07-01 11:19 | 2021-07-05 14:20 |  | 2021-07-13 12:30 | 2021-07-13 11:11 | 2021-07-06 08:42 | 2021-07-29 14:00 | CR0013573 | Service ManagementTML INVInvoiceInvoice CreationOff Dock CY Invoice Creation & Correction | OPUS-TES | 2021-W28 | 2021-07 | 64 | 81 | 97.0782 | 5 | 1 | 1 | 0.03 | 173249 | 2.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0 | 0.5 | 2021-04 | 0 | 0
859 | CR0013573 | CTASK0027785 | Closed | OPUS-TES | Thai Nguyen | 5 | 5 | 2021-07-01 01:00 | 2021-06-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Off Dock CY Invoice Creation & Correction | [202106] [CLT Internal] AS - Opus Container - TES - Off Dock CY Invoice Creation & Correction | 2021-04-07 10:37 | 2021-07-01 | 2021-06-30 13:24 | 2021-07-01 11:19 | 2021-07-05 14:20 |  | 2021-07-13 12:30 | 2021-07-13 11:11 | 2021-07-06 08:42 | 2021-07-29 14:00 | CR0013573 | Service ManagementTML INVInvoiceInvoice CreationOff Dock CY Invoice Creation & Correction | OPUS-TES | 2021-W28 | 2021-07 | 64 | 81 | 97.0782 | 5 | 1 | 1 | 0.03 | 173249 | 2.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0 | 0.5 | 2021-04 | 0 | 0
860 | CR0013573 | CTASK0027897 | Closed | OPUS-TES | Thai Nguyen | 1 | 1 | 2021-08-01 01:00 | 2021-07-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Off Dock CY Invoice Creation & Correction | [202107] [CLT Internal] AS - Opus Container - TES - Off Dock CY Invoice Creation & Correction | 2021-04-07 10:37 | 2021-07-01 | 2021-06-30 13:24 | 2021-07-01 11:19 | 2021-07-05 14:20 |  | 2021-07-13 12:30 | 2021-07-13 11:11 | 2021-07-06 08:42 | 2021-07-29 14:00 | CR0013573 | Service ManagementTML INVInvoiceInvoice CreationOff Dock CY Invoice Creation & Correction | OPUS-TES | 2021-W28 | 2021-07 | 64 | 81 | 97.0782 | 5 | 1 | 1 | 0.03 | 173249 | 2.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0 | 0.5 | 2021-04 | 0 | 0
861 | CR0013573 | CTASK0026326 | Closed | OPUS-TES | Thai Nguyen | 25 | 30 | 2021-05-01 01:00 | 2021-04-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Off Dock CY Invoice Creation & Correction | [202104] [CLT Internal] AS - Opus Container - TES - Off Dock CY Invoice Creation & Correction | 2021-04-07 10:37 | 2021-07-01 | 2021-06-30 13:24 | 2021-07-01 11:19 | 2021-07-05 14:20 |  | 2021-07-13 12:30 | 2021-07-13 11:11 | 2021-07-06 08:42 | 2021-07-29 14:00 | CR0013573 | Service ManagementTML INVInvoiceInvoice CreationOff Dock CY Invoice Creation & Correction | OPUS-TES | 2021-W28 | 2021-07 | 64 | 81 | 97.0782 | 5 | 1 | 1 | 0.03 | 173249 | 2.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0 | 0.5 | 2021-04 | 0 | 0
862 | CR0013573 | CTASK0025757 | Closed | OPUS-TES | Thai Nguyen | 22 | 25 | 2021-04-01 01:00 | 2021-03-01 01:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Off Dock CY Invoice Creation & Correction | [202103] [CLT Internal] AS - Opus Container - TES - Off Dock CY Invoice Creation & Correction | 2021-04-07 10:37 | 2021-07-01 | 2021-06-30 13:24 | 2021-07-01 11:19 | 2021-07-05 14:20 |  | 2021-07-13 12:30 | 2021-07-13 11:11 | 2021-07-06 08:42 | 2021-07-29 14:00 | CR0013573 | Service ManagementTML INVInvoiceInvoice CreationOff Dock CY Invoice Creation & Correction | OPUS-TES | 2021-W28 | 2021-07 | 64 | 81 | 97.0782 | 5 | 1 | 1 | 0.03 | 173249 | 2.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 0 | 0.5 | 2021-04 | 0 | 0
863 | CR0012830 | CTASK0024711 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 9 | 10 | 2021-01-18 17:44 | 2021-01-14 09:44 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Estimation] eRO enhancement for ONEPORT | 2021-01-20 13:08 | 2021-02-19 23:06 | 2021-02-19 13:21 | 2021-05-25 13:43 | 2021-05-25 13:54 |  | 2021-06-08 13:52 | 2021-06-08 10:26 | 2021-05-28 10:12 | 2021-07-08 14:00 | CR0012830 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2021-W23 | 2021-06 | 114 | 114 | 139.0301 | 3 | 3 | 1 | 0.03 | 193512 | 1.6 | 1 | 0 | 0 | 2 | 1 | 2 | 9 | 53 | 0.2963 | 0.3125 | 2021-01 | 0 | 0
864 | CR0012830 | CTASK0024753 | Closed | OPUS-BKG-MFT-M | Nhut Nguyen Minh | 85 | 80 | 2021-02-05 18:13 | 2021-01-18 09:13 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Development+ Testing+ Deployment]eRO enhancement for ONEPORT | 2021-01-20 13:08 | 2021-02-19 23:06 | 2021-02-19 13:21 | 2021-05-25 13:43 | 2021-05-25 13:54 |  | 2021-06-08 13:52 | 2021-06-08 10:26 | 2021-05-28 10:12 | 2021-07-08 14:00 | CR0012830 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2021-W23 | 2021-06 | 114 | 114 | 139.0301 | 3 | 3 | 1 | 0.03 | 193512 | 1.6 | 1 | 0 | 0 | 2 | 1 | 2 | 9 | 53 | 0.2963 | 0.3125 | 2021-01 | 0 | 0
865 | CR0012830 | CTASK0021400 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 20 | 24 | 2020-07-31 18:29 | 2020-07-21 09:28 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Estimation] eRO enhancement for ONEPORT | 2021-01-20 13:08 | 2021-02-19 23:06 | 2021-02-19 13:21 | 2021-05-25 13:43 | 2021-05-25 13:54 |  | 2021-06-08 13:52 | 2021-06-08 10:26 | 2021-05-28 10:12 | 2021-07-08 14:00 | CR0012830 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2021-W23 | 2021-06 | 114 | 114 | 139.0301 | 3 | 3 | 1 | 0.03 | 193512 | 1.6 | 1 | 0 | 0 | 2 | 1 | 2 | 9 | 53 | 0.2963 | 0.3125 | 2021-01 | 0 | 0
866 | CR0012460 | CTASK0019536 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-05-20 00:52 | 2020-05-18 09:52 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Testing][CLT Internal] Special Cargo Manifest for SS enhancement | 2020-04-27 13:10 | 2020-06-24 02:00 | 2020-06-18 03:50 | 2020-06-22 18:14 | 2020-07-30 09:32 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:32 | 2020-08-04 12:36 | CR0012460 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W32 | 2020-08 | 40 | 40 | 98.8682 | 5 | 1 | 1 | 0.02 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.52941 | 2020-04 | 0 | 0
867 | CR0012460 | CTASK0019539 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-07-31 18:39 | 2020-07-27 18:39 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Deployment][CLT Internal] Special Cargo Manifest for SS enhancement | 2020-04-27 13:10 | 2020-06-24 02:00 | 2020-06-18 03:50 | 2020-06-22 18:14 | 2020-07-30 09:32 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:32 | 2020-08-04 12:36 | CR0012460 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W32 | 2020-08 | 40 | 40 | 98.8682 | 5 | 1 | 1 | 0.02 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.52941 | 2020-04 | 0 | 0
868 | CR0012460 | CTASK0019535 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-05-02 | 2020-04-27 13:30 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Development][CLT Internal] Special Cargo Manifest for SS enhancement | 2020-04-27 13:10 | 2020-06-24 02:00 | 2020-06-18 03:50 | 2020-06-22 18:14 | 2020-07-30 09:32 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:32 | 2020-08-04 12:36 | CR0012460 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W32 | 2020-08 | 40 | 40 | 98.8682 | 5 | 1 | 1 | 0.02 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.52941 | 2020-04 | 0 | 0
869 | CR0012460 | CTASK0019401 | Closed | OPUS-BKG-M | Thien Lai | 20 | 20 | 2020-04-10 20:53 | 2020-04-06 20:53 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Design] [CLT Internal] Special Cargo Manifest for SS enhancement | 2020-04-27 13:10 | 2020-06-24 02:00 | 2020-06-18 03:50 | 2020-06-22 18:14 | 2020-07-30 09:32 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:32 | 2020-08-04 12:36 | CR0012460 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W32 | 2020-08 | 40 | 40 | 98.8682 | 5 | 1 | 1 | 0.02 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.52941 | 2020-04 | 0 | 0
870 | CR0012460 | CTASK0019537 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-05-02 00:33 | 2020-04-27 13:33 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Testing][CLT Internal] Special Cargo Manifest for SS enhancement | 2020-04-27 13:10 | 2020-06-24 02:00 | 2020-06-18 03:50 | 2020-06-22 18:14 | 2020-07-30 09:32 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 09:32 | 2020-08-04 12:36 | CR0012460 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2020-W32 | 2020-08 | 40 | 40 | 98.8682 | 5 | 1 | 1 | 0.02 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.52941 | 2020-04 | 0 | 0
871 | CR0012498 | CTASK0019720 | Closed | OPUS-PSO | Hieu Vu | 53 | 53 | 2020-05-29 15:42 | 2020-05-18 15:42 | Container | Vessel Operation | Port Service Order | Port Tariff | Port Tariff Creation | Object List | PSO Object update >> "Loadable TEU at Last Port" | 2020-05-15 10:25 | 2020-05-29 10:24 | 2020-05-29 09:00 | 2020-09-01 21:43 | 2020-09-07 13:39 |  | 2020-09-15 13:39 | 2020-09-15 13:05 | 2020-09-11 09:20 | 2020-10-17 13:00 | CR0012498 | Vessel OperationPort Service OrderPort TariffPort Tariff CreationObject List | OPUS-PSO | 2020-W38 | 2020-09 | 105 | 105 | 123.1347 | 2 | 1 | 2 | 0.04 | 183375 | 1.6 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 36 | 0 | 0.125 | 2020-05 | 0 | 0
872 | CR0012498 | CTASK0020105 | Closed | OPUS-PSO | Lanh Le | 52 | 52 | 2020-05-29 10:20 | 2020-05-18 10:20 | Container | Vessel Operation | Port Service Order | Port Tariff | Port Tariff Creation | Object List | PSO Object update >> "Loadable TEU at Last Port" | 2020-05-15 10:25 | 2020-05-29 10:24 | 2020-05-29 09:00 | 2020-09-01 21:43 | 2020-09-07 13:39 |  | 2020-09-15 13:39 | 2020-09-15 13:05 | 2020-09-11 09:20 | 2020-10-17 13:00 | CR0012498 | Vessel OperationPort Service OrderPort TariffPort Tariff CreationObject List | OPUS-PSO | 2020-W38 | 2020-09 | 105 | 105 | 123.1347 | 2 | 1 | 2 | 0.04 | 183422 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-05 | 0 | 0
873 | CR0012859 | CTASK0024558 | Closed | OPUS-PRD | Thanh Tran Ngoc | 8 | 10 | 2021-01-31 16:14 | 2021-01-01 16:14 | Container | Service Management | Product Catalog | Network Constraint |  |  | Adding Constraint History - JAN | 2020-09-16 11:30 | 2020-11-18 12:29 | 2020-11-17 08:32 | 2020-12-09 13:59 | 2021-01-08 16:13 |  | 2021-01-26 10:00 | 2021-01-26 12:00 | 2021-01-18 10:09 | 2021-02-25 14:00 | CR0012859 | Service ManagementProduct CatalogNetwork Constraint | OPUS-PRD | 2021-W4 | 2021-01 | 170 | 170 | 131.9377 | 5 | 1 | 1 | 0.05 | 193478 | 0.9 | 0 | 0 | 0 | 2 | 1 | 2 | 12 | 40 | 0 | 0 | 2020-09 | 0 | 0
874 | CR0012859 | CTASK0021846 | Closed | OPUS-PRD | Thanh Tran Ngoc | 20 | 20 | 2020-08-31 23:00 | 2020-08-13 17:48 | Container | Service Management | Product Catalog | Network Constraint |  |  | Adding Constraint History - AUG | 2020-09-16 11:30 | 2020-11-18 12:29 | 2020-11-17 08:32 | 2020-12-09 13:59 | 2021-01-08 16:13 |  | 2021-01-26 10:00 | 2021-01-26 12:00 | 2021-01-18 10:09 | 2021-02-25 14:00 | CR0012859 | Service ManagementProduct CatalogNetwork Constraint | OPUS-PRD | 2021-W4 | 2021-01 | 170 | 170 | 131.9377 | 5 | 1 | 1 | 0.05 | 193478 | 0.9 | 0 | 0 | 0 | 2 | 1 | 2 | 12 | 40 | 0 | 0 | 2020-09 | 0 | 0
875 | CR0012859 | CTASK0022763 | Closed | OPUS-PRD | Thanh Tran Ngoc | 55 | 50 |  |  | Container | Service Management | Product Catalog | Network Constraint |  |  | Adding Constraint History - OCT | 2020-09-16 11:30 | 2020-11-18 12:29 | 2020-11-17 08:32 | 2020-12-09 13:59 | 2021-01-08 16:13 |  | 2021-01-26 10:00 | 2021-01-26 12:00 | 2021-01-18 10:09 | 2021-02-25 14:00 | CR0012859 | Service ManagementProduct CatalogNetwork Constraint | OPUS-PRD | 2021-W4 | 2021-01 | 170 | 170 | 131.9377 | 5 | 1 | 1 | 0.05 | 193478 | 0.9 | 0 | 0 | 0 | 2 | 1 | 2 | 12 | 40 | 0 | 0 | 2020-09 | 0 | 0
876 | CR0012859 | CTASK0021866 | Closed | OPUS-PRD | Thanh Tran Ngoc | 40 | 40 | 2020-09-30 20:00 | 2020-09-01 09:00 | Container | Service Management | Product Catalog | Network Constraint |  |  | Adding Constraint History - SEP | 2020-09-16 11:30 | 2020-11-18 12:29 | 2020-11-17 08:32 | 2020-12-09 13:59 | 2021-01-08 16:13 |  | 2021-01-26 10:00 | 2021-01-26 12:00 | 2021-01-18 10:09 | 2021-02-25 14:00 | CR0012859 | Service ManagementProduct CatalogNetwork Constraint | OPUS-PRD | 2021-W4 | 2021-01 | 170 | 170 | 131.9377 | 5 | 1 | 1 | 0.05 | 193478 | 0.9 | 0 | 0 | 0 | 2 | 1 | 2 | 12 | 40 | 0 | 0 | 2020-09 | 0 | 0
877 | CR0012859 | CTASK0023374 | Closed | OPUS-PRD | Thanh Tran Ngoc | 47 | 50 | 2020-11-30 14:37 | 2020-11-01 14:37 | Container | Service Management | Product Catalog | Network Constraint |  |  | GHQ - Add Cnee field into Network Constraint - NOV | 2020-09-16 11:30 | 2020-11-18 12:29 | 2020-11-17 08:32 | 2020-12-09 13:59 | 2021-01-08 16:13 |  | 2021-01-26 10:00 | 2021-01-26 12:00 | 2021-01-18 10:09 | 2021-02-25 14:00 | CR0012859 | Service ManagementProduct CatalogNetwork Constraint | OPUS-PRD | 2021-W4 | 2021-01 | 170 | 170 | 131.9377 | 5 | 1 | 1 | 0.05 | 193478 | 0.9 | 0 | 0 | 0 | 2 | 1 | 2 | 12 | 40 | 0 | 0 | 2020-09 | 0 | 0
878 | CR0011555 | CTASK0021959 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 4 | 4 | 2020-08-25 19:30 | 2020-08-19 11:00 | Container | Service Management | Booking/Documentation | Setup |  |  | [Deployment]*ESA-JPN* No Missing CY Operator Code in Japan Cargo Release UI when the users re-download BL Data in Manifest Data Download UI | 2019-08-23 13:45 | 2019-09-20 13:45 | 2019-09-19 17:57 | 2020-08-14 11:06 | 2020-08-20 10:16 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-20 17:23 | 2020-09-24 13:00 | CR0011555 | Service ManagementBooking/DocumentationSetup | OPUS-BKG-IB | 2020-W35 | 2020-08 | 4 | 4 | 367.8438 | 1 | 1 | 1 | 0 | 173280 | 0.7 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 30 | 0 | 0 | 2019-08 | 0 | 0
879 | CR0010228 | CTASK0012585 | Closed | OPUS-BKG-OB | Kieu Le | 12 | 12 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | [~2019-04-19] Make history for M&D contents update. | 2019-02-20 15:17 | 2019-03-29 13:55 | 2019-03-06 11:32 | 2019-05-14 11:14 | 2019-05-22 11:40 |  | 2019-05-28 11:40 | 2019-05-28 11:09 | 2019-05-28 11:09 | 2019-05-28 17:41 | CR0010228 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2019-W22 | 2019-05 | 47 | 0 | 96.8495 | 2 | 1 | 1 | 0 | 153106 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 6 | 0 | 0 | 2019-02 | 0 | 0
880 | CR0010228 | CTASK0012590 | Closed | OPUS-BKG-OB | Kieu Le | 35 | 35 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | Make history for M&D contents update. | 2019-02-20 15:17 | 2019-03-29 13:55 | 2019-03-06 11:32 | 2019-05-14 11:14 | 2019-05-22 11:40 |  | 2019-05-28 11:40 | 2019-05-28 11:09 | 2019-05-28 11:09 | 2019-05-28 17:41 | CR0010228 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2019-W22 | 2019-05 | 47 | 0 | 96.8495 | 2 | 1 | 1 | 0 | 153106 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 6 | 0 | 0 | 2019-02 | 0 | 0
881 | CR0013708 | CTASK0026323 | Closed | OPUS-DMT | Cuong Nguyen | 30 | 30 | 2021-05-14 20:00 | 2021-04-05 08:00 | Container | Service Management | Demurrage/Detention | Billing | Sheet Option |  | [CTASK2] CLV_Desgin_Analysis_Development_Test_Deployment | 2021-05-06 10:59 | 2021-05-14 20:00 | 2021-05-14 14:16 | 2021-05-24 14:56 | 2021-05-25 09:13 |  | 2021-06-01 10:00 | 2021-06-01 10:00 | 2021-05-25 09:22 | 2021-07-01 14:00 | CR0013708 | Service ManagementDemurrage/DetentionBillingSheet Option | OPUS-DMT | 2021-W22 | 2021-06 | 30 | 30 | 25.9591 | 1 | 1 | 1 | 0.05 | 193529 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 6 | 53 | 0.11538 | 0.058824 | 2021-05 | 0 | 0
882 | CR0013517 | CTASK0025388 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 29 | 29 | 2021-03-06 01:59 | 2021-02-17 10:30 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Dev + Test] Kontainer - Add BRN data fields to OPUS database | 2021-02-18 11:46 | 2021-02-26 23:00 | 2021-02-23 10:53 | 2021-03-23 13:57 | 2021-03-29 14:30 |  | 2021-04-01 10:00 | 2021-04-01 10:00 | 2021-03-30 10:41 | 2021-05-01 14:00 | CR0013517 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W13 | 2021-04 | 36 | 36 | 41.9265 | 2 | 1 | 1 | 0.04 | 193470 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.36842 | 0.17391 | 2021-02 | 0 | 0
883 | CR0013517 | CTASK0026148 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 7 | 7 | 2021-03-31 23:00 | 2021-03-30 10:30 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Deployment] Kontainer - Add BRN data fields to OPUS database | 2021-02-18 11:46 | 2021-02-26 23:00 | 2021-02-23 10:53 | 2021-03-23 13:57 | 2021-03-29 14:30 |  | 2021-04-01 10:00 | 2021-04-01 10:00 | 2021-03-30 10:41 | 2021-05-01 14:00 | CR0013517 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W13 | 2021-04 | 36 | 36 | 41.9265 | 2 | 1 | 1 | 0.04 | 193470 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.36842 | 0.17391 | 2021-02 | 0 | 0
884 | CR0012187 | CTASK0018238 | Closed | OPUS-BKG-M | Nam Nguyen | 22 | 22 | 2020-02-21 12:01 | 2020-02-17 12:01 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [CLT Internal] BKG Cancel Validation Enhancement | 2020-02-14 19:02 | 2020-03-26 | 2020-03-23 09:42 | 2020-03-23 09:46 | 2020-03-23 13:18 |  | 2020-03-31 10:00 | 2020-03-31 10:00 | 2020-03-25 14:08 | 2020-04-30 13:00 | CR0012187 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W14 | 2020-03 | 67 | 64 | 45.6234 | 4 | 2 | 1 | 0.06 | 123048 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 25 | 0 | 0.46154 | 2020-02 | 0 | 0
885 | CR0012187 | CTASK0018703 | Closed | OPUS-BKG-M | Nam Nguyen | 16 | 16 | 2020-03-06 19:12 | 2020-03-02 19:12 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [CLT Internal] BKG Cancel Validation Enhancement | 2020-02-14 19:02 | 2020-03-26 | 2020-03-23 09:42 | 2020-03-23 09:46 | 2020-03-23 13:18 |  | 2020-03-31 10:00 | 2020-03-31 10:00 | 2020-03-25 14:08 | 2020-04-30 13:00 | CR0012187 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W14 | 2020-03 | 67 | 64 | 45.6234 | 4 | 2 | 1 | 0.06 | 123048 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 25 | 0 | 0.46154 | 2020-02 | 0 | 0
886 | CR0012187 | CTASK0018711 | Closed | OPUS-BKG-M | Nam Nguyen | 11 | 8 | 2020-03-13 12:07 | 2020-03-09 12:07 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [CLT Internal] BKG Cancel Validation Enhancement | 2020-02-14 19:02 | 2020-03-26 | 2020-03-23 09:42 | 2020-03-23 09:46 | 2020-03-23 13:18 |  | 2020-03-31 10:00 | 2020-03-31 10:00 | 2020-03-25 14:08 | 2020-04-30 13:00 | CR0012187 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W14 | 2020-03 | 67 | 64 | 45.6234 | 4 | 2 | 1 | 0.06 | 123048 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 25 | 0 | 0.46154 | 2020-02 | 0 | 0
887 | CR0012187 | CTASK0018187 | Closed | OPUS-BKG-OB | Nam Nguyen | 18 | 18 | 2020-02-05 20:44 | 2020-02-03 20:44 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Estimate][CLT Internal] BKG Cancel Validation Enhancement | 2020-02-14 19:02 | 2020-03-26 | 2020-03-23 09:42 | 2020-03-23 09:46 | 2020-03-23 13:18 |  | 2020-03-31 10:00 | 2020-03-31 10:00 | 2020-03-25 14:08 | 2020-04-30 13:00 | CR0012187 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W14 | 2020-03 | 67 | 64 | 45.6234 | 4 | 2 | 1 | 0.06 | 123048 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 25 | 0 | 0.46154 | 2020-02 | 0 | 0
888 | CR0013823 | CTASK0026370 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 4 | 4 | 2021-04-09 02:00 | 2021-04-08 02:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Est]Korea customs required to apply new location code in EDI. | 2021-04-15 13:47 | 2021-04-22 | 2021-04-21 10:29 | 2021-04-22 13:35 | 2021-04-22 14:52 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-23 13:20 | 2021-05-27 14:00 | CR0013823 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W17 | 2021-04 | 32 | 32 | 11.8426 | 5 | 1 | 1 | 0.11 | 193506 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 1.1212 | 1.25 | 2021-04 | 0 | 0
889 | CR0013823 | CTASK0026372 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2021-04-27 02:00 | 2021-04-01 02:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Test]Korea customs required to apply new location code in EDI. | 2021-04-15 13:47 | 2021-04-22 | 2021-04-21 10:29 | 2021-04-22 13:35 | 2021-04-22 14:52 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-23 13:20 | 2021-05-27 14:00 | CR0013823 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W17 | 2021-04 | 32 | 32 | 11.8426 | 5 | 1 | 1 | 0.11 | 193506 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 1.1212 | 1.25 | 2021-04 | 0 | 0
890 | CR0013823 | CTASK0026373 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 4 | 4 | 2021-04-27 02:00 | 2021-04-01 02:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Deploy]Korea customs required to apply new location code in EDI. | 2021-04-15 13:47 | 2021-04-22 | 2021-04-21 10:29 | 2021-04-22 13:35 | 2021-04-22 14:52 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-23 13:20 | 2021-05-27 14:00 | CR0013823 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W17 | 2021-04 | 32 | 32 | 11.8426 | 5 | 1 | 1 | 0.11 | 193506 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 1.1212 | 1.25 | 2021-04 | 0 | 0
891 | CR0013823 | CTASK0026371 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2021-04-27 02:00 | 2021-04-01 02:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Dev]Korea customs required to apply new location code in EDI. | 2021-04-15 13:47 | 2021-04-22 | 2021-04-21 10:29 | 2021-04-22 13:35 | 2021-04-22 14:52 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-23 13:20 | 2021-05-27 14:00 | CR0013823 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W17 | 2021-04 | 32 | 32 | 11.8426 | 5 | 1 | 1 | 0.11 | 193506 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 1.1212 | 1.25 | 2021-04 | 0 | 0
892 | CR0013823 | CTASK0026630 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2021-04-27 02:00 | 2021-04-20 02:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [PROD]Korea customs required to apply new location code in EDI. | 2021-04-15 13:47 | 2021-04-22 | 2021-04-21 10:29 | 2021-04-22 13:35 | 2021-04-22 14:52 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-23 13:20 | 2021-05-27 14:00 | CR0013823 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2021-W17 | 2021-04 | 32 | 32 | 11.8426 | 5 | 1 | 1 | 0.11 | 193506 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 1.1212 | 1.25 | 2021-04 | 0 | 0
893 | CR0013423 | CTASK0026756 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2021-05-31 11:41 | 2021-05-17 11:41 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Deployment] [LA ENHANCEMENT] - SPC - To add Call Indicator within Standby Master Constraint | 2021-01-29 09:42 | 2021-02-27 | 2021-02-26 16:56 | 2021-05-14 09:51 | 2021-05-14 10:42 |  | 2021-05-25 10:00 | 2021-05-25 10:12 | 2021-05-20 14:08 | 2021-06-24 14:00 | CR0013423 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W21 | 2021-05 | 0 | 0 | 116.0128 | 4 | 1 | 1 | 0 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
894 | CR0013423 | CTASK0026754 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2021-05-15 01:39 | 2021-05-03 11:39 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Testing] [LA ENHANCEMENT] - SPC - To add Call Indicator within Standby Master Constraint | 2021-01-29 09:42 | 2021-02-27 | 2021-02-26 16:56 | 2021-05-14 09:51 | 2021-05-14 10:42 |  | 2021-05-25 10:00 | 2021-05-25 10:12 | 2021-05-20 14:08 | 2021-06-24 14:00 | CR0013423 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W21 | 2021-05 | 0 | 0 | 116.0128 | 4 | 1 | 1 | 0 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
895 | CR0013423 | CTASK0026753 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2021-05-07 01:38 | 2021-05-03 10:38 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Development] [LA ENHANCEMENT] - SPC - To add Call Indicator within Standby Master Constraint | 2021-01-29 09:42 | 2021-02-27 | 2021-02-26 16:56 | 2021-05-14 09:51 | 2021-05-14 10:42 |  | 2021-05-25 10:00 | 2021-05-25 10:12 | 2021-05-20 14:08 | 2021-06-24 14:00 | CR0013423 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W21 | 2021-05 | 0 | 0 | 116.0128 | 4 | 1 | 1 | 0 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
896 | CR0013423 | CTASK0026752 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2021-05-05 01:34 | 2021-05-03 02:34 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Design] [LA ENHANCEMENT] - SPC - To add Call Indicator within Standby Master Constraint | 2021-01-29 09:42 | 2021-02-27 | 2021-02-26 16:56 | 2021-05-14 09:51 | 2021-05-14 10:42 |  | 2021-05-25 10:00 | 2021-05-25 10:12 | 2021-05-20 14:08 | 2021-06-24 14:00 | CR0013423 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W21 | 2021-05 | 0 | 0 | 116.0128 | 4 | 1 | 1 | 0 | 153106 | 2.3 | 1 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0.22951 | 0.13043 | 2021-01 | 0 | 0
897 | CR0013761 | CTASK0026024 | Closed | OPUS-SCO | Chuong Ta | 10 | 10 | 2021-04-30 17:06 | 2021-04-01 17:06 | Container | Statement Management | Statement Common | Setup | Office Information |  | [Chuong Ta][Apr 2021][CLT Internal] Change the SCO Office Information to trace assigned customers from Collection agents | 2021-03-30 09:33 | 2021-05-31 09:33 | 2021-04-08 14:37 | 2021-04-14 17:09 | 2021-04-16 13:08 |  | 2021-04-27 10:00 | 2021-04-27 10:03 | 2021-04-20 14:40 | 2021-05-27 14:00 | CR0013761 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W17 | 2021-04 | 50 | 50 | 28.0186 | 5 | 1 | 3 | 0.07 | 183379 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.32 | 0.375 | 2021-03 | 0 | 0
898 | CR0013761 | CTASK0026023 | Closed | OPUS-SCO | Nguyen Ha Vi | 15 | 15 | 2021-04-30 17:03 | 2021-04-01 17:03 | Container | Statement Management | Statement Common | Setup | Office Information |  | [Vi Nguyen][Apr 2021][CLT Internal] Change the SCO Office Information to trace assigned customers from Collection agents | 2021-03-30 09:33 | 2021-05-31 09:33 | 2021-04-08 14:37 | 2021-04-14 17:09 | 2021-04-16 13:08 |  | 2021-04-27 10:00 | 2021-04-27 10:03 | 2021-04-20 14:40 | 2021-05-27 14:00 | CR0013761 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W17 | 2021-04 | 50 | 50 | 28.0186 | 5 | 1 | 3 | 0.07 | 203664 | 0.8 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 1.8182 | 1.2857 | 2021-03 | 0 | 0
899 | CR0013761 | CTASK0026026 | Closed | OPUS-SCO | Lien Le | 5 | 5 | 2021-03-31 17:09 | 2021-03-22 17:09 | Container | Statement Management | Statement Common | Setup | Office Information |  | [Lien Le][Mar 2021][CLT Internal] Change the SCO Office Information to trace assigned customers from Collection agents | 2021-03-30 09:33 | 2021-05-31 09:33 | 2021-04-08 14:37 | 2021-04-14 17:09 | 2021-04-16 13:08 |  | 2021-04-27 10:00 | 2021-04-27 10:03 | 2021-04-20 14:40 | 2021-05-27 14:00 | CR0013761 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W17 | 2021-04 | 50 | 50 | 28.0186 | 5 | 1 | 3 | 0.07 | 193441 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.42308 | 0 | 2021-03 | 0 | 0
900 | CR0013761 | CTASK0026025 | Closed | OPUS-SCO | Chuong Ta | 10 | 10 | 2021-03-31 17:09 | 2021-03-22 17:09 | Container | Statement Management | Statement Common | Setup | Office Information |  | [Chuong Ta][Mar 2021][CLT Internal] Change the SCO Office Information to trace assigned customers from Collection agents | 2021-03-30 09:33 | 2021-05-31 09:33 | 2021-04-08 14:37 | 2021-04-14 17:09 | 2021-04-16 13:08 |  | 2021-04-27 10:00 | 2021-04-27 10:03 | 2021-04-20 14:40 | 2021-05-27 14:00 | CR0013761 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W17 | 2021-04 | 50 | 50 | 28.0186 | 5 | 1 | 3 | 0.07 | 183379 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 0.32 | 0.375 | 2021-03 | 0 | 0
901 | CR0013761 | CTASK0026022 | Closed | OPUS-SCO | Nguyen Ha Vi | 10 | 10 | 2021-03-31 17:02 | 2021-03-22 17:02 | Container | Statement Management | Statement Common | Setup | Office Information |  | [Vi Nguyen][Mar 2021][CLT Internal] Change the SCO Office Information to trace assigned customers from Collection agents | 2021-03-30 09:33 | 2021-05-31 09:33 | 2021-04-08 14:37 | 2021-04-14 17:09 | 2021-04-16 13:08 |  | 2021-04-27 10:00 | 2021-04-27 10:03 | 2021-04-20 14:40 | 2021-05-27 14:00 | CR0013761 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W17 | 2021-04 | 50 | 50 | 28.0186 | 5 | 1 | 3 | 0.07 | 203664 | 0.8 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 27 | 1.8182 | 1.2857 | 2021-03 | 0 | 0
902 | CR0012564 | CTASK0020423 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-07-21 22:06 | 2020-07-14 18:06 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Development] [CLT Internal] Data Integrity Enhancement for BKG_DG_DECL. | 2020-07-15 10:26 | 2020-08-06 | 2020-08-04 11:51 | 2020-08-06 09:22 | 2020-08-07 10:26 |  | 2020-08-18 10:00 | 2020-08-18 10:00 | 2020-08-07 10:27 | 2020-08-18 14:54 | CR0012564 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W34 | 2020-08 | 27 | 27 | 33.9821 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 30 | 0 | 0.52941 | 2020-07 | 0 | 0
903 | CR0012564 | CTASK0021616 | Closed | OPUS-BKG-M | Thien Lai | 3 | 3 | 2020-07-31 17:25 | 2020-07-29 17:25 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Testing] [CLT Internal] Data Integrity Enhancement for BKG_DG_DECL. | 2020-07-15 10:26 | 2020-08-06 | 2020-08-04 11:51 | 2020-08-06 09:22 | 2020-08-07 10:26 |  | 2020-08-18 10:00 | 2020-08-18 10:00 | 2020-08-07 10:27 | 2020-08-18 14:54 | CR0012564 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W34 | 2020-08 | 27 | 27 | 33.9821 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 30 | 0 | 0.52941 | 2020-07 | 0 | 0
904 | CR0012564 | CTASK0020431 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-08-18 18:49 | 2020-08-11 18:49 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Deployment] [CLT Internal] Data Integrity Enhancement for BKG_DG_DECL. | 2020-07-15 10:26 | 2020-08-06 | 2020-08-04 11:51 | 2020-08-06 09:22 | 2020-08-07 10:26 |  | 2020-08-18 10:00 | 2020-08-18 10:00 | 2020-08-07 10:27 | 2020-08-18 14:54 | CR0012564 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W34 | 2020-08 | 27 | 27 | 33.9821 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 30 | 0 | 0.52941 | 2020-07 | 0 | 0
905 | CR0012564 | CTASK0020267 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-05-30 00:07 | 2020-05-22 09:07 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Design] [CLT Internal] Data Integrity Enhancement for BKG_DG_DECL | 2020-07-15 10:26 | 2020-08-06 | 2020-08-04 11:51 | 2020-08-06 09:22 | 2020-08-07 10:26 |  | 2020-08-18 10:00 | 2020-08-18 10:00 | 2020-08-07 10:27 | 2020-08-18 14:54 | CR0012564 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W34 | 2020-08 | 27 | 27 | 33.9821 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 30 | 0 | 0.52941 | 2020-07 | 0 | 0
906 | CR0012564 | CTASK0020425 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-07-21 22:07 | 2020-07-14 18:07 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Testing] [CLT Internal] Data Integrity Enhancement for BKG_DG_DECL. | 2020-07-15 10:26 | 2020-08-06 | 2020-08-04 11:51 | 2020-08-06 09:22 | 2020-08-07 10:26 |  | 2020-08-18 10:00 | 2020-08-18 10:00 | 2020-08-07 10:27 | 2020-08-18 14:54 | CR0012564 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2020-W34 | 2020-08 | 27 | 27 | 33.9821 | 5 | 1 | 1 | 0.03 | 193567 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 30 | 0 | 0.52941 | 2020-07 | 0 | 0
907 | CR0012281 | CTASK0018564 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-05-09 00:13 | 2020-05-01 09:13 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal] Booking Creation FAX/EDI popup performance enhancement | 2020-03-06 19:09 | 2020-04-23 | 2020-04-17 17:10 | 2020-04-22 01:30 | 2020-04-28 17:36 |  | 2020-05-12 10:00 | 2020-05-12 10:00 | 2020-04-28 17:36 | 2020-06-11 13:00 | CR0012281 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W20 | 2020-05 | 39 | 41 | 66.6184 | 5 | 1 | 2 | 0.03 | 193567 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.52941 | 2020-03 | 0 | 0
908 | CR0012281 | CTASK0018559 | Closed | OPUS-BKG-M | Thien Lai | 6 | 6 | 2020-03-13 15:34 | 2020-03-09 15:34 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal] Booking Creation FAX/EDI popup performance enhancement | 2020-03-06 19:09 | 2020-04-23 | 2020-04-17 17:10 | 2020-04-22 01:30 | 2020-04-28 17:36 |  | 2020-05-12 10:00 | 2020-05-12 10:00 | 2020-04-28 17:36 | 2020-06-11 13:00 | CR0012281 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W20 | 2020-05 | 39 | 41 | 66.6184 | 5 | 1 | 2 | 0.03 | 193567 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.52941 | 2020-03 | 0 | 0
909 | CR0012281 | CTASK0019402 | Closed | OPUS-BKG-M | Kieu Le | 6 | 7 | 2020-04-09 01:44 | 2020-04-06 02:44 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] Booking Creation FAX/EDI popup performance enhancement | 2020-03-06 19:09 | 2020-04-23 | 2020-04-17 17:10 | 2020-04-22 01:30 | 2020-04-28 17:36 |  | 2020-05-12 10:00 | 2020-05-12 10:00 | 2020-04-28 17:36 | 2020-06-11 13:00 | CR0012281 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W20 | 2020-05 | 39 | 41 | 66.6184 | 5 | 1 | 2 | 0.03 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.4 | 2020-03 | 0 | 0
910 | CR0012281 | CTASK0018561 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-03-20 15:34 | 2020-03-16 15:33 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] Booking Creation FAX/EDI popup performance enhancement | 2020-03-06 19:09 | 2020-04-23 | 2020-04-17 17:10 | 2020-04-22 01:30 | 2020-04-28 17:36 |  | 2020-05-12 10:00 | 2020-05-12 10:00 | 2020-04-28 17:36 | 2020-06-11 13:00 | CR0012281 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W20 | 2020-05 | 39 | 41 | 66.6184 | 5 | 1 | 2 | 0.03 | 193567 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.52941 | 2020-03 | 0 | 0
911 | CR0012281 | CTASK0018508 | Closed | OPUS-BKG-M | Thien Lai | 15 | 16 | 2020-02-21 19:54 | 2020-02-20 19:54 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal] Booking Creation FAX/EDI popup performance enhancement | 2020-03-06 19:09 | 2020-04-23 | 2020-04-17 17:10 | 2020-04-22 01:30 | 2020-04-28 17:36 |  | 2020-05-12 10:00 | 2020-05-12 10:00 | 2020-04-28 17:36 | 2020-06-11 13:00 | CR0012281 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W20 | 2020-05 | 39 | 41 | 66.6184 | 5 | 1 | 2 | 0.03 | 193567 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.52941 | 2020-03 | 0 | 0
912 | CR0011875 | CTASK0022061 | Closed | OPUS-DMT | Cuong Nguyen | 5 | 6 | 2020-12-25 20:00 | 2020-12-01 08:00 | Container | Service Management | Demurrage/Detention | Charge Generation | Charge Calculation | Charge Calculation by Booking | [C.TASK4] CLV_Pair Test | 2020-12-03 16:13 | 2020-12-25 20:00 | 2020-12-24 15:06 | 2021-01-28 12:49 | 2021-02-08 11:33 |  | 2021-02-16 10:00 | 2021-02-16 09:49 | 2021-02-08 11:45 | 2021-03-18 14:00 | CR0011875 | Service ManagementDemurrage/DetentionCharge GenerationCharge CalculationCharge Calculation by Booking | OPUS-DMT | 2021-W7 | 2021-02 | 5 | 6 | 74.7406 | 1 | 1 | 1 | 0 | 193529 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 21 | 0 | 0.058824 | 2020-12 | 0 | 0
913 | CR0012534 | CTASK0019916 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 57 | 55 | 2020-05-20 19:30 | 2020-04-29 11:00 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | [Developement + Testing + Deployment][CLT Internal] Need to change the DB function to CLOB function to avoid overflow error | 2020-05-21 16:35 | 2020-08-01 | 2020-05-27 16:54 | 2020-06-22 18:17 | 2020-06-22 19:43 |  | 2020-06-30 09:30 | 2020-06-30 09:30 | 2020-07-02 17:34 | 2020-07-07 10:22 | CR0012534 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W27 | 2020-06 | 70 | 71 | 39.7049 | 2 | 1 | 1 | 0.07 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 29 | 0 | 0.18519 | 2020-05 | 0 | 0
914 | CR0012534 | CTASK0020244 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 13 | 16 | 2020-05-29 19:30 | 2020-05-21 11:00 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | [Deployment][CLT Internal] Need to change the DB function to CLOB function to avoid overflow error | 2020-05-21 16:35 | 2020-08-01 | 2020-05-27 16:54 | 2020-06-22 18:17 | 2020-06-22 19:43 |  | 2020-06-30 09:30 | 2020-06-30 09:30 | 2020-07-02 17:34 | 2020-07-07 10:22 | CR0012534 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W27 | 2020-06 | 70 | 71 | 39.7049 | 2 | 1 | 1 | 0.07 | 173280 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 29 | 0 | 0.18519 | 2020-05 | 0 | 0
915 | CR0013491 | CTASK0025919 | Closed | OPUS-SAP | Chuong Ta | 8 | 8 | 2021-03-31 16:33 | 2021-03-01 16:33 | Container | Service Management | Trans S/O | CSR | CSR Creation |  | NA *CSR* Expand CSR Tickets | 2021-04-14 10:32 | 2021-04-30 21:00 | 2021-04-20 09:42 | 2021-05-26 11:17 | 2021-05-28 09:48 |  | 2021-06-08 10:00 | 2021-06-08 10:00 | 2021-05-31 10:58 | 2021-06-22 08:18 | CR0013491 | Service ManagementTrans S/OCSRCSR Creation | OPUS-TRS | 2021-W23 | 2021-06 | 8 | 8 | 54.978 | 1 | 1 | 1 | 0.01 | 183379 | 2.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 53 | 0 | 0.375 | 2021-04 | 0 | 0
916 | CR0012027 | CTASK0018312 | Closed | OPUS-TES | Thai Nguyen | 204 | 210 | 2020-08-31 23:00 | 2020-02-11 09:00 | Container | Service Management | TML INV | Invoice | Invoice Creation | Off Dock CY Invoice Creation & Correction | [Actual] AR - BUE office OFF Doc CY Invoice applies all TIER tariffs - Does not apply correct TIER amount | 2020-03-23 16:25 | 2020-05-29 16:25 | 2020-05-20 16:26 | 2020-08-03 17:07 | 2020-08-05 15:34 |  | 2020-08-11 15:34 | 2020-08-11 10:21 | 2020-08-05 22:52 | 2020-09-10 13:00 | CR0012027 | Service ManagementTML INVInvoiceInvoice CreationOff Dock CY Invoice Creation & Correction | OPUS-TES | 2020-W33 | 2020-08 | 204 | 210 | 140.9641 | 1 | 1 | 1 | 0.06 | 173249 | 1.5 | 0 | 0 | 0 | 3 | 1 | 2 | 6 | 30 | 0 | 2 | 2020-03 | 0 | 0
917 | CR0013133 | CTASK0023942 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 72 | 70 | 2020-12-31 09:00 | 2020-12-01 09:00 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202012] (SVEG) EUA VEND : Regulatory Requirement - EU Full cntr Release via NXTPORT Secure Release Platform for BE customers | 2020-11-09 09:47 | 2020-12-31 21:00 | 2020-12-11 10:52 | 2020-12-28 14:02 | 2020-12-28 14:11 |  | 2021-01-12 10:00 | 2021-01-12 10:00 | 2020-12-29 11:20 | 2021-02-10 21:32 | CR0013133 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W2 | 2021-01 | 281 | 300 | 64.009 | 4 | 1 | 2 | 0.2 | 183432 | 1.7 | 0 | 0 | 0 | 3 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-11 | 0 | 0
918 | CR0013133 | CTASK0023943 | Closed | OPUS-TRS | Giang Nguyen Hoang | 68 | 70 | 2020-12-31 09:01 | 2020-12-01 09:01 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202012] (SVEG) EUA VEND : Regulatory Requirement - EU Full cntr Release via NXTPORT Secure Release Platform for BE customers | 2020-11-09 09:47 | 2020-12-31 21:00 | 2020-12-11 10:52 | 2020-12-28 14:02 | 2020-12-28 14:11 |  | 2021-01-12 10:00 | 2021-01-12 10:00 | 2020-12-29 11:20 | 2021-02-10 21:32 | CR0013133 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W2 | 2021-01 | 281 | 300 | 64.009 | 4 | 1 | 2 | 0.2 | 183440 | 1.7 | 0 | 0 | 0 | 3 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-11 | 0 | 0
919 | CR0013133 | CTASK0023301 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 67 | 80 | 2020-11-30 14:37 | 2020-11-02 14:37 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202011] (SVEG) EUA VEND : Regulatory Requirement - EU Full cntr Release via NXTPORT Secure Release Platform for BE customers | 2020-11-09 09:47 | 2020-12-31 21:00 | 2020-12-11 10:52 | 2020-12-28 14:02 | 2020-12-28 14:11 |  | 2021-01-12 10:00 | 2021-01-12 10:00 | 2020-12-29 11:20 | 2021-02-10 21:32 | CR0013133 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W2 | 2021-01 | 281 | 300 | 64.009 | 4 | 1 | 2 | 0.2 | 183432 | 1.7 | 0 | 0 | 0 | 3 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-11 | 0 | 0
920 | CR0013133 | CTASK0023302 | Closed | OPUS-TRS | Giang Nguyen Hoang | 74 | 80 | 2020-11-30 14:37 | 2020-11-02 14:37 | Container | Service Management | Trans S/O | Work Order | Issue |  | [202011] (SVEG) EUA VEND : Regulatory Requirement - EU Full cntr Release via NXTPORT Secure Release Platform for BE customers | 2020-11-09 09:47 | 2020-12-31 21:00 | 2020-12-11 10:52 | 2020-12-28 14:02 | 2020-12-28 14:11 |  | 2021-01-12 10:00 | 2021-01-12 10:00 | 2020-12-29 11:20 | 2021-02-10 21:32 | CR0013133 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2021-W2 | 2021-01 | 281 | 300 | 64.009 | 4 | 1 | 2 | 0.2 | 183440 | 1.7 | 0 | 0 | 0 | 3 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-11 | 0 | 0
921 | CR0011342 | CTASK0016744 | Closed | OPUS-EQR | Tien Le | 30 | 65 | 2019-11-30 | 2019-10-14 09:00 | Container | Equipment Management | EQ Reposition |  |  |  | GHQ EQR - EQR Closing Flag function | 2019-11-29 10:44 | 2019-11-29 23:00 | 2019-11-29 16:17 | 2020-03-23 20:45 | 2020-04-28 22:05 |  | 2020-05-08 10:30 | 2020-05-08 09:30 | 2020-04-29 10:24 | 2020-06-11 13:00 | CR0011342 | Equipment ManagementEQ Reposition | OPUS-EQR | 2020-W19 | 2020-05 | 242 | 140 | 160.9904 | 3 | 2 | 3 | 0.04 | 173286 | 1.2 | 0 | 0 | 0 | 2 | 1 | 3 | 4 | 26 | 0 | 0 | 2019-11 | 0 | 0
922 | CR0011342 | CTASK0019835 | Closed | OPUS-CTM | Tran Le | 9 | 10 |  |  | Container | Equipment Management | EQ Reposition |  |  |  | Investigate FS and integration test | 2019-11-29 10:44 | 2019-11-29 23:00 | 2019-11-29 16:17 | 2020-03-23 20:45 | 2020-04-28 22:05 |  | 2020-05-08 10:30 | 2020-05-08 09:30 | 2020-04-29 10:24 | 2020-06-11 13:00 | CR0011342 | Equipment ManagementEQ Reposition | OPUS-EQR | 2020-W19 | 2020-05 | 242 | 140 | 160.9904 | 3 | 2 | 3 | 0.04 | 193501 | 0.1 | 0 | 0 | 0 | 2 | 1 | 3 | 4 | 26 | 0 | 0 | 2019-11 | 0 | 0
923 | CR0011342 | CTASK0015285 | Closed | OPUS-EQR | Tuyen Truong | 203 | 65 | 2019-11-30 | 2019-10-14 09:00 | Container | Equipment Management | EQ Reposition |  |  |  | GHQ EQR - EQR Closing Flag function | 2019-11-29 10:44 | 2019-11-29 23:00 | 2019-11-29 16:17 | 2020-03-23 20:45 | 2020-04-28 22:05 |  | 2020-05-08 10:30 | 2020-05-08 09:30 | 2020-04-29 10:24 | 2020-06-11 13:00 | CR0011342 | Equipment ManagementEQ Reposition | OPUS-EQR | 2020-W19 | 2020-05 | 242 | 140 | 160.9904 | 3 | 2 | 3 | 0.04 | 173255 | 1.2 | 0 | 0 | 0 | 2 | 1 | 3 | 4 | 26 | 0 | 0 | 2019-11 | 0 | 0
924 | CR0010723 | CTASK0020079 | Closed | OPUS-DMT | Cuong Nguyen | 17 | 16 | 2020-07-31 20:00 | 2020-07-01 08:00 | Container | Service Management | Demurrage/Detention | Charge Generation | Charge Calculation | Charge Calculation by CNTR | [CTASK6-CLV Pair Test] EUA DMT // DMT Coverage Adjustment functionality | 2020-05-25 09:57 | 2020-07-31 20:00 | 2020-07-31 13:32 | 2020-09-02 01:33 | 2020-09-02 08:09 |  | 2020-09-08 10:00 | 2020-09-08 09:37 | 2020-09-03 09:31 | 2020-10-08 13:00 | CR0010723 | Service ManagementDemurrage/DetentionCharge GenerationCharge CalculationCharge Calculation by CNTR | OPUS-DMT | 2020-W37 | 2020-09 | 80 | 68 | 106.0024 | 2 | 1 | 1 | 0.03 | 193529 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-05 | 0 | 0
925 | CR0010723 | CTASK0020078 | Closed | OPUS-DMT | Cuong Nguyen | 63 | 52 | 2020-06-12 20:00 | 2020-05-25 08:00 | Container | Service Management | Demurrage/Detention | Charge Generation | Charge Calculation | Charge Calculation by CNTR | [CTASK5-CLV Analysis_Development_Test_Deployment] EUA DMT // DMT Coverage Adjustment functionality | 2020-05-25 09:57 | 2020-07-31 20:00 | 2020-07-31 13:32 | 2020-09-02 01:33 | 2020-09-02 08:09 |  | 2020-09-08 10:00 | 2020-09-08 09:37 | 2020-09-03 09:31 | 2020-10-08 13:00 | CR0010723 | Service ManagementDemurrage/DetentionCharge GenerationCharge CalculationCharge Calculation by CNTR | OPUS-DMT | 2020-W37 | 2020-09 | 80 | 68 | 106.0024 | 2 | 1 | 1 | 0.03 | 193529 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-05 | 0 | 0
926 | CR0013309 | CTASK0025456 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 16 | 16 | 2021-02-26 23:00 | 2021-02-23 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Deployment]BL Ready for Release Batch Report: Change report to include countries and offices under Expdoc RPA Phase 1B | 2020-12-16 10:44 | 2020-12-30 | 2020-12-28 19:30 | 2021-02-23 14:38 | 2021-02-23 15:40 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-23 15:50 | 2021-03-23 20:18 | CR0013309 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W9 | 2021-03 | 36 | 36 | 75.9692 | 2 | 1 | 1 | 0.02 | 193470 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 0.17391 | 2020-12 | 0 | 0
927 | CR0013309 | CTASK0023849 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 20 | 20 | 2020-12-30 01:59 | 2020-11-27 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | BL Ready for Release Batch Report: Change report to include countries and offices under Expdoc RPA Phase 1B | 2020-12-16 10:44 | 2020-12-30 | 2020-12-28 19:30 | 2021-02-23 14:38 | 2021-02-23 15:40 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-23 15:50 | 2021-03-23 20:18 | CR0013309 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W9 | 2021-03 | 36 | 36 | 75.9692 | 2 | 1 | 1 | 0.02 | 193470 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 0.17391 | 2020-12 | 0 | 0
928 | CR0013780 | CTASK0026263 | Closed | OPUS-SCO | Nguyen Ha Vi | 24 | 24 | 2021-04-30 18:30 | 2021-04-01 09:30 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | DSO grouping by credit agreement | 2021-04-08 09:58 | 2021-04-30 09:58 | 2021-04-09 17:51 | 2021-04-14 15:56 | 2021-04-14 16:41 |  | 2021-04-12 10:00 | 2021-04-12 09:14 | 2021-04-14 17:49 | 2021-05-15 14:00 | CR0013780 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2021-W15 | 2021-04 | 30 | 30 | 4.0011 | 2 | 1 | 2 | 0.31 | 203664 | 0.8 | 1 | 1 | 0 | 1 | 1 | 1 | 7 | 27 | 1.8182 | 1.2857 | 2021-04 | 1 | 1
929 | CR0013780 | CTASK0026364 | Closed | OPUS-SCO | Lien Le | 6 | 6 | 2021-04-30 18:30 | 2021-04-01 09:30 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | DSO grouping by credit agreement | 2021-04-08 09:58 | 2021-04-30 09:58 | 2021-04-09 17:51 | 2021-04-14 15:56 | 2021-04-14 16:41 |  | 2021-04-12 10:00 | 2021-04-12 09:14 | 2021-04-14 17:49 | 2021-05-15 14:00 | CR0013780 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2021-W15 | 2021-04 | 30 | 30 | 4.0011 | 2 | 1 | 2 | 0.31 | 193441 | 2.1 | 1 | 1 | 0 | 1 | 1 | 1 | 7 | 27 | 0.42308 | 0 | 2021-04 | 1 | 1
930 | CR0010828 | CTASK0018506 | Closed | OPUS-BKG-RPT | Thai Nguyen Quoc | 4 | 4 | 2020-02-24 19:00 | 2020-02-20 18:42 | Container | Service Management | Booking/Documentation | Report | Booking Status Report |  | Add report items into Booking Status Report | 2019-10-10 10:09 | 2019-12-11 | 2019-11-19 18:11 | 2020-02-12 12:53 | 2020-02-12 16:26 |  | 2020-03-10 09:00 | 2020-03-10 09:30 | 2020-02-28 11:01 | 2020-04-09 13:00 | CR0010828 | Service ManagementBooking/DocumentationReportBooking Status Report | OPUS-BKG-RPT | 2020-W11 | 2020-03 | 4 | 4 | 151.9519 | 1 | 1 | 1 | 0 | 193470 | 0.6 | 0 | 0 | 0 | 1 | 1 | 3 | 7 | 25 | 0 | 1.3333 | 2019-10 | 0 | 0
931 | CR0010949 | CTASK0018941 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 23 | 23 | 2020-03-25 10:57 | 2020-03-11 10:57 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Testing] Enable auto print function to Also Notify Party | 2019-08-12 12:32 | 2019-11-02 | 2019-11-01 15:49 | 2020-01-29 23:32 | 2020-01-30 14:40 |  | 2020-03-24 10:30 | 2020-03-24 10:00 | 2020-02-28 14:47 | 2020-04-23 13:00 | CR0010949 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W13 | 2020-03 | 23 | 23 | 224.915 | 1 | 1 | 1 | 0 | 193512 | 0.1 | 0 | 0 | 0 | 1 | 1 | 3 | 4 | 25 | 0 | 0.5 | 2019-08 | 0 | 0
932 | CR0013166 | CTASK0023501 | Closed | OPUS-PRI | Man Hoang | 97 | 90 | 2020-12-31 15:14 | 2020-11-09 15:14 | Container | Biz Common | Master Data | Partner | Group Customer |  | GHQ - MDA - Enhancement to <Group Customer Code> UI | 2020-11-11 15:22 | 2020-12-11 20:22 | 2020-12-11 11:56 | 2021-03-23 10:07 | 2021-03-23 10:08 |  | 2021-03-30 10:08 | 2021-03-30 23:30 | 2021-03-23 11:20 | 2021-04-30 14:00 | CR0013166 | Biz CommonMaster DataPartnerGroup Customer | OPUS-MDA | 2021-W13 | 2021-03 | 97 | 90 | 138.782 | 1 | 1 | 1 | 0.03 | 183431 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 46 | 0.58333 | 0.66667 | 2020-11 | 0 | 0
933 | CR0013389 | CTASK0026935 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 11 | 12 | 2021-05-31 17:20 | 2021-05-11 17:20 | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | [202105] NA *EDI* *CUSTOMS* VENDOR - Mapping of Consolidated Goods Flag in 404 EDI | 2021-05-11 17:18 | 2021-05-31 21:00 | 2021-05-27 09:59 | 2021-06-09 09:58 | 2021-06-15 09:50 |  | 2021-06-22 10:00 | 2021-06-22 14:24 | 2021-06-16 09:08 | 2021-06-22 14:29 | CR0013389 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2021-W25 | 2021-06 | 20 | 24 | 41.6955 | 2 | 1 | 2 | 0.02 | 183432 | 2.2 | 0 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0 | 0.22222 | 2021-05 | 0 | 0
934 | CR0013389 | CTASK0026936 | Closed | OPUS-TRS | Giang Nguyen Hoang | 9 | 12 | 2021-05-31 17:20 | 2021-05-11 17:20 | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | [202105] NA *EDI* *CUSTOMS* VENDOR - Mapping of Consolidated Goods Flag in 404 EDI | 2021-05-11 17:18 | 2021-05-31 21:00 | 2021-05-27 09:59 | 2021-06-09 09:58 | 2021-06-15 09:50 |  | 2021-06-22 10:00 | 2021-06-22 14:24 | 2021-06-16 09:08 | 2021-06-22 14:29 | CR0013389 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2021-W25 | 2021-06 | 20 | 24 | 41.6955 | 2 | 1 | 2 | 0.02 | 183440 | 2.2 | 0 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0 | 0 | 2021-05 | 0 | 0
935 | CR0014060 | CTASK0027634 | Closed | OPUS-SCO | Nguyen Ha Vi | 5 | 5 | 2021-06-30 10:43 | 2021-06-17 10:43 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Management By EMail |  | [June 2021][Vi Nguyen] [CLT Internal] Restriction on date retrieval condition from Collection Management By Email screen for NA users | 2021-06-17 11:47 | 2021-07-09 09:00 | 2021-06-28 16:58 | 2021-07-05 09:38 | 2021-07-05 09:56 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-06 08:43 | 2021-07-29 14:00 | CR0014060 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Management By EMail | OPUS-SAR | 2021-W28 | 2021-07 | 16 | 15 | 25.9257 | 2 | 2 | 2 | 0.02 | 203664 | 1 | 2 | 2 | 0 | 1 | 1 | 1 | 9 | 28 | 1.8182 | 2.5 | 2021-06 | 2 | 1
936 | CR0014060 | CTASK0027633 | Closed | OPUS-SAR | Lien Le | 11 | 10 | 2021-06-30 10:42 | 2021-06-17 10:42 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Management By EMail |  | [June 2021][Lien Le] [CLT Internal] Restriction on date retrieval condition from Collection Management By Email screen for NA users | 2021-06-17 11:47 | 2021-07-09 09:00 | 2021-06-28 16:58 | 2021-07-05 09:38 | 2021-07-05 09:56 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-06 08:43 | 2021-07-29 14:00 | CR0014060 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Management By EMail | OPUS-SAR | 2021-W28 | 2021-07 | 16 | 15 | 25.9257 | 2 | 2 | 2 | 0.02 | 193441 | 2.3 | 2 | 2 | 0 | 1 | 1 | 1 | 9 | 28 | 0.42308 | 0 | 2021-06 | 2 | 1
937 | CR0011438 | CTASK0015170 | Closed | OPUS-PSO | Hieu Vu | 14 | 14 |  |  | Container | Vessel Operation | Port Service Order | Invoice | Port charge Invoice Creation |  | [Development] Canal Transit Fee cost codes for EGSCA10 or PAPCA10 | 2019-07-12 10:34 | 2019-07-30 10:37 | 2019-07-18 08:52 | 2019-07-25 14:57 | 2019-08-06 10:20 |  | 2019-08-06 10:00 | 2019-08-06 09:00 | 2019-08-07 10:20 | 2019-08-07 11:35 | CR0011438 | Vessel OperationPort Service OrderInvoicePort charge Invoice Creation | OPUS-PSO | 2019-W32 | 2019-08 | 14 | 0 | 24.9767 | 1 | 1 | 1 | 0 | 183375 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 6 | 0 | 0 | 2019-07 | 0 | 0
938 | CR0012999 | CTASK0022093 | Closed | OPUS-BKG-OB | Nam Nguyen | 8 | 8 | 2020-10-12 12:02 | 2020-10-12 12:02 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Approval | [Deployment] [CLT Internal] C/A Approval - eliminate data instability | 2020-10-07 17:22 | 2020-10-17 | 2020-10-16 13:02 | 2020-10-29 08:47 | 2020-11-19 13:08 |  | 2020-12-22 10:00 | 2020-12-22 10:00 | 2020-11-19 13:10 | 2021-01-21 14:00 | CR0012999 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Approval | OPUS-BKG-M | 2020-W52 | 2020-12 | 66 | 72 | 75.6931 | 4 | 1 | 1 | 0.04 | 123048 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 30 | 0 | 0.047619 | 2020-10 | 0 | 0
939 | CR0012999 | CTASK0022005 | Closed | OPUS-BKG-OB | Nam Nguyen | 16 | 16 | 2020-08-25 23:54 | 2020-08-24 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Approval | [Estimation] [CLT Internal] C/A Approval - eliminate data instability | 2020-10-07 17:22 | 2020-10-17 | 2020-10-16 13:02 | 2020-10-29 08:47 | 2020-11-19 13:08 |  | 2020-12-22 10:00 | 2020-12-22 10:00 | 2020-11-19 13:10 | 2021-01-21 14:00 | CR0012999 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Approval | OPUS-BKG-M | 2020-W52 | 2020-12 | 66 | 72 | 75.6931 | 4 | 1 | 1 | 0.04 | 123048 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 30 | 0 | 0.047619 | 2020-10 | 0 | 0
940 | CR0012999 | CTASK0022091 | Closed | OPUS-BKG-OB | Nam Nguyen | 26 | 24 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Approval | [Development] [CLT Internal] C/A Approval - eliminate data instability | 2020-10-07 17:22 | 2020-10-17 | 2020-10-16 13:02 | 2020-10-29 08:47 | 2020-11-19 13:08 |  | 2020-12-22 10:00 | 2020-12-22 10:00 | 2020-11-19 13:10 | 2021-01-21 14:00 | CR0012999 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Approval | OPUS-BKG-M | 2020-W52 | 2020-12 | 66 | 72 | 75.6931 | 4 | 1 | 1 | 0.04 | 123048 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 30 | 0 | 0.047619 | 2020-10 | 0 | 0
941 | CR0012999 | CTASK0022092 | Closed | OPUS-BKG-OB | Nam Nguyen | 24 | 24 | 2020-12-31 12:17 | 2020-12-01 12:17 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Approval | [Test][CLT Internal] C/A Approval - eliminate data instability | 2020-10-07 17:22 | 2020-10-17 | 2020-10-16 13:02 | 2020-10-29 08:47 | 2020-11-19 13:08 |  | 2020-12-22 10:00 | 2020-12-22 10:00 | 2020-11-19 13:10 | 2021-01-21 14:00 | CR0012999 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Approval | OPUS-BKG-M | 2020-W52 | 2020-12 | 66 | 72 | 75.6931 | 4 | 1 | 1 | 0.04 | 123048 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 30 | 0 | 0.047619 | 2020-10 | 0 | 0
942 | CR0012393 | CTASK0020680 | Closed | OPUS-SPC | Thuan Tran | 19 | 19 | 2020-07-21 17:13 | 2020-06-08 17:13 | Container | Sales Management | Space Control | Allocation Control | Bottleneck Check |  | Additional logic in SPC bottleneck check to pick EQR closed qty if EQR is manually closed before vessel ATD | 2020-06-17 17:15 | 2020-07-31 17:14 | 2020-07-17 16:18 | 2020-08-31 17:12 | 2020-09-03 11:14 |  | 2020-09-10 11:14 | 2020-09-01 10:15 | 2020-09-03 13:38 | 2020-10-10 13:00 | CR0012393 | Sales ManagementSpace ControlAllocation ControlBottleneck Check | OPUS-SPC | 2020-W37 | 2020-09 | 60 | 60 | 84.7494 | 2 | 1 | 2 | 0.03 | 183423 | 1.6 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-06 | 0 | 0
943 | CR0012393 | CTASK0020679 | Closed | OPUS-SPC | Linh Nguyen | 41 | 41 | 2020-07-19 17:12 | 2020-06-08 17:11 | Container | Sales Management | Space Control | Allocation Control | Bottleneck Check |  | Additional logic in SPC bottleneck check to pick EQR closed qty if EQR is manually closed before vessel ATD | 2020-06-17 17:15 | 2020-07-31 17:14 | 2020-07-17 16:18 | 2020-08-31 17:12 | 2020-09-03 11:14 |  | 2020-09-10 11:14 | 2020-09-01 10:15 | 2020-09-03 13:38 | 2020-10-10 13:00 | CR0012393 | Sales ManagementSpace ControlAllocation ControlBottleneck Check | OPUS-SPC | 2020-W37 | 2020-09 | 60 | 60 | 84.7494 | 2 | 1 | 2 | 0.03 | 193464 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-06 | 0 | 0
944 | CR0011392 | CTASK0015624 | Closed | OPUS-TES | Thai Nguyen | 20 | 20 |  |  | Container | Service Management | TML INV |  |  |  | (actual) RE: TES invoice not verifying containers (request to add validation logic in TES ) | 2019-07-22 10:34 | 2019-10-12 | 2019-08-09 17:14 | 2019-08-14 16:43 | 2019-08-28 14:37 |  | 2019-09-03 09:00 | 2019-09-03 09:51 | 2019-08-28 14:39 | 2019-10-03 13:00 | CR0011392 | Service ManagementTML INV | OPUS-TES | 2019-W36 | 2019-09 | 20 | 0 | 42.9348 | 1 | 1 | 1 | 0 | 173249 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 6 | 0 | 0.6 | 2019-07 | 0 | 0
945 | CR0011870 | CTASK0018937 | Closed | OPUS-BKG-M | Loc Tran | 2 | 2 | 2020-06-12 12:30 | 2020-06-09 12:30 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal] Enhance Route Detail popup | 2020-03-16 11:59 | 2020-04-23 | 2020-04-20 16:49 | 2020-04-22 01:32 | 2020-06-01 19:14 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-01 19:14 | 2020-07-17 13:00 | CR0011870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W25 | 2020-06 | 40 | 44 | 91.9173 | 5 | 1 | 2 | 0.02 | 193503 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.36364 | 2020-03 | 0 | 0
946 | CR0011870 | CTASK0018754 | Closed | OPUS-BKG-M | Loc Tran | 10 | 10 | 2020-03-10 19:47 | 2020-03-04 14:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] Enhance Route Detail popup | 2020-03-16 11:59 | 2020-04-23 | 2020-04-20 16:49 | 2020-04-22 01:32 | 2020-06-01 19:14 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-01 19:14 | 2020-07-17 13:00 | CR0011870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W25 | 2020-06 | 40 | 44 | 91.9173 | 5 | 1 | 2 | 0.02 | 193503 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.36364 | 2020-03 | 0 | 0
947 | CR0011870 | CTASK0018936 | Closed | OPUS-BKG-M | Loc Tran | 7 | 8 | 2020-03-27 18:00 | 2020-03-25 10:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] Enhance Route Detail popup | 2020-03-16 11:59 | 2020-04-23 | 2020-04-20 16:49 | 2020-04-22 01:32 | 2020-06-01 19:14 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-01 19:14 | 2020-07-17 13:00 | CR0011870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W25 | 2020-06 | 40 | 44 | 91.9173 | 5 | 1 | 2 | 0.02 | 193503 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.36364 | 2020-03 | 0 | 0
948 | CR0011870 | CTASK0018934 | Closed | OPUS-BKG-M | Loc Tran | 14 | 16 | 2020-03-27 18:00 | 2020-03-23 10:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal] Enhance Route Detail popup | 2020-03-16 11:59 | 2020-04-23 | 2020-04-20 16:49 | 2020-04-22 01:32 | 2020-06-01 19:14 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-01 19:14 | 2020-07-17 13:00 | CR0011870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W25 | 2020-06 | 40 | 44 | 91.9173 | 5 | 1 | 2 | 0.02 | 193503 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.36364 | 2020-03 | 0 | 0
949 | CR0011870 | CTASK0018942 | Closed | OPUS-BKG-M | Kieu Le | 7 | 8 | 2020-04-10 18:51 | 2020-04-06 18:49 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] Enhance Route Detail popup | 2020-03-16 11:59 | 2020-04-23 | 2020-04-20 16:49 | 2020-04-22 01:32 | 2020-06-01 19:14 |  | 2020-06-16 10:00 | 2020-06-16 10:00 | 2020-06-01 19:14 | 2020-07-17 13:00 | CR0011870 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W25 | 2020-06 | 40 | 44 | 91.9173 | 5 | 1 | 2 | 0.02 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 29 | 0 | 0.4 | 2020-03 | 0 | 0
950 | CR0011778 | CTASK0016548 | Closed | OPUS-BKG-OB | Nam Nguyen | 33 | 51 | 2019-11-29 14:15 | 2019-10-01 14:15 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | (SCMT) new requirement and Sitpro mapping | 2019-10-10 13:05 | 2019-10-14 13:04 | 2019-10-14 11:20 | 2019-12-11 16:11 | 2019-12-11 16:48 |  | 2019-12-17 10:00 | 2019-12-17 10:46 | 2019-12-11 17:53 | 2020-01-16 14:00 | CR0011778 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2019-W51 | 2019-12 | 135 | 101 | 67.8719 | 3 | 3 | 3 | 0.06 | 123048 | 1 | 0 | 0 | 1 | 2 | 1 | 2 | 4 | 18 | 0 | 0.46154 | 2019-10 | 1 | 1
951 | CR0011778 | CTASK0016554 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 58 | 14 | 2019-10-09 13:00 | 2019-10-02 15:04 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | (SCMT) new requirement and Sitpro mapping - Sitpro India | 2019-10-10 13:05 | 2019-10-14 13:04 | 2019-10-14 11:20 | 2019-12-11 16:11 | 2019-12-11 16:48 |  | 2019-12-17 10:00 | 2019-12-17 10:46 | 2019-12-11 17:53 | 2020-01-16 14:00 | CR0011778 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2019-W51 | 2019-12 | 135 | 101 | 67.8719 | 3 | 3 | 3 | 0.06 | 173280 | 0.8 | 0 | 0 | 1 | 2 | 1 | 2 | 4 | 18 | 0 | 0 | 2019-10 | 1 | 1
952 | CR0011778 | CTASK0016551 | Closed | OPUS-BKG-M | Thien Lai | 44 | 36 | 2019-10-11 11:11 | 2019-09-30 11:10 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | (SCMT) new requirement and Sitpro mapping | 2019-10-10 13:05 | 2019-10-14 13:04 | 2019-10-14 11:20 | 2019-12-11 16:11 | 2019-12-11 16:48 |  | 2019-12-17 10:00 | 2019-12-17 10:46 | 2019-12-11 17:53 | 2020-01-16 14:00 | CR0011778 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2019-W51 | 2019-12 | 135 | 101 | 67.8719 | 3 | 3 | 3 | 0.06 | 193567 | 0.2 | 0 | 0 | 1 | 2 | 1 | 2 | 4 | 18 | 0 | 0.52941 | 2019-10 | 1 | 1
953 | CR0011766 | CTASK0016759 | Closed | OPUS-SAP | Lien Le | 6 | 6 |  |  | Container | Statement Management | Statement Account Payable |  |  |  | Change AP interface layput | 2019-10-11 14:36 | 2019-12-31 14:36 | 2019-10-25 18:20 | 2019-12-09 12:18 | 2019-12-09 12:20 |  | 2019-12-17 12:20 | 2019-12-17 19:53 | 2019-12-09 12:36 | 2020-01-17 14:00 | CR0011766 | Statement ManagementStatement Account Payable | OPUS-SAP | 2019-W51 | 2019-12 | 6 | 0 | 66.9051 | 1 | 1 | 1 | 0 | 193441 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 18 | 0 | 0 | 2019-10 | 0 | 0
954 | CR0013239 | CTASK0023483 | Closed | OPUS-BKG-OB | Nam Nguyen | 38 | 36 | 2021-01-16 18:23 | 2020-12-29 18:23 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [CLT Internal] Type of BL Data complete change event logging on BKG History | 2020-11-11 14:12 | 2020-12-03 | 2020-12-02 17:13 | 2021-05-18 11:41 | 2021-05-31 10:57 |  | 2021-06-15 10:00 | 2021-06-15 11:00 | 2021-05-31 10:58 | 2021-07-16 14:00 | CR0013239 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W24 | 2021-06 | 38 | 36 | 215.8251 | 1 | 1 | 1 | 0.01 | 123048 | 2.1 | 1 | 0 | 0 | 1 | 1 | 3 | 11 | 53 | 0.22222 | 0.047619 | 2020-11 | 0 | 0
955 | CR0013639 | CTASK0025559 | Closed | OPUS-BKG-M | Vinh Tran | 4 | 4 | 2021-06-17 02:00 | 2021-06-16 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Deployment] [CLT Internal] Supplement to CR0010299 to validate multi-stop date by chronological order in each multi-stop. | 2021-03-08 17:37 | 2021-03-25 | 2021-03-24 17:37 | 2021-05-13 17:16 | 2021-06-15 09:42 |  | 2021-06-22 10:00 | 2021-06-29 11:18 | 2021-06-16 09:03 | 2021-07-29 14:00 | CR0013639 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2021-W25 | 2021-06 | 56 | 56 | 105.6824 | 4 | 1 | 1 | 0.02 | 193525 | 1.8 | 2 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
956 | CR0013639 | CTASK0025556 | Closed | OPUS-BKG-M | Vinh Tran | 20 | 20 | 2021-03-25 02:00 | 2021-03-18 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Testing] [CLT Internal] Supplement to CR0010299 to validate multi-stop date by chronological order in each multi-stop. | 2021-03-08 17:37 | 2021-03-25 | 2021-03-24 17:37 | 2021-05-13 17:16 | 2021-06-15 09:42 |  | 2021-06-22 10:00 | 2021-06-29 11:18 | 2021-06-16 09:03 | 2021-07-29 14:00 | CR0013639 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2021-W25 | 2021-06 | 56 | 56 | 105.6824 | 4 | 1 | 1 | 0.02 | 193525 | 1.8 | 2 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
957 | CR0013639 | CTASK0025555 | Closed | OPUS-BKG-M | Vinh Tran | 24 | 24 | 2021-03-20 02:00 | 2021-03-15 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Development] [CLT Internal] Supplement to CR0010299 to validate multi-stop date by chronological order in each multi-stop. | 2021-03-08 17:37 | 2021-03-25 | 2021-03-24 17:37 | 2021-05-13 17:16 | 2021-06-15 09:42 |  | 2021-06-22 10:00 | 2021-06-29 11:18 | 2021-06-16 09:03 | 2021-07-29 14:00 | CR0013639 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2021-W25 | 2021-06 | 56 | 56 | 105.6824 | 4 | 1 | 1 | 0.02 | 193525 | 1.8 | 2 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
958 | CR0013639 | CTASK0025536 | Closed | OPUS-BKG-M | Vinh Tran | 8 | 8 | 2021-02-27 02:00 | 2021-02-22 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Design][CLT Internal] Supplement to CR0010299 to validate multi-stop date by chronological order in each multi-stop. | 2021-03-08 17:37 | 2021-03-25 | 2021-03-24 17:37 | 2021-05-13 17:16 | 2021-06-15 09:42 |  | 2021-06-22 10:00 | 2021-06-29 11:18 | 2021-06-16 09:03 | 2021-07-29 14:00 | CR0013639 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2021-W25 | 2021-06 | 56 | 56 | 105.6824 | 4 | 1 | 1 | 0.02 | 193525 | 1.8 | 2 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
959 | CR0013015 | CTASK0022587 | Closed | OPUS-BKG-IB | Thuc Tran | 2 | 2 | 2020-09-21 19:30 | 2020-09-21 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Estimation] EUA CR - Hide PIN# on D/O - Supplemental to CR0012203 | 2020-09-23 11:25 | 2020-10-30 23:24 | 2020-10-30 17:55 | 2020-11-05 20:40 | 2020-11-10 11:01 |  | 2020-11-17 11:00 | 2020-11-17 13:49 | 2020-11-11 16:00 | 2020-12-17 14:00 | CR0013015 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W47 | 2020-11 | 36 | 36 | 54.9827 | 4 | 1 | 1 | 0.03 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.18519 | 2020-09 | 0 | 0
960 | CR0013015 | CTASK0023493 | Closed | OPUS-BKG-IB | Thuc Tran | 6 | 6 | 2020-11-16 19:30 | 2020-11-09 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Deployment & Inspection]EUA CR - Hide PIN# on D/O - Supplemental to CR0012203 | 2020-09-23 11:25 | 2020-10-30 23:24 | 2020-10-30 17:55 | 2020-11-05 20:40 | 2020-11-10 11:01 |  | 2020-11-17 11:00 | 2020-11-17 13:49 | 2020-11-11 16:00 | 2020-12-17 14:00 | CR0013015 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W47 | 2020-11 | 36 | 36 | 54.9827 | 4 | 1 | 1 | 0.03 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.18519 | 2020-09 | 0 | 0
961 | CR0013015 | CTASK0022639 | Closed | OPUS-BKG-IB | Thuc Tran | 25 | 25 | 2020-10-30 19:30 | 2020-09-23 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Development + Inspection + Deployment] EUA CR - Hide PIN# on D/O - Supplemental to CR0012203 | 2020-09-23 11:25 | 2020-10-30 23:24 | 2020-10-30 17:55 | 2020-11-05 20:40 | 2020-11-10 11:01 |  | 2020-11-17 11:00 | 2020-11-17 13:49 | 2020-11-11 16:00 | 2020-12-17 14:00 | CR0013015 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W47 | 2020-11 | 36 | 36 | 54.9827 | 4 | 1 | 1 | 0.03 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.18519 | 2020-09 | 0 | 0
962 | CR0013015 | CTASK0023358 | Closed | OPUS-BKG-IB | Thuc Tran | 3 | 3 | 2020-11-04 19:30 | 2020-11-04 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Development] EUA CR - Hide PIN# on D/O - Supplemental to CR0012203 | 2020-09-23 11:25 | 2020-10-30 23:24 | 2020-10-30 17:55 | 2020-11-05 20:40 | 2020-11-10 11:01 |  | 2020-11-17 11:00 | 2020-11-17 13:49 | 2020-11-11 16:00 | 2020-12-17 14:00 | CR0013015 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W47 | 2020-11 | 36 | 36 | 54.9827 | 4 | 1 | 1 | 0.03 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.18519 | 2020-09 | 0 | 0
963 | CR0011823 | CTASK0017787 | Closed | OPUS-SCG | Pham Khanh Van | 95 | 80 |  |  | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] Add new field "Partner APVL No" in Awkward, Break-Bulk, Special Stow Application | 2020-01-08 11:29 | 2020-02-26 | 2020-02-25 16:30 | 2020-05-18 15:33 | 2020-05-20 13:14 |  | 2020-06-02 10:00 | 2020-06-02 09:30 | 2020-05-21 15:56 | 2020-07-02 13:00 | CR0011823 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W23 | 2020-06 | 95 | 80 | 145.938 | 1 | 1 | 1 | 0.02 | 193477 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0 | 2020-01 | 0 | 0
964 | CR0012053 | CTASK0017499 | Closed | OPUS-BKG-M | Vinh Tran | 24 | 24 | 2019-12-20 22:22 | 2019-12-16 22:21 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI |  | NYSHEX EDI logic needs to be changed | 2019-12-19 13:29 | 2019-12-24 | 2019-12-23 14:58 | 2020-01-09 17:42 | 2020-01-09 17:50 | 2019-12-23 14:58 | 2020-01-21 17:50 | 2020-01-28 11:14 | 2020-01-29 10:34 | 2020-02-28 14:00 | CR0012053 | Service ManagementBooking/DocumentationBookingFax/Email/EDI | OPUS-BKG-M | 2020-W4 | 2020-01 | 33 | 24 | 33.1806 | 2 | 1 | 1 | 0.03 | 193525 | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 10 | 0 | 0.45455 | 2019-12 | 0 | 0
965 | CR0012053 | CTASK0017485 | Closed | OPUS-BKG-M | Vinh Tran | 9 | 9 |  |  | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI |  | [Estimate] NYSHEX EDI logic needs to be changed | 2019-12-19 13:29 | 2019-12-24 | 2019-12-23 14:58 | 2020-01-09 17:42 | 2020-01-09 17:50 | 2019-12-23 14:58 | 2020-01-21 17:50 | 2020-01-28 11:14 | 2020-01-29 10:34 | 2020-02-28 14:00 | CR0012053 | Service ManagementBooking/DocumentationBookingFax/Email/EDI | OPUS-BKG-M | 2020-W4 | 2020-01 | 33 | 24 | 33.1806 | 2 | 1 | 1 | 0.03 | 193525 | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 10 | 0 | 0.45455 | 2019-12 | 0 | 0
966 | CR0012806 | CTASK0022292 | Closed | OPUS-BKG-OB | Nam Nguyen | 35 | 34 | 2020-09-10 23:39 | 2020-09-04 23:39 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Analysis+Development+Testing] Send BL image with filename based on customer request | 2020-09-16 15:53 | 2020-10-21 | 2020-10-19 11:51 | 2020-11-10 13:45 | 2020-11-11 16:16 |  | 2020-12-01 10:00 | 2020-12-01 10:30 | 2020-11-12 13:20 | 2020-12-31 14:00 | CR0012806 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W49 | 2020-12 | 35 | 34 | 75.7551 | 1 | 1 | 1 | 0.02 | 123048 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0.46154 | 2020-09 | 0 | 0
967 | CR0012913 | CTASK0021922 | Closed | OPUS-MNR | Tuyen Truong | 28 | 28 | 2020-09-05 01:00 | 2020-09-01 10:00 | Container | Equipment Management | M&R |  |  |  | GHQ - MNR Shipment Cost Assignment Logic Fix | 2020-09-24 16:53 | 2020-09-25 23:00 | 2020-09-25 17:59 | 2020-10-05 17:28 | 2020-10-07 12:17 |  | 2021-01-12 10:00 | 2021-01-12 10:30 | 2020-10-08 13:21 | 2021-02-14 14:00 | CR0012913 | Equipment ManagementM&R | OPUS-MNR | 2021-W2 | 2021-01 | 317 | 168 | 109.7129 | 4 | 1 | 2 | 0.06 | 173255 | 2 | 0 | 0 | 0 | 2 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-09 | 0 | 0
968 | CR0012913 | CTASK0021921 | Closed | OPUS-MNR | Tuyen Truong | 20 | 20 | 2020-09-01 01:00 | 2020-08-19 10:00 | Container | Equipment Management | M&R |  |  |  | GHQ - MNR Shipment Cost Assignment Logic Fix | 2020-09-24 16:53 | 2020-09-25 23:00 | 2020-09-25 17:59 | 2020-10-05 17:28 | 2020-10-07 12:17 |  | 2021-01-12 10:00 | 2021-01-12 10:30 | 2020-10-08 13:21 | 2021-02-14 14:00 | CR0012913 | Equipment ManagementM&R | OPUS-MNR | 2021-W2 | 2021-01 | 317 | 168 | 109.7129 | 4 | 1 | 2 | 0.06 | 173255 | 2 | 0 | 0 | 0 | 2 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-09 | 0 | 0
969 | CR0012913 | CTASK0021920 | Closed | OPUS-MNR | Tien Le | 135 | 35 | 2020-09-05 01:00 | 2020-09-01 10:00 | Container | Equipment Management | M&R |  |  |  | GHQ - MNR Shipment Cost Assignment Logic Fix | 2020-09-24 16:53 | 2020-09-25 23:00 | 2020-09-25 17:59 | 2020-10-05 17:28 | 2020-10-07 12:17 |  | 2021-01-12 10:00 | 2021-01-12 10:30 | 2020-10-08 13:21 | 2021-02-14 14:00 | CR0012913 | Equipment ManagementM&R | OPUS-MNR | 2021-W2 | 2021-01 | 317 | 168 | 109.7129 | 4 | 1 | 2 | 0.06 | 173286 | 2 | 0 | 0 | 0 | 2 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-09 | 0 | 0
970 | CR0012913 | CTASK0021915 | Closed | OPUS-MNR | Tien Le | 162 | 85 | 2020-09-01 01:00 | 2020-08-19 10:00 | Container | Equipment Management | M&R |  |  |  | [Documentation]GHQ - MNR Shipment Cost Assignment Logic Fix | 2020-09-24 16:53 | 2020-09-25 23:00 | 2020-09-25 17:59 | 2020-10-05 17:28 | 2020-10-07 12:17 |  | 2021-01-12 10:00 | 2021-01-12 10:30 | 2020-10-08 13:21 | 2021-02-14 14:00 | CR0012913 | Equipment ManagementM&R | OPUS-MNR | 2021-W2 | 2021-01 | 317 | 168 | 109.7129 | 4 | 1 | 2 | 0.06 | 173286 | 2 | 0 | 0 | 0 | 2 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-09 | 0 | 0
971 | CR0013262 | CTASK0024145 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 40 | 40 | 2021-01-29 02:00 | 2021-01-01 02:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [License Service] (HBA) EUA EDI AUTH¦ New EDI extraction option for GB customs | 2020-12-04 17:44 | 2020-12-16 | 2020-12-15 17:39 | 2020-12-29 10:47 | 2020-12-29 11:52 |  | 2020-12-30 10:00 | 2020-12-30 11:00 | 2020-12-29 11:58 | 2021-01-29 00:44 | CR0013262 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W53 | 2020-12 | 105 | 108 | 25.6781 | 3 | 1 | 1 | 0.18 | 193506 | 1.5 | 0 | 0 | 0 | 2 | 1 | 1 | 9 | 30 | 0 | 1.25 | 2020-12 | 0 | 0
972 | CR0013262 | CTASK0023991 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 57 | 60 | 2020-12-31 02:00 | 2020-12-03 02:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Dev-Test](HBA) EUA EDI AUTH¦ New EDI extraction option for GB customs | 2020-12-04 17:44 | 2020-12-16 | 2020-12-15 17:39 | 2020-12-29 10:47 | 2020-12-29 11:52 |  | 2020-12-30 10:00 | 2020-12-30 11:00 | 2020-12-29 11:58 | 2021-01-29 00:44 | CR0013262 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W53 | 2020-12 | 105 | 108 | 25.6781 | 3 | 1 | 1 | 0.18 | 193506 | 1.5 | 0 | 0 | 0 | 2 | 1 | 1 | 9 | 30 | 0 | 1.25 | 2020-12 | 0 | 0
973 | CR0013262 | CTASK0023983 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 8 | 8 | 2020-12-04 02:00 | 2020-12-03 02:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | (HBA) EUA EDI AUTH¦ New EDI extraction option for GB customs | 2020-12-04 17:44 | 2020-12-16 | 2020-12-15 17:39 | 2020-12-29 10:47 | 2020-12-29 11:52 |  | 2020-12-30 10:00 | 2020-12-30 11:00 | 2020-12-29 11:58 | 2021-01-29 00:44 | CR0013262 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2020-W53 | 2020-12 | 105 | 108 | 25.6781 | 3 | 1 | 1 | 0.18 | 193506 | 1.5 | 0 | 0 | 0 | 2 | 1 | 1 | 9 | 30 | 0 | 1.25 | 2020-12 | 0 | 0
974 | CR0011658 | CTASK0016177 | Closed | OPUS-BKG-M | Nam Nguyen | 10 | 12 | 2019-09-06 09:33 | 2019-09-02 09:33 | Container | Service Management | Booking/Documentation | Booking | Booking |  | ONE BRN Note under 'Declaimer' | 2019-08-29 12:58 | 2019-09-10 | 2019-09-04 11:21 | 2019-09-23 10:56 | 2019-09-23 14:47 | 2019-09-04 11:22 | 2019-10-01 14:47 | 2019-08-17 12:19 | 2019-09-27 14:34 | 2019-10-30 09:26 | CR0011658 | Service ManagementBooking/DocumentationBookingBooking | OPUS-BKG-M | 2019-W40 | 2019-10 | 10 | 12 | 33.0755 | 1 | 1 | 1 | 0.02 | 123048 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 10 | 0 | 0.5 | 2019-08 | 0 | 0
975 | CR0012532 | CTASK0019653 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2020-04-17 21:01 | 2020-04-13 21:01 | Container | Service Management | Booking/Documentation | Setup | Booking Receipt Notice & Draft BL Setup |  | [Design][CLT Internal] BRN Remarks UI setup (CSVC/EXP BOOKING) - CR0011132 enhancement | 2020-04-29 10:54 | 2020-06-25 | 2020-06-18 03:55 | 2020-06-22 18:16 | 2020-07-08 10:19 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:19 | 2020-07-14 11:20 | CR0012532 | Service ManagementBooking/DocumentationSetupBooking Receipt Notice & Draft BL Setup | OPUS-BKG-M | 2020-W29 | 2020-07 | 67 | 68 | 75.9624 | 5 | 1 | 1 | 0.04 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.52941 | 2020-04 | 0 | 0
976 | CR0012532 | CTASK0019669 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-05-16 00:14 | 2020-05-04 10:14 | Container | Service Management | Booking/Documentation | Setup | Booking Receipt Notice & Draft BL Setup |  | [Testing][CLT Internal] BRN Remarks UI setup (CSVC/EXP BOOKING) - CR0011132 enhancement | 2020-04-29 10:54 | 2020-06-25 | 2020-06-18 03:55 | 2020-06-22 18:16 | 2020-07-08 10:19 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:19 | 2020-07-14 11:20 | CR0012532 | Service ManagementBooking/DocumentationSetupBooking Receipt Notice & Draft BL Setup | OPUS-BKG-M | 2020-W29 | 2020-07 | 67 | 68 | 75.9624 | 5 | 1 | 1 | 0.04 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.52941 | 2020-04 | 0 | 0
977 | CR0012532 | CTASK0019667 | Closed | OPUS-BKG-M | Thien Lai | 32 | 32 | 2020-05-16 00:13 | 2020-05-04 10:13 | Container | Service Management | Booking/Documentation | Setup | Booking Receipt Notice & Draft BL Setup |  | [Development][CLT Internal] BRN Remarks UI setup (CSVC/EXP BOOKING) - CR0011132 enhancement | 2020-04-29 10:54 | 2020-06-25 | 2020-06-18 03:55 | 2020-06-22 18:16 | 2020-07-08 10:19 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:19 | 2020-07-14 11:20 | CR0012532 | Service ManagementBooking/DocumentationSetupBooking Receipt Notice & Draft BL Setup | OPUS-BKG-M | 2020-W29 | 2020-07 | 67 | 68 | 75.9624 | 5 | 1 | 1 | 0.04 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.52941 | 2020-04 | 0 | 0
978 | CR0012532 | CTASK0019668 | Closed | OPUS-BKG-M | Thien Lai | 7 | 8 | 2020-06-19 22:33 | 2020-06-15 09:33 | Container | Service Management | Booking/Documentation | Setup | Booking Receipt Notice & Draft BL Setup |  | [Testing][CLT Internal] BRN Remarks UI setup (CSVC/EXP BOOKING) - CR0011132 enhancement | 2020-04-29 10:54 | 2020-06-25 | 2020-06-18 03:55 | 2020-06-22 18:16 | 2020-07-08 10:19 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:19 | 2020-07-14 11:20 | CR0012532 | Service ManagementBooking/DocumentationSetupBooking Receipt Notice & Draft BL Setup | OPUS-BKG-M | 2020-W29 | 2020-07 | 67 | 68 | 75.9624 | 5 | 1 | 1 | 0.04 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.52941 | 2020-04 | 0 | 0
979 | CR0012532 | CTASK0019671 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-07-09 20:12 | 2020-07-08 10:12 | Container | Service Management | Booking/Documentation | Setup | Booking Receipt Notice & Draft BL Setup |  | [Deployment][CLT Internal] BRN Remarks UI setup (CSVC/EXP BOOKING) - CR0011132 enhancement | 2020-04-29 10:54 | 2020-06-25 | 2020-06-18 03:55 | 2020-06-22 18:16 | 2020-07-08 10:19 |  | 2020-07-14 10:00 | 2020-07-14 10:00 | 2020-07-08 10:19 | 2020-07-14 11:20 | CR0012532 | Service ManagementBooking/DocumentationSetupBooking Receipt Notice & Draft BL Setup | OPUS-BKG-M | 2020-W29 | 2020-07 | 67 | 68 | 75.9624 | 5 | 1 | 1 | 0.04 | 193567 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 27 | 0 | 0.52941 | 2020-04 | 0 | 0
980 | CR0013612 | CTASK0025455 | Closed | OPUS-SPC | Toai Phan | 20 | 20 | 2021-03-19 11:19 | 2021-02-23 11:19 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | CLT Internal]Automatically display the related date when upload week number as excel file to Master Constrain Table UI. | 2021-02-23 11:19 | 2021-03-12 11:19 | 2021-03-12 08:01 | 2021-03-30 12:57 | 2021-03-30 16:52 |  | 2021-04-09 16:52 | 2021-04-13 09:04 | 2021-04-05 08:47 | 2021-05-27 14:00 | CR0013612 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W14 | 2021-04 | 20 | 20 | 45.2309 | 1 | 1 | 1 | 0.02 | 183427 | 2.2 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 27 | 0 | 0 | 2021-02 | 0 | 0
981 | CR0012928 | CTASK0022438 | Closed | OPUS-PRI | Ngan Nham | 38 | 50 | 2020-09-30 18:13 | 2020-09-01 18:13 | Container | Biz Common | Master Data | Organization | EQ Control Location Unit |  | [Tiger ] - Triggering program Test/STG/EDU/PROD _MDA EAI I/F to Tiger (EQ Control Location) | 2020-09-17 10:53 | 2020-09-25 10:52 | 2020-09-17 16:25 | 2020-09-21 10:20 | 2020-09-21 10:27 |  | 2020-09-28 10:27 | 2020-09-28 09:11 | 2020-09-24 17:18 | 2020-10-28 13:00 | CR0012928 | Biz CommonMaster DataOrganizationEQ Control Location Unit | OPUS-MDA | 2020-W40 | 2020-09 | 38 | 50 | 10.9823 | 1 | 1 | 1 | 0.19 | 193461 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0.28571 | 2020-09 | 0 | 0
982 | CR0013240 | CTASK0023730 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 29 | 29 | 2020-11-27 19:30 | 2020-11-23 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest | EU ENS (Origin Office) |  | [Development+Testing+Deployment] (HBA) EUA EDI AUTH¦ CUSTOMS COMMON CODE for EU_MEMBER_CNT to be extended with region for possible selection of Northern Ireland for EU Advanced manifest | 2020-11-24 11:15 | 2020-12-04 | 2020-12-02 18:12 | 2020-12-29 11:18 | 2020-12-29 11:54 |  | 2020-12-30 10:00 | 2020-12-30 11:00 | 2020-12-29 11:57 | 2021-01-29 00:45 | CR0013240 | Service ManagementBooking/DocumentationAdvance ManifestEU ENS (Origin Office) | OPUS-BKG-MFT-E | 2020-W53 | 2020-12 | 41 | 48 | 35.9477 | 3 | 1 | 1 | 0.06 | 173280 | 1.9 | 0 | 0 | 1 | 1 | 1 | 1 | 9 | 30 | 0 | 0.18519 | 2020-11 | 1 | 1
983 | CR0013240 | CTASK0023495 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 4 | 4 | 2020-11-10 19:30 | 2020-11-09 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest | EU ENS (Origin Office) |  | [Estimation] (HBA) EUA EDI AUTH¦ CUSTOMS COMMON CODE for EU_MEMBER_CNT to be extended with region for possible selection of Northern Ireland for EU Advanced manifest | 2020-11-24 11:15 | 2020-12-04 | 2020-12-02 18:12 | 2020-12-29 11:18 | 2020-12-29 11:54 |  | 2020-12-30 10:00 | 2020-12-30 11:00 | 2020-12-29 11:57 | 2021-01-29 00:45 | CR0013240 | Service ManagementBooking/DocumentationAdvance ManifestEU ENS (Origin Office) | OPUS-BKG-MFT-E | 2020-W53 | 2020-12 | 41 | 48 | 35.9477 | 3 | 1 | 1 | 0.06 | 173280 | 1.9 | 0 | 0 | 1 | 1 | 1 | 1 | 9 | 30 | 0 | 0.18519 | 2020-11 | 1 | 1
984 | CR0013240 | CTASK0024342 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 8 | 15 | 2020-12-31 19:30 | 2020-12-24 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest | EU ENS (Origin Office) |  | [Development+Testing+Deployment] (HBA) EUA EDI AUTH¦ CUSTOMS COMMON CODE for EU_MEMBER_CNT to be extended with region for possible selection of Northern Ireland for EU Advanced manifest | 2020-11-24 11:15 | 2020-12-04 | 2020-12-02 18:12 | 2020-12-29 11:18 | 2020-12-29 11:54 |  | 2020-12-30 10:00 | 2020-12-30 11:00 | 2020-12-29 11:57 | 2021-01-29 00:45 | CR0013240 | Service ManagementBooking/DocumentationAdvance ManifestEU ENS (Origin Office) | OPUS-BKG-MFT-E | 2020-W53 | 2020-12 | 41 | 48 | 35.9477 | 3 | 1 | 1 | 0.06 | 173280 | 1.9 | 0 | 0 | 1 | 1 | 1 | 1 | 9 | 30 | 0 | 0.18519 | 2020-11 | 1 | 1
985 | CR0011413 | CTASK0015102 | Closed | OPUS-BKG-M | Kieu Le | 42 | 42 |  |  | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | ASIA - BKG - standby booking status report + change in GD4 hard-coding logic for SINHQ/HKGHQ | 2019-06-19 11:57 | 2019-07-02 | 2019-07-01 16:20 | 2019-07-04 12:02 | 2019-07-04 13:19 | 2019-07-01 16:21 | 2019-07-09 13:19 | 2019-07-09 12:48 | 2019-07-04 13:22 | 2019-07-17 17:50 | CR0011413 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2019-W28 | 2019-07 | 54 | 0 | 20.0569 | 2 | 1 | 1 | 0 | 153106 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 2019-06 | 0 | 0
986 | CR0011413 | CTASK0014864 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 |  |  | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | ASIA - BKG - standby booking status report + change in GD4 hard-coding logic for SINHQ/HKGHQ | 2019-06-19 11:57 | 2019-07-02 | 2019-07-01 16:20 | 2019-07-04 12:02 | 2019-07-04 13:19 | 2019-07-01 16:21 | 2019-07-09 13:19 | 2019-07-09 12:48 | 2019-07-04 13:22 | 2019-07-17 17:50 | CR0011413 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2019-W28 | 2019-07 | 54 | 0 | 20.0569 | 2 | 1 | 1 | 0 | 153106 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 2019-06 | 0 | 0
987 | CR0012220 | CTASK0018253 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 10 | 10 | 2020-02-12 18:47 | 2020-02-06 18:47 | Container | Service Management | Booking/Documentation | Advance Manifest | China 24HR | Manifest Transmit | [Estimate] Define the value of "POL_ETD" and add into segment 12 of IFCSUM(China 24HR). | 2020-03-11 16:23 | 2020-03-27 16:23 | 2020-03-25 14:23 |  | 2020-04-17 10:07 |  | 2020-04-21 10:00 | 2020-04-21 09:30 | 2020-04-17 11:12 | 2020-05-21 13:00 | CR0012220 | Service ManagementBooking/DocumentationAdvance ManifestChina 24HRManifest Transmit | OPUS-BKG-MFT-A | 2020-W17 | 2020-04 | 56 | 56 | 40.7338 | 2 | 1 | 1 | 0.06 | 193506 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 16 | 0 | 0.85714 | 2020-03 | 0 | 0
988 | CR0012220 | CTASK0018536 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 46 | 46 | 2020-03-24 16:31 | 2020-02-24 17:31 | Container | Service Management | Booking/Documentation | Advance Manifest | China 24HR | Manifest Transmit | [Development] Define the value of "POL_ETD" and add into segment 12 of IFCSUM(China 24HR). | 2020-03-11 16:23 | 2020-03-27 16:23 | 2020-03-25 14:23 |  | 2020-04-17 10:07 |  | 2020-04-21 10:00 | 2020-04-21 09:30 | 2020-04-17 11:12 | 2020-05-21 13:00 | CR0012220 | Service ManagementBooking/DocumentationAdvance ManifestChina 24HRManifest Transmit | OPUS-BKG-MFT-A | 2020-W17 | 2020-04 | 56 | 56 | 40.7338 | 2 | 1 | 1 | 0.06 | 193506 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 16 | 0 | 0.85714 | 2020-03 | 0 | 0
989 | CR0011523 | CTASK0016969 | Closed | OPUS-TRS | Giang Nguyen Hoang | 40 | 88 |  |  | Container | Biz Common | Master Data | Partner | Vendor |  | [Actual] GHQ - MDA Vendor Sanction Weekly Check | 2019-10-31 09:58 | 2019-11-30 18:00 | 2019-11-29 15:53 | 2020-02-28 21:33 | 2020-03-02 10:40 |  | 2020-03-10 11:00 | 2020-03-10 11:00 | 2020-03-02 11:17 | 2020-04-10 13:00 | CR0011523 | Biz CommonMaster DataPartnerVendor | OPUS-MDA | 2020-W11 | 2020-03 | 40 | 88 | 131.0433 | 1 | 1 | 1 | 0.03 | 183440 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0 | 2019-10 | 0 | 0
990 | CR0012057 | CTASK0018958 | Closed | OPUS-PRI | Nhien Nguyen | 101 | 60 |  |  | Container | Sales Management | Pricing | Surcharge | Surcharge Creation |  | [Development] EUA PRI // PUDO // Ability to file Surcharges based on M'ty Pick up CY and M'ty Return CYD | 2020-03-13 10:22 | 2020-04-30 10:22 | 2020-04-29 16:09 | 2020-06-19 23:54 | 2020-07-23 09:23 |  | 2020-08-25 09:23 | 2020-08-20 10:17 | 2020-07-23 19:07 | 2020-09-19 13:00 | CR0012057 | Sales ManagementPricingSurchargeSurcharge Creation | OPUS-PRI | 2020-W35 | 2020-08 | 266 | 160 | 164.959 | 2 | 1 | 2 | 0.04 | 183364 | 1.5 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 30 | 0 | 0 | 2020-03 | 0 | 0
991 | CR0012057 | CTASK0018959 | Closed | OPUS-PRI | Man Hoang | 165 | 100 | 2020-07-31 11:50 | 2020-07-01 11:50 | Container | Sales Management | Pricing | Surcharge | Surcharge Creation |  | [Development] EUA PRI // PUDO // Ability to file Surcharges based on M'ty Pick up CY and M'ty Return CY | 2020-03-13 10:22 | 2020-04-30 10:22 | 2020-04-29 16:09 | 2020-06-19 23:54 | 2020-07-23 09:23 |  | 2020-08-25 09:23 | 2020-08-20 10:17 | 2020-07-23 19:07 | 2020-09-19 13:00 | CR0012057 | Sales ManagementPricingSurchargeSurcharge Creation | OPUS-PRI | 2020-W35 | 2020-08 | 266 | 160 | 164.959 | 2 | 1 | 2 | 0.04 | 183431 | 1.3 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 30 | 0 | 0.66667 | 2020-03 | 0 | 0
992 | CR0012947 | CTASK0024730 | Closed | OPUS-BKG-OB | Nam Nguyen | 16 | 16 | 2021-01-22 13:46 | 2021-01-18 13:46 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | BL PDF file naming for Samsung, LG Pantos and HankookTire | 2020-09-18 15:11 | 2020-11-30 15:10 | 2020-11-25 13:27 | 2021-03-31 14:24 | 2021-04-05 10:27 |  | 2021-04-13 10:27 | 2021-04-13 10:39 | 2021-04-07 09:45 | 2021-05-13 14:00 | CR0012947 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2021-W15 | 2021-04 | 72 | 56 | 206.8032 | 4 | 1 | 1 | 0.01 | 123048 | 2 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 27 | 0.22222 | 0.46154 | 2020-09 | 0 | 0
993 | CR0012947 | CTASK0022434 | Closed | OPUS-BKG-OB | Nam Nguyen | 11 | 10 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [Analyse] BL PDF file naming for Samsung, LG Pantos and HankookTire | 2020-09-18 15:11 | 2020-11-30 15:10 | 2020-11-25 13:27 | 2021-03-31 14:24 | 2021-04-05 10:27 |  | 2021-04-13 10:27 | 2021-04-13 10:39 | 2021-04-07 09:45 | 2021-05-13 14:00 | CR0012947 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2021-W15 | 2021-04 | 72 | 56 | 206.8032 | 4 | 1 | 1 | 0.01 | 123048 | 2 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 27 | 0.22222 | 0.46154 | 2020-09 | 0 | 0
994 | CR0012947 | CTASK0026227 | Closed | OPUS-BKG-OB | Nam Nguyen | 6 | 2 | 2021-04-12 21:08 | 2021-04-01 21:07 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [Deployment]BL PDF file naming for Samsung, LG Pantos and HankookTire | 2020-09-18 15:11 | 2020-11-30 15:10 | 2020-11-25 13:27 | 2021-03-31 14:24 | 2021-04-05 10:27 |  | 2021-04-13 10:27 | 2021-04-13 10:39 | 2021-04-07 09:45 | 2021-05-13 14:00 | CR0012947 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2021-W15 | 2021-04 | 72 | 56 | 206.8032 | 4 | 1 | 1 | 0.01 | 123048 | 2 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 27 | 0.22222 | 0.46154 | 2020-09 | 0 | 0
995 | CR0012947 | CTASK0022531 | Closed | OPUS-BKG-OB | Nam Nguyen | 39 | 28 | 2020-11-06 00:51 | 2020-10-21 00:50 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [Development, Testing and Deployment] BL PDF file naming for Samsung, LG Pantos and HankookTire | 2020-09-18 15:11 | 2020-11-30 15:10 | 2020-11-25 13:27 | 2021-03-31 14:24 | 2021-04-05 10:27 |  | 2021-04-13 10:27 | 2021-04-13 10:39 | 2021-04-07 09:45 | 2021-05-13 14:00 | CR0012947 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2021-W15 | 2021-04 | 72 | 56 | 206.8032 | 4 | 1 | 1 | 0.01 | 123048 | 2 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 27 | 0.22222 | 0.46154 | 2020-09 | 0 | 0
996 | CR0013979 | CTASK0027108 | Closed | OPUS-SAP | Cuong Tran Hung | 8 | 8 | 2021-05-31 09:38 | 2021-05-20 09:38 | Container | Statement Management | Statement Account Payable | Payments | CSR Receipt Entry |  | [May 2021][Cuong Tran][CLT Internal] Resolve the time-out issue in rejecting a CSR | 2021-05-24 10:23 | 2021-07-15 10:23 | 2021-06-28 15:18 | 2021-07-05 09:53 | 2021-07-05 09:55 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-06 08:43 | 2021-07-29 14:00 | CR0013979 | Statement ManagementStatement Account PayablePaymentsCSR Receipt Entry | OPUS-SAP | 2021-W28 | 2021-07 | 45 | 44 | 49.9841 | 3 | 1 | 3 | 0.04 | 193530 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 9 | 28 | 1.2308 | 1.2222 | 2021-05 | 1 | 1
997 | CR0013979 | CTASK0027110 | Closed | OPUS-SAP | Lien Le | 9 | 8 | 2021-05-31 09:40 | 2021-05-20 09:40 | Container | Statement Management | Statement Account Payable | Payments | CSR Receipt Entry |  | [May 2021][Lien Le][CLT Internal] Resolve the time-out issue in rejecting a CSR | 2021-05-24 10:23 | 2021-07-15 10:23 | 2021-06-28 15:18 | 2021-07-05 09:53 | 2021-07-05 09:55 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-06 08:43 | 2021-07-29 14:00 | CR0013979 | Statement ManagementStatement Account PayablePaymentsCSR Receipt Entry | OPUS-SAP | 2021-W28 | 2021-07 | 45 | 44 | 49.9841 | 3 | 1 | 3 | 0.04 | 193441 | 2.2 | 1 | 1 | 0 | 1 | 1 | 1 | 9 | 28 | 0.42308 | 0 | 2021-05 | 1 | 1
998 | CR0013979 | CTASK0027109 | Closed | OPUS-SAP | Chuong Ta | 28 | 28 | 2021-05-31 09:39 | 2021-05-20 09:39 | Container | Statement Management | Statement Account Payable | Payments | CSR Receipt Entry |  | [May 2021][Chuong Ta[CLT Internal] Resolve the time-out issue in rejecting a CSR | 2021-05-24 10:23 | 2021-07-15 10:23 | 2021-06-28 15:18 | 2021-07-05 09:53 | 2021-07-05 09:55 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-06 08:43 | 2021-07-29 14:00 | CR0013979 | Statement ManagementStatement Account PayablePaymentsCSR Receipt Entry | OPUS-SAP | 2021-W28 | 2021-07 | 45 | 44 | 49.9841 | 3 | 1 | 3 | 0.04 | 183379 | 2.2 | 1 | 1 | 0 | 1 | 1 | 1 | 9 | 28 | 0.32 | 0.375 | 2021-05 | 1 | 1
999 | CR0014274 | CTASK0028424 | Closed | OPUS-TPB | Manh Nguyen | 13 | 12 | 2021-08-02 19:56 | 2021-07-29 09:56 | Container | Service Management | A/R Invoice |  |  |  | [Effort] Asia *AR INV* Remove tax scheme in India (Kerala Flood & Cess = 1%) for COKBB and unregistered customer only.(CR0011603) | 2021-07-29 17:48 | 2021-08-06 17:48 | 2021-07-30 10:26 | 2021-07-30 13:51 | 2021-07-30 14:15 |  | 2021-08-02 10:00 | 2021-08-02 10:00 | 2021-07-30 14:24 | 2021-08-03 12:03 | CR0014274 | Service ManagementA/R Invoice | OPUS-INV | 2021-W31 | 2021-08 | 13 | 14 | 3.6749 | 2 | 2 | 2 | 0.16 | 153138 | 2.8 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 22 | 0 | 0.16667 | 2021-07 | 0 | 0
1000 | CR0014274 | CTASK0028405 | Closed | OPUS-DMT | Cuong Nguyen | 2 | 2 | 2021-07-30 20:00 | 2021-07-28 08:00 | Container | Service Management | A/R Invoice |  |  |  | [CTASK2] CLV_Pair Test | 2021-07-29 17:48 | 2021-08-06 17:48 | 2021-07-30 10:26 | 2021-07-30 13:51 | 2021-07-30 14:15 |  | 2021-08-02 10:00 | 2021-08-02 10:00 | 2021-07-30 14:24 | 2021-08-03 12:03 | CR0014274 | Service ManagementA/R Invoice | OPUS-INV | 2021-W31 | 2021-08 | 13 | 14 | 3.6749 | 2 | 2 | 2 | 0.16 | 193529 | 2.2 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 22 | 0 | 0.22222 | 2021-07 | 0 | 0
1001 | CR0013552 | CTASK0025195 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-05-08 02:00 | 2021-05-04 10:44 | Container | Service Management | Booking/Documentation | Operation | Transshipment | T/S List by 1st VSL & 2nd VSL | [Testing][CLT Internal] OPUS OutOfMemoryError - T/S List by 1st VSL & 2nd VSL | 2021-04-29 09:05 | 2021-05-13 | 2021-05-10 14:11 | 2021-05-18 14:07 | 2021-05-18 16:29 |  | 2021-06-01 10:28 | 2021-06-01 14:35 | 2021-05-20 14:07 | 2021-07-02 14:00 | CR0013552 | Service ManagementBooking/DocumentationOperationTransshipmentT/S List by 1st VSL & 2nd VSL | OPUS-BKG-M | 2021-W22 | 2021-06 | 36 | 36 | 33.0582 | 4 | 1 | 1 | 0.05 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 6 | 53 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
1002 | CR0013552 | CTASK0025196 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-05-28 17:44 | 2021-05-24 17:44 | Container | Service Management | Booking/Documentation | Operation | Transshipment | T/S List by 1st VSL & 2nd VSL | [Deployment][CLT Internal] OPUS OutOfMemoryError - T/S List by 1st VSL & 2nd VSL | 2021-04-29 09:05 | 2021-05-13 | 2021-05-10 14:11 | 2021-05-18 14:07 | 2021-05-18 16:29 |  | 2021-06-01 10:28 | 2021-06-01 14:35 | 2021-05-20 14:07 | 2021-07-02 14:00 | CR0013552 | Service ManagementBooking/DocumentationOperationTransshipmentT/S List by 1st VSL & 2nd VSL | OPUS-BKG-M | 2021-W22 | 2021-06 | 36 | 36 | 33.0582 | 4 | 1 | 1 | 0.05 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 6 | 53 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
1003 | CR0013552 | CTASK0025193 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 20 | 20 | 2021-04-24 02:00 | 2021-04-19 11:01 | Container | Service Management | Booking/Documentation | Operation | Transshipment | T/S List by 1st VSL & 2nd VSL | [Development][CLT Internal] OPUS OutOfMemoryError - T/S List by 1st VSL & 2nd VSL | 2021-04-29 09:05 | 2021-05-13 | 2021-05-10 14:11 | 2021-05-18 14:07 | 2021-05-18 16:29 |  | 2021-06-01 10:28 | 2021-06-01 14:35 | 2021-05-20 14:07 | 2021-07-02 14:00 | CR0013552 | Service ManagementBooking/DocumentationOperationTransshipmentT/S List by 1st VSL & 2nd VSL | OPUS-BKG-M | 2021-W22 | 2021-06 | 36 | 36 | 33.0582 | 4 | 1 | 1 | 0.05 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 6 | 53 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
1004 | CR0013552 | CTASK0025162 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-02-04 19:30 | 2021-02-01 11:16 | Container | Service Management | Booking/Documentation | Operation | Transshipment | T/S List by 1st VSL & 2nd VSL | [Design] [CLT Internal] OPUS OutOfMemoryError - T/S List by 1st VSL & 2nd VSL | 2021-04-29 09:05 | 2021-05-13 | 2021-05-10 14:11 | 2021-05-18 14:07 | 2021-05-18 16:29 |  | 2021-06-01 10:28 | 2021-06-01 14:35 | 2021-05-20 14:07 | 2021-07-02 14:00 | CR0013552 | Service ManagementBooking/DocumentationOperationTransshipmentT/S List by 1st VSL & 2nd VSL | OPUS-BKG-M | 2021-W22 | 2021-06 | 36 | 36 | 33.0582 | 4 | 1 | 1 | 0.05 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 6 | 53 | 0.53659 | 0.28125 | 2021-04 | 0 | 0
1005 | CR0010997 | CTASK0016560 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 23 | 30 | 2019-10-11 17:00 | 2019-10-01 15:46 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (US Office) | AMS Report | NA *BKG* Add columns to AMS report (CSVC/ CUSTOMS) | 2019-09-26 17:04 | 2019-10-01 | 2019-09-26 17:10 | 2019-10-16 20:51 | 2019-10-17 11:19 |  | 2019-10-22 10:00 | 2019-10-22 10:00 | 2019-10-17 20:35 | 2019-11-21 14:00 | CR0010997 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (US Office)AMS Report | OPUS-BKG-MFT-M | 2019-W43 | 2019-10 | 23 | 30 | 25.7057 | 1 | 1 | 1 | 0.05 | 193470 | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 10 | 0 | 1.3333 | 2019-09 | 0 | 0
1006 | CR0013834 | CTASK0026399 | Closed | OPUS-SCG | Tran Anh Duy | 18 | 18 | 2021-05-07 18:30 | 2021-04-12 18:30 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [CLV] Request SPCL CGO APVL/Inquiry for Partner Lines - Update - POL - POD & ETB - ETD | 2021-04-20 16:48 | 2021-05-21 18:30 |  | 2021-05-11 09:38 | 2021-05-11 12:22 |  | 2021-05-18 18:30 | 2021-05-18 09:00 | 2021-05-12 09:32 | 2021-06-17 14:00 | CR0013834 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W20 | 2021-05 | 30 | 30 | 28.0711 | 2 | 1 | 1 | 0.04 | 193516 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0 | 0 | 2021-04 | 0 | 0
1007 | CR0013834 | CTASK0026398 | Closed | OPUS-SCG | Tran Anh Duy | 12 | 12 | 2021-05-07 18:30 | 2021-04-12 18:30 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [Documentation] Request SPCL CGO APVL/Inquiry for Partner Lines - Update - POL - POD & ETB - ETD | 2021-04-20 16:48 | 2021-05-21 18:30 |  | 2021-05-11 09:38 | 2021-05-11 12:22 |  | 2021-05-18 18:30 | 2021-05-18 09:00 | 2021-05-12 09:32 | 2021-06-17 14:00 | CR0013834 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W20 | 2021-05 | 30 | 30 | 28.0711 | 2 | 1 | 1 | 0.04 | 193516 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0 | 0 | 2021-04 | 0 | 0
1008 | CR0011922 | CTASK0019229 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 4 | 4 | 2020-03-27 19:30 | 2020-03-24 11:30 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Deployment] (HM) EUA Auth SARSDEC/CUSRES - Load Customs clearance information | 2020-01-29 13:03 | 2020-03-13 23:50 | 2020-03-12 14:50 | 2020-03-16 22:10 | 2020-03-18 16:47 |  | 2020-03-31 10:01 | 2020-03-31 10:30 | 2020-03-18 17:13 | 2020-04-30 13:00 | CR0011922 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W14 | 2020-03 | 4 | 4 | 61.8738 | 1 | 1 | 1 | 0 | 173280 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0.18519 | 2020-01 | 0 | 0
1009 | CR0010336 | CTASK0014422 | Closed | OPUS-MNR | Tien Le | 4 | 4 |  |  | Container | Vessel Operation | Port Service Order |  |  |  | [actual]TRS/TES/PSO/MNR Cash Rebate Handling (MNR) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 173286 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1010 | CR0010336 | CTASK0015597 | Closed | OPUS-PSO | Lanh Le | 30 | 30 |  |  | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183422 | 0.4 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1011 | CR0010336 | CTASK0013946 | Closed | OPUS-PSO | Hieu Vu | 24 | 40 | 2019-05-22 19:30 | 2019-05-20 10:30 | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183375 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1012 | CR0010336 | CTASK0015154 | Closed | OPUS-MNR | Tien Le | 32 | 32 |  |  | Container | Vessel Operation | Port Service Order |  |  |  | [initial]TRS/TES/PSO/MNR Cash Rebate Handling (MNR) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 173286 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1013 | CR0010336 | CTASK0013876 | Closed | OPUS-MNR | Tien Le | 8 | 8 |  |  | Container | Vessel Operation | Port Service Order |  |  |  | [actual]TRS/TES/PSO/MNR Cash Rebate Handling (MNR) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 173286 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1014 | CR0010336 | CTASK0013943 | Closed | OPUS-PSO | Lanh Le | 24 | 40 | 2019-05-22 19:30 | 2019-05-20 10:30 | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183422 | 0.4 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1015 | CR0010336 | CTASK0014718 | Closed | OPUS-MNR | Tien Le | 20 | 20 |  |  | Container | Vessel Operation | Port Service Order |  |  |  | [actual]TRS/TES/PSO/MNR Cash Rebate Handling (MNR) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 173286 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1016 | CR0010336 | CTASK0014495 | Closed | OPUS-PSO | Lanh Le | 32 | 40 | 2019-06-06 19:30 | 2019-06-03 10:30 | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183422 | 0.4 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1017 | CR0010336 | CTASK0013341 | Closed | OPUS-PSO | Lanh Le | 40 | 40 | 2019-05-10 19:30 | 2019-05-06 10:30 | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183422 | 0.4 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1018 | CR0010336 | CTASK0014276 | Closed | OPUS-MNR | Tien Le | 6 | 6 |  |  | Container | Vessel Operation | Port Service Order |  |  |  | [actual]TRS/TES/PSO/MNR Cash Rebate Handling | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 173286 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1019 | CR0010336 | CTASK0015386 | Closed | OPUS-PSO | Hieu Vu | 27 | 27 |  |  | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183375 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1020 | CR0010336 | CTASK0014923 | Closed | OPUS-MNR | Tien Le | 6 | 6 |  |  | Container | Vessel Operation | Port Service Order |  |  |  | [actual]TRS/TES/PSO/MNR Cash Rebate Handling (MNR) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 173286 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1021 | CR0010336 | CTASK0013551 | Closed | OPUS-PSO | Hieu Vu | 40 | 40 | 2019-05-17 19:30 | 2019-05-13 10:30 | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183375 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1022 | CR0010336 | CTASK0013554 | Closed | OPUS-PSO | Lanh Le | 40 | 40 | 2019-05-17 19:30 | 2019-05-13 10:30 | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183422 | 0.4 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1023 | CR0010336 | CTASK0014496 | Closed | OPUS-PSO | Hieu Vu | 32 | 40 | 2019-06-06 19:30 | 2019-06-03 10:30 | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183375 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1024 | CR0010336 | CTASK0013340 | Closed | OPUS-PSO | Hieu Vu | 40 | 40 | 2019-05-10 19:30 | 2019-05-06 10:30 | Container | Vessel Operation | Port Service Order |  |  |  | [Actual] TRS/TES/PSO/MNR Cash Rebate Handling (PSO) | 2019-04-26 08:37 | 2019-07-31 08:23 | 2019-07-26 14:01 | 2019-10-07 11:06 | 2019-10-16 14:19 |  | 2019-10-22 18:00 | 2019-10-15 08:09 | 2019-10-16 14:31 | 2019-11-29 14:00 | CR0010336 | Vessel OperationPort Service Order | OPUS-PSO | 2019-W43 | 2019-10 | 405 | 320 | 179.3911 | 16 | 2 | 3 | 0.07 | 183375 | 0.6 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 10 | 0 | 0 | 2019-04 | 0 | 0
1025 | CR0012689 | CTASK0021369 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2020-09-03 10:26 | 2020-08-01 10:26 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Testing]Change default EDI receiver ID from YICT-P to YICT in case phase in/out at KRPUS. | 2020-08-20 18:07 | 2020-09-17 | 2020-09-16 11:06 | 2020-09-17 18:05 | 2020-09-18 14:06 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-09-24 13:57 | 2020-11-12 14:00 | CR0012689 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2020-W42 | 2020-10 | 32 | 31 | 53.6621 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1026 | CR0012689 | CTASK0021367 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-07-31 10:23 | 2020-07-20 10:23 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Design]Change default EDI receiver ID from YICT-P to YICT in case phase in/out at KRPUS. | 2020-08-20 18:07 | 2020-09-17 | 2020-09-16 11:06 | 2020-09-17 18:05 | 2020-09-18 14:06 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-09-24 13:57 | 2020-11-12 14:00 | CR0012689 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2020-W42 | 2020-10 | 32 | 31 | 53.6621 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1027 | CR0012689 | CTASK0021370 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2020-10-31 10:26 | 2020-10-01 10:26 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Deployment]Change default EDI receiver ID from YICT-P to YICT in case phase in/out at KRPUS. | 2020-08-20 18:07 | 2020-09-17 | 2020-09-16 11:06 | 2020-09-17 18:05 | 2020-09-18 14:06 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-09-24 13:57 | 2020-11-12 14:00 | CR0012689 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2020-W42 | 2020-10 | 32 | 31 | 53.6621 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1028 | CR0012689 | CTASK0021368 | Closed | OPUS-BKG-M | Loc Tran | 10 | 10 | 2020-08-31 10:25 | 2020-08-01 10:25 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Development]Change default EDI receiver ID from YICT-P to YICT in case phase in/out at KRPUS. | 2020-08-20 18:07 | 2020-09-17 | 2020-09-16 11:06 | 2020-09-17 18:05 | 2020-09-18 14:06 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-09-24 13:57 | 2020-11-12 14:00 | CR0012689 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2020-W42 | 2020-10 | 32 | 31 | 53.6621 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1029 | CR0012689 | CTASK0022354 | Closed | OPUS-BKG-M | Loc Tran | 4 | 3 | 2020-09-30 17:58 | 2020-09-07 17:57 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking EDI Transmit to Terminal | [Testing]Change default EDI receiver ID from YICT-P to YICT in case phase in/out at KRPUS. | 2020-08-20 18:07 | 2020-09-17 | 2020-09-16 11:06 | 2020-09-17 18:05 | 2020-09-18 14:06 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-09-24 13:57 | 2020-11-12 14:00 | CR0012689 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking EDI Transmit to Terminal | OPUS-BKG-M | 2020-W42 | 2020-10 | 32 | 31 | 53.6621 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1030 | CR0012755 | CTASK0020866 | Closed | OPUS-BKG-M | Kieu Le | 32 | 32 | 2020-08-08 01:47 | 2020-07-27 02:47 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development][CLT Internal] Standby Recalculation Button Structure Enhancement | 2020-07-27 11:08 | 2020-09-17 02:00 | 2020-09-09 16:13 | 2020-10-05 20:05 | 2020-10-05 20:10 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-06 09:26 | 2020-12-03 14:00 | CR0012755 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W45 | 2020-11 | 99 | 109 | 98.9527 | 6 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-07 | 0 | 0
1031 | CR0012755 | CTASK0020791 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-06-25 01:12 | 2020-06-22 02:12 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design][CLT Internal] Standby Recalculation Button Structure Enhancement | 2020-07-27 11:08 | 2020-09-17 02:00 | 2020-09-09 16:13 | 2020-10-05 20:05 | 2020-10-05 20:10 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-06 09:26 | 2020-12-03 14:00 | CR0012755 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W45 | 2020-11 | 99 | 109 | 98.9527 | 6 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-07 | 0 | 0
1032 | CR0012755 | CTASK0021925 | Closed | OPUS-BKG-M | Kieu Le | 5 | 5 | 2020-08-21 19:34 | 2020-08-18 02:34 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design][CLT Internal] Standby Recalculation Button Structure Enhancement | 2020-07-27 11:08 | 2020-09-17 02:00 | 2020-09-09 16:13 | 2020-10-05 20:05 | 2020-10-05 20:10 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-06 09:26 | 2020-12-03 14:00 | CR0012755 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W45 | 2020-11 | 99 | 109 | 98.9527 | 6 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-07 | 0 | 0
1033 | CR0012755 | CTASK0020868 | Closed | OPUS-BKG-M | Kieu Le | 7 | 16 | 2020-09-01 01:52 | 2020-08-03 02:52 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing][CLT Internal] Standby Recalculation Button Structure Enhancement | 2020-07-27 11:08 | 2020-09-17 02:00 | 2020-09-09 16:13 | 2020-10-05 20:05 | 2020-10-05 20:10 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-06 09:26 | 2020-12-03 14:00 | CR0012755 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W45 | 2020-11 | 99 | 109 | 98.9527 | 6 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-07 | 0 | 0
1034 | CR0012755 | CTASK0021924 | Closed | OPUS-BKG-M | Kieu Le | 43 | 44 | 2020-08-31 19:26 | 2020-08-18 19:26 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development][CLT Internal] Standby Recalculation Button Structure Enhancement | 2020-07-27 11:08 | 2020-09-17 02:00 | 2020-09-09 16:13 | 2020-10-05 20:05 | 2020-10-05 20:10 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-06 09:26 | 2020-12-03 14:00 | CR0012755 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W45 | 2020-11 | 99 | 109 | 98.9527 | 6 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-07 | 0 | 0
1035 | CR0012755 | CTASK0020870 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2020-10-31 01:48 | 2020-10-01 02:48 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment][CLT Internal] Standby Recalculation Button Structure Enhancement | 2020-07-27 11:08 | 2020-09-17 02:00 | 2020-09-09 16:13 | 2020-10-05 20:05 | 2020-10-05 20:10 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-06 09:26 | 2020-12-03 14:00 | CR0012755 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W45 | 2020-11 | 99 | 109 | 98.9527 | 6 | 1 | 1 | 0.05 | 153106 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 16 | 0 | 0.4 | 2020-07 | 0 | 0
1036 | CR0014135 | CTASK0027847 | Closed | OPUS-DMT | Cuong Nguyen | 20 | 20 | 2021-07-30 20:00 | 2021-07-01 08:00 | Container | Service Management | A/R Invoice | Invoice Issue |  |  | [DMT_CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2021-07-05 14:28 | 2021-07-20 14:28 | 2021-07-07 14:57 | 2021-07-28 08:44 | 2021-07-28 09:31 |  | 2021-08-03 11:00 | 2021-08-03 11:00 | 2021-07-29 11:28 | 2021-08-10 14:00 | CR0014135 | Service ManagementA/R InvoiceInvoice Issue | OPUS-INV | 2021-W31 | 2021-08 | 49 | 47 | 28.8555 | 3 | 2 | 2 | 0.07 | 193529 | 2.1 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 22 | 0 | 0.22222 | 2021-07 | 0 | 0
1037 | CR0014135 | CTASK0027892 | Closed | OPUS-TPB | Manh Nguyen | 26 | 24 | 2021-08-01 01:00 | 2021-07-01 01:00 | Container | Service Management | A/R Invoice | Invoice Issue |  |  | [202107] OPUS invoice - email body for no reply | 2021-07-05 14:28 | 2021-07-20 14:28 | 2021-07-07 14:57 | 2021-07-28 08:44 | 2021-07-28 09:31 |  | 2021-08-03 11:00 | 2021-08-03 11:00 | 2021-07-29 11:28 | 2021-08-10 14:00 | CR0014135 | Service ManagementA/R InvoiceInvoice Issue | OPUS-INV | 2021-W31 | 2021-08 | 49 | 47 | 28.8555 | 3 | 2 | 2 | 0.07 | 153138 | 2.8 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 22 | 0 | 0.16667 | 2021-07 | 0 | 0
1038 | CR0014135 | CTASK0028508 | Closed | OPUS-TPB | Manh Nguyen | 3 | 3 | 2021-09-01 01:00 | 2021-08-01 01:00 | Container | Service Management | A/R Invoice | Invoice Issue |  |  | [202108] OPUS invoice - email body for no reply | 2021-07-05 14:28 | 2021-07-20 14:28 | 2021-07-07 14:57 | 2021-07-28 08:44 | 2021-07-28 09:31 |  | 2021-08-03 11:00 | 2021-08-03 11:00 | 2021-07-29 11:28 | 2021-08-10 14:00 | CR0014135 | Service ManagementA/R InvoiceInvoice Issue | OPUS-INV | 2021-W31 | 2021-08 | 49 | 47 | 28.8555 | 3 | 2 | 2 | 0.07 | 153138 | 2.8 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 22 | 0 | 0.16667 | 2021-07 | 0 | 0
1039 | CR0013068 | CTASK0023103 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2020-10-22 02:00 | 2020-10-21 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] NA *BKG* - Auto Upload - Validating Forwarder and Consignee | 2020-12-01 11:49 | 2020-12-19 | 2020-12-18 17:03 | 2021-05-07 10:00 | 2021-05-11 16:48 |  | 2021-05-25 11:00 | 2021-05-25 11:00 | 2021-05-13 14:50 | 2021-06-25 14:00 | CR0013068 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W21 | 2021-05 | 44 | 44 | 174.9658 | 5 | 1 | 1 | 0.01 | 193525 | 1.5 | 1 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1040 | CR0013068 | CTASK0023101 | Closed | OPUS-BKG-EBKG | Vinh Tran | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Documentation] NA *BKG* - Auto Upload - Validating Forwarder and Consignee | 2020-12-01 11:49 | 2020-12-19 | 2020-12-18 17:03 | 2021-05-07 10:00 | 2021-05-11 16:48 |  | 2021-05-25 11:00 | 2021-05-25 11:00 | 2021-05-13 14:50 | 2021-06-25 14:00 | CR0013068 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W21 | 2021-05 | 44 | 44 | 174.9658 | 5 | 1 | 1 | 0.01 | 193525 | 1.5 | 1 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1041 | CR0013068 | CTASK0023109 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-05-20 02:00 | 2021-05-19 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] NA *BKG* - Auto Upload - Validating Forwarder and Consignee | 2020-12-01 11:49 | 2020-12-19 | 2020-12-18 17:03 | 2021-05-07 10:00 | 2021-05-11 16:48 |  | 2021-05-25 11:00 | 2021-05-25 11:00 | 2021-05-13 14:50 | 2021-06-25 14:00 | CR0013068 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W21 | 2021-05 | 44 | 44 | 174.9658 | 5 | 1 | 1 | 0.01 | 193525 | 1.5 | 1 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1042 | CR0013068 | CTASK0023107 | Closed | OPUS-BKG-EBKG | Vinh Tran | 20 | 20 | 2020-12-16 02:00 | 2020-12-07 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] NA *BKG* - Auto Upload - Validating Forwarder and Consignee | 2020-12-01 11:49 | 2020-12-19 | 2020-12-18 17:03 | 2021-05-07 10:00 | 2021-05-11 16:48 |  | 2021-05-25 11:00 | 2021-05-25 11:00 | 2021-05-13 14:50 | 2021-06-25 14:00 | CR0013068 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W21 | 2021-05 | 44 | 44 | 174.9658 | 5 | 1 | 1 | 0.01 | 193525 | 1.5 | 1 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1043 | CR0013068 | CTASK0023104 | Closed | OPUS-BKG-EBKG | Vinh Tran | 16 | 16 | 2020-12-05 02:00 | 2020-11-30 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] NA *BKG* - Auto Upload - Validating Forwarder and Consignee | 2020-12-01 11:49 | 2020-12-19 | 2020-12-18 17:03 | 2021-05-07 10:00 | 2021-05-11 16:48 |  | 2021-05-25 11:00 | 2021-05-25 11:00 | 2021-05-13 14:50 | 2021-06-25 14:00 | CR0013068 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W21 | 2021-05 | 44 | 44 | 174.9658 | 5 | 1 | 1 | 0.01 | 193525 | 1.5 | 1 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1044 | CR0011678 | CTASK0016709 | Closed | OPUS-BKG-M | Vinh Tran | 2 | 2 |  |  | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Estimate] Adding search function to e-Booking and SI process | 2019-10-23 18:04 | 2019-11-26 | 2019-11-08 11:53 | 2019-11-28 11:53 | 2019-11-28 12:50 |  | 2019-12-10 12:50 | 2019-12-10 09:30 | 2019-12-03 12:21 | 2020-01-10 14:00 | CR0011678 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2019-W50 | 2019-12 | 59 | 50 | 47.7813 | 2 | 2 | 1 | 0.04 | 193525 | 0.4 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 18 | 0 | 0.45455 | 2019-10 | 0 | 0
1045 | CR0011678 | CTASK0016710 | Closed | OPUS-BKG-EBKG | Vinh Tran | 57 | 50 | 2019-11-08 20:14 | 2019-10-28 20:14 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | Adding search function to e-Booking and SI process | 2019-10-23 18:04 | 2019-11-26 | 2019-11-08 11:53 | 2019-11-28 11:53 | 2019-11-28 12:50 |  | 2019-12-10 12:50 | 2019-12-10 09:30 | 2019-12-03 12:21 | 2020-01-10 14:00 | CR0011678 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2019-W50 | 2019-12 | 59 | 50 | 47.7813 | 2 | 2 | 1 | 0.04 | 193525 | 0.4 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 18 | 0 | 0.45455 | 2019-10 | 0 | 0
1046 | CR0012726 | CTASK0020562 | Closed | OPUS-FLT | Tu Nguyen | 55 | 55 | 2020-07-31 11:30 | 2020-06-22 02:00 | Container | Support & Admin | Fleet Management |  |  |  | [FLT-CLV] System logic enhancement to use Actual Delivery Date as the trigger of Initial Inception Interface Data and Lease Start Date | 2020-06-16 15:40 | 2020-07-31 11:34 | 2020-07-21 11:01 | 2020-08-14 01:42 | 2020-08-14 09:24 |  | 2020-08-25 10:00 | 2020-08-25 10:31 | 2020-08-14 10:49 | 2020-09-26 13:00 | CR0012726 | Support & AdminFleet Management | OPUS-FLT | 2020-W35 | 2020-08 | 84 | 85 | 69.7638 | 2 | 1 | 1 | 0.05 | 123045 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 12 | 30 | 0 | 0 | 2020-06 | 0 | 0
1047 | CR0012726 | CTASK0020561 | Closed | OPUS-FLT | Tu Nguyen | 29 | 30 | 2020-07-31 20:00 | 2020-06-10 02:00 | Container | Support & Admin | Fleet Management |  |  |  | [Documentation] System logic enhancement to use Actual Delivery Date as the trigger of Initial Inception Interface Data and Lease Start Date | 2020-06-16 15:40 | 2020-07-31 11:34 | 2020-07-21 11:01 | 2020-08-14 01:42 | 2020-08-14 09:24 |  | 2020-08-25 10:00 | 2020-08-25 10:31 | 2020-08-14 10:49 | 2020-09-26 13:00 | CR0012726 | Support & AdminFleet Management | OPUS-FLT | 2020-W35 | 2020-08 | 84 | 85 | 69.7638 | 2 | 1 | 1 | 0.05 | 123045 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 12 | 30 | 0 | 0 | 2020-06 | 0 | 0
1048 | CR0011954 | CTASK0017741 | Closed | OPUS-TRS | Giang Nguyen Hoang | 34 | 34 | 2020-02-14 18:00 | 2020-01-06 09:00 | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | NA*TRS* Request is to add additional scenarios that were not initially included in CR0010609 to trigger auto rail billing cancellation | 2020-01-06 09:31 | 2020-02-29 18:00 | 2020-02-18 13:56 | 2020-03-09 23:42 | 2020-03-11 09:17 |  | 2020-03-17 11:00 | 2020-03-17 10:00 | 2020-03-12 07:58 | 2020-04-16 13:00 | CR0011954 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2020-W12 | 2020-03 | 63 | 68 | 71.0616 | 2 | 1 | 2 | 0.04 | 183440 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 25 | 0 | 0 | 2020-01 | 0 | 0
1049 | CR0011954 | CTASK0017740 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 29 | 34 | 2020-02-14 18:00 | 2020-01-06 09:00 | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | NA*TRS* Request is to add additional scenarios that were not initially included in CR0010609 to trigger auto rail billing cancellation | 2020-01-06 09:31 | 2020-02-29 18:00 | 2020-02-18 13:56 | 2020-03-09 23:42 | 2020-03-11 09:17 |  | 2020-03-17 11:00 | 2020-03-17 10:00 | 2020-03-12 07:58 | 2020-04-16 13:00 | CR0011954 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2020-W12 | 2020-03 | 63 | 68 | 71.0616 | 2 | 1 | 2 | 0.04 | 183432 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 25 | 0 | 0 | 2020-01 | 0 | 0
1050 | CR0011530 | CTASK0019424 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 27 | 35 | 2020-06-30 18:00 | 2020-05-01 18:00 | DOM Web Portal | [5 empty] | NA *Domestic Web Portal* Domestic Street Turn - Update logic and Add Validations | 2020-04-28 17:56 | 2020-09-11 21:00 | 2020-09-11 13:19 | 2021-01-11 13:06 | 2021-01-12 16:47 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-13 15:25 | 2021-02-25 14:00 | CR0011530 |  | OPUS-DOM | 2021-W4 | 2021-01 | 66 | 70 | 272.6693 | 2 | 1 | 2 | 0.01 | 183432 | 1.1 | 0 | 0 | 0 | 1 | 1 | 3 | 12 | 40 | 0 | 0 | 2020-04 | 0 | 0
1051 | CR0011530 | CTASK0019421 | Closed | OPUS-DOM | Giang Nguyen Hoang | 39 | 35 | 2020-06-30 17:59 | 2020-05-01 17:59 | DOM Web Portal | [5 empty] | (DOM)NA *Domestic Web Portal* Domestic Street Turn - Update logic and Add Validations | 2020-04-28 17:56 | 2020-09-11 21:00 | 2020-09-11 13:19 | 2021-01-11 13:06 | 2021-01-12 16:47 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-13 15:25 | 2021-02-25 14:00 | CR0011530 |  | OPUS-DOM | 2021-W4 | 2021-01 | 66 | 70 | 272.6693 | 2 | 1 | 2 | 0.01 | 183440 | 1.1 | 0 | 0 | 0 | 1 | 1 | 3 | 12 | 40 | 0 | 0 | 2020-04 | 0 | 0
1052 | CR0013391 | CTASK0024471 | Closed | OPUS-SCE | VInh Bui | 12 | 30 | 2021-01-31 16:32 | 2021-01-01 16:32 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [CLT Internal] The SO Candidates showing "S/O Status" is incorrect when Move Container | 2021-04-07 19:03 | 2021-04-23 19:03 | 2021-04-23 16:15 | 2021-05-11 11:47 | 2021-05-25 12:30 |  | 2021-06-01 11:00 | 2021-06-01 12:06 | 2021-05-25 15:21 | 2021-07-01 14:00 | CR0013391 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2021-W22 | 2021-06 | 12 | 30 | 54.6643 | 1 | 1 | 1 | 0.02 | 193469 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 6 | 53 | 0 | 0 | 2021-04 | 0 | 0
1053 | CR0011977 | CTASK0020361 | Closed | OPUS-BKG-RPT | Thai Nguyen Quoc | 11 | 14 | 2020-07-28 01:00 | 2020-07-20 10:30 | Container | Service Management | Booking/Documentation | Report | Booking Container Report |  | [Deployment] Booking Container report & Special Cargo report to have Sensitive cargo (out of RF Cargo application) for both Item and Parameter | 2020-06-03 15:57 | 2020-07-04 | 2020-07-02 15:20 | 2020-07-14 17:20 | 2020-07-15 14:16 |  | 2020-07-28 09:00 | 2020-07-28 10:00 | 2020-07-15 16:01 | 2020-08-27 13:00 | CR0011977 | Service ManagementBooking/DocumentationReportBooking Container Report | OPUS-BKG-RPT | 2020-W31 | 2020-07 | 94 | 100 | 54.7106 | 3 | 2 | 1 | 0.08 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.17391 | 2020-06 | 0 | 0
1054 | CR0011977 | CTASK0020359 | Closed | OPUS-BKG-RPT | Thai Nguyen Quoc | 67 | 70 | 2020-07-09 01:00 | 2020-06-03 09:00 | Container | Service Management | Booking/Documentation | Report | Booking Container Report |  | [Development+Test] Booking Container report & Special Cargo report to have Sensitive cargo (out of RF Cargo application) for both Item and Parameter | 2020-06-03 15:57 | 2020-07-04 | 2020-07-02 15:20 | 2020-07-14 17:20 | 2020-07-15 14:16 |  | 2020-07-28 09:00 | 2020-07-28 10:00 | 2020-07-15 16:01 | 2020-08-27 13:00 | CR0011977 | Service ManagementBooking/DocumentationReportBooking Container Report | OPUS-BKG-RPT | 2020-W31 | 2020-07 | 94 | 100 | 54.7106 | 3 | 2 | 1 | 0.08 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.17391 | 2020-06 | 0 | 0
1055 | CR0011977 | CTASK0020317 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 16 | 16 | 2020-05-28 19:30 | 2020-05-26 10:30 | Container | Service Management | Booking/Documentation | Report | Booking Container Report |  | [Analysis] Booking Container report & Special Cargo report to have Sensitive cargo (out of RF Cargo application) for both Item and Parameter | 2020-06-03 15:57 | 2020-07-04 | 2020-07-02 15:20 | 2020-07-14 17:20 | 2020-07-15 14:16 |  | 2020-07-28 09:00 | 2020-07-28 10:00 | 2020-07-15 16:01 | 2020-08-27 13:00 | CR0011977 | Service ManagementBooking/DocumentationReportBooking Container Report | OPUS-BKG-RPT | 2020-W31 | 2020-07 | 94 | 100 | 54.7106 | 3 | 2 | 1 | 0.08 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.17391 | 2020-06 | 0 | 0
1056 | CR0011859 | CTASK0017876 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 25 | 25 | 2020-01-14 15:12 | 2020-01-07 15:12 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Estimated]Update S/I contact information in Booking Request EDI(IFTMBF) to OPUS. (for Customer : Samsung SDS) | 2020-02-03 15:01 | 2020-02-24 14:59 | 2020-02-24 11:33 | 2020-03-04 12:32 | 2020-04-14 17:16 |  | 2020-05-12 10:00 | 2020-05-12 10:00 | 2020-04-17 11:03 | 2020-06-12 13:00 | CR0011859 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W20 | 2020-05 | 79 | 79 | 98.7912 | 3 | 2 | 1 | 0.03 | 193488 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 2.1667 | 2020-02 | 0 | 0
1057 | CR0011859 | CTASK0017916 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 50 | 50 | 2020-02-15 | 2020-02-03 09:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | Update S/I contact information in Booking Request EDI(IFTMBF) to OPUS. (for Customer : Samsung SDS) | 2020-02-03 15:01 | 2020-02-24 14:59 | 2020-02-24 11:33 | 2020-03-04 12:32 | 2020-04-14 17:16 |  | 2020-05-12 10:00 | 2020-05-12 10:00 | 2020-04-17 11:03 | 2020-06-12 13:00 | CR0011859 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W20 | 2020-05 | 79 | 79 | 98.7912 | 3 | 2 | 1 | 0.03 | 193488 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 2.1667 | 2020-02 | 0 | 0
1058 | CR0011859 | CTASK0019921 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 4 | 4 | 2020-05-05 14:23 | 2020-04-29 14:22 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment]Update S/I contact information in Booking Request EDI(IFTMBF) to OPUS. (for Customer : Samsung SDS) | 2020-02-03 15:01 | 2020-02-24 14:59 | 2020-02-24 11:33 | 2020-03-04 12:32 | 2020-04-14 17:16 |  | 2020-05-12 10:00 | 2020-05-12 10:00 | 2020-04-17 11:03 | 2020-06-12 13:00 | CR0011859 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W20 | 2020-05 | 79 | 79 | 98.7912 | 3 | 2 | 1 | 0.03 | 193488 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 2.1667 | 2020-02 | 0 | 0
1059 | CR0010763 | CTASK0013429 | Closed | OPUS-BKG-M | Kieu Le | 10 | 10 |  |  | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Summary Information | [~2019.05.14] Special Cargo Attachment Document Download (New Enhancement) | 2019-04-02 17:24 | 2019-06-30 17:23 | 2019-05-20 14:42 | 2019-06-25 14:52 | 2019-06-26 13:09 |  | 2019-07-02 11:00 | 2019-07-02 10:39 | 2019-06-26 15:27 | 2019-08-01 13:00 | CR0010763 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Summary Information | OPUS-BKG-M | 2019-W27 | 2019-07 | 115 | 0 | 90.7331 | 7 | 2 | 2 | 0 | 153106 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-04 | 0 | 0
1060 | CR0010763 | CTASK0012884 | Closed | OPUS-BKG-EBKG | Kieu Le | 40 | 40 |  |  | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Summary Information | [~2019.04.29] Special Cargo Attachment Document Download (New Enhancement) | 2019-04-02 17:24 | 2019-06-30 17:23 | 2019-05-20 14:42 | 2019-06-25 14:52 | 2019-06-26 13:09 |  | 2019-07-02 11:00 | 2019-07-02 10:39 | 2019-06-26 15:27 | 2019-08-01 13:00 | CR0010763 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Summary Information | OPUS-BKG-M | 2019-W27 | 2019-07 | 115 | 0 | 90.7331 | 7 | 2 | 2 | 0 | 153106 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-04 | 0 | 0
1061 | CR0010763 | CTASK0015333 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Summary Information | Special Cargo Attachment Document Download (New Enhancement) | 2019-04-02 17:24 | 2019-06-30 17:23 | 2019-05-20 14:42 | 2019-06-25 14:52 | 2019-06-26 13:09 |  | 2019-07-02 11:00 | 2019-07-02 10:39 | 2019-06-26 15:27 | 2019-08-01 13:00 | CR0010763 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Summary Information | OPUS-BKG-M | 2019-W27 | 2019-07 | 115 | 0 | 90.7331 | 7 | 2 | 2 | 0 | 153106 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-04 | 0 | 0
1062 | CR0010763 | CTASK0014863 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 |  |  | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Summary Information | Special Cargo Attachment Document Download (New Enhancement) | 2019-04-02 17:24 | 2019-06-30 17:23 | 2019-05-20 14:42 | 2019-06-25 14:52 | 2019-06-26 13:09 |  | 2019-07-02 11:00 | 2019-07-02 10:39 | 2019-06-26 15:27 | 2019-08-01 13:00 | CR0010763 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Summary Information | OPUS-BKG-M | 2019-W27 | 2019-07 | 115 | 0 | 90.7331 | 7 | 2 | 2 | 0 | 153106 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-04 | 0 | 0
1063 | CR0010763 | CTASK0013088 | Closed | OPUS-BKG-EBKG | Kieu Le | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Summary Information | [~2019.05.03] Special Cargo Attachment Document Download (New Enhancement) | 2019-04-02 17:24 | 2019-06-30 17:23 | 2019-05-20 14:42 | 2019-06-25 14:52 | 2019-06-26 13:09 |  | 2019-07-02 11:00 | 2019-07-02 10:39 | 2019-06-26 15:27 | 2019-08-01 13:00 | CR0010763 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Summary Information | OPUS-BKG-M | 2019-W27 | 2019-07 | 115 | 0 | 90.7331 | 7 | 2 | 2 | 0 | 153106 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-04 | 0 | 0
1064 | CR0010763 | CTASK0013296 | Closed | OPUS-BKG-M | Kieu Le | 32 | 32 |  |  | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Summary Information | [~2019.05.10] Special Cargo Attachment Document Download (New Enhancement) | 2019-04-02 17:24 | 2019-06-30 17:23 | 2019-05-20 14:42 | 2019-06-25 14:52 | 2019-06-26 13:09 |  | 2019-07-02 11:00 | 2019-07-02 10:39 | 2019-06-26 15:27 | 2019-08-01 13:00 | CR0010763 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Summary Information | OPUS-BKG-M | 2019-W27 | 2019-07 | 115 | 0 | 90.7331 | 7 | 2 | 2 | 0 | 153106 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-04 | 0 | 0
1065 | CR0010763 | CTASK0015351 | Closed | OPUS-BKG-M | Nhan Le | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Summary Information | Special Cargo Attachment Document Download (New Enhancement) | 2019-04-02 17:24 | 2019-06-30 17:23 | 2019-05-20 14:42 | 2019-06-25 14:52 | 2019-06-26 13:09 |  | 2019-07-02 11:00 | 2019-07-02 10:39 | 2019-06-26 15:27 | 2019-08-01 13:00 | CR0010763 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Summary Information | OPUS-BKG-M | 2019-W27 | 2019-07 | 115 | 0 | 90.7331 | 7 | 2 | 2 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 7 | 0 | 0 | 2019-04 | 0 | 0
1066 | CR0011890 | CTASK0017668 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2019-12-31 17:51 | 2019-12-31 17:51 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Design] NA *Standby* In the Standby Test pop up screen, "Recalculate" Button should not effect the final guidance of actual BKG | 2020-02-17 11:12 | 2020-03-17 | 2020-03-16 17:44 | 2020-05-11 10:32 | 2020-05-11 11:53 |  | 2020-06-02 10:00 | 2020-06-02 10:00 | 2020-05-22 23:01 | 2020-07-01 05:24 | CR0011890 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W23 | 2020-06 | 45 | 46 | 105.9497 | 4 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
1067 | CR0011890 | CTASK0018573 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2020-06-03 01:29 | 2020-05-26 02:43 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Deployment] NA *Standby* In the Standby Test pop up screen, "Recalculate" Button should not effect the final guidance of actual BKG | 2020-02-17 11:12 | 2020-03-17 | 2020-03-16 17:44 | 2020-05-11 10:32 | 2020-05-11 11:53 |  | 2020-06-02 10:00 | 2020-06-02 10:00 | 2020-05-22 23:01 | 2020-07-01 05:24 | CR0011890 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W23 | 2020-06 | 45 | 46 | 105.9497 | 4 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
1068 | CR0011890 | CTASK0018572 | Closed | OPUS-BKG-M | Kieu Le | 7 | 8 | 2020-02-28 19:11 | 2020-02-25 10:11 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Testing] NA *Standby* In the Standby Test pop up screen, "Recalculate" Button should not effect the final guidance of actual BKG | 2020-02-17 11:12 | 2020-03-17 | 2020-03-16 17:44 | 2020-05-11 10:32 | 2020-05-11 11:53 |  | 2020-06-02 10:00 | 2020-06-02 10:00 | 2020-05-22 23:01 | 2020-07-01 05:24 | CR0011890 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W23 | 2020-06 | 45 | 46 | 105.9497 | 4 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
1069 | CR0011890 | CTASK0017713 | Closed | OPUS-BKG-M | Kieu Le | 28 | 28 | 2020-02-28 08:32 | 2020-02-17 08:31 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Development] NA *Standby* In the Standby Test pop up screen, "Recalculate" Button should not effect the final guidance of actual BKG | 2020-02-17 11:12 | 2020-03-17 | 2020-03-16 17:44 | 2020-05-11 10:32 | 2020-05-11 11:53 |  | 2020-06-02 10:00 | 2020-06-02 10:00 | 2020-05-22 23:01 | 2020-07-01 05:24 | CR0011890 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W23 | 2020-06 | 45 | 46 | 105.9497 | 4 | 1 | 1 | 0.02 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-02 | 0 | 0
1070 | CR0013010 | CTASK0022766 | Closed | OPUS-PRI | Man Hoang | 34 | 30 | 2020-10-31 17:39 | 2020-10-01 17:39 | Container | Sales Management | Pricing | RFA | Proposal & Amendment | RFA Proposal & Amendment Creation | GHQ - PRI - Change Logic to retain past 3 months rates in latest RFA amendment | 2020-09-28 17:51 | 2020-10-31 17:51 | 2020-10-30 16:10 | 2021-01-11 09:27 | 2021-01-11 10:32 |  | 2021-01-19 10:31 | 2021-01-26 14:45 | 2021-01-15 09:15 | 2021-02-26 14:00 | CR0013010 | Sales ManagementPricingRFAProposal & AmendmentRFA Proposal & Amendment Creation | OPUS-PRI | 2021-W3 | 2021-01 | 51 | 40 | 112.6947 | 2 | 1 | 2 | 0.01 | 183431 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.58333 | 0.66667 | 2020-09 | 0 | 0
1071 | CR0013010 | CTASK0024686 | Closed | OPUS-PRI | Nhien Nguyen | 17 | 10 | 2020-10-31 19:19 | 2020-10-01 19:19 | Container | Sales Management | Pricing | RFA | Proposal & Amendment | RFA Proposal & Amendment Creation | GHQ - PRI - Change Logic to retain past 3 months rates in latest RFA amendment | 2020-09-28 17:51 | 2020-10-31 17:51 | 2020-10-30 16:10 | 2021-01-11 09:27 | 2021-01-11 10:32 |  | 2021-01-19 10:31 | 2021-01-26 14:45 | 2021-01-15 09:15 | 2021-02-26 14:00 | CR0013010 | Sales ManagementPricingRFAProposal & AmendmentRFA Proposal & Amendment Creation | OPUS-PRI | 2021-W3 | 2021-01 | 51 | 40 | 112.6947 | 2 | 1 | 2 | 0.01 | 183364 | 2 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.54545 | 0 | 2020-09 | 0 | 0
1072 | CR0013982 | CTASK0027601 | Implemented | OPUS-BKG-M | Dat Nguyen Hoang | 12 | 12 | 2021-06-25 19:37 | 2021-06-21 11:37 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal] TAA Ref No. Enhancement | 2021-07-08 14:50 | 2021-07-10 02:00 | 2021-07-08 14:50 | 2021-07-29 11:52 | 2021-07-29 12:19 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-07-30 10:30 |  | CR0013982 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W33 | 2021-08 | 24 | 24 | 39.7984 | 4 | 1 | 1 | 0.03 | 193488 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 22 | 0.53659 | 0 | 2021-07 | 0 | 0
1073 | CR0013982 | CTASK0027603 | Implemented | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-08-11 21:11 | 2021-08-09 21:11 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal] TAA Ref No. Enhancement | 2021-07-08 14:50 | 2021-07-10 02:00 | 2021-07-08 14:50 | 2021-07-29 11:52 | 2021-07-29 12:19 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-07-30 10:30 |  | CR0013982 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W33 | 2021-08 | 24 | 24 | 39.7984 | 4 | 1 | 1 | 0.03 | 193488 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 22 | 0.53659 | 0 | 2021-07 | 0 | 0
1074 | CR0013982 | CTASK0027602 | Implemented | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-07-07 19:11 | 2021-07-05 11:10 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] TAA Ref No. Enhancement | 2021-07-08 14:50 | 2021-07-10 02:00 | 2021-07-08 14:50 | 2021-07-29 11:52 | 2021-07-29 12:19 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-07-30 10:30 |  | CR0013982 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W33 | 2021-08 | 24 | 24 | 39.7984 | 4 | 1 | 1 | 0.03 | 193488 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 22 | 0.53659 | 0 | 2021-07 | 0 | 0
1075 | CR0013982 | CTASK0027600 | Implemented | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-06-15 19:31 | 2021-06-14 11:03 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal] TAA Ref No. Enhancement | 2021-07-08 14:50 | 2021-07-10 02:00 | 2021-07-08 14:50 | 2021-07-29 11:52 | 2021-07-29 12:19 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-07-30 10:30 |  | CR0013982 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W33 | 2021-08 | 24 | 24 | 39.7984 | 4 | 1 | 1 | 0.03 | 193488 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 22 | 0.53659 | 0 | 2021-07 | 0 | 0
1076 | CR0012085 | CTASK0017727 | Closed | OPUS-BKG-OB | Nam Nguyen | 1 | 1 | 2020-01-23 | 2020-01-06 09:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | B/L Issue [Alt+8] | OBDOC - New batch job to extract BLs ready for release | 2020-01-09 16:45 | 2020-02-04 | 2020-02-03 17:56 | 2020-05-07 09:47 | 2020-05-08 14:24 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-11 08:24 | 2020-06-03 13:36 | CR0012085 | Service ManagementBooking/DocumentationOutbound DocB/L CreationB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W21 | 2020-05 | 75 | 70 | 130.7187 | 2 | 1 | 2 | 0.02 | 123048 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.46154 | 2020-01 | 0 | 0
1077 | CR0012085 | CTASK0017728 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 75 | 70 | 2020-05-14 19:00 | 2020-01-06 09:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | B/L Issue [Alt+8] | OBDOC - New batch job to extract BLs ready for release | 2020-01-09 16:45 | 2020-02-04 | 2020-02-03 17:56 | 2020-05-07 09:47 | 2020-05-08 14:24 |  | 2020-05-19 10:00 | 2020-05-19 10:30 | 2020-05-11 08:24 | 2020-06-03 13:36 | CR0012085 | Service ManagementBooking/DocumentationOutbound DocB/L CreationB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W21 | 2020-05 | 75 | 70 | 130.7187 | 2 | 1 | 2 | 0.02 | 193470 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 1.3333 | 2020-01 | 0 | 0
1078 | CR0011338 | CTASK0015217 | Closed | OPUS-MNR | Tien Le | 126 | 50 | 2019-08-09 10:36 | 2019-07-01 10:35 | Container | Equipment Management | M&R |  |  |  | [initial]Request to fix system logic for failed MNR CSR due to VVD change in booking | 2019-06-28 14:34 | 2019-08-09 14:33 | 2019-08-09 10:31 | 2019-11-26 19:00 | 2019-11-27 13:29 |  | 2019-12-10 13:29 | 2019-12-03 11:37 | 2019-11-28 10:30 | 2019-12-10 10:41 | CR0011338 | Equipment ManagementM&R | OPUS-MNR | 2019-W50 | 2019-12 | 126 | 50 | 164.9551 | 1 | 1 | 1 | 0.01 | 173286 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 18 | 0 | 0 | 2019-06 | 0 | 0
1079 | CR0013703 | CTASK0025735 | Closed | OPUS-SCO | Nguyen Ha Vi | 8 | 8 | 2021-03-31 09:51 | 2021-03-09 09:51 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Vi Nguyen][March][NA *Collection Manager* Enhancements to CLEAR] | 2021-03-24 10:52 | 2021-05-31 10:51 | 2021-04-12 09:53 | 2021-05-11 08:37 | 2021-05-11 10:57 |  | 2021-05-18 10:00 | 2021-05-18 09:15 | 2021-05-12 10:21 | 2021-06-05 04:15 | CR0013703 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2021-W20 | 2021-05 | 20 | 20 | 54.9641 | 2 | 1 | 2 | 0.02 | 203664 | 0.8 | 2 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 1.8182 | 1.2857 | 2021-03 | 0 | 0
1080 | CR0013703 | CTASK0025733 | Closed | OPUS-SCO | Mohamed Hary | 12 | 12 | 2021-04-30 09:50 | 2021-04-01 09:49 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Mohamed Hary][April][NA *Collection Manager* Enhancements to CLEAR] | 2021-03-24 10:52 | 2021-05-31 10:51 | 2021-04-12 09:53 | 2021-05-11 08:37 | 2021-05-11 10:57 |  | 2021-05-18 10:00 | 2021-05-18 09:15 | 2021-05-12 10:21 | 2021-06-05 04:15 | CR0013703 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2021-W20 | 2021-05 | 20 | 20 | 54.9641 | 2 | 1 | 2 | 0.02 | 193489 | 1.8 | 2 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 0.72727 | 0.63636 | 2021-03 | 0 | 0
1081 | CR0014093 | CTASK0027795 | Implemented | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-09-01 01:39 | 2021-08-02 02:39 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Deployment] [CLT Internal] Enhance Remark 1 field on BRN PDF file | 2021-07-05 11:37 | 2021-07-29 02:00 | 2021-07-23 13:27 | 2021-07-29 11:22 | 2021-07-29 11:32 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-07-29 11:37 |  | CR0014093 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W33 | 2021-08 | 40 | 40 | 42.9327 | 4 | 1 | 1 | 0.04 | 153106 | 2.8 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 22 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
1082 | CR0014093 | CTASK0027789 | Implemented | OPUS-BKG-M | Kieu Le | 10 | 10 | 2021-07-01 01:31 | 2021-06-28 02:31 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Design] [CLT Internal] Enhance Remark 1 field on BRN PDF file | 2021-07-05 11:37 | 2021-07-29 02:00 | 2021-07-23 13:27 | 2021-07-29 11:22 | 2021-07-29 11:32 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-07-29 11:37 |  | CR0014093 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W33 | 2021-08 | 40 | 40 | 42.9327 | 4 | 1 | 1 | 0.04 | 153106 | 2.8 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 22 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
1083 | CR0014093 | CTASK0027791 | Implemented | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-07-10 01:35 | 2021-07-05 02:35 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Development] [CLT Internal] Enhance Remark 1 field on BRN PDF file | 2021-07-05 11:37 | 2021-07-29 02:00 | 2021-07-23 13:27 | 2021-07-29 11:22 | 2021-07-29 11:32 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-07-29 11:37 |  | CR0014093 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W33 | 2021-08 | 40 | 40 | 42.9327 | 4 | 1 | 1 | 0.04 | 153106 | 2.8 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 22 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
1084 | CR0014093 | CTASK0027793 | Implemented | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-07-23 18:37 | 2021-07-12 18:37 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Testing] [CLT Internal] Enhance Remark 1 field on BRN PDF file | 2021-07-05 11:37 | 2021-07-29 02:00 | 2021-07-23 13:27 | 2021-07-29 11:22 | 2021-07-29 11:32 |  | 2021-08-17 10:00 | 2021-08-17 13:00 | 2021-07-29 11:37 |  | CR0014093 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W33 | 2021-08 | 40 | 40 | 42.9327 | 4 | 1 | 1 | 0.04 | 153106 | 2.8 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 22 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
1085 | CR0012901 | CTASK0023445 | Closed | OPUS-BKG-M | Kieu Le | 14 | 14 | 2020-12-31 17:35 | 2020-12-01 17:35 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] ASIA - SPC - To show Standby booking with no/incorrect Target VVD in Standby booking Status Report and Standby booking detail popup | 2020-12-07 09:22 | 2021-01-14 02:00 | 2021-01-11 16:52 | 2021-05-07 09:44 | 2021-05-10 09:00 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-10 11:04 | 2021-06-24 14:00 | CR0012901 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W21 | 2021-05 | 62 | 62 | 169.0265 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 2 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
1086 | CR0012901 | CTASK0023447 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-05-31 17:36 | 2021-05-03 02:36 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] ASIA - SPC - To show Standby booking with no/incorrect Target VVD in Standby booking Status Report and Standby booking detail popup | 2020-12-07 09:22 | 2021-01-14 02:00 | 2021-01-11 16:52 | 2021-05-07 09:44 | 2021-05-10 09:00 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-10 11:04 | 2021-06-24 14:00 | CR0012901 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W21 | 2021-05 | 62 | 62 | 169.0265 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 2 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
1087 | CR0012901 | CTASK0023440 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2020-11-30 17:02 | 2020-11-02 17:02 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] ASIA - SPC - To show Standby booking with no/incorrect Target VVD in Standby booking Status Report and Standby booking detail popup | 2020-12-07 09:22 | 2021-01-14 02:00 | 2021-01-11 16:52 | 2021-05-07 09:44 | 2021-05-10 09:00 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-10 11:04 | 2021-06-24 14:00 | CR0012901 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W21 | 2021-05 | 62 | 62 | 169.0265 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 2 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
1088 | CR0012901 | CTASK0023442 | Closed | OPUS-BKG-M | Kieu Le | 28 | 28 | 2020-12-31 17:23 | 2020-12-01 17:22 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] ASIA - SPC - To show Standby booking with no/incorrect Target VVD in Standby booking Status Report and Standby booking detail popup | 2020-12-07 09:22 | 2021-01-14 02:00 | 2021-01-11 16:52 | 2021-05-07 09:44 | 2021-05-10 09:00 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-10 11:04 | 2021-06-24 14:00 | CR0012901 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W21 | 2021-05 | 62 | 62 | 169.0265 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 2 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
1089 | CR0012901 | CTASK0024519 | Closed | OPUS-BKG-M | Kieu Le | 10 | 10 | 2021-01-08 20:24 | 2021-01-04 20:24 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] ASIA - SPC - To show Standby booking with no/incorrect Target VVD in Standby booking Status Report and Standby booking detail popup | 2020-12-07 09:22 | 2021-01-14 02:00 | 2021-01-11 16:52 | 2021-05-07 09:44 | 2021-05-10 09:00 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-10 11:04 | 2021-06-24 14:00 | CR0012901 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W21 | 2021-05 | 62 | 62 | 169.0265 | 5 | 1 | 1 | 0.02 | 153106 | 2.2 | 2 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
1090 | CR0013781 | CTASK0026512 | Closed | OPUS-SCG | Trang Duy Thong | 25 | 28 | 2021-05-28 11:06 | 2021-04-15 11:06 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Documentation] OPUS ENHANCEMENT- Amendment changes to YELLOW and GREEN for AWK, BB and SS + Elapse Day Bug + Sort-Request Date | 2021-04-20 16:58 | 2021-06-04 16:58 | 2021-06-04 09:13 | 2021-06-22 15:46 | 2021-06-24 15:34 |  | 2021-06-29 09:50 | 2021-04-29 11:22 | 2021-06-25 13:33 | 2021-07-29 14:00 | CR0013781 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2021-W26 | 2021-06 | 158 | 168 | 69.7032 | 2 | 1 | 1 | 0.1 | 193511 | 0.9 | 1 | 0 | 0 | 2 | 1 | 2 | 16 | 53 | 0.81818 | 0 | 2021-04 | 0 | 0
1091 | CR0013781 | CTASK0026513 | Closed | OPUS-SCG | Trang Duy Thong | 133 | 140 | 2021-05-28 11:10 | 2021-04-15 11:10 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] OPUS ENHANCEMENT- Amendment changes to YELLOW and GREEN for AWK, BB and SS + Elapse Day Bug + Sort-Request Date | 2021-04-20 16:58 | 2021-06-04 16:58 | 2021-06-04 09:13 | 2021-06-22 15:46 | 2021-06-24 15:34 |  | 2021-06-29 09:50 | 2021-04-29 11:22 | 2021-06-25 13:33 | 2021-07-29 14:00 | CR0013781 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2021-W26 | 2021-06 | 158 | 168 | 69.7032 | 2 | 1 | 1 | 0.1 | 193511 | 0.9 | 1 | 0 | 0 | 2 | 1 | 2 | 16 | 53 | 0.81818 | 0 | 2021-04 | 0 | 0
1092 | CR0011992 | CTASK0019697 | Closed | OPUS-TRS | Giang Nguyen Hoang | 20 | 20 | 2020-04-30 11:10 | 2020-04-20 11:10 | Container | Service Management | Trans S/O |  |  |  | EUA - PARIS Project : Optimization of transports using external Software - ETL requirements for OPUS interface to PARIS phase 'zero' - CY shipments spin off | 2020-03-11 11:42 | 2020-05-31 18:00 | 2020-04-28 09:44 | 2020-09-04 21:40 | 2020-09-07 16:16 |  | 2020-09-15 11:00 | 2020-10-06 11:56 | 2020-09-08 17:56 | 2020-11-05 14:00 | CR0011992 | Service ManagementTrans S/O | OPUS-TRS | 2020-W38 | 2020-09 | 40 | 40 | 187.9705 | 2 | 1 | 2 | 0.01 | 183440 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 9 | 36 | 0 | 0 | 2020-03 | 0 | 0
1093 | CR0011992 | CTASK0019696 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 20 | 20 | 2020-04-30 11:09 | 2020-04-20 11:09 | Container | Service Management | Trans S/O |  |  |  | EUA - PARIS Project : Optimization of transports using external Software - ETL requirements for OPUS interface to PARIS phase 'zero' - CY shipments spin off | 2020-03-11 11:42 | 2020-05-31 18:00 | 2020-04-28 09:44 | 2020-09-04 21:40 | 2020-09-07 16:16 |  | 2020-09-15 11:00 | 2020-10-06 11:56 | 2020-09-08 17:56 | 2020-11-05 14:00 | CR0011992 | Service ManagementTrans S/O | OPUS-TRS | 2020-W38 | 2020-09 | 40 | 40 | 187.9705 | 2 | 1 | 2 | 0.01 | 183432 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 9 | 36 | 0 | 0 | 2020-03 | 0 | 0
1094 | CR0010566 | CTASK0021787 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 90 | 90 | 2020-10-31 19:30 | 2020-09-28 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Development+Testing+ Deployment] CUSTOMS SEA IMPENDING ARRIVAL EDI | 2020-10-20 15:07 | 2020-11-21 | 2020-11-18 13:38 | 2020-12-08 17:27 | 2020-12-09 09:04 |  | 2020-12-22 09:40 | 2020-12-22 10:47 | 2020-12-11 17:34 | 2021-01-20 07:20 | CR0010566 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2020-W52 | 2020-12 | 163 | 163 | 62.773 | 4 | 1 | 1 | 0.11 | 173280 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 30 | 0 | 0.18519 | 2020-10 | 0 | 0
1095 | CR0010566 | CTASK0023814 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 27 | 27 | 2020-12-31 19:30 | 2020-12-01 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Development+Testing+ Deployment] CUSTOMS SEA IMPENDING ARRIVAL EDI | 2020-10-20 15:07 | 2020-11-21 | 2020-11-18 13:38 | 2020-12-08 17:27 | 2020-12-09 09:04 |  | 2020-12-22 09:40 | 2020-12-22 10:47 | 2020-12-11 17:34 | 2021-01-20 07:20 | CR0010566 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2020-W52 | 2020-12 | 163 | 163 | 62.773 | 4 | 1 | 1 | 0.11 | 173280 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 30 | 0 | 0.18519 | 2020-10 | 0 | 0
1096 | CR0010566 | CTASK0023199 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 14 | 14 | 2020-11-30 19:30 | 2020-11-02 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Development+Testing+ Deployment] CUSTOMS SEA IMPENDING ARRIVAL EDI | 2020-10-20 15:07 | 2020-11-21 | 2020-11-18 13:38 | 2020-12-08 17:27 | 2020-12-09 09:04 |  | 2020-12-22 09:40 | 2020-12-22 10:47 | 2020-12-11 17:34 | 2021-01-20 07:20 | CR0010566 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2020-W52 | 2020-12 | 163 | 163 | 62.773 | 4 | 1 | 1 | 0.11 | 173280 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 30 | 0 | 0.18519 | 2020-10 | 0 | 0
1097 | CR0010566 | CTASK0021492 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 32 | 32 | 2020-08-14 19:30 | 2020-07-23 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Design+Analysis+Estimation] CUSTOMS SEA IMPENDING ARRIVAL EDI | 2020-10-20 15:07 | 2020-11-21 | 2020-11-18 13:38 | 2020-12-08 17:27 | 2020-12-09 09:04 |  | 2020-12-22 09:40 | 2020-12-22 10:47 | 2020-12-11 17:34 | 2021-01-20 07:20 | CR0010566 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2020-W52 | 2020-12 | 163 | 163 | 62.773 | 4 | 1 | 1 | 0.11 | 173280 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 4 | 30 | 0 | 0.18519 | 2020-10 | 0 | 0
1098 | CR0013899 | CTASK0027346 | Closed | OPUS-BSA | Tuan Pham Huu | 50 | 50 |  |  | Container | Sales Management | BSA |  |  |  | Request to interface to IBIS PLUS - BSA_VVD_PORT_DWN | 2021-06-09 11:13 | 2021-07-16 11:11 | 2021-07-15 10:13 | 2021-07-19 17:35 | 2021-08-04 15:03 |  | 2021-08-13 15:03 | 2021-08-10 11:36 | 2021-08-04 15:19 | 2021-08-17 14:00 | CR0013899 | Sales ManagementBSA | OPUS-STOW | 2021-W32 | 2021-08 | 50 | 50 | 65.1596 | 1 | 1 | 1 | 0.03 | 193523 | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 22 | 0 | 0 | 2021-06 | 0 | 0
1099 | CR0012020 | CTASK0020903 | Closed | OPUS-BKG-OB | Nam Nguyen | 44 | 44 | 2020-09-30 16:53 | 2020-09-01 16:53 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development]LA - BKG - L.OFC/Rep Assignment Logic | 2020-08-26 15:14 | 2020-10-02 09:27 | 2020-09-24 17:23 | 2020-11-25 18:24 | 2020-11-25 22:00 |  | 2020-12-15 10:00 | 2020-12-22 10:00 | 2020-12-02 10:10 | 2021-01-23 14:00 | CR0012020 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W51 | 2020-12 | 44 | 44 | 110.782 | 1 | 1 | 1 | 0.02 | 123048 | 1.9 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 30 | 0 | 0.46154 | 2020-08 | 0 | 0
1100 | CR0013951 | CTASK0026947 | Closed | OPUS-SCO | Cuong Tran Hung | 16 | 16 | 2021-05-31 10:30 | 2021-05-12 10:30 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Register Dispute |  | [May 2021][Lien Le][[CLT Internal] Improve the retrieval performance on [Register Dispute] function] | 2021-05-12 13:46 | 2021-07-15 13:46 | 2021-07-01 13:49 | 2021-07-01 16:02 | 2021-07-01 20:13 |  | 2021-07-06 10:00 | 2021-07-06 10:00 | 2021-07-02 10:27 | 2021-07-29 14:00 | CR0013951 | Statement ManagementStatement Account ReceivableDispute ManagerRegister Dispute | OPUS-SCO | 2021-W27 | 2021-07 | 16 | 16 | 54.843 | 1 | 1 | 1 | 0.01 | 193530 | 1.9 | 2 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 1.2308 | 1.2222 | 2021-05 | 0 | 0
1101 | CR0012474 | CTASK0020304 | Closed | OPUS-BKG-OB | Nam Nguyen | 8 | 8 | 2020-06-22 18:19 | 2020-06-08 18:18 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Status Report | [Development & Testing] [CLT Internal] Enhancement of ESM_BKG_0647 to prevent OOME | 2020-06-02 08:06 | 2020-06-30 08:05 | 2020-06-29 13:49 |  | 2020-07-13 11:00 |  | 2020-07-21 11:00 | 2020-07-21 10:00 | 2020-07-13 14:25 | 2020-07-22 08:35 | CR0012474 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Status Report | OPUS-BKG-OB | 2020-W30 | 2020-07 | 38 | 44 | 49.1211 | 5 | 1 | 2 | 0.04 | 123048 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 27 | 0 | 0.46154 | 2020-06 | 0 | 0
1102 | CR0012474 | CTASK0021268 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 10 | 10 | 2020-07-21 01:00 | 2020-07-15 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Status Report | [Deployment] [CLT Internal] Enhancement of ESM_BKG_0647 to prevent OOME | 2020-06-02 08:06 | 2020-06-30 08:05 | 2020-06-29 13:49 |  | 2020-07-13 11:00 |  | 2020-07-21 11:00 | 2020-07-21 10:00 | 2020-07-13 14:25 | 2020-07-22 08:35 | CR0012474 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Status Report | OPUS-BKG-OB | 2020-W30 | 2020-07 | 38 | 44 | 49.1211 | 5 | 1 | 2 | 0.04 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 27 | 0 | 0.17391 | 2020-06 | 0 | 0
1103 | CR0012474 | CTASK0020451 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 12 | 12 | 2020-06-12 19:30 | 2020-06-02 12:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Status Report | [Development] [CLT Internal] Enhancement of ESM_BKG_0647 to prevent OOME | 2020-06-02 08:06 | 2020-06-30 08:05 | 2020-06-29 13:49 |  | 2020-07-13 11:00 |  | 2020-07-21 11:00 | 2020-07-21 10:00 | 2020-07-13 14:25 | 2020-07-22 08:35 | CR0012474 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Status Report | OPUS-BKG-OB | 2020-W30 | 2020-07 | 38 | 44 | 49.1211 | 5 | 1 | 2 | 0.04 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 27 | 0 | 0.17391 | 2020-06 | 0 | 0
1104 | CR0012474 | CTASK0020305 | Closed | OPUS-BKG-OB | Nam Nguyen | 6 | 6 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Status Report | [Deployment][CLT Internal] Enhancement of ESM_BKG_0647 to prevent OOME | 2020-06-02 08:06 | 2020-06-30 08:05 | 2020-06-29 13:49 |  | 2020-07-13 11:00 |  | 2020-07-21 11:00 | 2020-07-21 10:00 | 2020-07-13 14:25 | 2020-07-22 08:35 | CR0012474 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Status Report | OPUS-BKG-OB | 2020-W30 | 2020-07 | 38 | 44 | 49.1211 | 5 | 1 | 2 | 0.04 | 123048 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 27 | 0 | 0.46154 | 2020-06 | 0 | 0
1105 | CR0012474 | CTASK0020283 | Closed | OPUS-BKG-OB | Nam Nguyen | 8 | 8 | 2020-05-26 19:21 | 2020-05-25 19:21 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Status Report | [Estimate][CLT Internal] Enhancement of ESM_BKG_0647 to prevent OOME | 2020-06-02 08:06 | 2020-06-30 08:05 | 2020-06-29 13:49 |  | 2020-07-13 11:00 |  | 2020-07-21 11:00 | 2020-07-21 10:00 | 2020-07-13 14:25 | 2020-07-22 08:35 | CR0012474 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Status Report | OPUS-BKG-OB | 2020-W30 | 2020-07 | 38 | 44 | 49.1211 | 5 | 1 | 2 | 0.04 | 123048 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 27 | 0 | 0.46154 | 2020-06 | 0 | 0
1106 | CR0013575 | CTASK0025653 | Closed | OPUS-BKG-M | Vinh Tran | 16 | 20 | 2021-05-08 02:00 | 2021-05-06 02:00 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Testing] Global *EDI* FF Update 301/301U - Adding generated booking remarks | 2021-03-19 18:10 | 2021-05-13 | 2021-05-11 09:31 | 2021-07-22 11:16 | 2021-07-22 15:24 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-26 10:04 | 2021-08-17 14:00 | CR0013575 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2021-W32 | 2021-08 | 68 | 76 | 143.6599 | 4 | 1 | 1 | 0.02 | 193525 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 10 | 22 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
1107 | CR0013575 | CTASK0025652 | Closed | OPUS-BKG-M | Vinh Tran | 32 | 36 | 2021-05-06 02:00 | 2021-04-19 02:00 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Development] Global *EDI* FF Update 301/301U - Adding generated booking remarks | 2021-03-19 18:10 | 2021-05-13 | 2021-05-11 09:31 | 2021-07-22 11:16 | 2021-07-22 15:24 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-26 10:04 | 2021-08-17 14:00 | CR0013575 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2021-W32 | 2021-08 | 68 | 76 | 143.6599 | 4 | 1 | 1 | 0.02 | 193525 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 10 | 22 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
1108 | CR0013575 | CTASK0025654 | Closed | OPUS-BKG-M | Vinh Tran | 4 | 4 | 2021-08-05 02:00 | 2021-08-03 02:00 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Deployment] Global *EDI* FF Update 301/301U - Adding generated booking remarks | 2021-03-19 18:10 | 2021-05-13 | 2021-05-11 09:31 | 2021-07-22 11:16 | 2021-07-22 15:24 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-26 10:04 | 2021-08-17 14:00 | CR0013575 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2021-W32 | 2021-08 | 68 | 76 | 143.6599 | 4 | 1 | 1 | 0.02 | 193525 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 10 | 22 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
1109 | CR0013575 | CTASK0025609 | Closed | OPUS-BKG-M | Vinh Tran | 16 | 16 | 2021-03-04 02:00 | 2021-03-01 02:00 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Design] Global *EDI* FF Update 301/301U - Adding generated booking remarks | 2021-03-19 18:10 | 2021-05-13 | 2021-05-11 09:31 | 2021-07-22 11:16 | 2021-07-22 15:24 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-26 10:04 | 2021-08-17 14:00 | CR0013575 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2021-W32 | 2021-08 | 68 | 76 | 143.6599 | 4 | 1 | 1 | 0.02 | 193525 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 10 | 22 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
1110 | CR0010257 | CTASK0014939 | Closed | OPUS-BKG-M | Nam Nguyen | 206 | 56 | 2019-10-15 11:17 | 2019-10-02 11:16 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | Extend pop up message to all tabs when multiple user access and updating concurrently in a booking. | 2019-02-15 10:31 | 2019-06-21 10:30 | 2019-06-19 14:34 | 2019-09-17 09:59 | 2019-09-17 11:07 | 2019-06-19 14:35 | 2019-09-24 11:07 | 2019-10-15 12:40 | 2019-09-17 11:10 | 2019-10-18 17:20 | CR0010257 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W39 | 2019-09 | 206 | 56 | 221.025 | 1 | 1 | 1 | 0.01 | 123048 | 0.4 | 0 | 0 | 3 | 1 | 1 | 3 | 3 | 6 | 0 | 0.5 | 2019-02 | 3 | 1
1111 | CR0013156 | CTASK0022853 | Closed | OPUS-FLT | Tu Nguyen | 41 | 41 | 2020-10-27 18:00 | 2020-10-05 09:00 | Container | Support & Admin | Fleet Management | Contract |  |  | [CLV] [CLT Internal] Logic enhancement for RE-FX contract trigger point. | 2020-10-06 13:10 | 2020-10-27 18:00 | 2020-10-22 15:03 | 2020-10-26 10:28 | 2020-10-26 13:22 |  | 2020-11-03 10:00 | 2020-11-03 10:00 | 2020-10-29 15:11 | 2020-12-04 14:00 | CR0013156 | Support & AdminFleet ManagementContract | OPUS-FLT | 2020-W45 | 2020-11 | 41 | 41 | 27.8682 | 1 | 1 | 1 | 0.06 | 123045 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0 | 2020-10 | 0 | 0
1112 | CR0012713 | CTASK0021372 | Closed | OPUS-SCO | Cuong Tran Hung | 60 | 60 | 2020-09-30 11:39 | 2020-09-01 11:39 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [September][Cuong Tran] EUA - Debtor Cockpit Improvements [CR2] | 2020-08-20 16:41 | 2020-09-30 16:41 | 2020-09-11 18:08 | 2020-12-23 10:30 | 2020-12-23 10:42 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:52 | 2021-01-19 20:47 | CR0012713 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2020-W53 | 2020-12 | 278 | 275 | 129.7213 | 8 | 1 | 4 | 0.09 | 193530 | 1.2 | 1 | 4 | 0 | 3 | 2 | 2 | 9 | 30 | 0 | 1.2222 | 2020-08 | 4 | 1
1113 | CR0012713 | CTASK0021322 | Closed | OPUS-SCO | Mohamed Hary | 20 | 20 | 2020-08-31 10:15 | 2020-08-01 10:15 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [August][Hary] EUA - Debtor Cockpit Improvements [CR2] | 2020-08-20 16:41 | 2020-09-30 16:41 | 2020-09-11 18:08 | 2020-12-23 10:30 | 2020-12-23 10:42 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:52 | 2021-01-19 20:47 | CR0012713 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2020-W53 | 2020-12 | 278 | 275 | 129.7213 | 8 | 1 | 4 | 0.09 | 193489 | 1.2 | 1 | 4 | 0 | 3 | 2 | 2 | 9 | 30 | 0 | 0.63636 | 2020-08 | 4 | 1
1114 | CR0012713 | CTASK0021320 | Closed | OPUS-SCO | Lien Le | 56 | 53 | 2020-08-31 10:14 | 2020-08-01 10:14 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [August][Lien Le] EUA - Debtor Cockpit Improvements [CR2] | 2020-08-20 16:41 | 2020-09-30 16:41 | 2020-09-11 18:08 | 2020-12-23 10:30 | 2020-12-23 10:42 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:52 | 2021-01-19 20:47 | CR0012713 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2020-W53 | 2020-12 | 278 | 275 | 129.7213 | 8 | 1 | 4 | 0.09 | 193441 | 1.4 | 1 | 4 | 0 | 3 | 2 | 2 | 9 | 30 | 0 | 1.2222 | 2020-08 | 4 | 1
1115 | CR0012713 | CTASK0021374 | Closed | OPUS-SCO | Cuong Tran Hung | 1 | 1 | 2020-10-31 11:40 | 2020-10-01 11:40 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [October][Cuong Tran] EUA - Debtor Cockpit Improvements [CR2] | 2020-08-20 16:41 | 2020-09-30 16:41 | 2020-09-11 18:08 | 2020-12-23 10:30 | 2020-12-23 10:42 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:52 | 2021-01-19 20:47 | CR0012713 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2020-W53 | 2020-12 | 278 | 275 | 129.7213 | 8 | 1 | 4 | 0.09 | 193530 | 1.2 | 1 | 4 | 0 | 3 | 2 | 2 | 9 | 30 | 0 | 1.2222 | 2020-08 | 4 | 1
1116 | CR0012713 | CTASK0021324 | Closed | OPUS-SCO | Chuong Ta | 16 | 16 | 2020-08-31 10:17 | 2020-08-01 10:17 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [August][Chuong Ta] EUA - Debtor Cockpit Improvements [CR2] | 2020-08-20 16:41 | 2020-09-30 16:41 | 2020-09-11 18:08 | 2020-12-23 10:30 | 2020-12-23 10:42 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:52 | 2021-01-19 20:47 | CR0012713 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2020-W53 | 2020-12 | 278 | 275 | 129.7213 | 8 | 1 | 4 | 0.09 | 183379 | 1.4 | 1 | 4 | 0 | 3 | 2 | 2 | 9 | 30 | 0 | 0.38462 | 2020-08 | 4 | 1
1117 | CR0012713 | CTASK0021378 | Closed | OPUS-SCO | Lien Le | 1 | 1 | 2020-10-31 11:43 | 2020-10-01 11:43 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [October][Lien Le] EUA - Debtor Cockpit Improvements [CR2] | 2020-08-20 16:41 | 2020-09-30 16:41 | 2020-09-11 18:08 | 2020-12-23 10:30 | 2020-12-23 10:42 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:52 | 2021-01-19 20:47 | CR0012713 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2020-W53 | 2020-12 | 278 | 275 | 129.7213 | 8 | 1 | 4 | 0.09 | 193441 | 1.4 | 1 | 4 | 0 | 3 | 2 | 2 | 9 | 30 | 0 | 1.2222 | 2020-08 | 4 | 1
1118 | CR0012713 | CTASK0021376 | Closed | OPUS-SCO | Lien Le | 106 | 106 | 2020-09-30 11:42 | 2020-09-01 11:42 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [September][Lien Le] EUA - Debtor Cockpit Improvements [CR2] | 2020-08-20 16:41 | 2020-09-30 16:41 | 2020-09-11 18:08 | 2020-12-23 10:30 | 2020-12-23 10:42 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:52 | 2021-01-19 20:47 | CR0012713 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2020-W53 | 2020-12 | 278 | 275 | 129.7213 | 8 | 1 | 4 | 0.09 | 193441 | 1.4 | 1 | 4 | 0 | 3 | 2 | 2 | 9 | 30 | 0 | 1.2222 | 2020-08 | 4 | 1
1119 | CR0012713 | CTASK0021323 | Closed | OPUS-SCO | Cuong Tran Hung | 20 | 20 | 2020-08-31 10:16 | 2020-08-01 10:16 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [August][Cuong Tran] EUA - Debtor Cockpit Improvements [CR2] | 2020-08-20 16:41 | 2020-09-30 16:41 | 2020-09-11 18:08 | 2020-12-23 10:30 | 2020-12-23 10:42 |  | 2020-12-28 10:00 | 2020-12-28 10:00 | 2020-12-23 17:52 | 2021-01-19 20:47 | CR0012713 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2020-W53 | 2020-12 | 278 | 275 | 129.7213 | 8 | 1 | 4 | 0.09 | 193530 | 1.2 | 1 | 4 | 0 | 3 | 2 | 2 | 9 | 30 | 0 | 1.2222 | 2020-08 | 4 | 1
1120 | CR0013337 | CTASK0024148 | Closed | OPUS-TRS | Giang Nguyen Hoang | 16 | 16 | 2020-12-31 13:22 | 2020-12-14 13:22 | Container | Service Management | Trans S/O |  |  |  | [202012] EUA - PARIS phase zero - only send 'pure CY' to PARIS system | 2020-12-14 13:23 | 2020-12-31 21:00 | 2020-12-30 11:57 | 2021-02-15 13:49 | 2021-02-16 11:19 |  | 2021-03-02 10:00 | 2021-03-02 09:08 | 2021-02-23 13:58 | 2021-04-02 14:00 | CR0013337 | Service ManagementTrans S/O | OPUS-TRS | 2021-W9 | 2021-03 | 34 | 32 | 77.8591 | 2 | 1 | 2 | 0.02 | 183440 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 0 | 2020-12 | 0 | 0
1121 | CR0013337 | CTASK0024147 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 18 | 16 | 2020-12-31 21:00 | 2020-12-14 13:21 | Container | Service Management | Trans S/O |  |  |  | [202012] EUA - PARIS phase zero - only send 'pure CY' to PARIS system | 2020-12-14 13:23 | 2020-12-31 21:00 | 2020-12-30 11:57 | 2021-02-15 13:49 | 2021-02-16 11:19 |  | 2021-03-02 10:00 | 2021-03-02 09:08 | 2021-02-23 13:58 | 2021-04-02 14:00 | CR0013337 | Service ManagementTrans S/O | OPUS-TRS | 2021-W9 | 2021-03 | 34 | 32 | 77.8591 | 2 | 1 | 2 | 0.02 | 183432 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 0 | 2020-12 | 0 | 0
1122 | CR0011360 | CTASK0019597 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 4 | 4 | 2020-04-15 18:31 | 2020-04-13 10:26 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] (HBA) EUA EDI¦ Split bookings to inherit original booking EDI request number and receiver. | 2019-12-27 10:18 | 2020-02-18 | 2020-02-17 16:42 | 2020-03-19 18:14 | 2020-03-20 11:20 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-03-20 17:07 | 2020-05-22 13:00 | CR0011360 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W17 | 2020-04 | 236 | 180 | 115.9877 | 7 | 3 | 4 | 0.06 | 193512 | 0.5 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 16 | 0 | 0.5 | 2019-12 | 1 | 1
1123 | CR0011360 | CTASK0017955 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 40 | 36 | 2020-02-07 12:21 | 2020-01-16 12:20 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | (HBA) EUA EDI¦ Split bookings to inherit original booking EDI request number and receiver. | 2019-12-27 10:18 | 2020-02-18 | 2020-02-17 16:42 | 2020-03-19 18:14 | 2020-03-20 11:20 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-03-20 17:07 | 2020-05-22 13:00 | CR0011360 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W17 | 2020-04 | 236 | 180 | 115.9877 | 7 | 3 | 4 | 0.06 | 193488 | 0.5 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 16 | 0 | 2.1667 | 2019-12 | 1 | 1
1124 | CR0011360 | CTASK0017863 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 88 | 59 | 2020-02-08 | 2020-01-09 15:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | (HBA) EUA EDI¦ Split bookings to inherit original booking EDI request number and receiver. | 2019-12-27 10:18 | 2020-02-18 | 2020-02-17 16:42 | 2020-03-19 18:14 | 2020-03-20 11:20 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-03-20 17:07 | 2020-05-22 13:00 | CR0011360 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W17 | 2020-04 | 236 | 180 | 115.9877 | 7 | 3 | 4 | 0.06 | 193512 | 0.5 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 16 | 0 | 0.5 | 2019-12 | 1 | 1
1125 | CR0011360 | CTASK0019607 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 5 | 2 | 2020-04-15 18:31 | 2020-04-13 10:26 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] (HBA) EUA EDI¦ Split bookings to inherit original booking EDI request number and receiver. | 2019-12-27 10:18 | 2020-02-18 | 2020-02-17 16:42 | 2020-03-19 18:14 | 2020-03-20 11:20 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-03-20 17:07 | 2020-05-22 13:00 | CR0011360 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W17 | 2020-04 | 236 | 180 | 115.9877 | 7 | 3 | 4 | 0.06 | 193488 | 0.5 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 16 | 0 | 2.1667 | 2019-12 | 1 | 1
1126 | CR0011360 | CTASK0016515 | Closed | OPUS-BKG-M | Loc Tran | 38 | 29 | 2020-02-07 09:59 | 2020-01-06 09:59 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | (HBA) EUA EDI¦ Split bookings to inherit original booking EDI request number and receiver. | 2019-12-27 10:18 | 2020-02-18 | 2020-02-17 16:42 | 2020-03-19 18:14 | 2020-03-20 11:20 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-03-20 17:07 | 2020-05-22 13:00 | CR0011360 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W17 | 2020-04 | 236 | 180 | 115.9877 | 7 | 3 | 4 | 0.06 | 193503 | 0.4 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 16 | 0 | 0.36364 | 2019-12 | 1 | 1
1127 | CR0011360 | CTASK0016516 | Closed | OPUS-BKG-M | Vinh Tran | 59 | 48 | 2020-02-07 10:00 | 2020-01-06 10:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | (HBA) EUA EDI¦ Split bookings to inherit original booking EDI request number and receiver. | 2019-12-27 10:18 | 2020-02-18 | 2020-02-17 16:42 | 2020-03-19 18:14 | 2020-03-20 11:20 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-03-20 17:07 | 2020-05-22 13:00 | CR0011360 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W17 | 2020-04 | 236 | 180 | 115.9877 | 7 | 3 | 4 | 0.06 | 193525 | 0.6 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 16 | 0 | 0.45455 | 2019-12 | 1 | 1
1128 | CR0011360 | CTASK0019596 | Closed | OPUS-BKG-M | Vinh Tran | 2 | 2 | 2020-04-16 02:00 | 2020-04-13 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] (HBA) EUA EDI¦ Split bookings to inherit original booking EDI request number and receiver. | 2019-12-27 10:18 | 2020-02-18 | 2020-02-17 16:42 | 2020-03-19 18:14 | 2020-03-20 11:20 |  | 2020-04-21 10:00 | 2020-04-21 10:00 | 2020-03-20 17:07 | 2020-05-22 13:00 | CR0011360 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W17 | 2020-04 | 236 | 180 | 115.9877 | 7 | 3 | 4 | 0.06 | 193525 | 0.6 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 16 | 0 | 0.45455 | 2019-12 | 1 | 1
1129 | CR0013736 | CTASK0026553 | Closed | OPUS-SCG | Tu Nguyen | 4 | 4 | 2021-04-20 18:01 | 2021-05-03 18:01 | Container | Vessel Operation | Special Cargo | DG Restriction | DG Restriction Creation (Upload) |  | [CLV][CLT Internal] Enhancement for uploading the DG Restriction | 2021-05-12 15:42 | 2021-06-26 | 2021-06-24 17:36 | 2021-07-21 17:00 | 2021-07-22 10:01 |  | 2021-07-27 10:00 | 2021-07-27 11:22 | 2021-07-22 11:12 | 2021-08-03 14:00 | CR0013736 | Vessel OperationSpecial CargoDG RestrictionDG Restriction Creation (Upload) | OPUS-SCG | 2021-W30 | 2021-07 | 32 | 33 | 75.7627 | 3 | 1 | 2 | 0.02 | 123045 | 2.6 | 1 | 0 | 0 | 1 | 1 | 2 | 7 | 28 | 0 | 0 | 2021-05 | 0 | 0
1130 | CR0013736 | CTASK0026551 | Closed | OPUS-SCG | Lanh Le | 18 | 19 | 2021-05-14 17:58 | 2021-04-26 17:58 | Container | Vessel Operation | Special Cargo | DG Restriction | DG Restriction Creation (Upload) |  | [CLV][CLT Internal] Enhancement for uploading the DG Restriction | 2021-05-12 15:42 | 2021-06-26 | 2021-06-24 17:36 | 2021-07-21 17:00 | 2021-07-22 10:01 |  | 2021-07-27 10:00 | 2021-07-27 11:22 | 2021-07-22 11:12 | 2021-08-03 14:00 | CR0013736 | Vessel OperationSpecial CargoDG RestrictionDG Restriction Creation (Upload) | OPUS-SCG | 2021-W30 | 2021-07 | 32 | 33 | 75.7627 | 3 | 1 | 2 | 0.02 | 183422 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 7 | 28 | 0 | 0 | 2021-05 | 0 | 0
1131 | CR0013736 | CTASK0026549 | Closed | OPUS-SCG | Lanh Le | 10 | 10 | 2021-05-28 17:42 | 2021-04-16 17:42 | Container | Vessel Operation | Special Cargo | DG Restriction | DG Restriction Creation (Upload) |  | [Documentation] [CLT Internal] Enhancement for uploading the DG Restriction | 2021-05-12 15:42 | 2021-06-26 | 2021-06-24 17:36 | 2021-07-21 17:00 | 2021-07-22 10:01 |  | 2021-07-27 10:00 | 2021-07-27 11:22 | 2021-07-22 11:12 | 2021-08-03 14:00 | CR0013736 | Vessel OperationSpecial CargoDG RestrictionDG Restriction Creation (Upload) | OPUS-SCG | 2021-W30 | 2021-07 | 32 | 33 | 75.7627 | 3 | 1 | 2 | 0.02 | 183422 | 2.5 | 1 | 0 | 0 | 1 | 1 | 2 | 7 | 28 | 0 | 0 | 2021-05 | 0 | 0
1132 | CR0012524 | CTASK0019965 | Closed | OPUS-OPF | Thuan Tran | 100 | 100 | 2020-06-02 05:34 | 2020-05-13 17:34 | Container | Vessel Operation | Operation & PFMC |  |  |  | [CLV] New UI for OPF_alliance_slan_list table | 2020-04-29 13:24 | 2020-06-13 13:22 | 2020-06-12 11:48 | 2020-09-23 15:27 | 2020-09-24 16:41 |  | 2020-10-06 09:30 | 2020-10-06 09:52 | 2020-09-24 17:21 | 2020-11-05 14:00 | CR0012524 | Vessel OperationOperation & PFMC | OPUS-OPF | 2020-W41 | 2020-10 | 100 | 100 | 159.8375 | 1 | 1 | 1 | 0.03 | 183423 | 1.5 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 20 | 0 | 0 | 2020-04 | 0 | 0
1133 | CR0013067 | CTASK0022485 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 11 | 18 | 2021-02-28 10:01 | 2021-02-01 10:01 | Container | Service Management | Domestic | Admin |  |  | NA *DOM* IMC Customer Creation - Request to make Email address field a mandatory input | 2021-02-01 11:28 | 2021-02-28 21:00 | 2021-02-24 09:35 | 2021-03-11 18:16 | 2021-03-17 13:18 |  | 2021-03-23 10:00 | 2021-04-13 15:26 | 2021-04-02 02:04 | 2021-05-14 14:00 | CR0013067 | Service ManagementDomesticAdmin | OPUS-DOM | 2021-W12 | 2021-03 | 29 | 36 | 49.9388 | 2 | 1 | 2 | 0.03 | 183432 | 1.9 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 46 | 0 | 0 | 2021-02 | 0 | 0
1134 | CR0013067 | CTASK0022486 | Closed | OPUS-DOM | Giang Nguyen Hoang | 18 | 18 | 2021-02-28 10:02 | 2021-02-01 10:02 | Container | Service Management | Domestic | Admin |  |  | NA *DOM* IMC Customer Creation - Request to make Email address field a mandatory input | 2021-02-01 11:28 | 2021-02-28 21:00 | 2021-02-24 09:35 | 2021-03-11 18:16 | 2021-03-17 13:18 |  | 2021-03-23 10:00 | 2021-04-13 15:26 | 2021-04-02 02:04 | 2021-05-14 14:00 | CR0013067 | Service ManagementDomesticAdmin | OPUS-DOM | 2021-W12 | 2021-03 | 29 | 36 | 49.9388 | 2 | 1 | 2 | 0.03 | 183440 | 1.9 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 46 | 0 | 0 | 2021-02 | 0 | 0
1135 | CR0012905 | CTASK0021775 | Closed | OPUS-SAP | Lien Le | 8 | 8 | 2020-09-30 16:44 | 2020-09-01 16:44 | Container | Statement Management | Statement Account Payable | Invoices | Invoices Entry |  | [September][SAP][Lien Le][Invoice Entry Item Type - to allow 11303019, and post to ERP as 11303010 with payment ref LC] | 2020-08-25 10:14 | 2020-09-30 10:13 | 2020-09-10 13:38 | 2020-09-16 07:56 | 2020-09-16 08:18 |  | 2020-09-22 08:18 | 2020-09-22 10:00 | 2020-09-17 13:14 | 2020-10-22 13:00 | CR0012905 | Statement ManagementStatement Account PayableInvoicesInvoices Entry | OPUS-SAP | 2020-W39 | 2020-09 | 56 | 54 | 27.9198 | 2 | 1 | 2 | 0.08 | 193441 | 1.5 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 1.2222 | 2020-08 | 1 | 1
1136 | CR0012905 | CTASK0021773 | Closed | OPUS-SAP | Chuong Ta | 48 | 46 | 2020-09-30 16:42 | 2020-09-01 16:42 | Container | Statement Management | Statement Account Payable | Invoices | Invoices Entry |  | [September][SAP][Chuong Ta][Invoice Entry Item Type - to allow 11303019, and post to ERP as 11303010 with payment ref LC] | 2020-08-25 10:14 | 2020-09-30 10:13 | 2020-09-10 13:38 | 2020-09-16 07:56 | 2020-09-16 08:18 |  | 2020-09-22 08:18 | 2020-09-22 10:00 | 2020-09-17 13:14 | 2020-10-22 13:00 | CR0012905 | Statement ManagementStatement Account PayableInvoicesInvoices Entry | OPUS-SAP | 2020-W39 | 2020-09 | 56 | 54 | 27.9198 | 2 | 1 | 2 | 0.08 | 183379 | 1.5 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 0.38462 | 2020-08 | 1 | 1
1137 | CR0012350 | CTASK0020134 | Closed | OPUS-FLT | Tu Nguyen | 11 | 11 |  |  | Container | Support & Admin | Fleet Management | Invoice |  |  | [CLV-FLT] FLT Accrual Logic Change | 2020-04-27 15:50 | 2020-05-31 18:00 | 2020-05-20 13:01 | 2020-06-09 20:40 | 2020-06-10 13:54 |  | 2020-06-16 09:00 | 2020-06-16 09:00 | 2020-06-10 15:06 | 2020-07-16 13:00 | CR0012350 | Support & AdminFleet ManagementInvoice | OPUS-FLT | 2020-W25 | 2020-06 | 11 | 0 | 49.7155 | 1 | 1 | 1 | 0 | 123045 | 1.6 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 29 | 0 | 0 | 2020-04 | 0 | 0
1138 | CR0010428 | CTASK0016163 | Closed | OPUS-PRI | Nhien Nguyen | 10 | 10 | 2019-08-23 19:33 | 2019-08-21 19:32 | Container | Sales Management | Pricing |  |  |  | [08/19 ~ 08/23] Asia - PRI - Apply "filter" in spreadsheet in UI | 2019-05-16 09:32 | 2019-07-31 09:32 | 2019-06-12 15:49 | 2019-08-19 10:27 | 2019-08-20 14:14 |  | 2019-08-27 11:14 | 2019-08-27 10:08 | 2019-08-27 09:26 | 2019-09-26 13:00 | CR0010428 | Sales ManagementPricing | OPUS-PRI | 2019-W35 | 2019-08 | 104 | 0 | 103.0707 | 5 | 1 | 2 | 0 | 183364 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 6 | 0 | 0 | 2019-05 | 0 | 0
1139 | CR0010428 | CTASK0013455 | Closed | OPUS-PRI | Nhien Nguyen | 24 | 24 | 2019-05-17 09:30 | 2019-05-13 09:30 | Container | Sales Management | Pricing |  |  |  | [05/13 ~ 05/17] Asia - PRI - Apply "filter" in spreadsheet in UI | 2019-05-16 09:32 | 2019-07-31 09:32 | 2019-06-12 15:49 | 2019-08-19 10:27 | 2019-08-20 14:14 |  | 2019-08-27 11:14 | 2019-08-27 10:08 | 2019-08-27 09:26 | 2019-09-26 13:00 | CR0010428 | Sales ManagementPricing | OPUS-PRI | 2019-W35 | 2019-08 | 104 | 0 | 103.0707 | 5 | 1 | 2 | 0 | 183364 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 6 | 0 | 0 | 2019-05 | 0 | 0
1140 | CR0010428 | CTASK0013645 | Closed | OPUS-PRI | Man Hoang | 6 | 6 | 2019-05-17 18:26 | 2019-05-13 18:26 | Container | Sales Management | Pricing |  |  |  | [5/13~5/17] Asia - PRI - Apply "filter" in spreadsheet in UI | 2019-05-16 09:32 | 2019-07-31 09:32 | 2019-06-12 15:49 | 2019-08-19 10:27 | 2019-08-20 14:14 |  | 2019-08-27 11:14 | 2019-08-27 10:08 | 2019-08-27 09:26 | 2019-09-26 13:00 | CR0010428 | Sales ManagementPricing | OPUS-PRI | 2019-W35 | 2019-08 | 104 | 0 | 103.0707 | 5 | 1 | 2 | 0 | 183431 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 6 | 0 | 0 | 2019-05 | 0 | 0
1141 | CR0010428 | CTASK0013995 | Closed | OPUS-PRI | Man Hoang | 32 | 32 |  |  | Container | Sales Management | Pricing |  |  |  | [05/20 ~ 05/24] Asia - PRI - Apply "filter" in spreadsheet in UI | 2019-05-16 09:32 | 2019-07-31 09:32 | 2019-06-12 15:49 | 2019-08-19 10:27 | 2019-08-20 14:14 |  | 2019-08-27 11:14 | 2019-08-27 10:08 | 2019-08-27 09:26 | 2019-09-26 13:00 | CR0010428 | Sales ManagementPricing | OPUS-PRI | 2019-W35 | 2019-08 | 104 | 0 | 103.0707 | 5 | 1 | 2 | 0 | 183431 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 6 | 0 | 0 | 2019-05 | 0 | 0
1142 | CR0010428 | CTASK0013994 | Closed | OPUS-PRI | Nhien Nguyen | 32 | 32 |  |  | Container | Sales Management | Pricing |  |  |  | [05/20 ~ 05/24] Asia - PRI - Apply "filter" in spreadsheet in UI | 2019-05-16 09:32 | 2019-07-31 09:32 | 2019-06-12 15:49 | 2019-08-19 10:27 | 2019-08-20 14:14 |  | 2019-08-27 11:14 | 2019-08-27 10:08 | 2019-08-27 09:26 | 2019-09-26 13:00 | CR0010428 | Sales ManagementPricing | OPUS-PRI | 2019-W35 | 2019-08 | 104 | 0 | 103.0707 | 5 | 1 | 2 | 0 | 183364 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 6 | 0 | 0 | 2019-05 | 0 | 0
1143 | CR0011713 | CTASK0016767 | Closed | OPUS-BKG-EBKG | Vinh Tran | 36 | 33 | 2019-11-29 18:31 | 2019-11-11 18:31 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | Add new fields/mapping logic for INDIA to M&D Tab under OPUS' e-Booking & S/I Process screen | 2019-11-08 12:18 | 2019-12-10 | 2019-12-02 18:13 | 2020-03-02 12:33 | 2020-03-23 10:07 | 2019-12-02 18:17 | 2020-07-21 10:00 | 2020-07-21 11:00 | 2020-07-01 16:28 | 2020-08-21 13:00 | CR0011713 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W30 | 2020-07 | 38 | 33 | 255.9041 | 2 | 2 | 1 | 0.01 | 193525 | 0.4 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 27 | 0 | 0.45455 | 2019-11 | 0 | 0
1144 | CR0011713 | CTASK0016750 | Closed | OPUS-BKG-M | Vinh Tran | 2 | 2 | 2019-10-17 02:00 | 2019-10-16 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Estimate] Add new fields/mapping logic for INDIA to M&D Tab under OPUS' e-Booking & S/I Process screen | 2019-11-08 12:18 | 2019-12-10 | 2019-12-02 18:13 | 2020-03-02 12:33 | 2020-03-23 10:07 | 2019-12-02 18:17 | 2020-07-21 10:00 | 2020-07-21 11:00 | 2020-07-01 16:28 | 2020-08-21 13:00 | CR0011713 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W30 | 2020-07 | 38 | 33 | 255.9041 | 2 | 2 | 1 | 0.01 | 193525 | 0.4 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 27 | 0 | 0.45455 | 2019-11 | 0 | 0
1145 | CR0010757 | CTASK0016895 | Closed | OPUS-TES | Manh Nguyen | 159 | 185 | 2020-02-29 13:36 | 2019-11-01 13:36 | Container | Service Management | Trans S/O |  |  |  | [Actual] GHQ - TRS/TES/PSO Agreement Approval Process | 2019-10-31 10:38 | 2019-12-31 18:00 | 2019-12-24 13:48 | 2020-02-11 10:06 | 2020-02-12 15:25 |  | 2020-02-25 11:00 | 2020-02-25 10:00 | 2020-02-12 15:44 | 2020-03-26 13:00 | CR0010757 | Service ManagementTrans S/O | OPUS-TRS | 2020-W9 | 2020-02 | 523 | 541 | 117.0154 | 5 | 3 | 5 | 0.19 | 153138 | 1.1 | 0 | 0 | 1 | 4 | 2 | 2 | 1 | 13 | 0 | 0.25 | 2019-10 | 1 | 1
1146 | CR0010757 | CTASK0017524 | Closed | OPUS-PSO | Hieu Vu | 100 | 100 | 2019-12-31 17:01 | 2019-11-15 17:01 | Container | Service Management | Trans S/O |  |  |  | GHQ - TRS/TES/PSO Agreement Approval Process (PSO) | 2019-10-31 10:38 | 2019-12-31 18:00 | 2019-12-24 13:48 | 2020-02-11 10:06 | 2020-02-12 15:25 |  | 2020-02-25 11:00 | 2020-02-25 10:00 | 2020-02-12 15:44 | 2020-03-26 13:00 | CR0010757 | Service ManagementTrans S/O | OPUS-TRS | 2020-W9 | 2020-02 | 523 | 541 | 117.0154 | 5 | 3 | 5 | 0.19 | 183375 | 1.1 | 0 | 0 | 1 | 4 | 2 | 2 | 1 | 13 | 0 | 0.125 | 2019-10 | 1 | 1
1147 | CR0010757 | CTASK0017103 | Closed | OPUS-TRS | Hieu Tran | 85 | 85 | 2019-12-27 18:00 | 2019-11-11 09:00 | Container | Service Management | Trans S/O |  |  |  | [Actual] GHQ - TRS/TES/PSO Agreement Approval Process (TRS) | 2019-10-31 10:38 | 2019-12-31 18:00 | 2019-12-24 13:48 | 2020-02-11 10:06 | 2020-02-12 15:25 |  | 2020-02-25 11:00 | 2020-02-25 10:00 | 2020-02-12 15:44 | 2020-03-26 13:00 | CR0010757 | Service ManagementTrans S/O | OPUS-TRS | 2020-W9 | 2020-02 | 523 | 541 | 117.0154 | 5 | 3 | 5 | 0.19 | 183400 | 1.1 | 0 | 0 | 1 | 4 | 2 | 2 | 1 | 13 | 0 | 0 | 2019-10 | 1 | 1
1148 | CR0010757 | CTASK0017102 | Closed | OPUS-TRS | Giang Nguyen Hoang | 85 | 85 | 2019-12-27 18:00 | 2019-11-11 09:00 | Container | Service Management | Trans S/O |  |  |  | [Actual] GHQ - TRS/TES/PSO Agreement Approval Process (TRS) | 2019-10-31 10:38 | 2019-12-31 18:00 | 2019-12-24 13:48 | 2020-02-11 10:06 | 2020-02-12 15:25 |  | 2020-02-25 11:00 | 2020-02-25 10:00 | 2020-02-12 15:44 | 2020-03-26 13:00 | CR0010757 | Service ManagementTrans S/O | OPUS-TRS | 2020-W9 | 2020-02 | 523 | 541 | 117.0154 | 5 | 3 | 5 | 0.19 | 183440 | 0.6 | 0 | 0 | 1 | 4 | 2 | 2 | 1 | 13 | 0 | 0 | 2019-10 | 1 | 1
1149 | CR0010757 | CTASK0017101 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 94 | 86 | 2019-12-27 18:00 | 2019-11-11 09:00 | Container | Service Management | Trans S/O |  |  |  | [Actual] GHQ - TRS/TES/PSO Agreement Approval Process (TRS) | 2019-10-31 10:38 | 2019-12-31 18:00 | 2019-12-24 13:48 | 2020-02-11 10:06 | 2020-02-12 15:25 |  | 2020-02-25 11:00 | 2020-02-25 10:00 | 2020-02-12 15:44 | 2020-03-26 13:00 | CR0010757 | Service ManagementTrans S/O | OPUS-TRS | 2020-W9 | 2020-02 | 523 | 541 | 117.0154 | 5 | 3 | 5 | 0.19 | 183432 | 0.6 | 0 | 0 | 1 | 4 | 2 | 2 | 1 | 13 | 0 | 0 | 2019-10 | 1 | 1
1150 | CR0013367 | CTASK0024407 | Closed | OPUS-BKG-EBKG | Vinh Tran | 20 | 20 | 2021-01-16 02:00 | 2021-01-12 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] [CLT Internal] to prevent unnecessary minor errors on e-booking | 2021-01-14 11:34 | 2021-02-04 | 2021-02-03 16:11 | 2021-02-18 09:09 | 2021-02-18 10:30 |  | 2021-03-16 11:00 | 2021-03-16 11:00 | 2021-03-03 18:16 | 2021-04-15 14:00 | CR0013367 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 52 | 52 | 60.9761 | 5 | 1 | 1 | 0.04 | 193525 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.41667 | 0.47368 | 2021-01 | 0 | 0
1151 | CR0013367 | CTASK0024406 | Closed | OPUS-BKG-EBKG | Vinh Tran | 8 | 8 | 2021-01-13 02:00 | 2021-01-11 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] [CLT Internal] to prevent unnecessary minor errors on e-booking | 2021-01-14 11:34 | 2021-02-04 | 2021-02-03 16:11 | 2021-02-18 09:09 | 2021-02-18 10:30 |  | 2021-03-16 11:00 | 2021-03-16 11:00 | 2021-03-03 18:16 | 2021-04-15 14:00 | CR0013367 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 52 | 52 | 60.9761 | 5 | 1 | 1 | 0.04 | 193525 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.41667 | 0.47368 | 2021-01 | 0 | 0
1152 | CR0013367 | CTASK0024405 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-01-01 02:00 | 2020-12-31 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] [CLT Internal] to prevent unnecessary minor errors on e-booking | 2021-01-14 11:34 | 2021-02-04 | 2021-02-03 16:11 | 2021-02-18 09:09 | 2021-02-18 10:30 |  | 2021-03-16 11:00 | 2021-03-16 11:00 | 2021-03-03 18:16 | 2021-04-15 14:00 | CR0013367 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 52 | 52 | 60.9761 | 5 | 1 | 1 | 0.04 | 193525 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.41667 | 0.47368 | 2021-01 | 0 | 0
1153 | CR0013367 | CTASK0024408 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-03-11 02:00 | 2021-03-08 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] [CLT Internal] to prevent unnecessary minor errors on e-booking | 2021-01-14 11:34 | 2021-02-04 | 2021-02-03 16:11 | 2021-02-18 09:09 | 2021-02-18 10:30 |  | 2021-03-16 11:00 | 2021-03-16 11:00 | 2021-03-03 18:16 | 2021-04-15 14:00 | CR0013367 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 52 | 52 | 60.9761 | 5 | 1 | 1 | 0.04 | 193525 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.41667 | 0.47368 | 2021-01 | 0 | 0
1154 | CR0013367 | CTASK0023902 | Closed | OPUS-BKG-EBKG | Vinh Tran | 16 | 16 | 2020-12-09 02:00 | 2020-11-30 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Analysis] [CLT Internal] to prevent unnecessary minor errors on e-booking | 2021-01-14 11:34 | 2021-02-04 | 2021-02-03 16:11 | 2021-02-18 09:09 | 2021-02-18 10:30 |  | 2021-03-16 11:00 | 2021-03-16 11:00 | 2021-03-03 18:16 | 2021-04-15 14:00 | CR0013367 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 52 | 52 | 60.9761 | 5 | 1 | 1 | 0.04 | 193525 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.41667 | 0.47368 | 2021-01 | 0 | 0
1155 | CR0013299 | CTASK0024010 | Closed | OPUS-BKG-IB | Thuc Tran | 109 | 109 | 2021-01-29 19:30 | 2020-12-07 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | General Full Container Release | [Development+Testing+Deployment][LAENHANCEMENT] - CARGO RELEASE & EDI COREOR ENHANCEMENT // MX | 2020-12-09 16:10 | 2021-01-22 23:07 | 2021-01-22 15:37 | 2021-02-26 11:00 | 2021-03-02 11:25 |  | 2021-03-09 11:23 | 2020-11-11 12:37 | 2021-03-03 18:18 | 2021-04-08 14:00 | CR0013299 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseGeneral Full Container Release | OPUS-BKG-IB | 2021-W10 | 2021-03 | 125 | 125 | 89.8006 | 2 | 1 | 1 | 0.06 | 173280 | 2 | 2 | 0 | 1 | 2 | 1 | 2 | 7 | 46 | 0.375 | 0.18519 | 2020-12 | 1 | 1
1156 | CR0013299 | CTASK0025579 | Closed | OPUS-BKG-IB | Thuc Tran | 16 | 16 | 2021-03-08 19:30 | 2021-03-01 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | General Full Container Release | [Reflection+Testing+Deployment][LAENHANCEMENT] - CARGO RELEASE & EDI COREOR ENHANCEMENT // MX | 2020-12-09 16:10 | 2021-01-22 23:07 | 2021-01-22 15:37 | 2021-02-26 11:00 | 2021-03-02 11:25 |  | 2021-03-09 11:23 | 2020-11-11 12:37 | 2021-03-03 18:18 | 2021-04-08 14:00 | CR0013299 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseGeneral Full Container Release | OPUS-BKG-IB | 2021-W10 | 2021-03 | 125 | 125 | 89.8006 | 2 | 1 | 1 | 0.06 | 173280 | 2 | 2 | 0 | 1 | 2 | 1 | 2 | 7 | 46 | 0.375 | 0.18519 | 2020-12 | 1 | 1
1157 | CR0012595 | CTASK0020189 | Closed | OPUS-BKG-M | Loc Tran | 29 | 29 | 2020-06-03 02:00 | 2020-05-21 16:33 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Development] NA *BKG* Update BRN when sending notice of Cancellation | 2020-05-21 17:48 | 2020-06-25 | 2020-06-22 08:50 | 2020-07-15 17:09 | 2020-07-16 10:57 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-17 06:49 | 2020-08-27 13:00 | CR0012595 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W31 | 2020-07 | 62 | 59 | 67.6749 | 6 | 1 | 1 | 0.04 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-05 | 0 | 0
1158 | CR0012595 | CTASK0020735 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-06-19 10:31 | 2020-06-15 10:31 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Testing] NA *BKG* Update BRN when sending notice of Cancellation | 2020-05-21 17:48 | 2020-06-25 | 2020-06-22 08:50 | 2020-07-15 17:09 | 2020-07-16 10:57 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-17 06:49 | 2020-08-27 13:00 | CR0012595 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W31 | 2020-07 | 62 | 59 | 67.6749 | 6 | 1 | 1 | 0.04 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-05 | 0 | 0
1159 | CR0012595 | CTASK0020194 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2020-07-28 18:46 | 2020-07-21 18:46 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Deployment] NA *BKG* Update BRN when sending notice of Cancellation | 2020-05-21 17:48 | 2020-06-25 | 2020-06-22 08:50 | 2020-07-15 17:09 | 2020-07-16 10:57 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-17 06:49 | 2020-08-27 13:00 | CR0012595 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W31 | 2020-07 | 62 | 59 | 67.6749 | 6 | 1 | 1 | 0.04 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-05 | 0 | 0
1160 | CR0012595 | CTASK0020124 | Closed | OPUS-BKG-M | Loc Tran | 12 | 12 | 2020-05-20 02:00 | 2020-05-14 18:45 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Design] NA *BKG* Update BRN when sending notice of Cancellation | 2020-05-21 17:48 | 2020-06-25 | 2020-06-22 08:50 | 2020-07-15 17:09 | 2020-07-16 10:57 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-17 06:49 | 2020-08-27 13:00 | CR0012595 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W31 | 2020-07 | 62 | 59 | 67.6749 | 6 | 1 | 1 | 0.04 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-05 | 0 | 0
1161 | CR0012595 | CTASK0020192 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2020-06-05 11:21 | 2020-05-27 11:20 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Testing] NA *BKG* Update BRN when sending notice of Cancellation | 2020-05-21 17:48 | 2020-06-25 | 2020-06-22 08:50 | 2020-07-15 17:09 | 2020-07-16 10:57 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-17 06:49 | 2020-08-27 13:00 | CR0012595 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W31 | 2020-07 | 62 | 59 | 67.6749 | 6 | 1 | 1 | 0.04 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-05 | 0 | 0
1162 | CR0012595 | CTASK0020929 | Closed | OPUS-BKG-M | Loc Tran | 3 | 3 | 2020-07-01 01:59 | 2020-06-24 17:59 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Development] NA *BKG* Update BRN when sending notice of Cancellation | 2020-05-21 17:48 | 2020-06-25 | 2020-06-22 08:50 | 2020-07-15 17:09 | 2020-07-16 10:57 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-17 06:49 | 2020-08-27 13:00 | CR0012595 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2020-W31 | 2020-07 | 62 | 59 | 67.6749 | 6 | 1 | 1 | 0.04 | 193503 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 27 | 0 | 0.36364 | 2020-05 | 0 | 0
1163 | CR0013750 | CTASK0026270 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-06-30 16:54 | 2021-06-01 16:54 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Inquiry | [Deployment] [CLT Internal] Literal SQL Tuning on Correction Inquiry | 2021-05-07 08:55 | 2021-06-20 16:51 | 2021-05-07 09:30 | 2021-05-12 17:22 | 2021-06-03 17:46 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:34 | 2021-07-28 14:00 | CR0013750 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Inquiry | OPUS-BKG-M | 2021-W25 | 2021-06 | 16 | 18 | 51.0449 | 3 | 1 | 1 | 0.01 | 153106 | 2.6 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.22951 | 0.13043 | 2021-05 | 0 | 0
1164 | CR0013750 | CTASK0026268 | Closed | OPUS-BKG-M | Kieu Le | 4 | 6 | 2021-05-29 01:55 | 2021-05-03 02:55 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Inquiry | [Test] [CLT Internal] Literal SQL Tuning on Correction Inquiry | 2021-05-07 08:55 | 2021-06-20 16:51 | 2021-05-07 09:30 | 2021-05-12 17:22 | 2021-06-03 17:46 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:34 | 2021-07-28 14:00 | CR0013750 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Inquiry | OPUS-BKG-M | 2021-W25 | 2021-06 | 16 | 18 | 51.0449 | 3 | 1 | 1 | 0.01 | 153106 | 2.6 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.22951 | 0.13043 | 2021-05 | 0 | 0
1165 | CR0013750 | CTASK0026267 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-04-24 01:55 | 2021-04-19 02:54 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Inquiry | [Development] [CLT Internal] Literal SQL Tuning on Correction Inquiry | 2021-05-07 08:55 | 2021-06-20 16:51 | 2021-05-07 09:30 | 2021-05-12 17:22 | 2021-06-03 17:46 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:34 | 2021-07-28 14:00 | CR0013750 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Inquiry | OPUS-BKG-M | 2021-W25 | 2021-06 | 16 | 18 | 51.0449 | 3 | 1 | 1 | 0.01 | 153106 | 2.6 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.22951 | 0.13043 | 2021-05 | 0 | 0
1166 | CR0013075 | CTASK0022899 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 8 | 2020-11-27 01:42 | 2020-11-25 01:42 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Testing] Auto-request must be done it when a booking is changed the calling sequence of a port. | 2020-11-06 12:33 | 2020-12-03 | 2020-12-01 18:15 | 2021-01-12 13:56 | 2021-01-12 14:54 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-13 16:10 | 2021-02-25 14:00 | CR0013075 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W4 | 2021-01 | 63 | 66 | 80.894 | 4 | 1 | 1 | 0.03 | 193488 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.53659 | 0.28125 | 2020-11 | 0 | 0
1167 | CR0013075 | CTASK0022900 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 7 | 6 | 2021-01-21 10:00 | 2021-01-19 01:04 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Deployment] Auto-request must be done it when a booking is changed the calling sequence of a port. | 2020-11-06 12:33 | 2020-12-03 | 2020-12-01 18:15 | 2021-01-12 13:56 | 2021-01-12 14:54 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-13 16:10 | 2021-02-25 14:00 | CR0013075 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W4 | 2021-01 | 63 | 66 | 80.894 | 4 | 1 | 1 | 0.03 | 193488 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.53659 | 0.28125 | 2020-11 | 0 | 0
1168 | CR0013075 | CTASK0022805 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 11 | 12 |  |  | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Design] Auto-request must be done it when a booking is changed the calling sequence of a port. | 2020-11-06 12:33 | 2020-12-03 | 2020-12-01 18:15 | 2021-01-12 13:56 | 2021-01-12 14:54 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-13 16:10 | 2021-02-25 14:00 | CR0013075 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W4 | 2021-01 | 63 | 66 | 80.894 | 4 | 1 | 1 | 0.03 | 193488 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.53659 | 0.28125 | 2020-11 | 0 | 0
1169 | CR0013075 | CTASK0022898 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 39 | 40 | 2020-11-13 18:31 | 2020-11-02 10:02 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Development] Auto-request must be done it when a booking is changed the calling sequence of a port. | 2020-11-06 12:33 | 2020-12-03 | 2020-12-01 18:15 | 2021-01-12 13:56 | 2021-01-12 14:54 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-13 16:10 | 2021-02-25 14:00 | CR0013075 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W4 | 2021-01 | 63 | 66 | 80.894 | 4 | 1 | 1 | 0.03 | 193488 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.53659 | 0.28125 | 2020-11 | 0 | 0
1170 | CR0012873 | CTASK0021720 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 14 | 14 | 2020-08-28 01:59 | 2020-08-20 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation |  | [Development + Testing] NA *DOC* Remove constraint validation for BL screens | 2020-08-20 09:49 | 2020-09-02 10:00 | 2020-09-01 18:54 | 2020-10-05 20:14 | 2020-10-06 08:27 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-08 13:24 | 2020-11-19 14:00 | CR0012873 | Service ManagementBooking/DocumentationOutbound DocB/L Creation | OPUS-BKG-OB | 2020-W43 | 2020-10 | 43 | 40 | 61.008 | 7 | 2 | 3 | 0.03 | 193470 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.17391 | 2020-08 | 0 | 0
1171 | CR0012873 | CTASK0022976 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 2 | 2 | 2020-10-17 02:00 | 2020-10-12 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation |  | [Deployment] NA *DOC* Remove constraint validation for BL screens | 2020-08-20 09:49 | 2020-09-02 10:00 | 2020-09-01 18:54 | 2020-10-05 20:14 | 2020-10-06 08:27 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-08 13:24 | 2020-11-19 14:00 | CR0012873 | Service ManagementBooking/DocumentationOutbound DocB/L Creation | OPUS-BKG-OB | 2020-W43 | 2020-10 | 43 | 40 | 61.008 | 7 | 2 | 3 | 0.03 | 193470 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.17391 | 2020-08 | 0 | 0
1172 | CR0012873 | CTASK0021724 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-10-31 17:57 | 2020-10-12 17:57 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation |  | [Deployment]NA *DOC* Remove constraint validation for BL screens | 2020-08-20 09:49 | 2020-09-02 10:00 | 2020-09-01 18:54 | 2020-10-05 20:14 | 2020-10-06 08:27 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-08 13:24 | 2020-11-19 14:00 | CR0012873 | Service ManagementBooking/DocumentationOutbound DocB/L Creation | OPUS-BKG-OB | 2020-W43 | 2020-10 | 43 | 40 | 61.008 | 7 | 2 | 3 | 0.03 | 193567 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.53333 | 2020-08 | 0 | 0
1173 | CR0012873 | CTASK0021711 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2020-08-05 19:30 | 2020-08-05 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation |  | [Analysis] NA *DOC* Remove constraint validation for BL screens | 2020-08-20 09:49 | 2020-09-02 10:00 | 2020-09-01 18:54 | 2020-10-05 20:14 | 2020-10-06 08:27 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-08 13:24 | 2020-11-19 14:00 | CR0012873 | Service ManagementBooking/DocumentationOutbound DocB/L Creation | OPUS-BKG-OB | 2020-W43 | 2020-10 | 43 | 40 | 61.008 | 7 | 2 | 3 | 0.03 | 193470 | 1.4 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.17391 | 2020-08 | 0 | 0
1174 | CR0012873 | CTASK0021721 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2020-08-07 11:12 | 2020-08-06 11:12 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation |  | [Design]NA *DOC* Remove constraint validation for BL screens | 2020-08-20 09:49 | 2020-09-02 10:00 | 2020-09-01 18:54 | 2020-10-05 20:14 | 2020-10-06 08:27 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-08 13:24 | 2020-11-19 14:00 | CR0012873 | Service ManagementBooking/DocumentationOutbound DocB/L Creation | OPUS-BKG-OB | 2020-W43 | 2020-10 | 43 | 40 | 61.008 | 7 | 2 | 3 | 0.03 | 193488 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28125 | 2020-08 | 0 | 0
1175 | CR0012873 | CTASK0021723 | Closed | OPUS-BKG-M | Thien Lai | 7 | 4 | 2020-09-10 17:55 | 2020-08-20 17:55 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation |  | [Testing]NA *DOC* Remove constraint validation for BL screens | 2020-08-20 09:49 | 2020-09-02 10:00 | 2020-09-01 18:54 | 2020-10-05 20:14 | 2020-10-06 08:27 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-08 13:24 | 2020-11-19 14:00 | CR0012873 | Service ManagementBooking/DocumentationOutbound DocB/L Creation | OPUS-BKG-OB | 2020-W43 | 2020-10 | 43 | 40 | 61.008 | 7 | 2 | 3 | 0.03 | 193567 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.53333 | 2020-08 | 0 | 0
1176 | CR0012873 | CTASK0021722 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-08-28 17:56 | 2020-08-20 17:56 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation |  | [Development]NA *DOC* Remove constraint validation for BL screens | 2020-08-20 09:49 | 2020-09-02 10:00 | 2020-09-01 18:54 | 2020-10-05 20:14 | 2020-10-06 08:27 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-08 13:24 | 2020-11-19 14:00 | CR0012873 | Service ManagementBooking/DocumentationOutbound DocB/L Creation | OPUS-BKG-OB | 2020-W43 | 2020-10 | 43 | 40 | 61.008 | 7 | 2 | 3 | 0.03 | 193567 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.53333 | 2020-08 | 0 | 0
1177 | CR0012872 | CTASK0023064 | Closed | OPUS-PRI | Nhien Nguyen | 70 | 70 | 2020-11-30 17:20 | 2020-11-01 17:20 | Container | Sales Management | Pricing | Service Contract | S/C Creation | S/C Proposal & Amendment Creation | NA *PRI* Update Contract Type options and add Customer Type to Affiliates for regulatory compliance | 2020-10-27 11:05 | 2020-11-30 21:05 | 2020-11-30 14:38 | 2021-02-23 12:52 | 2021-02-23 13:50 |  | 2021-03-02 13:50 | 2021-03-02 09:24 | 2021-02-23 13:59 | 2021-04-03 14:00 | CR0012872 | Sales ManagementPricingService ContractS/C CreationS/C Proposal & Amendment Creation | OPUS-PRI | 2021-W9 | 2021-03 | 70 | 70 | 126.114 | 1 | 1 | 1 | 0.02 | 183364 | 2.1 | 0 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0 | 1.2 | 2020-10 | 0 | 0
1178 | CR0013404 | CTASK0024707 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 10 | 10 |  |  | S/W | WEB |  |  |  |  | Actions for dynamic security vulnerability check results | 2020-12-17 11:12 | 2021-01-31 11:09 | 2020-12-17 14:19 |  | 2021-03-26 11:31 |  | 2021-03-21 11:31 | 2021-03-21 11:33 | 2021-03-26 11:32 | 2021-03-26 11:34 | CR0013404 | WEB | OPUS-BKG-OB | 2021-W11 | 2021-03 | 17 | 0 | 94.013 | 2 | 2 | 2 | 0 | 193470 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0 | 0.17391 | 2020-12 | 0 | 0
1179 | CR0013404 | CTASK0024751 | Closed | OPUS-BKG-EBKG | Vinh Tran | 7 | 7 | 2021-01-19 02:00 | 2021-01-14 02:00 | S/W | WEB |  |  |  |  | Actions for dynamic security vulnerability check results | 2020-12-17 11:12 | 2021-01-31 11:09 | 2020-12-17 14:19 |  | 2021-03-26 11:31 |  | 2021-03-21 11:31 | 2021-03-21 11:33 | 2021-03-26 11:32 | 2021-03-26 11:34 | CR0013404 | WEB | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 17 | 0 | 94.013 | 2 | 2 | 2 | 0 | 193525 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0 | 0.47368 | 2020-12 | 0 | 0
1180 | CR0012096 | CTASK0026339 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 8 | 8 | 2021-04-26 18:19 | 2021-04-05 18:19 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Deployment] EUA - New UI to manage MT Return CY for EQC steering | 2020-12-01 10:32 | 2020-12-31 23:32 | 2020-12-30 18:27 | 2021-04-02 10:39 | 2021-04-02 13:30 |  | 2021-04-27 13:22 | 2021-04-27 13:02 | 2021-04-05 08:47 | 2021-05-27 14:00 | CR0012096 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W17 | 2021-04 | 166 | 163 | 147.1181 | 5 | 2 | 1 | 0.05 | 193512 | 1.4 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 27 | 0.2963 | 0.3125 | 2020-12 | 0 | 0
1181 | CR0012096 | CTASK0025474 | Closed | OPUS-BKG-MFT-M | Nhut Nguyen Minh | 49 | 45 | 2021-03-15 10:58 | 2021-02-22 10:58 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EUA - New UI to manage MT Return CY for EQC steering | 2020-12-01 10:32 | 2020-12-31 23:32 | 2020-12-30 18:27 | 2021-04-02 10:39 | 2021-04-02 13:30 |  | 2021-04-27 13:22 | 2021-04-27 13:02 | 2021-04-05 08:47 | 2021-05-27 14:00 | CR0012096 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W17 | 2021-04 | 166 | 163 | 147.1181 | 5 | 2 | 1 | 0.05 | 193512 | 1.4 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 27 | 0.2963 | 0.3125 | 2020-12 | 0 | 0
1182 | CR0012096 | CTASK0022730 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 3 | 3 | 2020-09-26 18:49 | 2020-09-22 18:49 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Analysis] EUA - New UI to manage MT Return CY for EQC steering | 2020-12-01 10:32 | 2020-12-31 23:32 | 2020-12-30 18:27 | 2021-04-02 10:39 | 2021-04-02 13:30 |  | 2021-04-27 13:22 | 2021-04-27 13:02 | 2021-04-05 08:47 | 2021-05-27 14:00 | CR0012096 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W17 | 2021-04 | 166 | 163 | 147.1181 | 5 | 2 | 1 | 0.05 | 193512 | 1.4 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 27 | 0.2963 | 0.3125 | 2020-12 | 0 | 0
1183 | CR0012096 | CTASK0023195 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 93 | 94 | 2020-12-15 12:21 | 2020-11-25 12:21 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EUA - New UI to manage MT Return CY for EQC steering | 2020-12-01 10:32 | 2020-12-31 23:32 | 2020-12-30 18:27 | 2021-04-02 10:39 | 2021-04-02 13:30 |  | 2021-04-27 13:22 | 2021-04-27 13:02 | 2021-04-05 08:47 | 2021-05-27 14:00 | CR0012096 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W17 | 2021-04 | 166 | 163 | 147.1181 | 5 | 2 | 1 | 0.05 | 193512 | 1.4 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 27 | 0.2963 | 0.3125 | 2020-12 | 0 | 0
1184 | CR0012096 | CTASK0022942 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 13 | 13 | 2020-10-20 18:27 | 2020-10-13 09:27 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EUA - New UI to manage MT Return CY for EQC steering | 2020-12-01 10:32 | 2020-12-31 23:32 | 2020-12-30 18:27 | 2021-04-02 10:39 | 2021-04-02 13:30 |  | 2021-04-27 13:22 | 2021-04-27 13:02 | 2021-04-05 08:47 | 2021-05-27 14:00 | CR0012096 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W17 | 2021-04 | 166 | 163 | 147.1181 | 5 | 2 | 1 | 0.05 | 193512 | 1.4 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 27 | 0.2963 | 0.3125 | 2020-12 | 0 | 0
1185 | CR0013388 | CTASK0026424 | Closed | OPUS-SUP | Tran Le | 12 | 18 |  |  | Container | Biz Common | EDI Setup | Setup | Cargo Tracking Info. for Customer |  | [CLT Internal] OPUS service enhancement for UI Cargo Tracking Info. for Customer - Manage effort | 2021-04-16 14:56 | 2021-04-27 00:28 | 2021-04-26 19:54 | 2021-04-29 19:54 | 2021-05-06 16:38 |  | 2021-05-18 10:00 | 2021-05-18 11:21 | 2021-05-07 09:06 | 2021-05-31 09:16 | CR0013388 | Biz CommonEDI SetupSetupCargo Tracking Info. for Customer | OPUS-SUP | 2021-W20 | 2021-05 | 12 | 18 | 31.7947 | 1 | 1 | 1 | 0.02 | 193501 | 1.5 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.052632 | 0.076923 | 2021-04 | 0 | 0
1186 | CR0013413 | CTASK0024306 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-02-05 17:17 | 2021-02-01 17:17 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] OPUS CONTAINER - S/C NUMBER COPY | 2021-03-10 16:50 | 2021-03-12 22:50 | 2021-03-11 15:26 | 2021-03-18 15:34 | 2021-03-18 15:55 |  | 2021-03-30 15:55 | 2021-03-30 08:48 | 2021-03-31 16:59 | 2021-05-01 14:00 | CR0013413 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W13 | 2021-03 | 24 | 24 | 19.9612 | 4 | 1 | 1 | 0.05 | 193488 | 1.7 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
1187 | CR0013413 | CTASK0024310 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-03-25 02:00 | 2021-03-19 11:11 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal] OPUS CONTAINER - S/C NUMBER COPY | 2021-03-10 16:50 | 2021-03-12 22:50 | 2021-03-11 15:26 | 2021-03-18 15:34 | 2021-03-18 15:55 |  | 2021-03-30 15:55 | 2021-03-30 08:48 | 2021-03-31 16:59 | 2021-05-01 14:00 | CR0013413 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W13 | 2021-03 | 24 | 24 | 19.9612 | 4 | 1 | 1 | 0.05 | 193488 | 1.7 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
1188 | CR0013413 | CTASK0024309 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-01-11 20:04 | 2021-01-08 10:04 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal] OPUS CONTAINER - S/C NUMBER COPY | 2021-03-10 16:50 | 2021-03-12 22:50 | 2021-03-11 15:26 | 2021-03-18 15:34 | 2021-03-18 15:55 |  | 2021-03-30 15:55 | 2021-03-30 08:48 | 2021-03-31 16:59 | 2021-05-01 14:00 | CR0013413 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W13 | 2021-03 | 24 | 24 | 19.9612 | 4 | 1 | 1 | 0.05 | 193488 | 1.7 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
1189 | CR0013413 | CTASK0024308 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 12 | 12 | 2021-01-11 12:35 | 2021-01-05 12:35 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal] OPUS CONTAINER - S/C NUMBER COPY | 2021-03-10 16:50 | 2021-03-12 22:50 | 2021-03-11 15:26 | 2021-03-18 15:34 | 2021-03-18 15:55 |  | 2021-03-30 15:55 | 2021-03-30 08:48 | 2021-03-31 16:59 | 2021-05-01 14:00 | CR0013413 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W13 | 2021-03 | 24 | 24 | 19.9612 | 4 | 1 | 1 | 0.05 | 193488 | 1.7 | 1 | 0 | 0 | 1 | 1 | 1 | 12 | 46 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
1190 | CR0013026 | CTASK0023110 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 10 | 10 | 2020-11-02 19:30 | 2020-10-23 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | [Inspection + Deployment] [CLT internal] Displaying old EDI transmissions for a different old VVD and advising staff that it has already been sent though it hasn't. | 2020-09-23 10:21 | 2020-09-26 | 2020-09-24 15:43 | 2020-10-15 14:50 | 2020-10-29 17:15 |  | 2020-11-03 10:00 | 2020-11-03 09:30 | 2020-10-29 17:40 | 2020-12-03 14:00 | CR0013026 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W45 | 2020-11 | 28 | 28 | 40.9854 | 3 | 1 | 1 | 0.03 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0.18519 | 2020-09 | 0 | 0
1191 | CR0013026 | CTASK0022297 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 2 | 2 | 2020-09-08 19:30 | 2020-09-04 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | [Estimation] Displaying old EDI transmissions for a different old VVD and advising staff that it has already been sent though it hasn't. | 2020-09-23 10:21 | 2020-09-26 | 2020-09-24 15:43 | 2020-10-15 14:50 | 2020-10-29 17:15 |  | 2020-11-03 10:00 | 2020-11-03 09:30 | 2020-10-29 17:40 | 2020-12-03 14:00 | CR0013026 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W45 | 2020-11 | 28 | 28 | 40.9854 | 3 | 1 | 1 | 0.03 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0.18519 | 2020-09 | 0 | 0
1192 | CR0013026 | CTASK0022331 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 16 | 16 | 2020-09-15 19:30 | 2020-09-09 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | [Development + Inspection + Deployment] [CLT internal] Displaying old EDI transmissions for a different old VVD and advising staff that it has already been sent though it hasn't. | 2020-09-23 10:21 | 2020-09-26 | 2020-09-24 15:43 | 2020-10-15 14:50 | 2020-10-29 17:15 |  | 2020-11-03 10:00 | 2020-11-03 09:30 | 2020-10-29 17:40 | 2020-12-03 14:00 | CR0013026 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W45 | 2020-11 | 28 | 28 | 40.9854 | 3 | 1 | 1 | 0.03 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 0.18519 | 2020-09 | 0 | 0
1193 | CR0011354 | CTASK0015175 | Closed | OPUS-SCO | Lien Le | 249 | 249 |  |  | Container | Statement Management | Statement Account Receivable | Outstanding |  |  | EUA Enhancement to OPUS to Replace OnGuard EUA Local System | 2019-08-01 15:47 | 2019-11-10 16:47 | 2019-11-08 15:51 | 2019-11-11 10:21 | 2019-11-18 22:16 |  | 2019-11-18 22:16 | 2019-11-14 16:17 | 2019-11-26 16:16 | 2019-12-27 14:00 | CR0011354 | Statement ManagementStatement Account ReceivableOutstanding | OPUS-SAR | 2019-W47 | 2019-11 | 756 | 0 | 109.2699 | 3 | 1 | 3 | 0 | 193441 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 7 | 0 | 0 | 2019-08 | 0 | 0
1194 | CR0011354 | CTASK0015174 | Closed | OPUS-SCO | Chuong Ta | 248 | 248 |  |  | Container | Statement Management | Statement Account Receivable | Outstanding |  |  | EUA Enhancement to OPUS to Replace OnGuard EUA Local System | 2019-08-01 15:47 | 2019-11-10 16:47 | 2019-11-08 15:51 | 2019-11-11 10:21 | 2019-11-18 22:16 |  | 2019-11-18 22:16 | 2019-11-14 16:17 | 2019-11-26 16:16 | 2019-12-27 14:00 | CR0011354 | Statement ManagementStatement Account ReceivableOutstanding | OPUS-SAR | 2019-W47 | 2019-11 | 756 | 0 | 109.2699 | 3 | 1 | 3 | 0 | 183379 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 7 | 0 | 0 | 2019-08 | 0 | 0
1195 | CR0011354 | CTASK0015176 | Closed | OPUS-SCO | Hang To | 259 | 259 |  |  | Container | Statement Management | Statement Account Receivable | Outstanding |  |  | EUA Enhancement to OPUS to Replace OnGuard EUA Local System | 2019-08-01 15:47 | 2019-11-10 16:47 | 2019-11-08 15:51 | 2019-11-11 10:21 | 2019-11-18 22:16 |  | 2019-11-18 22:16 | 2019-11-14 16:17 | 2019-11-26 16:16 | 2019-12-27 14:00 | CR0011354 | Statement ManagementStatement Account ReceivableOutstanding | OPUS-SAR | 2019-W47 | 2019-11 | 756 | 0 | 109.2699 | 3 | 1 | 3 | 0 | 183344 | 0.3 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 7 | 0 | 0 | 2019-08 | 0 | 0
1196 | CR0013179 | CTASK0023096 | Closed | OPUS-BKG-M | Thien Lai | 14 | 16 | 2020-11-27 19:17 | 2020-11-23 19:17 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Testing] [CLT Internal] OOME resolution on Booking Receipt Notice (Fax/Email) | 2020-10-27 09:06 | 2020-12-03 | 2020-11-25 17:10 | 2020-11-26 13:07 | 2020-11-26 17:16 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2020-11-27 09:20 | 2021-02-18 14:00 | CR0013179 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W3 | 2021-01 | 40 | 44 | 84.0374 | 4 | 1 | 1 | 0.02 | 193567 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.5625 | 0.53333 | 2020-10 | 0 | 0
1197 | CR0013179 | CTASK0023033 | Closed | OPUS-BKG-M | Thien Lai | 12 | 12 | 2020-10-31 13:03 | 2020-10-13 13:03 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Design] [CLT Internal] OOME resolution on Booking Receipt Notice (Fax/Email) | 2020-10-27 09:06 | 2020-12-03 | 2020-11-25 17:10 | 2020-11-26 13:07 | 2020-11-26 17:16 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2020-11-27 09:20 | 2021-02-18 14:00 | CR0013179 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W3 | 2021-01 | 40 | 44 | 84.0374 | 4 | 1 | 1 | 0.02 | 193567 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.5625 | 0.53333 | 2020-10 | 0 | 0
1198 | CR0013179 | CTASK0023094 | Closed | OPUS-BKG-M | Thien Lai | 6 | 8 | 2020-10-31 19:17 | 2020-10-26 19:17 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Development] [CLT Internal] OOME resolution on Booking Receipt Notice (Fax/Email) | 2020-10-27 09:06 | 2020-12-03 | 2020-11-25 17:10 | 2020-11-26 13:07 | 2020-11-26 17:16 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2020-11-27 09:20 | 2021-02-18 14:00 | CR0013179 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W3 | 2021-01 | 40 | 44 | 84.0374 | 4 | 1 | 1 | 0.02 | 193567 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.5625 | 0.53333 | 2020-10 | 0 | 0
1199 | CR0013179 | CTASK0023098 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-01-31 19:17 | 2021-01-01 19:17 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Deployment] [CLT Internal] OOME resolution on Booking Receipt Notice (Fax/Email) | 2020-10-27 09:06 | 2020-12-03 | 2020-11-25 17:10 | 2020-11-26 13:07 | 2020-11-26 17:16 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2020-11-27 09:20 | 2021-02-18 14:00 | CR0013179 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2021-W3 | 2021-01 | 40 | 44 | 84.0374 | 4 | 1 | 1 | 0.02 | 193567 | 1.3 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0.5625 | 0.53333 | 2020-10 | 0 | 0
1200 | CR0013131 | CTASK0024111 | Closed | OPUS-DMT | Cuong Nguyen | 2 | 2 | 2020-12-18 20:00 | 2020-12-10 08:00 | Container | Service Management | Demurrage/Detention | Charge Generation |  |  | [CTASK2] CLV_Analysis_Pair Test | 2020-12-07 16:34 | 2020-12-18 20:00 | 2020-12-17 10:36 | 2021-01-18 09:23 | 2021-01-18 09:45 |  | 2021-01-26 10:00 | 2021-01-26 09:11 | 2021-01-19 11:43 | 2021-02-25 14:00 | CR0013131 | Service ManagementDemurrage/DetentionCharge Generation | OPUS-DMT | 2021-W4 | 2021-01 | 2 | 2 | 49.7267 | 1 | 1 | 1 | 0 | 193529 | 1.5 | 0 | 0 | 0 | 1 | 1 | 1 | 12 | 40 | 0 | 0.058824 | 2020-12 | 0 | 0
1201 | CR0013927 | CTASK0026826 | Closed | OPUS-CTM | Tran Le | 46 | 46 |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | [Documentation][CLT Internal] Modify logic to prevent XX event creation of empty revenue bkg when shipment has not arrived at POD/DEL | 2021-05-11 12:24 | 2021-06-03 21:54 | 2021-06-03 10:30 | 2021-06-04 13:31 | 2021-06-08 13:42 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-09 16:40 | 2021-07-15 14:00 | CR0013927 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2021-W24 | 2021-06 | 28 | 92 | 34.8998 | 2 | 1 | 1 | 0.11 | 193501 | 1.6 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.052632 | 0.076923 | 2021-05 | 0 | 0
1202 | CR0013927 | CTASK0026827 | Closed | OPUS-CTM | Tran Le | 28 | 46 |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | Manage effort | 2021-05-11 12:24 | 2021-06-03 21:54 | 2021-06-03 10:30 | 2021-06-04 13:31 | 2021-06-08 13:42 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-09 16:40 | 2021-07-15 14:00 | CR0013927 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2021-W24 | 2021-06 | 28 | 92 | 34.8998 | 2 | 1 | 1 | 0.11 | 193501 | 1.6 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.052632 | 0.076923 | 2021-05 | 0 | 0
1203 | CR0012046 | CTASK0020213 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 12 | 12 | 2020-05-26 18:27 | 2020-05-18 18:27 | Container | Service Management | Booking/Documentation | Inbound Doc |  |  | [PROD] *ESA-JPN* Showing QR Code on Arrival Notice for JPN | 2020-02-05 10:19 | 2020-02-24 10:18 | 2020-02-24 09:30 | 2020-05-11 18:50 | 2020-05-12 13:14 |  | 2020-05-26 10:13 | 2020-05-26 11:06 | 2020-05-14 20:05 | 2020-06-25 13:00 | CR0012046 | Service ManagementBooking/DocumentationInbound Doc | OPUS-BKG-IB | 2020-W22 | 2020-05 | 28 | 28 | 110.9963 | 2 | 1 | 1 | 0.01 | 193506 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.85714 | 2020-02 | 0 | 0
1204 | CR0012046 | CTASK0018781 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 16 | 16 | 2020-03-13 16:06 | 2020-03-05 17:05 | Container | Service Management | Booking/Documentation | Inbound Doc |  |  | [Development]*ESA-JPN* Showing QR Code on Arrival Notice for JPN | 2020-02-05 10:19 | 2020-02-24 10:18 | 2020-02-24 09:30 | 2020-05-11 18:50 | 2020-05-12 13:14 |  | 2020-05-26 10:13 | 2020-05-26 11:06 | 2020-05-14 20:05 | 2020-06-25 13:00 | CR0012046 | Service ManagementBooking/DocumentationInbound Doc | OPUS-BKG-IB | 2020-W22 | 2020-05 | 28 | 28 | 110.9963 | 2 | 1 | 1 | 0.01 | 193506 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.85714 | 2020-02 | 0 | 0
1205 | CR0011718 | CTASK0019394 | Closed | OPUS-ACM | Huynh Tuan Khanh | 60 | 60 |  |  | Container | Sales Management | CNTR BIZ PFMC Analysis | Multi-Dimension Report | Sales PFMC | Inquiry by Customized Condition | ASIA - COA - D3 TEU converting logic in COA/BKG modules | 2020-02-03 09:16 | 2020-03-24 08:14 | 2020-03-23 14:42 | 2020-06-10 09:23 | 2020-06-12 12:49 |  | 2020-06-23 22:00 | 2020-06-23 22:09 | 2020-06-18 18:09 | 2020-10-01 13:00 | CR0011718 | Sales ManagementCNTR BIZ PFMC AnalysisMulti-Dimension ReportSales PFMCInquiry by Customized Condition | OPUS-COA | 2020-W26 | 2020-06 | 60 | 60 | 141.5307 | 1 | 1 | 1 | 0.02 | 193499 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0 | 2020-02 | 0 | 0
1206 | CR0013355 | CTASK0024955 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 2 | 2 | 2021-03-11 02:00 | 2021-03-05 11:19 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 193488 | 1.7 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.53659 | 0.28125 | 2021-02 | 0 | 0
1207 | CR0013355 | CTASK0024954 | Closed | OPUS-BKG-MFT-M | Nhut Nguyen Minh | 8 | 8 | 2021-02-28 11:28 | 2021-02-01 11:28 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 193512 | 1.7 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.2963 | 0.3125 | 2021-02 | 0 | 0
1208 | CR0013355 | CTASK0024908 | Closed | OPUS-BKG-CHG | Nam Nguyen | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 123048 | 2.4 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.22222 | 0.047619 | 2021-02 | 0 | 0
1209 | CR0013355 | CTASK0024956 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-08-06 19:25 | 2021-08-04 11:25 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 193488 | 1.7 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.53659 | 0.28125 | 2021-02 | 0 | 0
1210 | CR0013355 | CTASK0024950 | Closed | OPUS-MDA | Lanh Le | 3 | 3 | 2021-02-26 20:00 | 2021-02-22 08:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 183422 | 2.3 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0 | 0 | 2021-02 | 0 | 0
1211 | CR0013355 | CTASK0024951 | Closed | OPUS-BKG-MFT-M | Nhut Nguyen Minh | 5 | 5 | 2021-03-12 15:59 | 2021-02-08 15:59 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 193512 | 1.7 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.2963 | 0.3125 | 2021-02 | 0 | 0
1212 | CR0013355 | CTASK0024949 | Closed | OPUS-MDA | Lanh Le | 3 | 3 | 2021-03-05 20:00 | 2021-03-01 08:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 183422 | 2.3 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0 | 0 | 2021-02 | 0 | 0
1213 | CR0013355 | CTASK0024952 | Closed | OPUS-BKG-MFT-M | Nhut Nguyen Minh | 2 | 2 | 2021-03-12 16:00 | 2021-02-08 16:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 193512 | 1.7 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.2963 | 0.3125 | 2021-02 | 0 | 0
1214 | CR0013355 | CTASK0024953 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 22 | 22 | 2021-02-27 02:00 | 2021-02-22 10:45 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 193488 | 1.7 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.53659 | 0.28125 | 2021-02 | 0 | 0
1215 | CR0013355 | CTASK0024943 | Closed | OPUS-BKG-CHG | Nam Nguyen | 8 | 8 | 2021-02-26 17:11 | 2021-02-09 17:11 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 123048 | 2.4 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.22222 | 0.047619 | 2021-02 | 0 | 0
1216 | CR0013355 | CTASK0024946 | Closed | OPUS-MDA | Lanh Le | 2 | 2 | 2021-03-31 20:00 | 2021-03-05 08:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 183422 | 2.3 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0 | 0 | 2021-02 | 0 | 0
1217 | CR0013355 | CTASK0024947 | Closed | OPUS-MDA | Lanh Le | 2 | 2 | 2021-03-05 20:00 | 2021-03-01 08:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 183422 | 2.3 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0 | 0 | 2021-02 | 0 | 0
1218 | CR0013355 | CTASK0024873 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-01-26 19:30 | 2021-01-21 11:05 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 193488 | 1.7 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.53659 | 0.28125 | 2021-02 | 0 | 0
1219 | CR0013355 | CTASK0024945 | Closed | OPUS-BKG-CHG | Nam Nguyen | 5 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 123048 | 2.4 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.22222 | 0.047619 | 2021-02 | 0 | 0
1220 | CR0013355 | CTASK0024941 | Closed | OPUS-BKG-CHG | Nam Nguyen | 17 | 16 | 2021-02-05 01:17 | 2021-02-01 01:17 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 123048 | 2.4 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.22222 | 0.047619 | 2021-02 | 0 | 0
1221 | CR0013355 | CTASK0024883 | Closed | OPUS-BKG-MFT-M | Nhut Nguyen Minh | 3 | 2 | 2021-01-27 18:50 | 2021-01-25 09:50 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Remove POP-UP's from OPUS | 2021-02-22 09:53 | 2021-03-13 | 2021-03-11 17:54 | 2021-07-19 10:15 | 2021-07-19 10:51 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-06 10:27 | 2021-08-17 14:00 | CR0013355 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W32 | 2021-08 | 102 | 101 | 169.0051 | 16 | 4 | 4 | 0.02 | 193512 | 1.7 | 3 | 0 | 0 | 2 | 2 | 3 | 10 | 22 | 0.2963 | 0.3125 | 2021-02 | 0 | 0
1222 | CR0011762 | CTASK0016555 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 23 | 7 | 2019-10-09 16:40 | 2019-10-01 16:40 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | (SCMT) India declare cargo value - default value | 2019-10-11 16:18 | 2019-10-22 16:17 | 2019-10-16 13:08 | 2019-11-06 11:27 | 2019-12-11 16:48 |  | 2019-12-17 10:00 | 2019-12-17 10:00 | 2019-12-11 17:08 | 2019-12-23 19:15 | CR0011762 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2019-W51 | 2019-12 | 23 | 7 | 66.7377 | 1 | 1 | 1 | 0 | 173280 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 18 | 0 | 0 | 2019-10 | 0 | 0
1223 | CR0011817 | CTASK0016743 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 37 | 71 | 2019-11-08 16:26 | 2019-10-16 15:26 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | AR - Advance Manifest - to show error or acceptance description at ACK column fro ADVMAN response XML and OPS Tax Id column | 2019-10-21 15:05 | 2019-11-09 | 2019-11-07 18:27 | 2019-11-12 04:09 | 2019-11-21 11:32 |  | 2019-11-26 10:00 | 2019-11-26 10:00 | 2019-11-23 03:10 | 2019-12-26 14:00 | CR0011817 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2019-W48 | 2019-11 | 37 | 71 | 35.7885 | 1 | 1 | 1 | 0.08 | 193470 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 7 | 0 | 1.3333 | 2019-10 | 0 | 0
1224 | CR0012954 | CTASK0021944 | Closed | OPUS-BKG-IB | Thuc Tran | 16 | 16 | 2020-08-25 19:30 | 2020-08-14 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Code Validate | [Development + Testing + Deployment][Internal CR] Change inner validation check logic for customer code in Code validation screen | 2020-08-20 18:40 | 2020-09-11 23:39 | 2020-09-08 18:29 | 2020-10-06 12:58 | 2020-10-08 11:54 |  | 2020-10-20 11:53 | 2020-10-27 10:40 | 2020-10-21 16:54 | 2020-11-26 14:00 | CR0012954 | Service ManagementBooking/DocumentationInbound DocArrival NoticeCode Validate | OPUS-BKG-IB | 2020-W43 | 2020-10 | 37 | 37 | 60.7173 | 3 | 1 | 1 | 0.03 | 173280 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.18519 | 2020-08 | 0 | 0
1225 | CR0012954 | CTASK0022903 | Closed | OPUS-BKG-IB | Thuc Tran | 15 | 15 | 2020-10-15 19:30 | 2020-10-06 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Code Validate | [Deployment+Testing][Internal CR] Change inner validation check logic for customer code in Code validation screen | 2020-08-20 18:40 | 2020-09-11 23:39 | 2020-09-08 18:29 | 2020-10-06 12:58 | 2020-10-08 11:54 |  | 2020-10-20 11:53 | 2020-10-27 10:40 | 2020-10-21 16:54 | 2020-11-26 14:00 | CR0012954 | Service ManagementBooking/DocumentationInbound DocArrival NoticeCode Validate | OPUS-BKG-IB | 2020-W43 | 2020-10 | 37 | 37 | 60.7173 | 3 | 1 | 1 | 0.03 | 173280 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.18519 | 2020-08 | 0 | 0
1226 | CR0012954 | CTASK0021779 | Closed | OPUS-BKG-IB | Thuc Tran | 6 | 6 | 2020-08-12 19:30 | 2020-08-10 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Code Validate | [Estimation][Internal CR] Change inner validation check logic for customer code in Code validation screen | 2020-08-20 18:40 | 2020-09-11 23:39 | 2020-09-08 18:29 | 2020-10-06 12:58 | 2020-10-08 11:54 |  | 2020-10-20 11:53 | 2020-10-27 10:40 | 2020-10-21 16:54 | 2020-11-26 14:00 | CR0012954 | Service ManagementBooking/DocumentationInbound DocArrival NoticeCode Validate | OPUS-BKG-IB | 2020-W43 | 2020-10 | 37 | 37 | 60.7173 | 3 | 1 | 1 | 0.03 | 173280 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.18519 | 2020-08 | 0 | 0
1227 | CR0012109 | CTASK0017732 | Closed | OPUS-MNR | Tuyen Truong | 15 | 20 | 2020-04-03 15:58 | 2020-01-20 15:58 | Container | Equipment Management | M&R |  |  |  | [CLT Internal] Total Loss Improvement | 2020-03-26 16:40 | 2020-04-03 19:39 | 2020-04-03 14:30 | 2020-04-24 10:48 | 2020-04-24 13:07 |  | 2020-05-07 10:30 | 2020-05-05 09:30 | 2020-04-24 13:14 | 2020-06-12 13:00 | CR0012109 | Equipment ManagementM&R | OPUS-MNR | 2020-W19 | 2020-05 | 15 | 20 | 41.7427 | 1 | 1 | 1 | 0.02 | 173255 | 1.5 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 26 | 0 | 0 | 2020-03 | 0 | 0
1228 | CR0010332 | CTASK0017480 | Closed | OPUS-BKG-M | Loc Tran | 14 | 14 | 2019-12-20 16:20 | 2019-12-16 16:20 | Container | Service Management | Product Catalog |  |  |  | PRD - Ability to set up Import Cargo Availability for better transport planning & more accurate reflection of cargo tracking information | 2019-11-14 11:38 | 2020-01-11 | 2020-01-10 17:18 | 2021-03-10 14:42 | 2021-05-25 11:19 |  | 2021-06-01 11:00 | 2021-06-01 10:00 | 2021-05-27 14:44 | 2021-07-01 14:00 | CR0010332 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W22 | 2021-06 | 0 | 14 | 564.9733 | 1 | 1 | 1 | 0 | 193503 | 0.3 | 1 | 0 | 0 | 1 | 1 | 5 | 6 | 53 | 0.33333 | 0.36364 | 2019-11 | 0 | 0
1229 | CR0013939 | CTASK0027049 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2021-05-31 11:20 | 2021-05-05 11:20 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Inquiry | [Design][CLT Internal] CA Inquiry and Report Enhancement | 2021-05-18 08:56 | 2021-06-17 02:00 | 2021-06-15 14:39 | 2021-06-23 16:38 | 2021-06-23 16:58 |  | 2021-07-06 10:00 | 2021-07-06 10:00 | 2021-06-24 13:02 | 2021-07-29 14:00 | CR0013939 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Inquiry | OPUS-BKG-M | 2021-W27 | 2021-07 | 32 | 39 | 49.0447 | 4 | 1 | 1 | 0.03 | 193503 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0.33333 | 0.28571 | 2021-05 | 0 | 0
1230 | CR0013939 | CTASK0027053 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-06-30 13:52 | 2021-06-28 13:52 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Inquiry | [Deployment][CLT Internal] CA Inquiry and Report Enhancement | 2021-05-18 08:56 | 2021-06-17 02:00 | 2021-06-15 14:39 | 2021-06-23 16:38 | 2021-06-23 16:58 |  | 2021-07-06 10:00 | 2021-07-06 10:00 | 2021-06-24 13:02 | 2021-07-29 14:00 | CR0013939 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Inquiry | OPUS-BKG-M | 2021-W27 | 2021-07 | 32 | 39 | 49.0447 | 4 | 1 | 1 | 0.03 | 193503 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0.33333 | 0.28571 | 2021-05 | 0 | 0
1231 | CR0013939 | CTASK0027050 | Closed | OPUS-BKG-M | Loc Tran | 12 | 12 | 2021-05-31 15:40 | 2021-05-07 15:40 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Inquiry | [Development][CLT Internal] CA Inquiry and Report Enhancement | 2021-05-18 08:56 | 2021-06-17 02:00 | 2021-06-15 14:39 | 2021-06-23 16:38 | 2021-06-23 16:58 |  | 2021-07-06 10:00 | 2021-07-06 10:00 | 2021-06-24 13:02 | 2021-07-29 14:00 | CR0013939 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Inquiry | OPUS-BKG-M | 2021-W27 | 2021-07 | 32 | 39 | 49.0447 | 4 | 1 | 1 | 0.03 | 193503 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0.33333 | 0.28571 | 2021-05 | 0 | 0
1232 | CR0013939 | CTASK0027051 | Closed | OPUS-BKG-M | Loc Tran | 8 | 15 | 2021-05-31 11:04 | 2021-05-04 11:04 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Inquiry | [Testing][CLT Internal] CA Inquiry and Report Enhancement | 2021-05-18 08:56 | 2021-06-17 02:00 | 2021-06-15 14:39 | 2021-06-23 16:38 | 2021-06-23 16:58 |  | 2021-07-06 10:00 | 2021-07-06 10:00 | 2021-06-24 13:02 | 2021-07-29 14:00 | CR0013939 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Inquiry | OPUS-BKG-M | 2021-W27 | 2021-07 | 32 | 39 | 49.0447 | 4 | 1 | 1 | 0.03 | 193503 | 1.8 | 1 | 0 | 0 | 1 | 1 | 1 | 8 | 28 | 0.33333 | 0.28571 | 2021-05 | 0 | 0
1233 | CR0013390 | CTASK0024504 | Closed | OPUS-SCE | Thanh Tran Ngoc | 1 | 1 | 2021-02-01 15:34 | 2021-01-07 15:34 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [Documentation] OPUS service enhancement for UI COP Detail | 2021-04-07 11:15 | 2021-04-30 11:11 | 2021-04-29 14:34 | 2021-05-20 13:04 | 2021-05-26 11:23 |  | 2021-06-15 13:00 | 2021-06-15 11:23 | 2021-06-02 09:18 | 2021-07-15 14:00 | CR0013390 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2021-W24 | 2021-06 | 11 | 20 | 69.0727 | 3 | 1 | 2 | 0.01 | 193478 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0 | 0 | 2021-04 | 0 | 0
1234 | CR0013390 | CTASK0026568 | Closed | OPUS-SCE | Son Nguyen The | 11 | 11 | 2021-04-30 11:04 | 2021-04-01 11:04 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [CLT Internal] OPUS service enhancement for UI COP Detail | 2021-04-07 11:15 | 2021-04-30 11:11 | 2021-04-29 14:34 | 2021-05-20 13:04 | 2021-05-26 11:23 |  | 2021-06-15 13:00 | 2021-06-15 11:23 | 2021-06-02 09:18 | 2021-07-15 14:00 | CR0013390 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2021-W24 | 2021-06 | 11 | 20 | 69.0727 | 3 | 1 | 2 | 0.01 | 193531 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0 | 0 | 2021-04 | 0 | 0
1235 | CR0013390 | CTASK0024506 | Closed | OPUS-SCE | Thanh Tran Ngoc | 20 | 20 | 2021-04-30 15:37 | 2021-03-01 15:37 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [CLT Internal] OPUS service enhancement for UI COP Detail | 2021-04-07 11:15 | 2021-04-30 11:11 | 2021-04-29 14:34 | 2021-05-20 13:04 | 2021-05-26 11:23 |  | 2021-06-15 13:00 | 2021-06-15 11:23 | 2021-06-02 09:18 | 2021-07-15 14:00 | CR0013390 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2021-W24 | 2021-06 | 11 | 20 | 69.0727 | 3 | 1 | 2 | 0.01 | 193478 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0 | 0 | 2021-04 | 0 | 0
1236 | CR0010782 | CTASK0024579 | Implemented | OPUS-TRS | Giang Nguyen Hoang | 27 | 24 | 2021-01-31 11:44 | 2021-01-11 11:44 | Container | Service Management | Trans S/O |  |  |  | [202101] GHQ TRS Empty SO Linkage | 2021-01-11 11:40 | 2021-02-05 21:00 | 2021-02-05 11:06 | 2021-06-30 14:44 | 2021-07-12 16:23 |  | 2021-08-17 10:00 | 2021-08-17 14:30 | 2021-08-05 13:32 |  | CR0010782 | Service ManagementTrans S/O | OPUS-TRS | 2021-W33 | 2021-08 | 50 | 48 | 217.9307 | 2 | 1 | 2 | 0.01 | 183440 | 1.8 | 0 | 0 | 0 | 1 | 1 | 3 | 5 | 22 | 0 | 0 | 2021-01 | 0 | 0
1237 | CR0010782 | CTASK0024578 | Implemented | OPUS-TRS | Nhat Phan Dinh Minh | 23 | 24 | 2021-01-31 11:43 | 2021-01-11 11:43 | Container | Service Management | Trans S/O |  |  |  | [202101] GHQ TRS Empty SO Linkage | 2021-01-11 11:40 | 2021-02-05 21:00 | 2021-02-05 11:06 | 2021-06-30 14:44 | 2021-07-12 16:23 |  | 2021-08-17 10:00 | 2021-08-17 14:30 | 2021-08-05 13:32 |  | CR0010782 | Service ManagementTrans S/O | OPUS-TRS | 2021-W33 | 2021-08 | 50 | 48 | 217.9307 | 2 | 1 | 2 | 0.01 | 183432 | 1.8 | 0 | 0 | 0 | 1 | 1 | 3 | 5 | 22 | 0 | 0 | 2021-01 | 0 | 0
1238 | CR0013732 | CTASK0026405 | Closed | OPUS-BKG-M | Vinh Tran | 8 | 8 | 2021-05-21 02:00 | 2021-05-19 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Development] [CLT Internal] Literal SQL Tuning on TRO Notice | 2021-05-31 18:16 | 2021-06-10 | 2021-06-01 09:50 | 2021-06-03 16:42 | 2021-06-03 18:14 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:36 | 2021-07-28 14:00 | CR0013732 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2021-W25 | 2021-06 | 30 | 34 | 26.6552 | 4 | 1 | 1 | 0.05 | 193525 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
1239 | CR0013732 | CTASK0026407 | Closed | OPUS-BKG-M | Vinh Tran | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Deployment] [CLT Internal] Literal SQL Tuning on TRO Notice | 2021-05-31 18:16 | 2021-06-10 | 2021-06-01 09:50 | 2021-06-03 16:42 | 2021-06-03 18:14 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:36 | 2021-07-28 14:00 | CR0013732 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2021-W25 | 2021-06 | 30 | 34 | 26.6552 | 4 | 1 | 1 | 0.05 | 193525 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
1240 | CR0013732 | CTASK0026409 | Closed | OPUS-BKG-M | Vinh Tran | 6 | 6 | 2021-04-10 02:00 | 2021-04-09 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Design] [CLT Internal] Literal SQL Tuning on TRO Notice | 2021-05-31 18:16 | 2021-06-10 | 2021-06-01 09:50 | 2021-06-03 16:42 | 2021-06-03 18:14 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:36 | 2021-07-28 14:00 | CR0013732 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2021-W25 | 2021-06 | 30 | 34 | 26.6552 | 4 | 1 | 1 | 0.05 | 193525 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
1241 | CR0013732 | CTASK0026406 | Closed | OPUS-BKG-M | Vinh Tran | 16 | 16 | 2021-05-22 02:00 | 2021-05-21 02:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Trans. Request Order(O/B-Europe) | [Testing] [CLT Internal] Literal SQL Tuning on TRO Notice | 2021-05-31 18:16 | 2021-06-10 | 2021-06-01 09:50 | 2021-06-03 16:42 | 2021-06-03 18:14 |  | 2021-06-27 10:00 | 2021-06-27 12:00 | 2021-06-04 15:36 | 2021-07-28 14:00 | CR0013732 | Service ManagementBooking/DocumentationBookingBookingTrans. Request Order(O/B-Europe) | OPUS-BKG-M | 2021-W25 | 2021-06 | 30 | 34 | 26.6552 | 4 | 1 | 1 | 0.05 | 193525 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
1242 | CR0013005 | CTASK0023707 | Closed | OPUS-MGS | Tuyen Truong | 112 | 65 | 2021-01-01 01:56 | 2020-12-01 10:00 | Container | Equipment Management | M.G. Set | M.G Set Movement | Movement Inquiry by Mgset |  | NA *MGS* Modify Auto-Detach Logic for Clip-On Gensets | 2020-11-23 18:03 | 2021-02-13 01:02 | 2021-02-09 17:16 | 2021-04-08 16:35 | 2021-04-13 11:32 |  | 2021-04-20 12:00 | 2021-04-20 11:00 | 2021-04-14 11:03 | 2021-05-29 14:00 | CR0013005 | Equipment ManagementM.G. SetM.G Set MovementMovement Inquiry by Mgset | OPUS-MGS | 2021-W16 | 2021-04 | 476 | 242 | 147.7481 | 4 | 1 | 2 | 0.07 | 173255 | 2.2 | 1 | 0 | 0 | 3 | 1 | 2 | 5 | 27 | 0 | 0 | 2020-11 | 0 | 0
1243 | CR0013005 | CTASK0023708 | Closed | OPUS-MGS | Tuyen Truong | 123 | 40 | 2021-02-01 01:57 | 2021-01-01 10:00 | Container | Equipment Management | M.G. Set | M.G Set Movement | Movement Inquiry by Mgset |  | NA *MGS* Modify Auto-Detach Logic for Clip-On Gensets | 2020-11-23 18:03 | 2021-02-13 01:02 | 2021-02-09 17:16 | 2021-04-08 16:35 | 2021-04-13 11:32 |  | 2021-04-20 12:00 | 2021-04-20 11:00 | 2021-04-14 11:03 | 2021-05-29 14:00 | CR0013005 | Equipment ManagementM.G. SetM.G Set MovementMovement Inquiry by Mgset | OPUS-MGS | 2021-W16 | 2021-04 | 476 | 242 | 147.7481 | 4 | 1 | 2 | 0.07 | 173255 | 2.2 | 1 | 0 | 0 | 3 | 1 | 2 | 5 | 27 | 0 | 0 | 2020-11 | 0 | 0
1244 | CR0013005 | CTASK0023709 | Closed | OPUS-MGS | Tien Le | 96 | 37 | 2021-02-01 01:59 | 2021-01-01 10:00 | Container | Equipment Management | M.G. Set | M.G Set Movement | Movement Inquiry by Mgset |  | NA *MGS* Modify Auto-Detach Logic for Clip-On Gensets | 2020-11-23 18:03 | 2021-02-13 01:02 | 2021-02-09 17:16 | 2021-04-08 16:35 | 2021-04-13 11:32 |  | 2021-04-20 12:00 | 2021-04-20 11:00 | 2021-04-14 11:03 | 2021-05-29 14:00 | CR0013005 | Equipment ManagementM.G. SetM.G Set MovementMovement Inquiry by Mgset | OPUS-MGS | 2021-W16 | 2021-04 | 476 | 242 | 147.7481 | 4 | 1 | 2 | 0.07 | 173286 | 2.2 | 1 | 0 | 0 | 3 | 1 | 2 | 5 | 27 | 0 | 0 | 2020-11 | 0 | 0
1245 | CR0013005 | CTASK0023706 | Closed | OPUS-MGS | Tien Le | 145 | 100 | 2021-01-01 01:50 | 2020-12-01 10:00 | Container | Equipment Management | M.G. Set | M.G Set Movement | Movement Inquiry by Mgset |  | NA *MGS* Modify Auto-Detach Logic for Clip-On Gensets | 2020-11-23 18:03 | 2021-02-13 01:02 | 2021-02-09 17:16 | 2021-04-08 16:35 | 2021-04-13 11:32 |  | 2021-04-20 12:00 | 2021-04-20 11:00 | 2021-04-14 11:03 | 2021-05-29 14:00 | CR0013005 | Equipment ManagementM.G. SetM.G Set MovementMovement Inquiry by Mgset | OPUS-MGS | 2021-W16 | 2021-04 | 476 | 242 | 147.7481 | 4 | 1 | 2 | 0.07 | 173286 | 2.2 | 1 | 0 | 0 | 3 | 1 | 2 | 5 | 27 | 0 | 0 | 2020-11 | 0 | 0
1246 | CR0013361 | CTASK0024338 | Closed | OPUS-PRI | Ngan Nham | 128 | 128 | 2021-01-30 01:00 | 2020-12-28 01:00 | Container | Sales Management |  |  |  |  | [Development] *API* Service Contract Filing in Support Of MOBILE APP multi route Filing | 2020-12-21 17:21 | 2021-01-30 01:00 | 2021-01-28 10:09 | 2021-02-10 10:53 | 2021-02-10 11:16 |  | 2021-02-15 10:43 | 2021-02-16 11:00 | 2021-02-10 11:51 | 2021-03-01 06:36 | CR0013361 | Sales Management | OPUS-PRI | 2021-W7 | 2021-02 | 128 | 128 | 55.7238 | 1 | 1 | 1 | 0.1 | 193461 | 2.1 | 0 | 0 | 0 | 2 | 1 | 2 | 5 | 21 | 0 | 0 | 2020-12 | 0 | 0
1247 | CR0013495 | CTASK0025810 | Closed | OPUS-VSK | Linh Nguyen | 56 | 56 | 2021-05-26 | 2021-03-25 19:20 | Container | Vessel Operation | Vessel Schedule | VSL SKD |  |  | [CLV] Request to change interface logic for deleted VVD to IBIS PLUS | 2021-04-13 17:59 | 2021-05-06 17:58 | 2021-05-06 09:30 | 2021-05-12 09:00 | 2021-05-12 12:49 |  | 2021-05-18 11:00 | 2021-05-18 10:45 | 2021-05-12 13:22 | 2021-06-17 14:00 | CR0013495 | Vessel OperationVessel ScheduleVSL SKD | OPUS-VSK | 2021-W20 | 2021-05 | 64 | 64 | 34.7087 | 3 | 1 | 2 | 0.08 | 193464 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.375 | 1.5 | 2021-04 | 0 | 0
1248 | CR0013495 | CTASK0025809 | Closed | OPUS-VSK | Thuan Tran | 8 | 8 |  |  | Container | Vessel Operation | Vessel Schedule | VSL SKD |  |  | [CLV] Request to change interface logic for deleted VVD to IBIS PLUS | 2021-04-13 17:59 | 2021-05-06 17:58 | 2021-05-06 09:30 | 2021-05-12 09:00 | 2021-05-12 12:49 |  | 2021-05-18 11:00 | 2021-05-18 10:45 | 2021-05-12 13:22 | 2021-06-17 14:00 | CR0013495 | Vessel OperationVessel ScheduleVSL SKD | OPUS-VSK | 2021-W20 | 2021-05 | 64 | 64 | 34.7087 | 3 | 1 | 2 | 0.08 | 183423 | 2.4 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0 | 0 | 2021-04 | 0 | 0
1249 | CR0013495 | CTASK0025806 | Closed | OPUS-VSK | Linh Nguyen | 1 | 1 |  |  | Container | Vessel Operation | Vessel Schedule | VSL SKD |  |  | [Document] Request to change interface logic for deleted VVD to IBIS PLUS | 2021-04-13 17:59 | 2021-05-06 17:58 | 2021-05-06 09:30 | 2021-05-12 09:00 | 2021-05-12 12:49 |  | 2021-05-18 11:00 | 2021-05-18 10:45 | 2021-05-12 13:22 | 2021-06-17 14:00 | CR0013495 | Vessel OperationVessel ScheduleVSL SKD | OPUS-VSK | 2021-W20 | 2021-05 | 64 | 64 | 34.7087 | 3 | 1 | 2 | 0.08 | 193464 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 10 | 28 | 0.375 | 1.5 | 2021-04 | 0 | 0
1250 | CR0011580 | CTASK0016614 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 8 | 12 |  |  | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | [Actual] NA VENDOR EDI - Recording the parent booking number in Railbill Flat File. | 2019-10-01 17:19 | 2019-10-18 18:00 | 2019-10-17 14:53 | 2019-11-27 23:53 | 2019-12-06 17:44 |  | 2019-12-17 10:00 | 2019-12-17 11:00 | 2019-12-06 21:33 | 2019-12-17 21:30 | CR0011580 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2019-W51 | 2019-12 | 8 | 12 | 76.6951 | 1 | 1 | 1 | 0.01 | 183432 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 18 | 0 | 0 | 2019-10 | 0 | 0
1251 | CR0013967 | CTASK0027007 | Closed | OPUS-SAP | Cuong Tran Hung | 12 | 12 | 2021-05-31 15:30 | 2021-05-13 15:30 | Container | Statement Management | Statement Account Payable | Invoices | Invoices Entry |  | [May 2021][Cuong Tran][CLT Internal] Removing the restriction of center code. | 2021-05-17 09:03 | 2021-07-15 09:02 | 2021-05-24 10:24 | 2021-06-07 14:58 | 2021-06-09 16:58 |  | 2021-06-15 10:00 | 2021-06-15 11:00 | 2021-06-10 14:23 | 2021-07-15 14:00 | CR0013967 | Statement ManagementStatement Account PayableInvoicesInvoices Entry | OPUS-SAP | 2021-W24 | 2021-06 | 63 | 62 | 29.0399 | 3 | 1 | 3 | 0.09 | 193530 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 1.2308 | 1.2222 | 2021-05 | 0 | 0
1252 | CR0013967 | CTASK0027006 | Closed | OPUS-SAP | Chuong Ta | 42 | 42 | 2021-05-31 16:47 | 2021-05-13 16:47 | Container | Statement Management | Statement Account Payable | Invoices | Invoices Entry |  | [May 2021][Chuong Ta][CLT Internal] Removing the restriction of center code. | 2021-05-17 09:03 | 2021-07-15 09:02 | 2021-05-24 10:24 | 2021-06-07 14:58 | 2021-06-09 16:58 |  | 2021-06-15 10:00 | 2021-06-15 11:00 | 2021-06-10 14:23 | 2021-07-15 14:00 | CR0013967 | Statement ManagementStatement Account PayableInvoicesInvoices Entry | OPUS-SAP | 2021-W24 | 2021-06 | 63 | 62 | 29.0399 | 3 | 1 | 3 | 0.09 | 183379 | 2.2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.32 | 0.375 | 2021-05 | 0 | 0
1253 | CR0013967 | CTASK0027008 | Closed | OPUS-SAP | Lien Le | 9 | 8 | 2021-05-31 16:48 | 2021-05-13 16:48 | Container | Statement Management | Statement Account Payable | Invoices | Invoices Entry |  | [May 2021]Lien Le][CLT Internal] Removing the restriction of center code. | 2021-05-17 09:03 | 2021-07-15 09:02 | 2021-05-24 10:24 | 2021-06-07 14:58 | 2021-06-09 16:58 |  | 2021-06-15 10:00 | 2021-06-15 11:00 | 2021-06-10 14:23 | 2021-07-15 14:00 | CR0013967 | Statement ManagementStatement Account PayableInvoicesInvoices Entry | OPUS-SAP | 2021-W24 | 2021-06 | 63 | 62 | 29.0399 | 3 | 1 | 3 | 0.09 | 193441 | 2.2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.42308 | 0 | 2021-05 | 0 | 0
1254 | CR0010570 | CTASK0017131 | Closed | OPUS-TRS | Giang Nguyen Hoang | 3 | 12 |  |  | Container | Service Management | Trans S/O | Service Order | Creation | CY & Door (EUR) | [Actual] EUA _ TRS ENHANCED WITH NEW DOOR ECC FIELD AND LOGIC in GLOBAL TRS RELATED screens | 2019-10-31 09:59 | 2019-11-30 18:00 | 2019-11-14 15:58 | 2020-01-23 15:25 | 2020-02-10 09:59 |  | 2020-02-18 12:00 | 2020-02-18 10:00 | 2020-02-13 21:27 | 2020-03-19 13:00 | CR0010570 | Service ManagementTrans S/OService OrderCreationCY & Door (EUR) | OPUS-TRS | 2020-W8 | 2020-02 | 57 | 84 | 110.0837 | 2 | 1 | 2 | 0.03 | 183440 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 13 | 0 | 0 | 2019-10 | 0 | 0
1255 | CR0010570 | CTASK0016826 | Closed | OPUS-TRS | Hieu Tran | 54 | 72 |  |  | Container | Service Management | Trans S/O | Service Order | Creation | CY & Door (EUR) | [Actual] EUA _ TRS ENHANCED WITH NEW DOOR ECC FIELD AND LOGIC in GLOBAL TRS RELATED screens. | 2019-10-31 09:59 | 2019-11-30 18:00 | 2019-11-14 15:58 | 2020-01-23 15:25 | 2020-02-10 09:59 |  | 2020-02-18 12:00 | 2020-02-18 10:00 | 2020-02-13 21:27 | 2020-03-19 13:00 | CR0010570 | Service ManagementTrans S/OService OrderCreationCY & Door (EUR) | OPUS-TRS | 2020-W8 | 2020-02 | 57 | 84 | 110.0837 | 2 | 1 | 2 | 0.03 | 183400 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 13 | 0 | 0 | 2019-10 | 0 | 0
1256 | CR0011848 | CTASK0020320 | Closed | OPUS-PRD | Thanh Tran Ngoc | 50 | 50 | 2020-06-12 18:00 | 2020-05-27 09:00 | Container | Service Management | Product Catalog |  |  |  | GHQ - Allow PRD Route Constraint Setup by Country level | 2020-05-27 10:14 | 2020-06-19 18:13 | 2020-06-18 17:13 | 2020-07-29 20:05 | 2020-08-04 16:16 |  | 2020-08-18 10:00 | 2020-08-18 13:17 | 2020-08-12 18:31 | 2020-09-20 13:00 | CR0011848 | Service ManagementProduct Catalog | OPUS-PRD | 2020-W34 | 2020-08 | 50 | 50 | 82.9903 | 1 | 1 | 1 | 0.03 | 193478 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 30 | 0 | 0 | 2020-05 | 0 | 0
1257 | CR0012245 | CTASK0019429 | Closed | OPUS-BKG-M | Kieu Le | 5 | 5 | 2020-04-09 02:00 | 2020-04-06 02:06 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] AS - OPUS Container - BRN is sent even Booking status is "Wait" | 2020-03-04 12:51 | 2020-04-09 | 2020-04-06 17:49 | 2020-04-06 20:59 | 2020-04-07 09:30 |  | 2020-04-09 10:00 | 2020-04-09 10:00 | 2020-04-07 09:34 | 2020-04-09 10:33 | CR0012245 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W15 | 2020-04 | 44 | 44 | 35.8812 | 4 | 1 | 2 | 0.05 | 153106 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 16 | 0 | 0.4 | 2020-03 | 0 | 0
1258 | CR0012245 | CTASK0018278 | Closed | OPUS-BKG-M | Loc Tran | 21 | 21 | 2020-02-14 18:33 | 2020-02-07 18:33 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] AS - OPUS Container - BRN is sent even Booking status is "Wait" | 2020-03-04 12:51 | 2020-04-09 | 2020-04-06 17:49 | 2020-04-06 20:59 | 2020-04-07 09:30 |  | 2020-04-09 10:00 | 2020-04-09 10:00 | 2020-04-07 09:34 | 2020-04-09 10:33 | CR0012245 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W15 | 2020-04 | 44 | 44 | 35.8812 | 4 | 1 | 2 | 0.05 | 193503 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 16 | 0 | 0.36364 | 2020-03 | 0 | 0
1259 | CR0012245 | CTASK0018374 | Closed | OPUS-BKG-M | Loc Tran | 16 | 16 | 2020-03-13 12:52 | 2020-03-04 12:52 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] AS - OPUS Container - BRN is sent even Booking status is "Wait" | 2020-03-04 12:51 | 2020-04-09 | 2020-04-06 17:49 | 2020-04-06 20:59 | 2020-04-07 09:30 |  | 2020-04-09 10:00 | 2020-04-09 10:00 | 2020-04-07 09:34 | 2020-04-09 10:33 | CR0012245 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W15 | 2020-04 | 44 | 44 | 35.8812 | 4 | 1 | 2 | 0.05 | 193503 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 16 | 0 | 0.36364 | 2020-03 | 0 | 0
1260 | CR0012245 | CTASK0018377 | Closed | OPUS-BKG-M | Loc Tran | 2 | 2 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] AS - OPUS Container - BRN is sent even Booking status is "Wait" | 2020-03-04 12:51 | 2020-04-09 | 2020-04-06 17:49 | 2020-04-06 20:59 | 2020-04-07 09:30 |  | 2020-04-09 10:00 | 2020-04-09 10:00 | 2020-04-07 09:34 | 2020-04-09 10:33 | CR0012245 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W15 | 2020-04 | 44 | 44 | 35.8812 | 4 | 1 | 2 | 0.05 | 193503 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 16 | 0 | 0.36364 | 2020-03 | 0 | 0
1261 | CR0011895 | CTASK0022085 | Closed | OPUS-BKG-M | Kieu Le | 28 | 28 | 2020-09-30 17:41 | 2020-09-01 17:41 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Development] Opus_Portcast API Connection | 2020-09-10 09:57 | 2020-12-03 | 2020-12-02 17:12 | 2020-12-28 09:40 | 2020-12-28 19:50 |  | 2021-01-12 10:00 | 2021-01-12 14:54 | 2020-12-31 09:39 | 2021-02-12 14:00 | CR0011895 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W2 | 2021-01 | 45 | 50 | 124.0023 | 5 | 1 | 1 | 0.02 | 153106 | 1.9 | 1 | 0 | 1 | 1 | 1 | 2 | 14 | 40 | 0.22951 | 0.4 | 2020-09 | 1 | 1
1262 | CR0011895 | CTASK0022083 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2020-09-30 17:40 | 2020-09-01 17:40 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Design] Opus_Portcast API Connection | 2020-09-10 09:57 | 2020-12-03 | 2020-12-02 17:12 | 2020-12-28 09:40 | 2020-12-28 19:50 |  | 2021-01-12 10:00 | 2021-01-12 14:54 | 2020-12-31 09:39 | 2021-02-12 14:00 | CR0011895 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W2 | 2021-01 | 45 | 50 | 124.0023 | 5 | 1 | 1 | 0.02 | 153106 | 1.9 | 1 | 0 | 1 | 1 | 1 | 2 | 14 | 40 | 0.22951 | 0.4 | 2020-09 | 1 | 1
1263 | CR0011895 | CTASK0024165 | Closed | OPUS-BKG-M | Kieu Le | 5 | 5 | 2020-11-30 19:44 | 2020-11-16 19:43 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Testing] Opus_Portcast API Connection | 2020-09-10 09:57 | 2020-12-03 | 2020-12-02 17:12 | 2020-12-28 09:40 | 2020-12-28 19:50 |  | 2021-01-12 10:00 | 2021-01-12 14:54 | 2020-12-31 09:39 | 2021-02-12 14:00 | CR0011895 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W2 | 2021-01 | 45 | 50 | 124.0023 | 5 | 1 | 1 | 0.02 | 153106 | 1.9 | 1 | 0 | 1 | 1 | 1 | 2 | 14 | 40 | 0.22951 | 0.4 | 2020-09 | 1 | 1
1264 | CR0011895 | CTASK0022086 | Closed | OPUS-BKG-M | Kieu Le | 7 | 7 | 2020-12-31 17:42 | 2020-12-01 02:42 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Testing] Opus_Portcast API Connection | 2020-09-10 09:57 | 2020-12-03 | 2020-12-02 17:12 | 2020-12-28 09:40 | 2020-12-28 19:50 |  | 2021-01-12 10:00 | 2021-01-12 14:54 | 2020-12-31 09:39 | 2021-02-12 14:00 | CR0011895 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W2 | 2021-01 | 45 | 50 | 124.0023 | 5 | 1 | 1 | 0.02 | 153106 | 1.9 | 1 | 0 | 1 | 1 | 1 | 2 | 14 | 40 | 0.22951 | 0.4 | 2020-09 | 1 | 1
1265 | CR0011895 | CTASK0022088 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-01-29 17:43 | 2021-01-01 17:43 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Deployment] Opus_Portcast API Connection | 2020-09-10 09:57 | 2020-12-03 | 2020-12-02 17:12 | 2020-12-28 09:40 | 2020-12-28 19:50 |  | 2021-01-12 10:00 | 2021-01-12 14:54 | 2020-12-31 09:39 | 2021-02-12 14:00 | CR0011895 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W2 | 2021-01 | 45 | 50 | 124.0023 | 5 | 1 | 1 | 0.02 | 153106 | 1.9 | 1 | 0 | 1 | 1 | 1 | 2 | 14 | 40 | 0.22951 | 0.4 | 2020-09 | 1 | 1
1266 | CR0011646 | CTASK0018571 | Closed | OPUS-BKG-M | Thien Lai | 22 | 22 | 2020-02-10 19:05 | 2020-01-30 19:05 | Container | Vessel Operation | Special Cargo |  |  |  | [Development] Enhance Booking and SCG modules to handle flexitank applications | 2019-12-10 14:36 | 2019-12-27 14:36 | 2019-12-27 08:54 | 2020-02-17 15:58 | 2020-02-17 17:25 |  | 2020-03-17 07:30 | 2020-03-17 07:30 | 2020-03-09 12:24 | 2020-04-16 13:00 | CR0011646 | Vessel OperationSpecial Cargo | OPUS-SCG | 2020-W12 | 2020-03 | 26 | 26 | 97.7041 | 2 | 1 | 1 | 0.01 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 25 | 0 | 0.52941 | 2019-12 | 0 | 0
1267 | CR0011646 | CTASK0018574 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-03-11 22:39 | 2020-03-09 15:39 | Container | Vessel Operation | Special Cargo |  |  |  | [Deployment] Enhance Booking and SCG modules to handle flexitank applications | 2019-12-10 14:36 | 2019-12-27 14:36 | 2019-12-27 08:54 | 2020-02-17 15:58 | 2020-02-17 17:25 |  | 2020-03-17 07:30 | 2020-03-17 07:30 | 2020-03-09 12:24 | 2020-04-16 13:00 | CR0011646 | Vessel OperationSpecial Cargo | OPUS-SCG | 2020-W12 | 2020-03 | 26 | 26 | 97.7041 | 2 | 1 | 1 | 0.01 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 25 | 0 | 0.52941 | 2019-12 | 0 | 0
1268 | CR0014016 | CTASK0027295 | Closed | OPUS-BKG-M | Kieu Le | 14 | 14 | 2021-07-21 13:41 | 2021-07-01 02:40 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] Asia - Opus_Portcast API Connection - Add "Revenue Lane" & "Trade" | 2021-06-28 11:16 | 2021-07-22 02:00 | 2021-07-15 10:49 | 2021-07-16 11:04 | 2021-07-16 11:17 |  | 2021-07-27 10:00 | 2021-07-27 09:15 | 2021-07-19 16:51 | 2021-08-03 14:00 | CR0014016 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W30 | 2021-07 | 24 | 26 | 28.9472 | 4 | 1 | 1 | 0.04 | 153106 | 2.7 | 3 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.22951 | 0.13043 | 2021-06 | 0 | 0
1269 | CR0014016 | CTASK0027298 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-07-30 13:45 | 2021-07-01 13:45 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] Asia - Opus_Portcast API Connection - Add "Revenue Lane" & "Trade" | 2021-06-28 11:16 | 2021-07-22 02:00 | 2021-07-15 10:49 | 2021-07-16 11:04 | 2021-07-16 11:17 |  | 2021-07-27 10:00 | 2021-07-27 09:15 | 2021-07-19 16:51 | 2021-08-03 14:00 | CR0014016 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W30 | 2021-07 | 24 | 26 | 28.9472 | 4 | 1 | 1 | 0.04 | 153106 | 2.7 | 3 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.22951 | 0.13043 | 2021-06 | 0 | 0
1270 | CR0014016 | CTASK0027292 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-06-04 13:37 | 2021-06-01 02:37 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design ]Asia - Opus_Portcast API Connection - Add "Revenue Lane" & "Trade" | 2021-06-28 11:16 | 2021-07-22 02:00 | 2021-07-15 10:49 | 2021-07-16 11:04 | 2021-07-16 11:17 |  | 2021-07-27 10:00 | 2021-07-27 09:15 | 2021-07-19 16:51 | 2021-08-03 14:00 | CR0014016 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W30 | 2021-07 | 24 | 26 | 28.9472 | 4 | 1 | 1 | 0.04 | 153106 | 2.7 | 3 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.22951 | 0.13043 | 2021-06 | 0 | 0
1271 | CR0014016 | CTASK0027294 | Closed | OPUS-BKG-M | Kieu Le | 6 | 8 | 2021-06-30 22:40 | 2021-06-28 02:39 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] Asia - Opus_Portcast API Connection - Add "Revenue Lane" & "Trade" | 2021-06-28 11:16 | 2021-07-22 02:00 | 2021-07-15 10:49 | 2021-07-16 11:04 | 2021-07-16 11:17 |  | 2021-07-27 10:00 | 2021-07-27 09:15 | 2021-07-19 16:51 | 2021-08-03 14:00 | CR0014016 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W30 | 2021-07 | 24 | 26 | 28.9472 | 4 | 1 | 1 | 0.04 | 153106 | 2.7 | 3 | 0 | 0 | 1 | 1 | 1 | 7 | 28 | 0.22951 | 0.13043 | 2021-06 | 0 | 0
1272 | CR0011472 | CTASK0015683 | Closed | OPUS-BKG-M | Thien Lai | 39 | 8 | 2019-10-04 14:58 | 2019-09-30 14:57 | Container | Service Management | Product Catalog | Block Stowage | Block Stowage Group Creation & Inquiry |  | NA * PRD * Add Effective Date Columns From & To in Block Stowage Group Creation & Inquiry | 2019-09-04 17:55 | 2019-11-05 | 2019-10-25 16:12 | 2019-11-22 04:32 | 2019-11-22 11:32 |  | 2019-12-03 09:30 | 2019-12-03 09:44 | 2019-12-03 04:55 | 2020-01-02 14:00 | CR0011472 | Service ManagementProduct CatalogBlock StowageBlock Stowage Group Creation & Inquiry | OPUS-BKG-M | 2019-W49 | 2019-12 | 39 | 16 | 89.6491 | 2 | 1 | 1 | 0.01 | 193567 | 0.1 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 18 | 0 | 0.52941 | 2019-09 | 0 | 0
1273 | CR0011472 | CTASK0016713 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2019-10-25 09:14 | 2019-10-14 09:14 | Container | Service Management | Product Catalog | Block Stowage | Block Stowage Group Creation & Inquiry |  | NA * PRD * Add Effective Date Columns From & To in Block Stowage Group Creation & Inquiry | 2019-09-04 17:55 | 2019-11-05 | 2019-10-25 16:12 | 2019-11-22 04:32 | 2019-11-22 11:32 |  | 2019-12-03 09:30 | 2019-12-03 09:44 | 2019-12-03 04:55 | 2020-01-02 14:00 | CR0011472 | Service ManagementProduct CatalogBlock StowageBlock Stowage Group Creation & Inquiry | OPUS-BKG-M | 2019-W49 | 2019-12 | 39 | 16 | 89.6491 | 2 | 1 | 1 | 0.01 | 193567 | 0.1 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 18 | 0 | 0.52941 | 2019-09 | 0 | 0
1274 | CR0013999 | CTASK0027267 | Closed | OPUS-SAR | Lien Le | 7 | 7 | 2021-06-30 15:20 | 2021-06-01 15:19 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Register Dispute |  | [Lien Le][June 2021][CR0013999][Asia *SAR* Register Dispute - Email notification] | 2021-06-08 17:45 | 2021-07-05 18:00 | 2021-06-09 09:26 | 2021-06-10 10:21 | 2021-06-10 10:50 |  | 2021-06-15 10:00 | 2021-06-15 11:00 | 2021-06-10 14:24 | 2021-06-28 10:43 | CR0013999 | Statement ManagementStatement Account ReceivableDispute ManagerRegister Dispute | OPUS-SAR | 2021-W24 | 2021-06 | 27 | 25 | 6.6768 | 2 | 2 | 2 | 0.16 | 193441 | 2.2 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.42308 | 0 | 2021-06 | 0 | 0
1275 | CR0013999 | CTASK0027268 | Closed | OPUS-SCO | Nguyen Ha Vi | 20 | 18 | 2021-06-30 15:23 | 2021-06-01 15:23 | Container | Statement Management | Statement Account Receivable | Dispute Manager | Register Dispute |  | [Vi Nguyen][June 2021][CR0013999][Asia *SAR* Register Dispute - Email notification] | 2021-06-08 17:45 | 2021-07-05 18:00 | 2021-06-09 09:26 | 2021-06-10 10:21 | 2021-06-10 10:50 |  | 2021-06-15 10:00 | 2021-06-15 11:00 | 2021-06-10 14:24 | 2021-06-28 10:43 | CR0013999 | Statement ManagementStatement Account ReceivableDispute ManagerRegister Dispute | OPUS-SCO | 2021-W24 | 2021-06 | 27 | 25 | 6.6768 | 2 | 2 | 2 | 0.16 | 203664 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 1.8182 | 2.5 | 2021-06 | 0 | 0
1276 | CR0012429 | CTASK0020158 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 16 | 16 | 2020-05-22 18:34 | 2020-05-18 14:01 | Container | Service Management | Booking/Documentation | Code | HTS (Harmonized Tariff Schedule) Code |  | [Development]Asia *DOC* - Submission of 8 digits HS code for shipment to UAE | 2020-05-13 07:58 | 2020-06-05 07:57 | 2020-06-02 11:01 | 2020-07-09 03:41 | 2020-07-28 11:00 |  | 2020-08-04 11:00 | 2020-08-11 10:02 | 2020-07-28 11:04 | 2020-08-28 16:01 | CR0012429 | Service ManagementBooking/DocumentationCodeHTS (Harmonized Tariff Schedule) Code | OPUS-BKG-EBKG | 2020-W32 | 2020-08 | 40 | 40 | 83.1268 | 5 | 1 | 1 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 2.1667 | 2020-05 | 0 | 0
1277 | CR0012429 | CTASK0020159 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 4 | 4 | 2020-06-01 18:37 | 2020-05-22 14:36 | Container | Service Management | Booking/Documentation | Code | HTS (Harmonized Tariff Schedule) Code |  | [Testing]Asia *DOC* - Submission of 8 digits HS code for shipment to UAE | 2020-05-13 07:58 | 2020-06-05 07:57 | 2020-06-02 11:01 | 2020-07-09 03:41 | 2020-07-28 11:00 |  | 2020-08-04 11:00 | 2020-08-11 10:02 | 2020-07-28 11:04 | 2020-08-28 16:01 | CR0012429 | Service ManagementBooking/DocumentationCodeHTS (Harmonized Tariff Schedule) Code | OPUS-BKG-EBKG | 2020-W32 | 2020-08 | 40 | 40 | 83.1268 | 5 | 1 | 1 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 2.1667 | 2020-05 | 0 | 0
1278 | CR0012429 | CTASK0020002 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 2 | 2 | 2020-05-19 15:46 | 2020-05-18 14:01 | Container | Service Management | Booking/Documentation | Code | HTS (Harmonized Tariff Schedule) Code |  | [Design]Asia *DOC* - Submission of 8 digits HS code for shipment to UAE | 2020-05-13 07:58 | 2020-06-05 07:57 | 2020-06-02 11:01 | 2020-07-09 03:41 | 2020-07-28 11:00 |  | 2020-08-04 11:00 | 2020-08-11 10:02 | 2020-07-28 11:04 | 2020-08-28 16:01 | CR0012429 | Service ManagementBooking/DocumentationCodeHTS (Harmonized Tariff Schedule) Code | OPUS-BKG-EBKG | 2020-W32 | 2020-08 | 40 | 40 | 83.1268 | 5 | 1 | 1 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 2.1667 | 2020-05 | 0 | 0
1279 | CR0012429 | CTASK0021173 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 16 | 16 | 2020-07-14 18:37 | 2020-07-10 17:37 | Container | Service Management | Booking/Documentation | Code | HTS (Harmonized Tariff Schedule) Code |  | Asia *DOC* - Submission of 8 digits HS code for shipment to UAE | 2020-05-13 07:58 | 2020-06-05 07:57 | 2020-06-02 11:01 | 2020-07-09 03:41 | 2020-07-28 11:00 |  | 2020-08-04 11:00 | 2020-08-11 10:02 | 2020-07-28 11:04 | 2020-08-28 16:01 | CR0012429 | Service ManagementBooking/DocumentationCodeHTS (Harmonized Tariff Schedule) Code | OPUS-BKG-EBKG | 2020-W32 | 2020-08 | 40 | 40 | 83.1268 | 5 | 1 | 1 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 2.1667 | 2020-05 | 0 | 0
1280 | CR0012429 | CTASK0020160 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 2 | 2 | 2020-07-30 18:57 | 2020-07-29 13:57 | Container | Service Management | Booking/Documentation | Code | HTS (Harmonized Tariff Schedule) Code |  | [Deployment]Asia *DOC* - Submission of 8 digits HS code for shipment to UAE | 2020-05-13 07:58 | 2020-06-05 07:57 | 2020-06-02 11:01 | 2020-07-09 03:41 | 2020-07-28 11:00 |  | 2020-08-04 11:00 | 2020-08-11 10:02 | 2020-07-28 11:04 | 2020-08-28 16:01 | CR0012429 | Service ManagementBooking/DocumentationCodeHTS (Harmonized Tariff Schedule) Code | OPUS-BKG-EBKG | 2020-W32 | 2020-08 | 40 | 40 | 83.1268 | 5 | 1 | 1 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 2.1667 | 2020-05 | 0 | 0
1281 | CR0012588 | CTASK0020982 | Closed | OPUS-CTM | Tran Le | 167 | 226 |  |  | Container | Service Management | CNTR Movement |  |  |  | CTM to pass events validation for cross boarder locations based on CTM exception UI set up | 2020-07-06 10:50 | 2020-09-30 | 2020-09-29 14:52 | 2020-11-25 14:12 | 2020-12-09 19:32 |  | 2020-12-22 11:00 | 2020-12-22 10:00 | 2020-12-10 14:59 | 2021-01-21 14:00 | CR0012588 | Service ManagementCNTR Movement | OPUS-CTM | 2020-W52 | 2020-12 | 242 | 326 | 169.0068 | 3 | 2 | 2 | 0.08 | 193501 | 0.7 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 30 | 0 | 0 | 2020-07 | 0 | 0
1282 | CR0012588 | CTASK0022481 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 15 | 15 | 2020-12-22 02:00 | 2020-12-15 10:30 | Container | Service Management | CNTR Movement |  |  |  | [Deployment] CTM to pass events validation for cross boarder locations based on CTM exception UI set up | 2020-07-06 10:50 | 2020-09-30 | 2020-09-29 14:52 | 2020-11-25 14:12 | 2020-12-09 19:32 |  | 2020-12-22 11:00 | 2020-12-22 10:00 | 2020-12-10 14:59 | 2021-01-21 14:00 | CR0012588 | Service ManagementCNTR Movement | OPUS-CTM | 2020-W52 | 2020-12 | 242 | 326 | 169.0068 | 3 | 2 | 2 | 0.08 | 193470 | 1.3 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 30 | 0 | 0.17391 | 2020-07 | 0 | 0
1283 | CR0012588 | CTASK0021234 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 60 | 85 | 2020-09-25 19:30 | 2020-07-13 10:30 | Container | Service Management | CNTR Movement |  |  |  | [Development + Testing] CTM to pass events validation for cross boarder locations based on CTM exception UI set up | 2020-07-06 10:50 | 2020-09-30 | 2020-09-29 14:52 | 2020-11-25 14:12 | 2020-12-09 19:32 |  | 2020-12-22 11:00 | 2020-12-22 10:00 | 2020-12-10 14:59 | 2021-01-21 14:00 | CR0012588 | Service ManagementCNTR Movement | OPUS-CTM | 2020-W52 | 2020-12 | 242 | 326 | 169.0068 | 3 | 2 | 2 | 0.08 | 193470 | 1.3 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 30 | 0 | 0.17391 | 2020-07 | 0 | 0
1284 | CR0013186 | CTASK0023071 | Closed | OPUS-SCE | VInh Bui | 20 | 20 | 2020-10-31 18:26 | 2020-10-01 18:26 | Container | Service Management | SCEM | Visibility | Customer EDI Monitoring |  | [Internal] Trigger retroactive cargo tracking EDIs after customer information update | 2020-11-06 16:03 | 2020-11-10 16:02 | 2020-11-06 16:03 | 2021-04-28 16:30 | 2021-05-06 16:44 |  | 2021-05-18 11:00 | 2021-05-18 09:00 | 2021-05-07 09:05 | 2021-06-17 14:00 | CR0013186 | Service ManagementSCEMVisibilityCustomer EDI Monitoring | OPUS-SCE | 2021-W20 | 2021-05 | 21 | 20 | 192.7899 | 2 | 1 | 1 | 0 | 193469 | 1.1 | 0 | 0 | 0 | 1 | 1 | 3 | 10 | 28 | 0 | 0 | 2020-11 | 0 | 0
1285 | CR0013186 | CTASK0023057 | Closed | OPUS-SCE | VInh Bui | 1 | 1 |  |  | Container | Service Management | SCEM | Visibility | Customer EDI Monitoring |  | [Documentation][Internal] Trigger retroactive cargo tracking EDIs after customer information update | 2020-11-06 16:03 | 2020-11-10 16:02 | 2020-11-06 16:03 | 2021-04-28 16:30 | 2021-05-06 16:44 |  | 2021-05-18 11:00 | 2021-05-18 09:00 | 2021-05-07 09:05 | 2021-06-17 14:00 | CR0013186 | Service ManagementSCEMVisibilityCustomer EDI Monitoring | OPUS-SCE | 2021-W20 | 2021-05 | 21 | 20 | 192.7899 | 2 | 1 | 1 | 0 | 193469 | 1.1 | 0 | 0 | 0 | 1 | 1 | 3 | 10 | 28 | 0 | 0 | 2020-11 | 0 | 0
1286 | CR0013443 | CTASK0024600 | Closed | OPUS-ACM | Huynh Tuan Khanh | 20 | 20 | 2021-02-26 09:35 | 2021-01-04 09:35 | Container | Biz Common | Master Data | Partner | Customer Integration |  | Asia *MDA* Customer Integration allow user to input GST for NP & BT customer (SR0117320) | 2021-01-12 10:30 | 2021-02-05 10:30 | 2021-01-29 10:45 | 2021-02-02 11:13 | 2021-02-02 13:20 |  | 2021-02-09 13:20 | 2021-02-09 15:21 | 2021-02-02 16:18 | 2021-02-25 12:48 | CR0013443 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2021-W6 | 2021-02 | 40 | 40 | 28.1184 | 2 | 2 | 2 | 0.06 | 193499 | 1.6 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0 | 0 | 2021-01 | 0 | 0
1287 | CR0013443 | CTASK0024603 | Closed | OPUS-MDA | Toai Phan | 20 | 20 | 2021-01-22 10:38 | 2021-01-12 10:38 | Container | Biz Common | Master Data | Partner | Customer Integration |  | Asia *MDA* Customer Integration allow user to input GST for NP & BT customer (SR0117320) | 2021-01-12 10:30 | 2021-02-05 10:30 | 2021-01-29 10:45 | 2021-02-02 11:13 | 2021-02-02 13:20 |  | 2021-02-09 13:20 | 2021-02-09 15:21 | 2021-02-02 16:18 | 2021-02-25 12:48 | CR0013443 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2021-W6 | 2021-02 | 40 | 40 | 28.1184 | 2 | 2 | 2 | 0.06 | 183427 | 2.1 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0.44444 | 0 | 2021-01 | 0 | 0
1288 | CR0013831 | CTASK0026691 | Closed | OPUS-BKG-M | Thien Lai | 12 | 12 | 2021-05-28 18:23 | 2021-05-18 18:23 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] DG Mini popup enhancement | 2021-05-18 14:34 | 2021-06-17 | 2021-06-08 14:17 | 2021-06-09 14:15 | 2021-06-09 14:43 |  | 2021-06-22 10:00 | 2021-06-22 10:00 | 2021-06-09 16:40 | 2021-07-22 14:00 | CR0013831 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W25 | 2021-06 | 56 | 56 | 34.8099 | 4 | 1 | 1 | 0.07 | 193567 | 1.8 | 1 | 0 | 2 | 1 | 1 | 1 | 11 | 53 | 0.5625 | 0.53333 | 2021-05 | 2 | 1
1289 | CR0013831 | CTASK0026470 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-04-23 17:48 | 2021-04-12 17:48 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] DG Mini popup enhancement | 2021-05-18 14:34 | 2021-06-17 | 2021-06-08 14:17 | 2021-06-09 14:15 | 2021-06-09 14:43 |  | 2021-06-22 10:00 | 2021-06-22 10:00 | 2021-06-09 16:40 | 2021-07-22 14:00 | CR0013831 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W25 | 2021-06 | 56 | 56 | 34.8099 | 4 | 1 | 1 | 0.07 | 193567 | 1.8 | 1 | 0 | 2 | 1 | 1 | 1 | 11 | 53 | 0.5625 | 0.53333 | 2021-05 | 2 | 1
1290 | CR0013831 | CTASK0026692 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2021-06-18 18:23 | 2021-06-07 18:23 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] DG Mini popup enhancement | 2021-05-18 14:34 | 2021-06-17 | 2021-06-08 14:17 | 2021-06-09 14:15 | 2021-06-09 14:43 |  | 2021-06-22 10:00 | 2021-06-22 10:00 | 2021-06-09 16:40 | 2021-07-22 14:00 | CR0013831 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W25 | 2021-06 | 56 | 56 | 34.8099 | 4 | 1 | 1 | 0.07 | 193567 | 1.8 | 1 | 0 | 2 | 1 | 1 | 1 | 11 | 53 | 0.5625 | 0.53333 | 2021-05 | 2 | 1
1291 | CR0013831 | CTASK0026689 | Closed | OPUS-BKG-M | Thien Lai | 24 | 24 | 2021-05-28 18:23 | 2021-05-18 18:23 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] DG Mini popup enhancement | 2021-05-18 14:34 | 2021-06-17 | 2021-06-08 14:17 | 2021-06-09 14:15 | 2021-06-09 14:43 |  | 2021-06-22 10:00 | 2021-06-22 10:00 | 2021-06-09 16:40 | 2021-07-22 14:00 | CR0013831 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W25 | 2021-06 | 56 | 56 | 34.8099 | 4 | 1 | 1 | 0.07 | 193567 | 1.8 | 1 | 0 | 2 | 1 | 1 | 1 | 11 | 53 | 0.5625 | 0.53333 | 2021-05 | 2 | 1
1292 | CR0011609 | CTASK0021098 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2020-08-01 02:00 | 2020-07-23 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] (HBU) EUA CUST - Request to show information in e-SI I/Opus Danger tab to be added to the e-SI Instruction preview PDF | 2020-06-03 10:17 | 2020-08-01 | 2020-07-31 15:50 | 2021-01-25 17:01 | 2021-02-04 11:01 |  | 2021-03-02 11:00 | 2021-03-02 10:00 | 2021-02-09 13:05 | 2021-03-02 21:07 | CR0011609 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W9 | 2021-03 | 118 | 98 | 272.0302 | 4 | 2 | 1 | 0.02 | 193525 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 13 | 46 | 0.41667 | 0.47368 | 2020-06 | 0 | 0
1293 | CR0011609 | CTASK0021100 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-02-27 02:00 | 2021-02-22 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] (HBU) EUA CUST - Request to show information in e-SI I/Opus Danger tab to be added to the e-SI Instruction preview PDF | 2020-06-03 10:17 | 2020-08-01 | 2020-07-31 15:50 | 2021-01-25 17:01 | 2021-02-04 11:01 |  | 2021-03-02 11:00 | 2021-03-02 10:00 | 2021-02-09 13:05 | 2021-03-02 21:07 | CR0011609 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W9 | 2021-03 | 118 | 98 | 272.0302 | 4 | 2 | 1 | 0.02 | 193525 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 13 | 46 | 0.41667 | 0.47368 | 2020-06 | 0 | 0
1294 | CR0011609 | CTASK0017767 | Closed | OPUS-BKG-M | Vinh Tran | 20 | 20 | 2020-01-14 02:00 | 2020-01-07 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Estimate] //Request to show information in e-SI I/Opus Danger tab to be added to the e-SI Instruction preview PDF | 2020-06-03 10:17 | 2020-08-01 | 2020-07-31 15:50 | 2021-01-25 17:01 | 2021-02-04 11:01 |  | 2021-03-02 11:00 | 2021-03-02 10:00 | 2021-02-09 13:05 | 2021-03-02 21:07 | CR0011609 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W9 | 2021-03 | 118 | 98 | 272.0302 | 4 | 2 | 1 | 0.02 | 193525 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 13 | 46 | 0.41667 | 0.47368 | 2020-06 | 0 | 0
1295 | CR0011609 | CTASK0017988 | Closed | OPUS-BKG-EBKG | Vinh Tran | 90 | 90 | 2020-07-25 02:00 | 2020-07-07 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] (HBU) EUA CUST - Request to show information in e-SI I/Opus Danger tab to be added to the e-SI Instruction preview PDF | 2020-06-03 10:17 | 2020-08-01 | 2020-07-31 15:50 | 2021-01-25 17:01 | 2021-02-04 11:01 |  | 2021-03-02 11:00 | 2021-03-02 10:00 | 2021-02-09 13:05 | 2021-03-02 21:07 | CR0011609 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W9 | 2021-03 | 118 | 98 | 272.0302 | 4 | 2 | 1 | 0.02 | 193525 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 13 | 46 | 0.41667 | 0.47368 | 2020-06 | 0 | 0
1296 | CR0013820 | CTASK0027423 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 4 | 8 | 2021-06-30 19:58 | 2021-06-01 19:57 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Fixbug] [CLT Internal] Literal SQL Tuning on Container Loading/Discharging List | 2021-04-20 10:49 | 2021-05-13 | 2021-05-12 11:14 | 2021-05-18 17:49 | 2021-06-18 13:32 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-18 16:11 | 2021-07-29 14:00 | CR0013820 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 52 | 56 | 69.9663 | 4 | 2 | 2 | 0.03 | 193606 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 4.25 | 2.25 | 2021-04 | 0 | 0
1297 | CR0013820 | CTASK0026314 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 16 | 16 | 2021-05-31 02:00 | 2021-05-03 02:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Test][CLT Internal] Literal SQL Tuning on Container Loading/Discharging List | 2021-04-20 10:49 | 2021-05-13 | 2021-05-12 11:14 | 2021-05-18 17:49 | 2021-06-18 13:32 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-18 16:11 | 2021-07-29 14:00 | CR0013820 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 52 | 56 | 69.9663 | 4 | 2 | 2 | 0.03 | 193506 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 1.1212 | 1.25 | 2021-04 | 0 | 0
1298 | CR0013820 | CTASK0026312 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 4 | 4 | 2021-04-07 02:00 | 2021-04-07 02:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Est][CLT Internal] Literal SQL Tuning on Container Loading/Discharging List | 2021-04-20 10:49 | 2021-05-13 | 2021-05-12 11:14 | 2021-05-18 17:49 | 2021-06-18 13:32 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-18 16:11 | 2021-07-29 14:00 | CR0013820 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 52 | 56 | 69.9663 | 4 | 2 | 2 | 0.03 | 193506 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 1.1212 | 1.25 | 2021-04 | 0 | 0
1299 | CR0013820 | CTASK0026313 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 28 | 28 | 2021-05-31 02:00 | 2021-05-03 02:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Dev-Deploy][CLT Internal] Literal SQL Tuning on Container Loading/Discharging List | 2021-04-20 10:49 | 2021-05-13 | 2021-05-12 11:14 | 2021-05-18 17:49 | 2021-06-18 13:32 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-18 16:11 | 2021-07-29 14:00 | CR0013820 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 52 | 56 | 69.9663 | 4 | 2 | 2 | 0.03 | 193506 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 1.1212 | 1.25 | 2021-04 | 0 | 0
1300 | CR0011748 | CTASK0016588 | Closed | OPUS-BKG-M | Thien Lai | 94 | 84 | 2019-11-08 15:19 | 2019-10-21 15:18 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | eCommerce & OPUS eBook to automatically auto populate the booking data from ONE eCommerce to OPUS Booking Creation bypass the need to click "Upload" button in the OPUS eBook & eSI screen | 2019-10-15 14:00 | 2020-02-11 | 2020-02-10 17:16 | 2020-06-19 17:52 | 2020-06-23 10:33 | 2020-02-10 17:17 | 2020-06-30 10:00 | 2020-06-30 10:11 | 2020-06-26 09:43 | 2020-07-30 13:00 | CR0011748 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 94 | 84 | 258.8336 | 1 | 1 | 1 | 0.01 | 193567 | 0.2 | 0 | 0 | 1 | 1 | 1 | 3 | 8 | 29 | 0 | 0.52941 | 2019-10 | 1 | 1
1301 | CR0012725 | CTASK0020577 | Closed | OPUS-FLT | Hieu Vu | 10 | 10 | 2020-06-30 18:00 | 2020-06-11 09:00 | Container | Support & Admin | Fleet Management |  |  |  | [FLT-CLV] New GL Account Mapping for the Monthly Reversal of CAPEX Portion of Off-Hire | 2020-06-18 17:37 | 2020-06-30 18:00 | 2020-06-24 10:03 | 2020-06-24 20:50 | 2020-06-25 14:46 |  | 2020-06-30 10:00 | 2020-06-30 10:00 | 2020-06-25 18:33 | 2020-07-31 13:00 | CR0012725 | Support & AdminFleet Management | OPUS-FLT | 2020-W27 | 2020-06 | 10 | 10 | 11.6829 | 1 | 1 | 1 | 0.04 | 183375 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 29 | 0 | 0.125 | 2020-06 | 0 | 0
1302 | CR0011112 | CTASK0018956 | Closed | OPUS-PRI | Ngan Nham | 267 | 130 | 2020-05-30 14:36 | 2020-03-02 14:36 | Container | Sales Management | Pricing |  |  |  | [Development]EAS - Add <IMDG Class/UN No./PSA Group> conditions in PRI/DMT modules | 2020-03-19 14:06 | 2020-05-08 14:05 | 2020-05-08 13:30 | 2020-08-14 14:15 | 2020-08-14 15:19 |  | 2020-08-25 15:19 | 2020-08-20 10:15 | 2020-08-14 15:24 | 2020-09-19 13:00 | CR0011112 | Sales ManagementPricing | OPUS-PRI | 2020-W35 | 2020-08 | 267 | 190 | 159.051 | 2 | 1 | 2 | 0.05 | 193461 | 1.3 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 30 | 0 | 0.28571 | 2020-03 | 0 | 0
1303 | CR0011112 | CTASK0018957 | Closed | OPUS-PRI | Man Hoang | 60 | 60 |  |  | Container | Sales Management | Pricing |  |  |  | [Development]EAS - Add <IMDG Class/UN No./PSA Group> conditions in PRI/DMT modules | 2020-03-19 14:06 | 2020-05-08 14:05 | 2020-05-08 13:30 | 2020-08-14 14:15 | 2020-08-14 15:19 |  | 2020-08-25 15:19 | 2020-08-20 10:15 | 2020-08-14 15:24 | 2020-09-19 13:00 | CR0011112 | Sales ManagementPricing | OPUS-PRI | 2020-W35 | 2020-08 | 267 | 190 | 159.051 | 2 | 1 | 2 | 0.05 | 183431 | 1.3 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 30 | 0 | 0.66667 | 2020-03 | 0 | 0
1304 | CR0013447 | CTASK0025302 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-06-11 13:51 | 2021-06-08 13:51 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment]Change the logic of sending Booking Confirmation EDI (IFTMBC) to Ship agent | 2021-02-22 09:59 | 2021-03-25 02:00 | 2021-03-24 18:04 | 2021-05-24 17:43 | 2021-06-08 17:39 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-09 13:42 | 2021-07-16 14:00 | CR0013447 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 63 | 57 | 113.0008 | 4 | 1 | 1 | 0.02 | 193503 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.33333 | 0.28571 | 2021-02 | 0 | 0
1305 | CR0013447 | CTASK0025300 | Closed | OPUS-BKG-M | Loc Tran | 15 | 15 | 2021-03-31 16:36 | 2021-03-01 16:36 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing]Change the logic of sending Booking Confirmation EDI (IFTMBC) to Ship agent | 2021-02-22 09:59 | 2021-03-25 02:00 | 2021-03-24 18:04 | 2021-05-24 17:43 | 2021-06-08 17:39 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-09 13:42 | 2021-07-16 14:00 | CR0013447 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 63 | 57 | 113.0008 | 4 | 1 | 1 | 0.02 | 193503 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.33333 | 0.28571 | 2021-02 | 0 | 0
1306 | CR0013447 | CTASK0025297 | Closed | OPUS-BKG-M | Loc Tran | 32 | 30 | 2021-02-28 12:42 | 2021-02-18 12:42 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development]Change the logic of sending Booking Confirmation EDI (IFTMBC) to Ship agent | 2021-02-22 09:59 | 2021-03-25 02:00 | 2021-03-24 18:04 | 2021-05-24 17:43 | 2021-06-08 17:39 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-09 13:42 | 2021-07-16 14:00 | CR0013447 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 63 | 57 | 113.0008 | 4 | 1 | 1 | 0.02 | 193503 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.33333 | 0.28571 | 2021-02 | 0 | 0
1307 | CR0013447 | CTASK0025190 | Closed | OPUS-BKG-M | Loc Tran | 12 | 8 | 2021-02-28 12:43 | 2021-02-04 12:43 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] CR0013447 - Change the logic of sending Booking Confirmation EDI (IFTMBC) to Ship agent | 2021-02-22 09:59 | 2021-03-25 02:00 | 2021-03-24 18:04 | 2021-05-24 17:43 | 2021-06-08 17:39 |  | 2021-06-15 10:00 | 2021-06-15 10:00 | 2021-06-09 13:42 | 2021-07-16 14:00 | CR0013447 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 63 | 57 | 113.0008 | 4 | 1 | 1 | 0.02 | 193503 | 1.6 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.33333 | 0.28571 | 2021-02 | 0 | 0
1308 | CR0012952 | CTASK0022512 | Closed | OPUS-BKG-EBKG | Vinh Tran | 6 | 6 | 2020-12-02 02:00 | 2020-12-01 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment][CLT Internal] e-Booking Auto upload success check logic supplement | 2020-09-15 23:21 | 2020-09-25 | 2020-09-24 18:43 | 2020-10-15 17:09 | 2020-10-26 10:23 |  | 2020-11-17 11:00 | 2020-11-17 09:30 | 2020-10-26 10:29 | 2020-12-18 14:00 | CR0012952 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W47 | 2020-11 | 34 | 40 | 62.4851 | 3 | 1 | 1 | 0.03 | 193525 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.47368 | 2020-09 | 0 | 0
1309 | CR0012952 | CTASK0022036 | Closed | OPUS-BKG-EBKG | Vinh Tran | 18 | 18 | 2020-09-19 02:00 | 2020-09-11 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Develoment/Test][CLT Internal] e-Booking Auto upload success check logic supplement | 2020-09-15 23:21 | 2020-09-25 | 2020-09-24 18:43 | 2020-10-15 17:09 | 2020-10-26 10:23 |  | 2020-11-17 11:00 | 2020-11-17 09:30 | 2020-10-26 10:29 | 2020-12-18 14:00 | CR0012952 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W47 | 2020-11 | 34 | 40 | 62.4851 | 3 | 1 | 1 | 0.03 | 193525 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.47368 | 2020-09 | 0 | 0
1310 | CR0012952 | CTASK0022009 | Closed | OPUS-BKG-EBKG | Vinh Tran | 16 | 16 | 2020-08-27 02:00 | 2020-08-20 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] [CLT Internal] e-Booking Auto upload success check logic supplement | 2020-09-15 23:21 | 2020-09-25 | 2020-09-24 18:43 | 2020-10-15 17:09 | 2020-10-26 10:23 |  | 2020-11-17 11:00 | 2020-11-17 09:30 | 2020-10-26 10:29 | 2020-12-18 14:00 | CR0012952 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W47 | 2020-11 | 34 | 40 | 62.4851 | 3 | 1 | 1 | 0.03 | 193525 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0.47368 | 2020-09 | 0 | 0
1311 | CR0012059 | CTASK0020453 | Closed | OPUS-BKG-CLLCDL | Thuc Tran | 6 | 8 | 2020-06-03 19:30 | 2020-06-02 11:00 | Container | Equipment Management | EQ Reposition |  |  |  | [Estimation] GHQ - EQR Volume update discrepancy | 2020-08-18 15:14 | 2020-09-11 23:00 | 2020-09-11 15:46 | 2020-11-10 10:52 | 2020-11-19 14:27 |  | 2021-03-23 10:30 | 2021-03-23 10:00 | 2020-12-02 10:07 | 2021-04-22 14:00 | CR0012059 | Equipment ManagementEQ Reposition | OPUS-EQR | 2021-W12 | 2021-03 | 107 | 107 | 216.8026 | 5 | 3 | 3 | 0.02 | 173280 | 1.7 | 1 | 0 | 0 | 2 | 1 | 3 | 6 | 46 | 0.375 | 0.18519 | 2020-08 | 0 | 0
1312 | CR0012059 | CTASK0020782 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 36 | 36 | 2020-09-01 09:00 | 2020-08-02 09:00 | Container | Equipment Management | EQ Reposition |  |  |  | [Development+Test+Deployment] GHQ - EQR Volume update discrepancy | 2020-08-18 15:14 | 2020-09-11 23:00 | 2020-09-11 15:46 | 2020-11-10 10:52 | 2020-11-19 14:27 |  | 2021-03-23 10:30 | 2021-03-23 10:00 | 2020-12-02 10:07 | 2021-04-22 14:00 | CR0012059 | Equipment ManagementEQ Reposition | OPUS-EQR | 2021-W12 | 2021-03 | 107 | 107 | 216.8026 | 5 | 3 | 3 | 0.02 | 193506 | 1.2 | 1 | 0 | 0 | 2 | 1 | 3 | 6 | 46 | 1.1212 | 1.25 | 2020-08 | 0 | 0
1313 | CR0012059 | CTASK0024144 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 1 | 1 | 2020-12-08 02:00 | 2020-12-08 02:00 | Container | Equipment Management | EQ Reposition |  |  |  | [Deployment]GHQ - EQR Volume update discrepancy | 2020-08-18 15:14 | 2020-09-11 23:00 | 2020-09-11 15:46 | 2020-11-10 10:52 | 2020-11-19 14:27 |  | 2021-03-23 10:30 | 2021-03-23 10:00 | 2020-12-02 10:07 | 2021-04-22 14:00 | CR0012059 | Equipment ManagementEQ Reposition | OPUS-EQR | 2021-W12 | 2021-03 | 107 | 107 | 216.8026 | 5 | 3 | 3 | 0.02 | 193506 | 1.2 | 1 | 0 | 0 | 2 | 1 | 3 | 6 | 46 | 1.1212 | 1.25 | 2020-08 | 0 | 0
1314 | CR0012059 | CTASK0025798 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 2 | 2 | 2021-03-23 02:00 | 2021-03-10 02:00 | Container | Equipment Management | EQ Reposition |  |  |  | [Deploy-Test]GHQ - EQR Volume update discrepancy | 2020-08-18 15:14 | 2020-09-11 23:00 | 2020-09-11 15:46 | 2020-11-10 10:52 | 2020-11-19 14:27 |  | 2021-03-23 10:30 | 2021-03-23 10:00 | 2020-12-02 10:07 | 2021-04-22 14:00 | CR0012059 | Equipment ManagementEQ Reposition | OPUS-EQR | 2021-W12 | 2021-03 | 107 | 107 | 216.8026 | 5 | 3 | 3 | 0.02 | 193506 | 1.2 | 1 | 0 | 0 | 2 | 1 | 3 | 6 | 46 | 1.1212 | 1.25 | 2020-08 | 0 | 0
1315 | CR0012059 | CTASK0020783 | Closed | OPUS-BKG-RPT | Nam Nguyen | 62 | 60 | 2020-08-30 | 2020-08-09 09:00 | Container | Equipment Management | EQ Reposition |  |  |  | [Development+Test+Deployment] GHQ - EQR Volume update discrepancy | 2020-08-18 15:14 | 2020-09-11 23:00 | 2020-09-11 15:46 | 2020-11-10 10:52 | 2020-11-19 14:27 |  | 2021-03-23 10:30 | 2021-03-23 10:00 | 2020-12-02 10:07 | 2021-04-22 14:00 | CR0012059 | Equipment ManagementEQ Reposition | OPUS-EQR | 2021-W12 | 2021-03 | 107 | 107 | 216.8026 | 5 | 3 | 3 | 0.02 | 123048 | 1.9 | 1 | 0 | 0 | 2 | 1 | 3 | 6 | 46 | 0.22222 | 0.46154 | 2020-08 | 0 | 0
1316 | CR0013579 | CTASK0025382 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-03-31 18:14 | 2021-03-01 18:14 | Container | Service Management | Booking/Documentation | Booking |  |  | [Deployment] Booking Main Reference No. "Regional BKG No." | 2021-02-22 11:47 | 2021-02-27 02:00 | 2021-02-25 11:45 | 2021-03-03 16:59 | 2021-03-05 13:20 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-03-05 14:32 | 2021-03-09 12:32 | CR0013579 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W10 | 2021-03 | 52 | 52 | 14.9254 | 4 | 1 | 1 | 0.15 | 193567 | 1.6 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 46 | 0 | 0.53333 | 2021-02 | 0 | 0
1317 | CR0013579 | CTASK0025380 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-02-28 18:14 | 2021-02-17 18:14 | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing] Booking Main Reference No. "Regional BKG No." | 2021-02-22 11:47 | 2021-02-27 02:00 | 2021-02-25 11:45 | 2021-03-03 16:59 | 2021-03-05 13:20 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-03-05 14:32 | 2021-03-09 12:32 | CR0013579 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W10 | 2021-03 | 52 | 52 | 14.9254 | 4 | 1 | 1 | 0.15 | 193567 | 1.6 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 46 | 0 | 0.53333 | 2021-02 | 0 | 0
1318 | CR0013579 | CTASK0025143 | Closed | OPUS-BKG-M | Thien Lai | 12 | 12 | 2021-02-05 16:29 | 2021-02-01 16:29 | Container | Service Management | Booking/Documentation | Booking |  |  | [Design] Booking Main Reference No. "Regional BKG No." | 2021-02-22 11:47 | 2021-02-27 02:00 | 2021-02-25 11:45 | 2021-03-03 16:59 | 2021-03-05 13:20 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-03-05 14:32 | 2021-03-09 12:32 | CR0013579 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W10 | 2021-03 | 52 | 52 | 14.9254 | 4 | 1 | 1 | 0.15 | 193567 | 1.6 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 46 | 0 | 0.53333 | 2021-02 | 0 | 0
1319 | CR0013579 | CTASK0025378 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-02-28 18:14 | 2021-02-17 18:14 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development] Booking Main Reference No. "Regional BKG No." | 2021-02-22 11:47 | 2021-02-27 02:00 | 2021-02-25 11:45 | 2021-03-03 16:59 | 2021-03-05 13:20 |  | 2021-03-09 10:00 | 2021-03-09 10:00 | 2021-03-05 14:32 | 2021-03-09 12:32 | CR0013579 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W10 | 2021-03 | 52 | 52 | 14.9254 | 4 | 1 | 1 | 0.15 | 193567 | 1.6 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 46 | 0 | 0.53333 | 2021-02 | 0 | 0
1320 | CR0010951 | CTASK0019139 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 12 | 12 | 2020-03-24 18:00 | 2020-03-23 10:30 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Analysis] (SvEG) EUA EDI VEND : COPRAR transmission history screen including APERAK function | 2020-04-01 14:40 | 2020-07-28 14:39 | 2020-06-30 13:18 | 2020-10-01 11:09 | 2020-10-14 11:15 |  | 2020-10-27 10:15 | 2020-10-27 10:24 | 2020-10-16 10:50 | 2020-11-05 23:36 | CR0010951 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W44 | 2020-10 | 95 | 112 | 208.8154 | 4 | 1 | 1 | 0.02 | 193470 | 1 | 0 | 0 | 0 | 2 | 1 | 3 | 7 | 20 | 0 | 0.17391 | 2020-04 | 0 | 0
1321 | CR0010951 | CTASK0019220 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 56 | 66 | 2020-05-15 19:30 | 2020-04-06 10:30 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [DEVELOPMENT] (SvEG) EUA EDI VEND : COPRAR transmission history screen including APERAK function | 2020-04-01 14:40 | 2020-07-28 14:39 | 2020-06-30 13:18 | 2020-10-01 11:09 | 2020-10-14 11:15 |  | 2020-10-27 10:15 | 2020-10-27 10:24 | 2020-10-16 10:50 | 2020-11-05 23:36 | CR0010951 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W44 | 2020-10 | 95 | 112 | 208.8154 | 4 | 1 | 1 | 0.02 | 193470 | 1 | 0 | 0 | 0 | 2 | 1 | 3 | 7 | 20 | 0 | 0.17391 | 2020-04 | 0 | 0
1322 | CR0010951 | CTASK0019221 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 17 | 24 | 2020-05-29 19:30 | 2020-05-14 10:30 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [TEST] (SvEG) EUA EDI VEND : COPRAR transmission history screen including APERAK function | 2020-04-01 14:40 | 2020-07-28 14:39 | 2020-06-30 13:18 | 2020-10-01 11:09 | 2020-10-14 11:15 |  | 2020-10-27 10:15 | 2020-10-27 10:24 | 2020-10-16 10:50 | 2020-11-05 23:36 | CR0010951 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W44 | 2020-10 | 95 | 112 | 208.8154 | 4 | 1 | 1 | 0.02 | 193470 | 1 | 0 | 0 | 0 | 2 | 1 | 3 | 7 | 20 | 0 | 0.17391 | 2020-04 | 0 | 0
1323 | CR0010951 | CTASK0019222 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 10 | 10 | 2020-10-27 01:00 | 2020-10-15 10:30 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [DEPLOYMENT] (SvEG) EUA EDI VEND : COPRAR transmission history screen including APERAK function | 2020-04-01 14:40 | 2020-07-28 14:39 | 2020-06-30 13:18 | 2020-10-01 11:09 | 2020-10-14 11:15 |  | 2020-10-27 10:15 | 2020-10-27 10:24 | 2020-10-16 10:50 | 2020-11-05 23:36 | CR0010951 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W44 | 2020-10 | 95 | 112 | 208.8154 | 4 | 1 | 1 | 0.02 | 193470 | 1 | 0 | 0 | 0 | 2 | 1 | 3 | 7 | 20 | 0 | 0.17391 | 2020-04 | 0 | 0
1324 | CR0011123 | CTASK0015288 | Closed | OPUS-EQR | Tuyen Truong | 17 | 40 | 2019-11-29 23:00 | 2019-11-25 09:00 | Container | Equipment Management | EQ Reposition | Exec Plan |  |  | Change logic to pick up EQR POD ATA information accurately | 2019-11-29 09:35 | 2019-11-29 23:00 | 2019-11-29 10:25 | 2019-12-18 17:29 | 2019-12-23 19:20 |  | 2019-12-26 10:30 | 2019-12-26 10:00 | 2020-01-05 14:38 | 2020-01-08 12:41 | CR0011123 | Equipment ManagementEQ RepositionExec Plan | OPUS-EQR | 2019-W52 | 2019-12 | 17 | 40 | 27.0385 | 1 | 1 | 1 | 0.06 | 173255 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 18 | 0 | 0 | 2019-11 | 0 | 0
1325 | CR0013616 | CTASK0025348 | Closed | OPUS-BKG-OB | Nam Nguyen | 23 | 30 | 2021-03-26 15:42 | 2021-02-19 15:42 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [BKG-OB] [CLT-Internal] This CR is to display BL properly as user's requested on specific case | 2021-03-12 10:10 | 2021-05-07 10:10 | 2021-05-04 13:56 | 2021-06-03 10:57 | 2021-06-18 08:05 |  | 2021-06-29 08:05 | 2021-06-29 09:52 | 2021-06-18 16:13 | 2021-07-29 14:00 | CR0013616 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2021-W26 | 2021-06 | 23 | 30 | 108.9137 | 1 | 1 | 1 | 0.01 | 123048 | 2.4 | 1 | 0 | 0 | 1 | 1 | 2 | 16 | 53 | 0.22222 | 0.047619 | 2021-03 | 0 | 0
1326 | CR0013225 | CTASK0026589 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 8 | 8 | 2021-04-27 02:00 | 2021-04-20 02:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [PROD]EUA - Additional search criteria for CLL/CDL and Special Cargo Manifest UI | 2021-01-06 11:54 | 2021-02-09 | 2021-02-08 14:06 | 2021-04-13 18:12 | 2021-04-15 13:21 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-20 10:41 | 2021-05-27 14:00 | CR0013225 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W17 | 2021-04 | 176 | 180 | 110.9206 | 4 | 1 | 1 | 0.07 | 193506 | 1.6 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 27 | 1.1212 | 1.25 | 2021-01 | 0 | 0
1327 | CR0013225 | CTASK0024081 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 107 | 110 | 2021-01-29 02:00 | 2021-01-01 02:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Dev-Test]EUA - Additional search criteria for CLL/CDL and Special Cargo Manifest UI | 2021-01-06 11:54 | 2021-02-09 | 2021-02-08 14:06 | 2021-04-13 18:12 | 2021-04-15 13:21 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-20 10:41 | 2021-05-27 14:00 | CR0013225 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W17 | 2021-04 | 176 | 180 | 110.9206 | 4 | 1 | 1 | 0.07 | 193506 | 1.6 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 27 | 1.1212 | 1.25 | 2021-01 | 0 | 0
1328 | CR0013225 | CTASK0024584 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 53 | 54 |  |  | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Dev-Test]EUA - Additional search criteria for CLL/CDL and Special Cargo Manifest UI | 2021-01-06 11:54 | 2021-02-09 | 2021-02-08 14:06 | 2021-04-13 18:12 | 2021-04-15 13:21 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-20 10:41 | 2021-05-27 14:00 | CR0013225 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W17 | 2021-04 | 176 | 180 | 110.9206 | 4 | 1 | 1 | 0.07 | 193506 | 1.6 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 27 | 1.1212 | 1.25 | 2021-01 | 0 | 0
1329 | CR0013225 | CTASK0023951 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 8 | 8 | 2020-12-03 02:00 | 2020-12-02 02:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | EUA - Additional search criteria for CLL/CDL and Special Cargo Manifest UI | 2021-01-06 11:54 | 2021-02-09 | 2021-02-08 14:06 | 2021-04-13 18:12 | 2021-04-15 13:21 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-20 10:41 | 2021-05-27 14:00 | CR0013225 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W17 | 2021-04 | 176 | 180 | 110.9206 | 4 | 1 | 1 | 0.07 | 193506 | 1.6 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 27 | 1.1212 | 1.25 | 2021-01 | 0 | 0
1330 | CR0012042 | CTASK0017460 | Closed | OPUS-MNR | Tuyen Truong | 28 | 40 | 2019-12-27 09:26 | 2019-12-13 09:26 | Container | Equipment Management | M&R | Repair | Invoice | MNR EDI Invoice Parking Lot | When button action execution, display progressbar | 2019-12-27 17:40 | 2020-01-03 18:47 | 2020-01-03 17:22 | 2020-01-09 09:37 | 2020-01-09 09:41 |  | 2020-01-22 09:40 | 2020-01-14 14:28 | 2020-01-09 17:18 | 2020-01-17 13:49 | CR0012042 | Equipment ManagementM&RRepairInvoiceMNR EDI Invoice Parking Lot | OPUS-MNR | 2020-W4 | 2020-01 | 28 | 40 | 25.6664 | 2 | 1 | 2 | 0.06 | 173255 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 10 | 0 | 0 | 2019-12 | 0 | 0
1331 | CR0012042 | CTASK0017459 | Closed | OPUS-MNR | Tien Le | 1 | 1 | 2019-12-27 09:25 | 2019-12-13 09:25 | Container | Equipment Management | M&R | Repair | Invoice | MNR EDI Invoice Parking Lot | [initial] When button action execution, display progressbar | 2019-12-27 17:40 | 2020-01-03 18:47 | 2020-01-03 17:22 | 2020-01-09 09:37 | 2020-01-09 09:41 |  | 2020-01-22 09:40 | 2020-01-14 14:28 | 2020-01-09 17:18 | 2020-01-17 13:49 | CR0012042 | Equipment ManagementM&RRepairInvoiceMNR EDI Invoice Parking Lot | OPUS-MNR | 2020-W4 | 2020-01 | 28 | 40 | 25.6664 | 2 | 1 | 2 | 0.06 | 173286 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 10 | 0 | 0 | 2019-12 | 0 | 0
1332 | CR0012604 | CTASK0020016 | Closed | OPUS-SCG | Tu Nguyen | 10 | 20 | 2020-05-30 13:39 | 2020-05-11 13:38 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | [Documentation] [CLV][CLT Internal] DG Enhancement | 2020-05-14 16:16 | 2020-06-01 16:15 | 2020-05-27 16:04 | 2020-06-11 17:47 | 2020-06-12 14:10 |  | 2020-06-23 09:30 | 2020-06-23 13:28 | 2020-06-15 16:39 | 2020-07-24 13:00 | CR0012604 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2020-W26 | 2020-06 | 38 | 38 | 39.7181 | 3 | 1 | 2 | 0.04 | 123045 | 1.6 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 29 | 0 | 0 | 2020-05 | 0 | 0
1333 | CR0012604 | CTASK0020018 | Closed | OPUS-SCG | Pham Khanh Van | 20 | 10 | 2020-06-01 19:00 | 2020-05-11 13:56 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | [CLV] [CLT Internal] DG Enhancement | 2020-05-14 16:16 | 2020-06-01 16:15 | 2020-05-27 16:04 | 2020-06-11 17:47 | 2020-06-12 14:10 |  | 2020-06-23 09:30 | 2020-06-23 13:28 | 2020-06-15 16:39 | 2020-07-24 13:00 | CR0012604 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2020-W26 | 2020-06 | 38 | 38 | 39.7181 | 3 | 1 | 2 | 0.04 | 193477 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 29 | 0 | 0 | 2020-05 | 0 | 0
1334 | CR0012604 | CTASK0020520 | Closed | OPUS-SCG | Pham Khanh Van | 8 | 8 | 2020-06-12 12:03 | 2020-06-05 12:02 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | [CLV] [CLT Internal] DG Enhancement | 2020-05-14 16:16 | 2020-06-01 16:15 | 2020-05-27 16:04 | 2020-06-11 17:47 | 2020-06-12 14:10 |  | 2020-06-23 09:30 | 2020-06-23 13:28 | 2020-06-15 16:39 | 2020-07-24 13:00 | CR0012604 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2020-W26 | 2020-06 | 38 | 38 | 39.7181 | 3 | 1 | 2 | 0.04 | 193477 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 29 | 0 | 0 | 2020-05 | 0 | 0
1335 | CR0011419 | CTASK0021800 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 6 | 6 | 2020-08-28 16:19 | 2020-08-11 16:19 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment]ASIA -BKG - enhance current HS code & bkg route hard code table to include NCM & HTS, create override hardstop user id for blacklist, sanction, HS / HTS / NCM + bkg | 2019-07-01 16:24 | 2019-07-23 | 2019-07-19 17:42 | 2020-07-31 03:44 | 2020-08-11 13:18 |  | 2020-08-25 13:18 | 2020-08-25 10:20 | 2020-08-13 15:05 | 2020-09-24 13:00 | CR0011419 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W35 | 2020-08 | 42 | 43 | 420.8705 | 3 | 2 | 1 | 0 | 193512 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 30 | 0 | 0.5 | 2019-07 | 0 | 0
1336 | CR0011419 | CTASK0020683 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 24 | 25 | 2020-06-26 18:46 | 2020-06-16 18:46 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development+ Testing+ Deployment]ASIA -BKG - enhance current HS code & bkg route hard code table to include NCM & HTS, create override hardstop user id for blacklist, sanction, HS / HTS / NCM + bkg | 2019-07-01 16:24 | 2019-07-23 | 2019-07-19 17:42 | 2020-07-31 03:44 | 2020-08-11 13:18 |  | 2020-08-25 13:18 | 2020-08-25 10:20 | 2020-08-13 15:05 | 2020-09-24 13:00 | CR0011419 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W35 | 2020-08 | 42 | 43 | 420.8705 | 3 | 2 | 1 | 0 | 193512 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 30 | 0 | 0.5 | 2019-07 | 0 | 0
1337 | CR0011419 | CTASK0020637 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 12 | 12 | 2020-06-16 17:40 | 2020-06-11 17:40 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [BKG-IB] ASIA -BKG - enhance current HS code & bkg route hard code table to include NCM & HTS, create override hardstop user id for blacklist, sanction, HS / HTS / NCM + bkg route set up | 2019-07-01 16:24 | 2019-07-23 | 2019-07-19 17:42 | 2020-07-31 03:44 | 2020-08-11 13:18 |  | 2020-08-25 13:18 | 2020-08-25 10:20 | 2020-08-13 15:05 | 2020-09-24 13:00 | CR0011419 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W35 | 2020-08 | 42 | 43 | 420.8705 | 3 | 2 | 1 | 0 | 193512 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 12 | 30 | 0 | 0.5 | 2019-07 | 0 | 0
1338 | CR0010433 | CTASK0024018 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 1 | 1 | 2020-12-11 02:00 | 2020-12-01 02:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Deployment] Trinidad y Tobago Manifest - OPUS User Interface (related to ECR0000415) | 2019-09-25 16:35 | 2019-11-08 23:35 | 2019-11-07 18:31 | 2020-11-24 04:15 | 2020-12-04 13:53 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2021-01-07 10:31 | 2021-01-13 06:31 | CR0010433 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W2 | 2021-01 | 146 | 107 | 474.7259 | 2 | 2 | 1 | 0.01 | 193506 | 0.3 | 0 | 0 | 0 | 2 | 1 | 5 | 14 | 40 | 0 | 0.85714 | 2019-09 | 0 | 0
1339 | CR0010433 | CTASK0015861 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 145 | 106 | 2019-10-19 06:30 | 2019-09-18 21:30 | Container | Service Management | Booking/Documentation | Manifest |  |  | Trinidad y Tobago Manifest - OPUS User Interface (related to ECR0000415) | 2019-09-25 16:35 | 2019-11-08 23:35 | 2019-11-07 18:31 | 2020-11-24 04:15 | 2020-12-04 13:53 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2021-01-07 10:31 | 2021-01-13 06:31 | CR0010433 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W2 | 2021-01 | 146 | 107 | 474.7259 | 2 | 2 | 1 | 0.01 | 193506 | 0.3 | 0 | 0 | 0 | 2 | 1 | 5 | 14 | 40 | 0 | 0.85714 | 2019-09 | 0 | 0
1340 | CR0013448 | CTASK0024347 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 30 | 30 | 2021-01-09 10:55 | 2020-12-24 10:55 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Analysis][CLT Internal] to prevent unnecessary minor errors on booking inbound | 2021-03-11 17:15 | 2021-05-14 23:14 | 2021-05-13 17:04 | 2021-05-18 11:00 | 2021-06-02 14:17 |  | 2021-06-08 12:00 | 2021-06-08 10:32 | 2021-06-03 11:41 | 2021-07-08 14:00 | CR0013448 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W23 | 2021-06 | 52 | 52 | 88.7813 | 2 | 1 | 1 | 0.02 | 193512 | 1.7 | 2 | 0 | 0 | 1 | 1 | 2 | 9 | 53 | 0.2963 | 0.3125 | 2021-03 | 0 | 0
1341 | CR0013448 | CTASK0024586 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 22 | 22 | 2021-01-22 16:22 | 2021-01-11 16:22 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Development+ Testing+ Deployment][CLT Internal] to prevent unnecessary minor errors on booking inbound | 2021-03-11 17:15 | 2021-05-14 23:14 | 2021-05-13 17:04 | 2021-05-18 11:00 | 2021-06-02 14:17 |  | 2021-06-08 12:00 | 2021-06-08 10:32 | 2021-06-03 11:41 | 2021-07-08 14:00 | CR0013448 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W23 | 2021-06 | 52 | 52 | 88.7813 | 2 | 1 | 1 | 0.02 | 193512 | 1.7 | 2 | 0 | 0 | 1 | 1 | 2 | 9 | 53 | 0.2963 | 0.3125 | 2021-03 | 0 | 0
1342 | CR0013257 | CTASK0024539 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 3 | 3 | 2021-01-11 18:40 | 2021-01-05 10:40 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Deployment]EUA - Reinstate Muli Email Release Send disabled with CR0012123 | 2020-11-25 19:07 | 2020-12-31 23:06 | 2020-12-29 14:07 | 2021-01-05 11:03 | 2021-01-06 11:43 |  | 2021-01-12 11:43 | 2021-01-12 14:41 | 2021-01-07 15:55 | 2021-02-12 14:00 | CR0013257 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W2 | 2021-01 | 24 | 23 | 47.6917 | 2 | 1 | 1 | 0.02 | 193512 | 1.4 | 1 | 0 | 0 | 1 | 1 | 1 | 14 | 40 | 0.2963 | 0.3125 | 2020-11 | 0 | 0
1343 | CR0013257 | CTASK0023735 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 21 | 20 | 2020-12-11 16:06 | 2020-11-25 09:06 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment]EUA - Reinstate Muli Email Release Send disabled with CR0012123 | 2020-11-25 19:07 | 2020-12-31 23:06 | 2020-12-29 14:07 | 2021-01-05 11:03 | 2021-01-06 11:43 |  | 2021-01-12 11:43 | 2021-01-12 14:41 | 2021-01-07 15:55 | 2021-02-12 14:00 | CR0013257 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W2 | 2021-01 | 24 | 23 | 47.6917 | 2 | 1 | 1 | 0.02 | 193512 | 1.4 | 1 | 0 | 0 | 1 | 1 | 1 | 14 | 40 | 0.2963 | 0.3125 | 2020-11 | 0 | 0
1344 | CR0012673 | CTASK0020547 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 2 | 2 | 2021-03-04 19:56 | 2021-03-03 10:56 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Deployment]To receive "SMP Package qty", "SMP Package type" value from GLOVIS. As per customer's request. | 2020-06-29 10:02 | 2020-07-16 | 2020-07-14 14:26 | 2020-11-05 16:34 | 2021-02-04 11:53 |  | 2021-03-09 11:00 | 2021-03-09 11:00 | 2021-02-22 18:07 | 2021-04-08 14:00 | CR0012673 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W10 | 2021-03 | 16 | 16 | 253.04 | 4 | 1 | 1 | 0 | 193488 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 46 | 0.53659 | 0.28125 | 2020-06 | 0 | 0
1345 | CR0012673 | CTASK0020544 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 2 | 2 | 2020-06-05 18:44 | 2020-06-04 10:44 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Design]To receive "SMP Package qty", "SMP Package type" value from GLOVIS. As per customer's request. | 2020-06-29 10:02 | 2020-07-16 | 2020-07-14 14:26 | 2020-11-05 16:34 | 2021-02-04 11:53 |  | 2021-03-09 11:00 | 2021-03-09 11:00 | 2021-02-22 18:07 | 2021-04-08 14:00 | CR0012673 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W10 | 2021-03 | 16 | 16 | 253.04 | 4 | 1 | 1 | 0 | 193488 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 46 | 0.53659 | 0.28125 | 2020-06 | 0 | 0
1346 | CR0012673 | CTASK0020546 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 4 | 4 | 2020-07-08 18:11 | 2020-07-07 10:12 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Testing]To receive "SMP Package qty", "SMP Package type" value from GLOVIS. As per customer's request. | 2020-06-29 10:02 | 2020-07-16 | 2020-07-14 14:26 | 2020-11-05 16:34 | 2021-02-04 11:53 |  | 2021-03-09 11:00 | 2021-03-09 11:00 | 2021-02-22 18:07 | 2021-04-08 14:00 | CR0012673 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W10 | 2021-03 | 16 | 16 | 253.04 | 4 | 1 | 1 | 0 | 193488 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 46 | 0.53659 | 0.28125 | 2020-06 | 0 | 0
1347 | CR0012673 | CTASK0020545 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 8 | 8 | 2020-07-07 19:13 | 2020-07-01 11:13 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Development]To receive "SMP Package qty", "SMP Package type" value from GLOVIS. As per customer's request. | 2020-06-29 10:02 | 2020-07-16 | 2020-07-14 14:26 | 2020-11-05 16:34 | 2021-02-04 11:53 |  | 2021-03-09 11:00 | 2021-03-09 11:00 | 2021-02-22 18:07 | 2021-04-08 14:00 | CR0012673 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W10 | 2021-03 | 16 | 16 | 253.04 | 4 | 1 | 1 | 0 | 193488 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 7 | 46 | 0.53659 | 0.28125 | 2020-06 | 0 | 0
1348 | CR0012145 | CTASK0019579 | Closed | OPUS-BKG-M | Kieu Le | 19 | 20 | 2020-06-16 01:55 | 2020-06-10 02:55 | Container | Sales Management | Space Control |  |  |  | [Testing] NA *Standby* Enhancing Equipment Management in Standby // Approved Customer Functionality | 2020-04-27 16:06 | 2020-06-27 | 2020-06-26 18:08 | 2020-07-13 12:39 | 2020-07-13 14:08 |  | 2020-07-21 10:00 | 2020-07-21 10:15 | 2020-07-17 04:22 | 2020-08-06 03:41 | CR0012145 | Sales ManagementSpace Control | OPUS-SPC | 2020-W30 | 2020-07 | 247 | 252 | 84.7462 | 8 | 2 | 3 | 0.12 | 153106 | 1.6 | 0 | 0 | 1 | 3 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-04 | 1 | 1
1349 | CR0012145 | CTASK0019581 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-07-16 01:57 | 2020-07-14 02:56 | Container | Sales Management | Space Control |  |  |  | [Deployment] NA *Standby* Enhancing Equipment Management in Standby // Approved Customer Functionality | 2020-04-27 16:06 | 2020-06-27 | 2020-06-26 18:08 | 2020-07-13 12:39 | 2020-07-13 14:08 |  | 2020-07-21 10:00 | 2020-07-21 10:15 | 2020-07-17 04:22 | 2020-08-06 03:41 | CR0012145 | Sales ManagementSpace Control | OPUS-SPC | 2020-W30 | 2020-07 | 247 | 252 | 84.7462 | 8 | 2 | 3 | 0.12 | 153106 | 1.6 | 0 | 0 | 1 | 3 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-04 | 1 | 1
1350 | CR0012145 | CTASK0020342 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 | 2020-06-04 01:49 | 2020-06-01 02:49 | Container | Sales Management | Space Control |  |  |  | [Development] NA *Standby* Enhancing Equipment Management in Standby // Approved Customer Functionality | 2020-04-27 16:06 | 2020-06-27 | 2020-06-26 18:08 | 2020-07-13 12:39 | 2020-07-13 14:08 |  | 2020-07-21 10:00 | 2020-07-21 10:15 | 2020-07-17 04:22 | 2020-08-06 03:41 | CR0012145 | Sales ManagementSpace Control | OPUS-SPC | 2020-W30 | 2020-07 | 247 | 252 | 84.7462 | 8 | 2 | 3 | 0.12 | 153106 | 1.6 | 0 | 0 | 1 | 3 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-04 | 1 | 1
1351 | CR0012145 | CTASK0020343 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-06-13 01:51 | 2020-06-01 02:50 | Container | Sales Management | Space Control |  |  |  | [Testing] NA *Standby* Enhancing Equipment Management in Standby // Approved Customer Functionality | 2020-04-27 16:06 | 2020-06-27 | 2020-06-26 18:08 | 2020-07-13 12:39 | 2020-07-13 14:08 |  | 2020-07-21 10:00 | 2020-07-21 10:15 | 2020-07-17 04:22 | 2020-08-06 03:41 | CR0012145 | Sales ManagementSpace Control | OPUS-SPC | 2020-W30 | 2020-07 | 247 | 252 | 84.7462 | 8 | 2 | 3 | 0.12 | 153106 | 1.6 | 0 | 0 | 1 | 3 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-04 | 1 | 1
1352 | CR0012145 | CTASK0019473 | Closed | OPUS-BKG-M | Kieu Le | 24 | 24 | 2020-04-18 01:37 | 2020-04-08 02:37 | Container | Sales Management | Space Control |  |  |  | [Design] NA *Standby* Enhancing Equipment Management in Standby // Approved Customer Functionality | 2020-04-27 16:06 | 2020-06-27 | 2020-06-26 18:08 | 2020-07-13 12:39 | 2020-07-13 14:08 |  | 2020-07-21 10:00 | 2020-07-21 10:15 | 2020-07-17 04:22 | 2020-08-06 03:41 | CR0012145 | Sales ManagementSpace Control | OPUS-SPC | 2020-W30 | 2020-07 | 247 | 252 | 84.7462 | 8 | 2 | 3 | 0.12 | 153106 | 1.6 | 0 | 0 | 1 | 3 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-04 | 1 | 1
1353 | CR0012145 | CTASK0019674 | Closed | OPUS-SPC | Thuan Tran | 88 | 88 | 2020-06-13 20:05 | 2020-04-17 13:05 | Container | Sales Management | Space Control |  |  |  | [Development][CLV] NA *Standby* Enhancing Equipment Management in Standby // Approved Customer Functionality | 2020-04-27 16:06 | 2020-06-27 | 2020-06-26 18:08 | 2020-07-13 12:39 | 2020-07-13 14:08 |  | 2020-07-21 10:00 | 2020-07-21 10:15 | 2020-07-17 04:22 | 2020-08-06 03:41 | CR0012145 | Sales ManagementSpace Control | OPUS-SPC | 2020-W30 | 2020-07 | 247 | 252 | 84.7462 | 8 | 2 | 3 | 0.12 | 183423 | 1.5 | 0 | 0 | 1 | 3 | 1 | 2 | 6 | 27 | 0 | 0 | 2020-04 | 1 | 1
1354 | CR0012145 | CTASK0019576 | Closed | OPUS-BKG-M | Kieu Le | 58 | 62 | 2020-05-30 02:00 | 2020-04-20 02:13 | Container | Sales Management | Space Control |  |  |  | [Development] NA *Standby* Enhancing Equipment Management in Standby // Approved Customer Functionality | 2020-04-27 16:06 | 2020-06-27 | 2020-06-26 18:08 | 2020-07-13 12:39 | 2020-07-13 14:08 |  | 2020-07-21 10:00 | 2020-07-21 10:15 | 2020-07-17 04:22 | 2020-08-06 03:41 | CR0012145 | Sales ManagementSpace Control | OPUS-SPC | 2020-W30 | 2020-07 | 247 | 252 | 84.7462 | 8 | 2 | 3 | 0.12 | 153106 | 1.6 | 0 | 0 | 1 | 3 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-04 | 1 | 1
1355 | CR0012145 | CTASK0020781 | Closed | OPUS-SPC | Linh Nguyen | 30 | 30 | 2020-06-30 15:53 | 2020-06-01 15:53 | Container | Sales Management | Space Control |  |  |  | [Development][CLV] NA *Standby* Enhancing Equipment Management in Standby // Approved Customer Functionality | 2020-04-27 16:06 | 2020-06-27 | 2020-06-26 18:08 | 2020-07-13 12:39 | 2020-07-13 14:08 |  | 2020-07-21 10:00 | 2020-07-21 10:15 | 2020-07-17 04:22 | 2020-08-06 03:41 | CR0012145 | Sales ManagementSpace Control | OPUS-SPC | 2020-W30 | 2020-07 | 247 | 252 | 84.7462 | 8 | 2 | 3 | 0.12 | 193464 | 1.2 | 0 | 0 | 1 | 3 | 1 | 2 | 6 | 27 | 0 | 0 | 2020-04 | 1 | 1
1356 | CR0012407 | CTASK0019093 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2020-06-06 01:26 | 2020-06-01 02:26 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment][CLT Internal] Unnecessary button 'Apply' on direction column shouldn't be shown in order to prevent any user's confusion. | 2020-03-27 16:22 | 2020-04-30 | 2020-03-31 11:22 | 2020-04-22 01:30 | 2020-05-28 17:51 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-05-28 17:51 | 2020-07-09 13:00 | CR0012407 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W24 | 2020-06 | 6 | 6 | 73.7348 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-03 | 0 | 0
1357 | CR0012407 | CTASK0019044 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2020-03-24 16:01 | 2020-03-19 16:01 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design][CLT Internal] Unnecessary button 'Apply' on direction column shouldn't be shown in order to prevent any user's confusion. | 2020-03-27 16:22 | 2020-04-30 | 2020-03-31 11:22 | 2020-04-22 01:30 | 2020-05-28 17:51 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-05-28 17:51 | 2020-07-09 13:00 | CR0012407 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W24 | 2020-06 | 6 | 6 | 73.7348 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-03 | 0 | 0
1358 | CR0012407 | CTASK0019091 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2020-04-03 01:49 | 2020-03-30 02:49 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing][CLT Internal] Unnecessary button 'Apply' on direction column shouldn't be shown in order to prevent any user's confusion. | 2020-03-27 16:22 | 2020-04-30 | 2020-03-31 11:22 | 2020-04-22 01:30 | 2020-05-28 17:51 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-05-28 17:51 | 2020-07-09 13:00 | CR0012407 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W24 | 2020-06 | 6 | 6 | 73.7348 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-03 | 0 | 0
1359 | CR0012407 | CTASK0019079 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Documentation][CLT Internal] Unnecessary button 'Apply' on direction column shouldn't be shown in order to prevent any user's confusion. | 2020-03-27 16:22 | 2020-04-30 | 2020-03-31 11:22 | 2020-04-22 01:30 | 2020-05-28 17:51 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-05-28 17:51 | 2020-07-09 13:00 | CR0012407 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W24 | 2020-06 | 6 | 6 | 73.7348 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-03 | 0 | 0
1360 | CR0012407 | CTASK0019082 | Closed | OPUS-BKG-M | Kieu Le | 1 | 1 | 2020-04-03 19:45 | 2020-03-30 10:45 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development][CLT Internal] Unnecessary button 'Apply' on direction column shouldn't be shown in order to prevent any user's confusion. | 2020-03-27 16:22 | 2020-04-30 | 2020-03-31 11:22 | 2020-04-22 01:30 | 2020-05-28 17:51 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-05-28 17:51 | 2020-07-09 13:00 | CR0012407 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W24 | 2020-06 | 6 | 6 | 73.7348 | 5 | 1 | 1 | 0 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 29 | 0 | 0.4 | 2020-03 | 0 | 0
1361 | CR0013942 | CTASK0027571 | Closed | OPUS-CTM | Phu Nguyen Hoang | 1 | 1 |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | [Documentation][CLT Internal] revert features of CR0011234 | 2021-06-03 11:43 | 2021-06-15 18:00 | 2021-06-15 13:53 | 2021-06-22 15:35 | 2021-06-22 18:33 |  | 2021-06-29 18:30 | 2021-06-29 17:38 | 2021-06-23 16:34 | 2021-07-29 14:00 | CR0013942 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2021-W26 | 2021-06 | 25 | 25 | 26.2829 | 2 | 1 | 1 | 0.04 | 193463 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 16 | 53 | 0.16667 | 0 | 2021-06 | 0 | 0
1362 | CR0013942 | CTASK0026975 | Closed | OPUS-CTM | Phu Nguyen Hoang | 25 | 25 |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | [CLT Internal] revert features of CR0011234 | 2021-06-03 11:43 | 2021-06-15 18:00 | 2021-06-15 13:53 | 2021-06-22 15:35 | 2021-06-22 18:33 |  | 2021-06-29 18:30 | 2021-06-29 17:38 | 2021-06-23 16:34 | 2021-07-29 14:00 | CR0013942 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2021-W26 | 2021-06 | 25 | 25 | 26.2829 | 2 | 1 | 1 | 0.04 | 193463 | 2.3 | 1 | 0 | 0 | 1 | 1 | 1 | 16 | 53 | 0.16667 | 0 | 2021-06 | 0 | 0
1363 | CR0013522 | CTASK0024685 | Closed | OPUS-CTM | Tran Le | 30 | 33 |  |  | Container | Service Management | CNTR Movement | MVMT Creation | Domestic MVMT |  | Modify CP creation logic - Manage effort | 2021-03-10 14:27 | 2021-03-24 21:00 | 2021-03-24 15:36 | 2021-04-13 10:22 | 2021-04-14 11:41 |  | 2021-04-20 09:00 | 2021-04-20 09:00 | 2021-04-14 17:48 | 2021-05-20 14:00 | CR0013522 | Service ManagementCNTR MovementMVMT CreationDomestic MVMT | OPUS-CTM | 2021-W16 | 2021-04 | 30 | 33 | 40.7731 | 2 | 1 | 1 | 0.03 | 193501 | 1.4 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 27 | 0.052632 | 0.076923 | 2021-03 | 0 | 0
1364 | CR0013522 | CTASK0024682 | Closed | OPUS-CTM | Tran Le | 1 | 1 |  |  | Container | Service Management | CNTR Movement | MVMT Creation | Domestic MVMT |  | [Documentation] Modify CP creation logic | 2021-03-10 14:27 | 2021-03-24 21:00 | 2021-03-24 15:36 | 2021-04-13 10:22 | 2021-04-14 11:41 |  | 2021-04-20 09:00 | 2021-04-20 09:00 | 2021-04-14 17:48 | 2021-05-20 14:00 | CR0013522 | Service ManagementCNTR MovementMVMT CreationDomestic MVMT | OPUS-CTM | 2021-W16 | 2021-04 | 30 | 33 | 40.7731 | 2 | 1 | 1 | 0.03 | 193501 | 1.4 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 27 | 0.052632 | 0.076923 | 2021-03 | 0 | 0
1365 | CR0013171 | CTASK0023509 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 4 | 4 | 2020-11-17 02:00 | 2020-11-11 02:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Analytics]Multiple seal number in FF - CR0011660 | 2020-11-24 11:21 | 2020-12-16 | 2020-12-14 16:45 | 2021-01-05 16:30 | 2021-06-09 13:29 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-25 10:11 | 2021-07-29 14:00 | CR0013171 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 5 | 5 | 216.9437 | 2 | 1 | 1 | 0 | 193506 | 1.5 | 0 | 0 | 0 | 1 | 1 | 3 | 16 | 53 | 0 | 1.25 | 2020-11 | 0 | 0
1366 | CR0013171 | CTASK0023558 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 1 | 1 | 2020-12-09 02:00 | 2020-12-01 02:00 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Development-Testing]Multiple seal number in FF - CR0011660 | 2020-11-24 11:21 | 2020-12-16 | 2020-12-14 16:45 | 2021-01-05 16:30 | 2021-06-09 13:29 |  | 2021-06-29 10:00 | 2021-06-29 10:00 | 2021-06-25 10:11 | 2021-07-29 14:00 | CR0013171 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W26 | 2021-06 | 5 | 5 | 216.9437 | 2 | 1 | 1 | 0 | 193506 | 1.5 | 0 | 0 | 0 | 1 | 1 | 3 | 16 | 53 | 0 | 1.25 | 2020-11 | 0 | 0
1367 | CR0010330 | CTASK0025096 | Closed | OPUS-PRD | Thanh Tran Ngoc | 23 | 16 | 2021-03-31 16:43 | 2021-03-01 16:43 | Container | Service Management | Product Catalog |  |  |  | PRD - Ability to inquire E2E routes with cargo nature constraints on inland routes in PRD & PRI and make BKGs - MAR | 2021-01-13 13:22 | 2021-03-26 20:00 | 2021-03-26 12:53 | 2021-07-09 15:03 | 2021-08-05 09:36 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-05 13:31 | 2021-08-17 14:00 | CR0010330 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W32 | 2021-08 | 110 | 110 | 208.8597 | 5 | 1 | 2 | 0.02 | 193478 | 1.3 | 0 | 0 | 0 | 2 | 1 | 3 | 10 | 22 | 0 | 0 | 2021-01 | 0 | 0
1368 | CR0010330 | CTASK0025095 | Closed | OPUS-PRD | Thanh Tran Ngoc | 44 | 44 | 2021-02-28 16:21 | 2021-02-01 16:21 | Container | Service Management | Product Catalog |  |  |  | PRD - Ability to inquire E2E routes with cargo nature constraints on inland routes in PRD & PRI and make BKGs - FEB | 2021-01-13 13:22 | 2021-03-26 20:00 | 2021-03-26 12:53 | 2021-07-09 15:03 | 2021-08-05 09:36 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-05 13:31 | 2021-08-17 14:00 | CR0010330 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W32 | 2021-08 | 110 | 110 | 208.8597 | 5 | 1 | 2 | 0.02 | 193478 | 1.3 | 0 | 0 | 0 | 2 | 1 | 3 | 10 | 22 | 0 | 0 | 2021-01 | 0 | 0
1369 | CR0010330 | CTASK0026309 | Closed | OPUS-PRD | VInh Bui | 1 | 1 | 2021-04-30 08:57 | 2021-04-01 08:57 | Container | Service Management | Product Catalog |  |  |  | PRD - Ability to inquire E2E routes with cargo nature constraints on inland routes in PRD & PRI and make BKGs - APR | 2021-01-13 13:22 | 2021-03-26 20:00 | 2021-03-26 12:53 | 2021-07-09 15:03 | 2021-08-05 09:36 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-05 13:31 | 2021-08-17 14:00 | CR0010330 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W32 | 2021-08 | 110 | 110 | 208.8597 | 5 | 1 | 2 | 0.02 | 193469 | 1.3 | 0 | 0 | 0 | 2 | 1 | 3 | 10 | 22 | 0 | 0 | 2021-01 | 0 | 0
1370 | CR0010330 | CTASK0025738 | Closed | OPUS-PRD | VInh Bui | 36 | 40 | 2021-03-31 12:33 | 2021-03-01 12:33 | Container | Service Management | Product Catalog |  |  |  | PRD - Ability to inquire E2E routes with cargo nature constraints on inland routes in PRD & PRI and make BKGs - MAR | 2021-01-13 13:22 | 2021-03-26 20:00 | 2021-03-26 12:53 | 2021-07-09 15:03 | 2021-08-05 09:36 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-05 13:31 | 2021-08-17 14:00 | CR0010330 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W32 | 2021-08 | 110 | 110 | 208.8597 | 5 | 1 | 2 | 0.02 | 193469 | 1.3 | 0 | 0 | 0 | 2 | 1 | 3 | 10 | 22 | 0 | 0 | 2021-01 | 0 | 0
1371 | CR0010330 | CTASK0026999 | Closed | OPUS-PRD | VInh Bui | 7 | 10 | 2021-07-31 14:03 | 2021-07-01 14:03 | Container | Service Management | Product Catalog |  |  |  | PRD - Ability to inquire E2E routes with cargo nature constraints on inland routes in PRD & PRI and make BKGs - 2021 JULY | 2021-01-13 13:22 | 2021-03-26 20:00 | 2021-03-26 12:53 | 2021-07-09 15:03 | 2021-08-05 09:36 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-08-05 13:31 | 2021-08-17 14:00 | CR0010330 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W32 | 2021-08 | 110 | 110 | 208.8597 | 5 | 1 | 2 | 0.02 | 193469 | 1.3 | 0 | 0 | 0 | 2 | 1 | 3 | 10 | 22 | 0 | 0 | 2021-01 | 0 | 0
1372 | CR0012706 | CTASK0020619 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 20 | 20 | 2020-06-30 15:40 | 2020-06-11 15:40 | DOM Web Portal | ONE Operation | Settings |  |  |  | (DOM) NA * DOM * Shipper Address information is not mapping correctly from Dom Web Portal to OPUS EDI 404 | 2020-06-11 15:38 | 2020-06-30 21:00 | 2020-06-29 11:46 | 2020-07-03 05:35 | 2020-07-07 11:42 |  | 2020-07-14 11:00 | 2020-07-14 11:00 | 2020-07-08 01:09 | 2020-08-13 13:00 | CR0012706 | ONE OperationSettings | OPUS-DOM | 2020-W29 | 2020-07 | 40 | 40 | 32.8067 | 2 | 1 | 2 | 0.05 | 183432 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 27 | 0 | 0 | 2020-06 | 0 | 0
1373 | CR0012706 | CTASK0020620 | Closed | OPUS-DOM | Giang Nguyen Hoang | 20 | 20 | 2020-06-30 15:40 | 2020-06-11 15:40 | DOM Web Portal | ONE Operation | Settings |  |  |  | (DOM) NA * DOM * Shipper Address information is not mapping correctly from Dom Web Portal to OPUS EDI 404 | 2020-06-11 15:38 | 2020-06-30 21:00 | 2020-06-29 11:46 | 2020-07-03 05:35 | 2020-07-07 11:42 |  | 2020-07-14 11:00 | 2020-07-14 11:00 | 2020-07-08 01:09 | 2020-08-13 13:00 | CR0012706 | ONE OperationSettings | OPUS-DOM | 2020-W29 | 2020-07 | 40 | 40 | 32.8067 | 2 | 1 | 2 | 0.05 | 183440 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 27 | 0 | 0 | 2020-06 | 0 | 0
1374 | CR0013947 | CTASK0027088 | Closed | OPUS-SCG | Tu Nguyen | 18 | 16 | 2021-07-23 14:20 | 2021-07-05 14:20 | Container | Vessel Operation | Special Cargo | DG Restriction | Port Limit | DG Port/Terminal Limits – Check – Total Weight/TEU/Unit | [CLV-Tester] Request to enhance port limit restriction pop up for DG bookings. | 2021-06-02 11:10 | 2021-07-07 11:09 | 2021-07-02 14:12 | 2021-07-15 14:59 | 2021-07-15 16:34 |  | 2021-07-27 10:34 | 2021-07-27 10:50 | 2021-07-15 17:06 | 2021-08-03 14:00 | CR0013947 | Vessel OperationSpecial CargoDG RestrictionPort LimitDG Port/Terminal Limits – Check – Total Weight/TEU/Unit | OPUS-SCG | 2021-W30 | 2021-07 | 18 | 16 | 54.9749 | 1 | 1 | 1 | 0.01 | 123045 | 2.7 | 1 | 0 | 0 | 1 | 1 | 2 | 7 | 28 | 0 | 0 | 2021-06 | 0 | 0
1375 | CR0012641 | CTASK0020143 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 26 | 38 | 2020-07-10 12:37 | 2020-05-18 10:30 | Container | Service Management | Booking/Documentation | Report | VGM Dashboard |  | [Analysis][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-09-04 15:49 | 2020-09-15 19:30 | 2020-09-14 18:10 | 2020-10-05 20:00 | 2020-10-13 17:03 |  | 2020-10-27 10:00 | 2020-10-27 09:51 | 2020-10-14 15:51 | 2020-11-26 14:00 | CR0012641 | Service ManagementBooking/DocumentationReportVGM Dashboard | OPUS-BKG-RPT | 2020-W44 | 2020-10 | 105 | 123 | 52.758 | 4 | 1 | 2 | 0.1 | 193470 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 20 | 0 | 0.17391 | 2020-09 | 0 | 0
1376 | CR0012641 | CTASK0023004 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2020-12-18 18:00 | 2020-12-14 10:30 | Container | Service Management | Booking/Documentation | Report | VGM Dashboard |  | [Deployment][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-09-04 15:49 | 2020-09-15 19:30 | 2020-09-14 18:10 | 2020-10-05 20:00 | 2020-10-13 17:03 |  | 2020-10-27 10:00 | 2020-10-27 09:51 | 2020-10-14 15:51 | 2020-11-26 14:00 | CR0012641 | Service ManagementBooking/DocumentationReportVGM Dashboard | OPUS-BKG-RPT | 2020-W44 | 2020-10 | 105 | 123 | 52.758 | 4 | 1 | 2 | 0.1 | 193470 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 20 | 0 | 0.17391 | 2020-09 | 0 | 0
1377 | CR0012641 | CTASK0022308 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 18 | 24 | 2020-09-11 19:30 | 2020-09-04 10:30 | Container | Service Management | Booking/Documentation | Report | VGM Dashboard |  | [Development][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-09-04 15:49 | 2020-09-15 19:30 | 2020-09-14 18:10 | 2020-10-05 20:00 | 2020-10-13 17:03 |  | 2020-10-27 10:00 | 2020-10-27 09:51 | 2020-10-14 15:51 | 2020-11-26 14:00 | CR0012641 | Service ManagementBooking/DocumentationReportVGM Dashboard | OPUS-BKG-RPT | 2020-W44 | 2020-10 | 105 | 123 | 52.758 | 4 | 1 | 2 | 0.1 | 193470 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 20 | 0 | 0.17391 | 2020-09 | 0 | 0
1378 | CR0012641 | CTASK0020150 | Closed | OPUS-BKG-OB | Nam Nguyen | 57 | 57 | 2020-06-25 17:06 | 2020-05-18 16:50 | Container | Service Management | Booking/Documentation | Report | VGM Dashboard |  | [Analysis][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-09-04 15:49 | 2020-09-15 19:30 | 2020-09-14 18:10 | 2020-10-05 20:00 | 2020-10-13 17:03 |  | 2020-10-27 10:00 | 2020-10-27 09:51 | 2020-10-14 15:51 | 2020-11-26 14:00 | CR0012641 | Service ManagementBooking/DocumentationReportVGM Dashboard | OPUS-BKG-RPT | 2020-W44 | 2020-10 | 105 | 123 | 52.758 | 4 | 1 | 2 | 0.1 | 123048 | 1.9 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 20 | 0 | 0.46154 | 2020-09 | 0 | 0
1379 | CR0012801 | CTASK0021459 | Closed | OPUS-ACM | Huynh Tuan Khanh | 24 | 24 | 2020-07-31 18:08 | 2020-07-01 18:08 | Container | Sales Management | Pricing |  |  |  | [TIGER] Triggering program Test/STG/EDU/PROD_MDA EAI I/F to Tiger (Customer Address] | 2020-07-29 16:39 | 2020-09-01 | 2020-08-03 17:54 | 2020-08-06 14:49 | 2020-08-06 15:15 |  | 2020-08-11 15:15 | 2020-08-11 09:11 | 2020-08-06 15:16 | 2020-09-10 13:00 | CR0012801 | Sales ManagementPricing | OPUS-PRI | 2020-W33 | 2020-08 | 24 | 24 | 12.9417 | 1 | 1 | 1 | 0.08 | 193499 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 30 | 0 | 0 | 2020-07 | 0 | 0
1380 | CR0011838 | CTASK0017785 | Closed | OPUS-SCG | Trang Duy Thong | 40 | 40 | 2020-01-17 13:26 | 2020-01-07 13:26 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] Display "Port of Receipt", "Requested Date" in "SPCL CGO APVL for OWN BKG" for AK/SS/BB Applications | 2020-01-06 15:51 | 2020-01-24 15:50 | 2020-01-14 11:13 | 2020-02-06 09:50 | 2020-02-11 12:19 |  | 2020-02-18 07:30 | 2020-02-18 10:00 | 2020-02-11 16:22 | 2020-03-19 13:00 | CR0011838 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W8 | 2020-02 | 40 | 40 | 42.6519 | 1 | 1 | 1 | 0.04 | 193511 | -0.4 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 13 | 0 | 11 | 2020-01 | 0 | 0
1381 | CR0011725 | CTASK0017625 | Closed | OPUS-BKG-M | Thien Lai | 18 | 18 |  |  | Container | Service Management | Booking/Documentation | Operation | Special Container List |  | [Estimate] Date & Time include in Attached file in - Dangerous Cargo Application | 2020-01-31 17:29 | 2020-02-25 | 2020-02-24 11:47 | 2020-04-28 23:28 | 2020-04-29 09:56 |  | 2020-05-26 10:00 | 2020-05-26 10:00 | 2020-04-29 13:54 | 2020-06-25 13:00 | CR0011725 | Service ManagementBooking/DocumentationOperationSpecial Container List | OPUS-BKG-M | 2020-W22 | 2020-05 | 54 | 34 | 115.6883 | 2 | 1 | 1 | 0.01 | 193567 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.52941 | 2020-01 | 0 | 0
1382 | CR0011725 | CTASK0017686 | Closed | OPUS-BKG-M | Thien Lai | 36 | 34 | 2020-02-14 08:47 | 2020-02-03 08:47 | Container | Service Management | Booking/Documentation | Operation | Special Container List |  | + Date & Time include in Attached file in - Dangerous Cargo Application | 2020-01-31 17:29 | 2020-02-25 | 2020-02-24 11:47 | 2020-04-28 23:28 | 2020-04-29 09:56 |  | 2020-05-26 10:00 | 2020-05-26 10:00 | 2020-04-29 13:54 | 2020-06-25 13:00 | CR0011725 | Service ManagementBooking/DocumentationOperationSpecial Container List | OPUS-BKG-M | 2020-W22 | 2020-05 | 54 | 34 | 115.6883 | 2 | 1 | 1 | 0.01 | 193567 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 26 | 0 | 0.52941 | 2020-01 | 0 | 0
1383 | CR0011648 | CTASK0016351 | Closed | OPUS-PSO | Hieu Vu | 145 | 140 | 2019-11-15 09:14 | 2019-10-01 09:14 | Container | Vessel Operation | Port Service Order |  |  |  | PSO - Port Charge invoice creation screen needs additional duplication check logic to avoid double payments | 2019-09-25 16:20 | 2019-11-29 18:00 | 2019-11-13 09:34 | 2020-01-23 02:10 | 2020-02-20 10:42 |  | 2020-02-04 17:00 | 2020-03-04 00:53 | 2020-02-20 22:48 | 2020-03-19 16:06 | CR0011648 | Vessel OperationPort Service Order | OPUS-PSO | 2020-W6 | 2020-02 | 145 | 140 | 132.0278 | 1 | 1 | 1 | 0.04 | 183375 | 1 | 0 | 0 | 0 | 2 | 1 | 2 | 3 | 13 | 0 | 0 | 2019-09 | 0 | 0
1384 | CR0010673 | CTASK0017406 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 51 | 50 | 2019-12-31 13:59 | 2019-12-09 13:59 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | CARLST - CARGO LIST MESSAGE SHOULD INCLUDE COASTAL CARGO - AU CUSTOMS REQUIREMENT | 2019-12-23 15:33 | 2020-01-10 15:33 | 2019-12-23 15:36 | 2020-03-04 12:58 | 2020-04-07 19:17 |  | 2020-04-14 10:00 | 2020-04-14 09:48 | 2020-04-09 15:59 | 2020-05-14 13:00 | CR0010673 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W16 | 2020-04 | 91 | 90 | 112.7687 | 3 | 1 | 1 | 0.03 | 173280 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 16 | 0 | 0.18519 | 2019-12 | 0 | 0
1385 | CR0010673 | CTASK0019518 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 8 | 8 | 2020-04-14 19:30 | 2020-04-10 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | [Deployment]CARLST - CARGO LIST MESSAGE SHOULD INCLUDE COASTAL CARGO - AU CUSTOMS REQUIREMENT | 2019-12-23 15:33 | 2020-01-10 15:33 | 2019-12-23 15:36 | 2020-03-04 12:58 | 2020-04-07 19:17 |  | 2020-04-14 10:00 | 2020-04-14 09:48 | 2020-04-09 15:59 | 2020-05-14 13:00 | CR0010673 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W16 | 2020-04 | 91 | 90 | 112.7687 | 3 | 1 | 1 | 0.03 | 173280 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 16 | 0 | 0.18519 | 2019-12 | 0 | 0
1386 | CR0010673 | CTASK0018035 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 32 | 32 |  | 2020-01-21 11:00 | Container | Service Management | Booking/Documentation | Manifest | Australia | Australia Cargo List Report - CARLST | CARLST - CARGO LIST MESSAGE SHOULD INCLUDE COASTAL CARGO - AU CUSTOMS REQUIREMENT | 2019-12-23 15:33 | 2020-01-10 15:33 | 2019-12-23 15:36 | 2020-03-04 12:58 | 2020-04-07 19:17 |  | 2020-04-14 10:00 | 2020-04-14 09:48 | 2020-04-09 15:59 | 2020-05-14 13:00 | CR0010673 | Service ManagementBooking/DocumentationManifestAustraliaAustralia Cargo List Report - CARLST | OPUS-BKG-MFT-A | 2020-W16 | 2020-04 | 91 | 90 | 112.7687 | 3 | 1 | 1 | 0.03 | 173280 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 16 | 0 | 0.18519 | 2019-12 | 0 | 0
1387 | CR0013373 | CTASK0024216 | Closed | OPUS-MDA | Tran Le | 32 | 40 | 2021-01-29 20:00 | 2020-12-01 08:00 | Container | Biz Common | Master Data | Admin | Process Status |  | [CTASK2] CLV_Design_Analysis_Development_TEST_Deployment | 2020-12-17 11:59 | 2020-12-31 20:00 | 2020-12-31 09:32 | 2021-01-08 10:15 | 2021-01-08 10:52 |  | 2021-01-12 10:00 | 2021-01-12 14:25 | 2021-01-08 11:46 | 2021-02-12 14:00 | CR0013373 | Biz CommonMaster DataAdminProcess Status | OPUS-MDA | 2021-W2 | 2021-01 | 32 | 44 | 25.9175 | 2 | 1 | 2 | 0.07 | 193501 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 14 | 40 | 0 | 0.076923 | 2020-12 | 0 | 0
1388 | CR0013373 | CTASK0024217 | Closed | OPUS-MDA | Cuong Nguyen | 4 | 4 | 2020-12-31 20:00 | 2020-12-01 08:00 | Container | Biz Common | Master Data | Admin | Process Status |  | [CTASK3] CLV_Pair Test | 2020-12-17 11:59 | 2020-12-31 20:00 | 2020-12-31 09:32 | 2021-01-08 10:15 | 2021-01-08 10:52 |  | 2021-01-12 10:00 | 2021-01-12 14:25 | 2021-01-08 11:46 | 2021-02-12 14:00 | CR0013373 | Biz CommonMaster DataAdminProcess Status | OPUS-MDA | 2021-W2 | 2021-01 | 32 | 44 | 25.9175 | 2 | 1 | 2 | 0.07 | 193529 | 1.5 | 0 | 0 | 0 | 1 | 1 | 1 | 14 | 40 | 0 | 0.058824 | 2020-12 | 0 | 0
1389 | CR0011842 | CTASK0017030 | Closed | OPUS-TES | Thai Nguyen | 60 | 60 |  |  | Container | Service Management | TML INV |  |  |  | [Actual] GHQ - Add new TES Cost Code | 2019-11-28 16:15 | 2019-12-14 | 2019-12-10 11:07 | 2019-12-17 17:49 | 2019-12-18 15:40 | 2019-12-10 13:21 | 2019-12-24 09:00 | 2019-12-24 11:35 | 2019-12-24 11:34 | 2020-01-05 16:18 | CR0011842 | Service ManagementTML INV | OPUS-TES | 2019-W52 | 2019-12 | 60 | 0 | 25.6982 | 1 | 1 | 1 | 0 | 173249 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 18 | 0 | 2 | 2019-11 | 0 | 0
1390 | CR0012397 | CTASK0025950 | Closed | OPUS-BKG-IB | Thuc Tran | 20 | 20 | 2021-03-29 19:30 | 2021-03-18 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Deployment+Inspection] Asia *IB DOC* -DO release (NZ) | 2020-11-23 16:56 | 2020-12-31 23:55 | 2020-12-21 15:40 | 2021-03-16 19:45 | 2021-03-18 16:45 |  | 2021-03-30 16:43 | 2021-03-30 10:00 | 2021-03-19 10:29 | 2021-04-06 16:16 | CR0012397 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W13 | 2021-03 | 131 | 131 | 126.991 | 4 | 1 | 1 | 0.04 | 173280 | 1.9 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 46 | 0.375 | 0.18519 | 2020-11 | 0 | 0
1391 | CR0012397 | CTASK0024322 | Closed | OPUS-BKG-IB | Thuc Tran | 32 | 32 | 2021-02-05 19:30 | 2021-01-01 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Development+Inspection+Deployment] Asia *IB DOC* -DO release (NZ) | 2020-11-23 16:56 | 2020-12-31 23:55 | 2020-12-21 15:40 | 2021-03-16 19:45 | 2021-03-18 16:45 |  | 2021-03-30 16:43 | 2021-03-30 10:00 | 2021-03-19 10:29 | 2021-04-06 16:16 | CR0012397 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W13 | 2021-03 | 131 | 131 | 126.991 | 4 | 1 | 1 | 0.04 | 173280 | 1.9 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 46 | 0.375 | 0.18519 | 2020-11 | 0 | 0
1392 | CR0012397 | CTASK0023353 | Closed | OPUS-BKG-IB | Thuc Tran | 55 | 55 | 2020-11-24 19:30 | 2020-11-06 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Development+Inspection+Deployment] Asia *IB DOC* -DO release (NZ) | 2020-11-23 16:56 | 2020-12-31 23:55 | 2020-12-21 15:40 | 2021-03-16 19:45 | 2021-03-18 16:45 |  | 2021-03-30 16:43 | 2021-03-30 10:00 | 2021-03-19 10:29 | 2021-04-06 16:16 | CR0012397 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W13 | 2021-03 | 131 | 131 | 126.991 | 4 | 1 | 1 | 0.04 | 173280 | 1.9 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 46 | 0.375 | 0.18519 | 2020-11 | 0 | 0
1393 | CR0012397 | CTASK0023813 | Closed | OPUS-BKG-IB | Thuc Tran | 24 | 24 | 2020-12-31 19:30 | 2020-12-01 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release |  | [Development+Inspection+Deployment] Asia *IB DOC* -DO release (NZ) | 2020-11-23 16:56 | 2020-12-31 23:55 | 2020-12-21 15:40 | 2021-03-16 19:45 | 2021-03-18 16:45 |  | 2021-03-30 16:43 | 2021-03-30 10:00 | 2021-03-19 10:29 | 2021-04-06 16:16 | CR0012397 | Service ManagementBooking/DocumentationInbound DocCargo Release | OPUS-BKG-IB | 2021-W13 | 2021-03 | 131 | 131 | 126.991 | 4 | 1 | 1 | 0.04 | 173280 | 1.9 | 2 | 0 | 0 | 2 | 1 | 2 | 12 | 46 | 0.375 | 0.18519 | 2020-11 | 0 | 0
1394 | CR0013758 | CTASK0026341 | Closed | OPUS-BKG-MFT-M | Nhut Nguyen Minh | 13 | 12 | 2021-04-12 18:25 | 2021-04-01 18:25 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Estimation] EUA CR - Change of Search/Results and D/O logic / New Report Layout | 2021-04-23 16:53 | 2021-06-25 23:53 | 2021-06-25 15:30 | 2021-07-08 10:43 | 2021-07-12 13:06 |  | 2021-07-20 13:03 | 2021-07-20 12:57 | 2021-07-14 15:47 | 2021-07-29 14:00 | CR0013758 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W29 | 2021-07 | 189 | 194 | 87.8402 | 3 | 2 | 1 | 0.09 | 193512 | 1.8 | 2 | 0 | 0 | 2 | 1 | 2 | 4 | 28 | 0.2963 | 0.3125 | 2021-04 | 0 | 0
1395 | CR0013758 | CTASK0028138 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 12 | 12 | 2021-07-20 15:11 | 2021-07-12 09:11 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Deployment] EUA CR - Change of Search/Results and D/O logic / New Report Layout | 2021-04-23 16:53 | 2021-06-25 23:53 | 2021-06-25 15:30 | 2021-07-08 10:43 | 2021-07-12 13:06 |  | 2021-07-20 13:03 | 2021-07-20 12:57 | 2021-07-14 15:47 | 2021-07-29 14:00 | CR0013758 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W29 | 2021-07 | 189 | 194 | 87.8402 | 3 | 2 | 1 | 0.09 | 193512 | 1.8 | 2 | 0 | 0 | 2 | 1 | 2 | 4 | 28 | 0.2963 | 0.3125 | 2021-04 | 0 | 0
1396 | CR0013758 | CTASK0026977 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 164 | 170 | 2021-06-25 16:54 | 2021-05-12 16:54 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EU Full Container Release / Full Release CY / Arrival (local) VVD | 2021-04-23 16:53 | 2021-06-25 23:53 | 2021-06-25 15:30 | 2021-07-08 10:43 | 2021-07-12 13:06 |  | 2021-07-20 13:03 | 2021-07-20 12:57 | 2021-07-14 15:47 | 2021-07-29 14:00 | CR0013758 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W29 | 2021-07 | 189 | 194 | 87.8402 | 3 | 2 | 1 | 0.09 | 193512 | 1.8 | 2 | 0 | 0 | 2 | 1 | 2 | 4 | 28 | 0.2963 | 0.3125 | 2021-04 | 0 | 0
1397 | CR0013617 | CTASK0025860 | Closed | OPUS-BKG-OB | Nam Nguyen | 36 | 36 | 2021-03-29 19:39 | 2021-03-12 19:39 | Container | Service Management | Booking/Documentation |  |  |  | [Sprint4][Design] CR0013617 - //Supplement to CR0013229// OLE Instance Booking Confirmation- Change of Opus logic | 2021-03-03 11:27 | 2021-03-30 | 2021-03-26 16:37 | 2021-04-01 09:15 | 2021-04-01 09:25 |  | 2021-04-06 10:00 | 2021-04-06 10:00 | 2021-04-01 11:04 | 2021-05-06 14:00 | CR0013617 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W14 | 2021-04 | 154 | 174 | 33.9397 | 8 | 2 | 2 | 0.21 | 123048 | 2.4 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 27 | 0.22222 | 0.047619 | 2021-03 | 2 | 1
1398 | CR0013617 | CTASK0025601 | Closed | OPUS-BKG-M | Kieu Le | 36 | 48 | 2021-03-31 15:53 | 2021-03-01 15:53 | Container | Service Management | Booking/Documentation |  |  |  | [Sprint3][Development] CR0013617 - //Supplement to CR0013229// OLE Instance Booking Confirmation- Change of Opus logic | 2021-03-03 11:27 | 2021-03-30 | 2021-03-26 16:37 | 2021-04-01 09:15 | 2021-04-01 09:25 |  | 2021-04-06 10:00 | 2021-04-06 10:00 | 2021-04-01 11:04 | 2021-05-06 14:00 | CR0013617 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W14 | 2021-04 | 154 | 174 | 33.9397 | 8 | 2 | 2 | 0.21 | 153106 | 2.4 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 27 | 0.22951 | 0.13043 | 2021-03 | 2 | 1
1399 | CR0013617 | CTASK0025391 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-02-26 12:02 | 2021-02-18 02:02 | Container | Service Management | Booking/Documentation |  |  |  | [Development] CR0013617 - //Supplement to CR0013229// OLE Instance Booking Confirmation- Change of Opus logic | 2021-03-03 11:27 | 2021-03-30 | 2021-03-26 16:37 | 2021-04-01 09:15 | 2021-04-01 09:25 |  | 2021-04-06 10:00 | 2021-04-06 10:00 | 2021-04-01 11:04 | 2021-05-06 14:00 | CR0013617 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W14 | 2021-04 | 154 | 174 | 33.9397 | 8 | 2 | 2 | 0.21 | 153106 | 2.4 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 27 | 0.22951 | 0.13043 | 2021-03 | 2 | 1
1400 | CR0013617 | CTASK0025602 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-03-31 15:55 | 2021-03-01 15:55 | Container | Service Management | Booking/Documentation |  |  |  | [Sprint3][Testing] CR0013617 - //Supplement to CR0013229// OLE Instance Booking Confirmation- Change of Opus logic | 2021-03-03 11:27 | 2021-03-30 | 2021-03-26 16:37 | 2021-04-01 09:15 | 2021-04-01 09:25 |  | 2021-04-06 10:00 | 2021-04-06 10:00 | 2021-04-01 11:04 | 2021-05-06 14:00 | CR0013617 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W14 | 2021-04 | 154 | 174 | 33.9397 | 8 | 2 | 2 | 0.21 | 153106 | 2.4 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 27 | 0.22951 | 0.13043 | 2021-03 | 2 | 1
1401 | CR0013617 | CTASK0025396 | Closed | OPUS-BKG-M | Kieu Le | 14 | 18 | 2021-04-30 12:07 | 2021-04-01 02:06 | Container | Service Management | Booking/Documentation |  |  |  | [Deployment] CR0013617 - //Supplement to CR0013229// OLE Instance Booking Confirmation- Change of Opus logic | 2021-03-03 11:27 | 2021-03-30 | 2021-03-26 16:37 | 2021-04-01 09:15 | 2021-04-01 09:25 |  | 2021-04-06 10:00 | 2021-04-06 10:00 | 2021-04-01 11:04 | 2021-05-06 14:00 | CR0013617 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W14 | 2021-04 | 154 | 174 | 33.9397 | 8 | 2 | 2 | 0.21 | 153106 | 2.4 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 27 | 0.22951 | 0.13043 | 2021-03 | 2 | 1
1402 | CR0013617 | CTASK0025394 | Closed | OPUS-BKG-M | Kieu Le | 8 | 12 | 2021-02-27 01:05 | 2021-02-18 12:05 | Container | Service Management | Booking/Documentation |  |  |  | [Testing] CR0013617 - //Supplement to CR0013229// OLE Instance Booking Confirmation- Change of Opus logic | 2021-03-03 11:27 | 2021-03-30 | 2021-03-26 16:37 | 2021-04-01 09:15 | 2021-04-01 09:25 |  | 2021-04-06 10:00 | 2021-04-06 10:00 | 2021-04-01 11:04 | 2021-05-06 14:00 | CR0013617 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W14 | 2021-04 | 154 | 174 | 33.9397 | 8 | 2 | 2 | 0.21 | 153106 | 2.4 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 27 | 0.22951 | 0.13043 | 2021-03 | 2 | 1
1403 | CR0013617 | CTASK0025241 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-02-27 01:47 | 2021-02-08 02:47 | Container | Service Management | Booking/Documentation |  |  |  | [Design] CR0013617 - //Supplement to CR0013229// OLE Instance Booking Confirmation- Change of Opus logic | 2021-03-03 11:27 | 2021-03-30 | 2021-03-26 16:37 | 2021-04-01 09:15 | 2021-04-01 09:25 |  | 2021-04-06 10:00 | 2021-04-06 10:00 | 2021-04-01 11:04 | 2021-05-06 14:00 | CR0013617 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W14 | 2021-04 | 154 | 174 | 33.9397 | 8 | 2 | 2 | 0.21 | 153106 | 2.4 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 27 | 0.22951 | 0.13043 | 2021-03 | 2 | 1
1404 | CR0013617 | CTASK0025571 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 | 2021-03-31 18:53 | 2021-03-01 02:53 | Container | Service Management | Booking/Documentation |  |  |  | [Sprint3][Design] CR0013617 - //Supplement to CR0013229// OLE Instance Booking Confirmation- Change of Opus logic | 2021-03-03 11:27 | 2021-03-30 | 2021-03-26 16:37 | 2021-04-01 09:15 | 2021-04-01 09:25 |  | 2021-04-06 10:00 | 2021-04-06 10:00 | 2021-04-01 11:04 | 2021-05-06 14:00 | CR0013617 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W14 | 2021-04 | 154 | 174 | 33.9397 | 8 | 2 | 2 | 0.21 | 153106 | 2.4 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 27 | 0.22951 | 0.13043 | 2021-03 | 2 | 1
1405 | CR0012122 | CTASK0017815 | Closed | OPUS-JOO | Toai Phan | 8 | 8 |  |  | S/W | [5 empty] | [CLV] TLS 1.2 Support (TEST) | 2020-01-08 10:17 | 2020-01-10 10:16 | 2020-01-10 15:29 |  | 2020-01-12 14:52 |  | 2020-01-12 14:00 | 2020-01-12 14:53 | 2020-01-12 14:53 | 2020-01-30 19:26 | CR0012122 |  | OPUS-JOO | 2020-W2 | 2020-01 | 16 | 0 | 4.1549 | 2 | 1 | 1 | 0 | 183427 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 10 | 0 | 2 | 2020-01 | 0 | 0
1406 | CR0012122 | CTASK0017816 | Closed | OPUS-JOO | Toai Phan | 8 | 8 |  |  | S/W | [5 empty] | [CLV] TLS 1.2 Support (STG) | 2020-01-08 10:17 | 2020-01-10 10:16 | 2020-01-10 15:29 |  | 2020-01-12 14:52 |  | 2020-01-12 14:00 | 2020-01-12 14:53 | 2020-01-12 14:53 | 2020-01-30 19:26 | CR0012122 |  | OPUS-JOO | 2020-W2 | 2020-01 | 16 | 0 | 4.1549 | 2 | 1 | 1 | 0 | 183427 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 10 | 0 | 2 | 2020-01 | 0 | 0
1407 | CR0012518 | CTASK0024762 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 70 | 49 | 2021-02-28 16:03 | 2021-02-01 16:03 | Container | Service Management | Trans S/O | Work Order |  |  | [202102] CR0011187- Enhance logic in transportation status in TRS module for 'empties' transportation | 2021-01-19 13:43 | 2021-03-05 21:00 | 2021-03-05 09:48 | 2021-05-06 10:22 | 2021-05-11 09:58 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-20 14:08 | 2021-06-24 14:00 | CR0012518 | Service ManagementTrans S/OWork Order | OPUS-TRS | 2021-W21 | 2021-05 | 217 | 178 | 125.8454 | 4 | 1 | 2 | 0.06 | 183432 | 1.9 | 0 | 0 | 0 | 2 | 1 | 2 | 8 | 28 | 0 | 0 | 2021-01 | 0 | 0
1408 | CR0012518 | CTASK0024529 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 39 | 40 | 2021-01-31 10:19 | 2021-01-14 10:18 | Container | Service Management | Trans S/O | Work Order |  |  | [202101] CR0011187- Enhance logic in transportation status in TRS module for 'empties' transportation | 2021-01-19 13:43 | 2021-03-05 21:00 | 2021-03-05 09:48 | 2021-05-06 10:22 | 2021-05-11 09:58 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-20 14:08 | 2021-06-24 14:00 | CR0012518 | Service ManagementTrans S/OWork Order | OPUS-TRS | 2021-W21 | 2021-05 | 217 | 178 | 125.8454 | 4 | 1 | 2 | 0.06 | 183432 | 1.9 | 0 | 0 | 0 | 2 | 1 | 2 | 8 | 28 | 0 | 0 | 2021-01 | 0 | 0
1409 | CR0012518 | CTASK0024530 | Closed | OPUS-TRS | Giang Nguyen Hoang | 43 | 40 | 2021-01-31 10:19 | 2021-01-14 10:19 | Container | Service Management | Trans S/O | Work Order |  |  | [202101] CR0011187- Enhance logic in transportation status in TRS module for 'empties' transportation | 2021-01-19 13:43 | 2021-03-05 21:00 | 2021-03-05 09:48 | 2021-05-06 10:22 | 2021-05-11 09:58 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-20 14:08 | 2021-06-24 14:00 | CR0012518 | Service ManagementTrans S/OWork Order | OPUS-TRS | 2021-W21 | 2021-05 | 217 | 178 | 125.8454 | 4 | 1 | 2 | 0.06 | 183440 | 1.9 | 0 | 0 | 0 | 2 | 1 | 2 | 8 | 28 | 0 | 0 | 2021-01 | 0 | 0
1410 | CR0012518 | CTASK0024763 | Closed | OPUS-TRS | Giang Nguyen Hoang | 65 | 49 | 2021-02-28 16:04 | 2021-02-01 16:04 | Container | Service Management | Trans S/O | Work Order |  |  | [202102] CR0011187- Enhance logic in transportation status in TRS module for 'empties' transportation | 2021-01-19 13:43 | 2021-03-05 21:00 | 2021-03-05 09:48 | 2021-05-06 10:22 | 2021-05-11 09:58 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-20 14:08 | 2021-06-24 14:00 | CR0012518 | Service ManagementTrans S/OWork Order | OPUS-TRS | 2021-W21 | 2021-05 | 217 | 178 | 125.8454 | 4 | 1 | 2 | 0.06 | 183440 | 1.9 | 0 | 0 | 0 | 2 | 1 | 2 | 8 | 28 | 0 | 0 | 2021-01 | 0 | 0
1411 | CR0013841 | CTASK0026651 | Closed | OPUS-PRD | Son Nguyen The | 1 | 1 | 2021-04-30 08:25 | 2021-04-23 08:24 | Container | Service Management | Product Catalog |  |  |  | GHQ - PRD TT Tool Add new column (Trunk Service Lane) - APR | 2021-06-14 09:41 | 2021-07-02 20:00 | 2021-06-24 11:38 | 2021-07-12 15:30 | 2021-07-14 08:06 |  | 2021-07-20 10:00 | 2021-07-20 10:00 | 2021-07-14 15:41 | 2021-07-27 17:50 | CR0013841 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W29 | 2021-07 | 46 | 46 | 36.0129 | 3 | 1 | 1 | 0.05 | 193531 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 28 | 0 | 0 | 2021-06 | 0 | 0
1412 | CR0013841 | CTASK0026652 | Closed | OPUS-PRD | Son Nguyen The | 38 | 38 | 2021-06-30 08:24 | 2021-06-01 08:24 | Container | Service Management | Product Catalog |  |  |  | GHQ - PRD TT Tool Add new column (Trunk Service Lane) - JUN | 2021-06-14 09:41 | 2021-07-02 20:00 | 2021-06-24 11:38 | 2021-07-12 15:30 | 2021-07-14 08:06 |  | 2021-07-20 10:00 | 2021-07-20 10:00 | 2021-07-14 15:41 | 2021-07-27 17:50 | CR0013841 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W29 | 2021-07 | 46 | 46 | 36.0129 | 3 | 1 | 1 | 0.05 | 193531 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 28 | 0 | 0 | 2021-06 | 0 | 0
1413 | CR0013841 | CTASK0027870 | Closed | OPUS-PRD | Son Nguyen The | 8 | 8 |  |  | Container | Service Management | Product Catalog |  |  |  | GHQ - PRD TT Tool Add new column (Trunk Service Lane) - JULY | 2021-06-14 09:41 | 2021-07-02 20:00 | 2021-06-24 11:38 | 2021-07-12 15:30 | 2021-07-14 08:06 |  | 2021-07-20 10:00 | 2021-07-20 10:00 | 2021-07-14 15:41 | 2021-07-27 17:50 | CR0013841 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W29 | 2021-07 | 46 | 46 | 36.0129 | 3 | 1 | 1 | 0.05 | 193531 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 28 | 0 | 0 | 2021-06 | 0 | 0
1414 | CR0012669 | CTASK0021197 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 7 | 7 | 2020-08-13 18:38 | 2020-08-11 18:38 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] Additional layout adjustment in RD of the 'Empty Container Release Order'. | 2020-08-12 09:16 | 2020-09-10 | 2020-09-07 17:31 | 2020-09-08 17:37 | 2020-09-08 18:09 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-09-09 10:07 | 2020-11-12 14:00 | CR0012669 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W42 | 2020-10 | 38 | 40 | 62.0303 | 4 | 1 | 2 | 0.03 | 193488 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28125 | 2020-08 | 0 | 0
1415 | CR0012669 | CTASK0021200 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2020-08-14 18:48 | 2020-08-13 18:47 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] Additional layout adjustment in RD of the 'Empty Container Release Order'. | 2020-08-12 09:16 | 2020-09-10 | 2020-09-07 17:31 | 2020-09-08 17:37 | 2020-09-08 18:09 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-09-09 10:07 | 2020-11-12 14:00 | CR0012669 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W42 | 2020-10 | 38 | 40 | 62.0303 | 4 | 1 | 2 | 0.03 | 193488 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28125 | 2020-08 | 0 | 0
1416 | CR0012669 | CTASK0021087 | Closed | OPUS-BKG-M | Loc Tran | 23 | 23 | 2020-07-14 19:36 | 2020-07-06 19:36 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design][CLT Internal] Additional layout adjustment in RD of the 'Empty Container Release Order'. | 2020-08-12 09:16 | 2020-09-10 | 2020-09-07 17:31 | 2020-09-08 17:37 | 2020-09-08 18:09 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-09-09 10:07 | 2020-11-12 14:00 | CR0012669 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W42 | 2020-10 | 38 | 40 | 62.0303 | 4 | 1 | 2 | 0.03 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1417 | CR0012669 | CTASK0021203 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 2 | 4 | 2020-09-30 18:36 | 2020-09-01 18:36 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] Additional layout adjustment in RD of the 'Empty Container Release Order'. | 2020-08-12 09:16 | 2020-09-10 | 2020-09-07 17:31 | 2020-09-08 17:37 | 2020-09-08 18:09 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-09-09 10:07 | 2020-11-12 14:00 | CR0012669 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W42 | 2020-10 | 38 | 40 | 62.0303 | 4 | 1 | 2 | 0.03 | 193488 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 20 | 0 | 0.28125 | 2020-08 | 0 | 0
1418 | CR0012813 | CTASK0021070 | Closed | OPUS-FLT | Tu Nguyen | 1 | 1 | 2020-07-24 18:00 | 2020-07-17 09:00 | Container | Support & Admin | Fleet Management | Invoice | Time Charter Invoice | Time Charter Invoice | [CLV-FLT] Enable Row Copy Function for Bunker Expense-Additive | 2020-07-31 13:15 | 2020-08-14 18:00 | 2020-08-12 18:01 | 2020-08-14 17:53 | 2020-08-19 11:46 |  | 2020-08-25 10:00 | 2020-08-25 10:31 | 2020-08-19 16:52 | 2020-09-26 13:00 | CR0012813 | Support & AdminFleet ManagementInvoiceTime Charter InvoiceTime Charter Invoice | OPUS-FLT | 2020-W35 | 2020-08 | 1 | 1 | 24.8646 | 1 | 1 | 1 | 0 | 123045 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 12 | 30 | 0 | 0 | 2020-07 | 0 | 0
1419 | CR0013174 | CTASK0022915 | Closed | OPUS-BKG-M | Thien Lai | 12 | 12 | 2020-10-31 15:26 | 2020-10-08 15:26 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] Prevent entering special characters for Booking Cancel Reason | 2020-10-16 11:28 | 2020-11-26 | 2020-11-13 17:33 | 2020-11-27 14:50 | 2020-11-27 16:41 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2020-11-27 16:49 | 2021-02-12 14:00 | CR0013174 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W2 | 2021-01 | 48 | 48 | 87.9388 | 3 | 1 | 1 | 0.02 | 193567 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0.5625 | 0.53333 | 2020-10 | 0 | 0
1420 | CR0013174 | CTASK0023171 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-01-31 19:16 | 2021-01-01 19:16 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] Prevent entering special characters for Booking Cancel Reason | 2020-10-16 11:28 | 2020-11-26 | 2020-11-13 17:33 | 2020-11-27 14:50 | 2020-11-27 16:41 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2020-11-27 16:49 | 2021-02-12 14:00 | CR0013174 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W2 | 2021-01 | 48 | 48 | 87.9388 | 3 | 1 | 1 | 0.02 | 193567 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0.5625 | 0.53333 | 2020-10 | 0 | 0
1421 | CR0013174 | CTASK0023030 | Closed | OPUS-BKG-M | Thien Lai | 28 | 28 | 2020-10-31 11:37 | 2020-10-01 11:37 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [CLT Internal] Prevent entering special characters for Booking Cancel Reason | 2020-10-16 11:28 | 2020-11-26 | 2020-11-13 17:33 | 2020-11-27 14:50 | 2020-11-27 16:41 |  | 2021-01-12 10:00 | 2021-01-12 14:00 | 2020-11-27 16:49 | 2021-02-12 14:00 | CR0013174 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W2 | 2021-01 | 48 | 48 | 87.9388 | 3 | 1 | 1 | 0.02 | 193567 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0.5625 | 0.53333 | 2020-10 | 0 | 0
1422 | CR0011543 | CTASK0017781 | Closed | OPUS-SCE | VInh Bui | 57 | 57 | 2020-01-17 09:56 | 2019-12-16 09:56 | Container | Service Management | SCEM |  |  |  | [ACTUAL] EDI 315 AV & AL trigger logic change for Internal Memo BL | 2019-12-13 14:30 | 2020-01-17 11:48 | 2020-01-10 15:39 | 2020-01-29 04:17 | 2020-02-06 10:14 |  | 2020-02-11 12:13 | 2020-02-25 08:20 | 2020-02-14 06:00 | 2020-04-06 13:00 | CR0011543 | Service ManagementSCEM | OPUS-SCE | 2020-W7 | 2020-02 | 57 | 0 | 59.9054 | 1 | 1 | 1 | 0 | 193469 | 0.2 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 13 | 0 | 0 | 2019-12 | 0 | 0
1423 | CR0012792 | CTASK0021384 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 28 | 28 | 2020-09-30 13:00 | 2020-09-01 13:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Development-Testing] Change to another special character from "~" as separator in OPUS Korea manifest F/F | 2020-09-15 15:20 | 2020-09-17 | 2020-09-16 16:05 | 2020-10-13 19:39 | 2020-10-14 10:17 |  | 2020-10-20 10:00 | 2020-10-20 09:30 | 2020-10-14 15:56 | 2020-11-20 14:00 | CR0012792 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2020-W43 | 2020-10 | 48 | 48 | 34.7779 | 3 | 1 | 1 | 0.06 | 193506 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 20 | 0 | 1.25 | 2020-09 | 0 | 0
1424 | CR0012792 | CTASK0023011 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 12 | 12 | 2020-10-20 13:00 | 2020-10-15 13:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Deploy-Test]Change to another special character from "~" as separator in OPUS Korea manifest F/F | 2020-09-15 15:20 | 2020-09-17 | 2020-09-16 16:05 | 2020-10-13 19:39 | 2020-10-14 10:17 |  | 2020-10-20 10:00 | 2020-10-20 09:30 | 2020-10-14 15:56 | 2020-11-20 14:00 | CR0012792 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2020-W43 | 2020-10 | 48 | 48 | 34.7779 | 3 | 1 | 1 | 0.06 | 193506 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 20 | 0 | 1.25 | 2020-09 | 0 | 0
1425 | CR0012792 | CTASK0021269 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 8 | 8 | 2020-07-21 13:00 | 2020-07-16 13:00 | Container | Service Management | Booking/Documentation | Manifest | Korea |  | [Analytics]Change to another special character from "~" as separator in OPUS Korea manifest F/F | 2020-09-15 15:20 | 2020-09-17 | 2020-09-16 16:05 | 2020-10-13 19:39 | 2020-10-14 10:17 |  | 2020-10-20 10:00 | 2020-10-20 09:30 | 2020-10-14 15:56 | 2020-11-20 14:00 | CR0012792 | Service ManagementBooking/DocumentationManifestKorea | OPUS-BKG-MFT-A | 2020-W43 | 2020-10 | 48 | 48 | 34.7779 | 3 | 1 | 1 | 0.06 | 193506 | 1.3 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 20 | 0 | 1.25 | 2020-09 | 0 | 0
1426 | CR0012998 | CTASK0021995 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 6 | 6 | 2020-08-31 19:30 | 2020-08-24 11:00 | Container | Service Management | Booking/Documentation | Manifest | EUA |  | [Estimation + Development + Testing + Deployment] [CLT internal] (HBA) EUA EDI CUST¦ Issues in Excel Upload EUA CUSTOMS SPAIN | 2020-08-31 16:54 | 2020-09-05 | 2020-09-04 16:14 | 2020-09-07 10:15 | 2020-09-08 16:10 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-09-08 17:59 | 2020-10-15 13:00 | CR0012998 | Service ManagementBooking/DocumentationManifestEUA | OPUS-BKG-MFT-E | 2020-W38 | 2020-09 | 10 | 12 | 14.7124 | 2 | 1 | 1 | 0.03 | 173280 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.18519 | 2020-08 | 0 | 0
1427 | CR0012998 | CTASK0022349 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 4 | 6 | 2020-09-10 19:30 | 2020-09-07 11:00 | Container | Service Management | Booking/Documentation | Manifest | EUA |  | [Development + Testing + Deployment] [CLT internal] (HBA) EUA EDI CUST¦ Issues in Excel Upload EUA CUSTOMS SPAIN | 2020-08-31 16:54 | 2020-09-05 | 2020-09-04 16:14 | 2020-09-07 10:15 | 2020-09-08 16:10 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-09-08 17:59 | 2020-10-15 13:00 | CR0012998 | Service ManagementBooking/DocumentationManifestEUA | OPUS-BKG-MFT-E | 2020-W38 | 2020-09 | 10 | 12 | 14.7124 | 2 | 1 | 1 | 0.03 | 173280 | 1.7 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0.18519 | 2020-08 | 0 | 0
1428 | CR0012904 | CTASK0021778 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 3 | 3 | 2020-08-11 19:30 | 2020-08-10 11:00 | Container | Service Management | Booking/Documentation | Manifest | Brazil |  | [Estimation] LA – "Opus FF" EDI seal mapping – Brazil Manifest | 2020-09-23 11:06 | 2020-09-26 | 2020-09-24 15:41 | 2020-11-07 10:21 | 2020-11-12 18:22 |  | 2020-12-01 10:00 | 2020-12-01 09:30 | 2020-11-19 13:11 | 2020-12-31 14:00 | CR0012904 | Service ManagementBooking/DocumentationManifestBrazil | OPUS-BKG-MFT-M | 2020-W49 | 2020-12 | 25 | 25 | 68.9543 | 3 | 1 | 1 | 0.02 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0.18519 | 2020-09 | 0 | 0
1429 | CR0012904 | CTASK0021892 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 16 | 16 | 2020-08-28 19:30 | 2020-08-18 11:00 | Container | Service Management | Booking/Documentation | Manifest | Brazil |  | [Development + Testing + Deployment] LA – "Opus FF" EDI seal mapping – Brazil Manifest | 2020-09-23 11:06 | 2020-09-26 | 2020-09-24 15:41 | 2020-11-07 10:21 | 2020-11-12 18:22 |  | 2020-12-01 10:00 | 2020-12-01 09:30 | 2020-11-19 13:11 | 2020-12-31 14:00 | CR0012904 | Service ManagementBooking/DocumentationManifestBrazil | OPUS-BKG-MFT-M | 2020-W49 | 2020-12 | 25 | 25 | 68.9543 | 3 | 1 | 1 | 0.02 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0.18519 | 2020-09 | 0 | 0
1430 | CR0012904 | CTASK0023639 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 6 | 6 | 2020-11-23 19:30 | 2020-11-17 11:00 | Container | Service Management | Booking/Documentation | Manifest | Brazil |  | [Deployment] LA – "Opus FF" EDI seal mapping – Brazil Manifest | 2020-09-23 11:06 | 2020-09-26 | 2020-09-24 15:41 | 2020-11-07 10:21 | 2020-11-12 18:22 |  | 2020-12-01 10:00 | 2020-12-01 09:30 | 2020-11-19 13:11 | 2020-12-31 14:00 | CR0012904 | Service ManagementBooking/DocumentationManifestBrazil | OPUS-BKG-MFT-M | 2020-W49 | 2020-12 | 25 | 25 | 68.9543 | 3 | 1 | 1 | 0.02 | 173280 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 30 | 0 | 0.18519 | 2020-09 | 0 | 0
1431 | CR0012541 | CTASK0019845 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 20 | 20 | 2020-06-30 16:26 | 2020-06-03 16:26 | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | NA * TRS * Connect CERS No field developed in SPP (CR0012325) with OPUS Rail billing UI's fields (CR0012324) | 2020-06-03 16:25 | 2020-06-30 21:00 | 2020-06-29 17:38 | 2020-07-07 01:43 | 2020-07-07 11:42 |  | 2020-07-14 11:00 | 2020-07-14 11:00 | 2020-07-08 01:08 | 2020-08-13 13:00 | CR0012541 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2020-W29 | 2020-07 | 40 | 40 | 40.7744 | 2 | 1 | 2 | 0.04 | 183432 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 27 | 0 | 0 | 2020-06 | 0 | 0
1432 | CR0012541 | CTASK0019846 | Closed | OPUS-TRS | Giang Nguyen Hoang | 20 | 20 | 2020-06-30 16:27 | 2020-06-03 16:27 | Container | Service Management | Trans S/O | USA/CA Rail | USA/CA Rail 404 EDI |  | NA * TRS * Connect CERS No field developed in SPP (CR0012325) with OPUS Rail billing UI's fields (CR0012324) | 2020-06-03 16:25 | 2020-06-30 21:00 | 2020-06-29 17:38 | 2020-07-07 01:43 | 2020-07-07 11:42 |  | 2020-07-14 11:00 | 2020-07-14 11:00 | 2020-07-08 01:08 | 2020-08-13 13:00 | CR0012541 | Service ManagementTrans S/OUSA/CA RailUSA/CA Rail 404 EDI | OPUS-TRS | 2020-W29 | 2020-07 | 40 | 40 | 40.7744 | 2 | 1 | 2 | 0.04 | 183440 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 27 | 0 | 0 | 2020-06 | 0 | 0
1433 | CR0012623 | CTASK0020595 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2020-07-24 19:38 | 2020-07-14 11:38 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] FMC No logic enhancement | 2020-07-15 10:24 | 2020-08-08 | 2020-08-07 10:22 | 2020-08-12 21:54 | 2020-08-13 16:04 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-13 16:04 | 2020-09-08 10:28 | CR0012623 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W37 | 2020-09 | 49 | 48 | 54.9837 | 6 | 1 | 2 | 0.04 | 193503 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.36364 | 2020-07 | 0 | 0
1434 | CR0012623 | CTASK0020068 | Closed | OPUS-BKG-M | Kieu Le | 18 | 18 | 2020-05-22 01:29 | 2020-05-13 17:29 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] FMC No logic enhancement | 2020-07-15 10:24 | 2020-08-08 | 2020-08-07 10:22 | 2020-08-12 21:54 | 2020-08-13 16:04 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-13 16:04 | 2020-09-08 10:28 | CR0012623 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W37 | 2020-09 | 49 | 48 | 54.9837 | 6 | 1 | 2 | 0.04 | 153106 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.4 | 2020-07 | 0 | 0
1435 | CR0012623 | CTASK0021685 | Closed | OPUS-BKG-M | Loc Tran | 1 | 1 | 2020-08-31 18:26 | 2020-08-04 18:26 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] FMC No logic enhancement | 2020-07-15 10:24 | 2020-08-08 | 2020-08-07 10:22 | 2020-08-12 21:54 | 2020-08-13 16:04 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-13 16:04 | 2020-09-08 10:28 | CR0012623 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W37 | 2020-09 | 49 | 48 | 54.9837 | 6 | 1 | 2 | 0.04 | 193503 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.36364 | 2020-07 | 0 | 0
1436 | CR0012623 | CTASK0020600 | Closed | OPUS-BKG-M | Loc Tran | 3 | 3 | 2020-09-30 18:54 | 2020-09-01 18:54 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] FMC No logic enhancement | 2020-07-15 10:24 | 2020-08-08 | 2020-08-07 10:22 | 2020-08-12 21:54 | 2020-08-13 16:04 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-13 16:04 | 2020-09-08 10:28 | CR0012623 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W37 | 2020-09 | 49 | 48 | 54.9837 | 6 | 1 | 2 | 0.04 | 193503 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.36364 | 2020-07 | 0 | 0
1437 | CR0012623 | CTASK0020565 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2020-06-11 01:48 | 2020-06-08 02:48 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] FMC No logic enhancement | 2020-07-15 10:24 | 2020-08-08 | 2020-08-07 10:22 | 2020-08-12 21:54 | 2020-08-13 16:04 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-13 16:04 | 2020-09-08 10:28 | CR0012623 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W37 | 2020-09 | 49 | 48 | 54.9837 | 6 | 1 | 2 | 0.04 | 153106 | 1.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.4 | 2020-07 | 0 | 0
1438 | CR0012623 | CTASK0020598 | Closed | OPUS-BKG-M | Loc Tran | 13 | 12 | 2020-07-31 19:37 | 2020-07-14 19:36 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] FMC No logic enhancement | 2020-07-15 10:24 | 2020-08-08 | 2020-08-07 10:22 | 2020-08-12 21:54 | 2020-08-13 16:04 |  | 2020-09-08 10:00 | 2020-09-08 10:00 | 2020-08-13 16:04 | 2020-09-08 10:28 | CR0012623 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W37 | 2020-09 | 49 | 48 | 54.9837 | 6 | 1 | 2 | 0.04 | 193503 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.36364 | 2020-07 | 0 | 0
1439 | CR0012212 | CTASK0019892 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 7 | 20 | 2020-06-30 17:00 | 2020-04-28 16:59 | Container | Service Management | Trans S/O |  |  |  | EUA - PARIS Project : Optimization of transports using external Software - ETL requirements for OPUS interface to PARIS phase 'zero' - Empty CY tranport jobs spin off | 2020-04-28 16:58 | 2020-07-31 18:00 | 2020-07-16 11:45 | 2020-09-04 21:39 | 2020-09-10 09:52 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-09-10 17:11 | 2020-10-15 13:00 | CR0012212 | Service ManagementTrans S/O | OPUS-TRS | 2020-W38 | 2020-09 | 25 | 40 | 139.7096 | 2 | 1 | 2 | 0.01 | 183432 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-04 | 0 | 0
1440 | CR0012212 | CTASK0019893 | Closed | OPUS-TRS | Giang Nguyen Hoang | 18 | 20 | 2020-06-30 17:00 | 2020-04-28 17:00 | Container | Service Management | Trans S/O |  |  |  | EUA - PARIS Project : Optimization of transports using external Software - ETL requirements for OPUS interface to PARIS phase 'zero' - Empty CY tranport jobs spin off | 2020-04-28 16:58 | 2020-07-31 18:00 | 2020-07-16 11:45 | 2020-09-04 21:39 | 2020-09-10 09:52 |  | 2020-09-15 10:00 | 2020-09-15 10:00 | 2020-09-10 17:11 | 2020-10-15 13:00 | CR0012212 | Service ManagementTrans S/O | OPUS-TRS | 2020-W38 | 2020-09 | 25 | 40 | 139.7096 | 2 | 1 | 2 | 0.01 | 183440 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-04 | 0 | 0
1441 | CR0012382 | CTASK0018996 | Closed | OPUS-SAP | Chuong Ta | 364 | 136 | 2020-06-30 11:33 | 2020-03-17 11:33 | Container | Statement Management | Statement Account Payable |  |  |  | [CLV EFFORT][JOO] Fixed clearing issue in SAP (over 999 lines) | 2020-03-30 18:39 | 2020-05-27 23:39 | 2020-05-25 13:13 | 2020-05-27 10:24 | 2020-05-27 10:44 |  | 2020-06-02 10:44 | 2020-06-02 11:38 | 2020-05-27 10:54 | 2020-07-02 13:00 | CR0012382 | Statement ManagementStatement Account Payable | OPUS-SAP | 2020-W23 | 2020-06 | 364 | 136 | 63.6703 | 1 | 1 | 1 | 0.09 | 183379 | 1.1 | 0 | 0 | 0 | 2 | 1 | 2 | 5 | 29 | 0 | 0.38462 | 2020-03 | 0 | 0
1442 | CR0012620 | CTASK0020083 | Closed | OPUS-SCG | Pham Khanh Van | 80 | 80 | 2020-07-31 10:14 | 2020-06-18 10:14 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | [CLV]New DG EDI application with DAL(SCG) | 2020-05-25 10:31 | 2020-08-01 | 2020-07-22 17:37 | 2020-08-04 16:19 | 2020-08-12 10:49 |  | 2020-08-18 09:40 | 2020-08-18 09:30 | 2020-08-13 16:28 | 2020-09-17 13:00 | CR0012620 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2020-W34 | 2020-08 | 164 | 160 | 84.9644 | 2 | 1 | 2 | 0.08 | 193477 | 1 | 0 | 0 | 0 | 2 | 1 | 2 | 3 | 30 | 0 | 0 | 2020-05 | 0 | 0
1443 | CR0012620 | CTASK0020865 | Closed | OPUS-SCG | Trang Duy Thong | 84 | 80 | 2020-07-10 10:00 | 2020-06-25 10:00 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Application for Partner Lines |  | [CLV]New DG EDI application with DAL(SCG) | 2020-05-25 10:31 | 2020-08-01 | 2020-07-22 17:37 | 2020-08-04 16:19 | 2020-08-12 10:49 |  | 2020-08-18 09:40 | 2020-08-18 09:30 | 2020-08-13 16:28 | 2020-09-17 13:00 | CR0012620 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Application for Partner Lines | OPUS-SCG | 2020-W34 | 2020-08 | 164 | 160 | 84.9644 | 2 | 1 | 2 | 0.08 | 193511 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 3 | 30 | 0 | 11 | 2020-05 | 0 | 0
1444 | CR0011926 | CTASK0019647 | Closed | OPUS-BKG-M | Vinh Tran | 6 | 6 | 2020-04-17 02:00 | 2020-04-16 02:00 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Testing][CLT Internal] NA *OPUS* Containers not Auto Attaching in the Reefer Application | 2020-03-23 09:22 | 2020-08-27 | 2020-06-22 12:25 | 2020-06-22 18:13 | 2020-07-30 14:30 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 14:33 | 2020-08-04 12:38 | CR0011926 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W32 | 2020-08 | 50 | 46 | 134.0262 | 6 | 1 | 3 | 0.01 | 193525 | 0.8 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.45455 | 2020-03 | 0 | 0
1445 | CR0011926 | CTASK0017060 | Closed | OPUS-BKG-M | Thien Lai | 24 | 24 | 2020-04-03 17:27 | 2020-03-23 17:27 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Development][CLT Internal] NA *OPUS* Containers not Auto Attaching in the Reefer Application | 2020-03-23 09:22 | 2020-08-27 | 2020-06-22 12:25 | 2020-06-22 18:13 | 2020-07-30 14:30 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 14:33 | 2020-08-04 12:38 | CR0011926 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W32 | 2020-08 | 50 | 46 | 134.0262 | 6 | 1 | 3 | 0.01 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.52941 | 2020-03 | 0 | 0
1446 | CR0011926 | CTASK0018939 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-07-31 18:50 | 2020-07-27 18:50 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Deployment][CLT Internal] NA *OPUS* Containers not Auto Attaching in the Reefer Application | 2020-03-23 09:22 | 2020-08-27 | 2020-06-22 12:25 | 2020-06-22 18:13 | 2020-07-30 14:30 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 14:33 | 2020-08-04 12:38 | CR0011926 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W32 | 2020-08 | 50 | 46 | 134.0262 | 6 | 1 | 3 | 0.01 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.52941 | 2020-03 | 0 | 0
1447 | CR0011926 | CTASK0018858 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-03-10 22:38 | 2020-03-09 18:38 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Design][CLT Internal] NA *OPUS* Containers not Auto Attaching in the Reefer Application | 2020-03-23 09:22 | 2020-08-27 | 2020-06-22 12:25 | 2020-06-22 18:13 | 2020-07-30 14:30 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 14:33 | 2020-08-04 12:38 | CR0011926 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W32 | 2020-08 | 50 | 46 | 134.0262 | 6 | 1 | 3 | 0.01 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.52941 | 2020-03 | 0 | 0
1448 | CR0011926 | CTASK0017059 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2019-11-09 01:05 | 2019-11-07 18:05 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Estimated][CLT Internal] NA *OPUS* Containers not Auto Attaching in the Reefer Application | 2020-03-23 09:22 | 2020-08-27 | 2020-06-22 12:25 | 2020-06-22 18:13 | 2020-07-30 14:30 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 14:33 | 2020-08-04 12:38 | CR0011926 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W32 | 2020-08 | 50 | 46 | 134.0262 | 6 | 1 | 3 | 0.01 | 153106 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.4 | 2020-03 | 0 | 0
1449 | CR0011926 | CTASK0017061 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-04-03 15:42 | 2020-03-25 02:42 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Testing][CLT Internal] NA *OPUS* Containers not Auto Attaching in the Reefer Application | 2020-03-23 09:22 | 2020-08-27 | 2020-06-22 12:25 | 2020-06-22 18:13 | 2020-07-30 14:30 |  | 2020-08-04 10:00 | 2020-08-04 10:00 | 2020-07-30 14:33 | 2020-08-04 12:38 | CR0011926 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W32 | 2020-08 | 50 | 46 | 134.0262 | 6 | 1 | 3 | 0.01 | 193567 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.52941 | 2020-03 | 0 | 0
1450 | CR0013266 | CTASK0023582 | Closed | OPUS-BKG-EBKG | Vinh Tran | 8 | 8 | 2020-12-16 02:00 | 2020-12-07 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] [CLT Internal] eBKG - Add validation regarding to-be customer | 2020-12-10 11:29 | 2020-12-19 | 2020-12-18 13:31 | 2021-01-29 11:33 | 2021-02-09 09:55 |  | 2021-03-16 11:00 | 2021-03-16 11:00 | 2021-03-03 18:15 | 2021-04-15 14:00 | CR0013266 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 32 | 32 | 95.9797 | 4 | 1 | 1 | 0.01 | 193525 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1451 | CR0013266 | CTASK0023580 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2020-11-17 02:00 | 2020-11-16 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] [CLT Internal] eBKG - Add validation regarding to-be customer | 2020-12-10 11:29 | 2020-12-19 | 2020-12-18 13:31 | 2021-01-29 11:33 | 2021-02-09 09:55 |  | 2021-03-16 11:00 | 2021-03-16 11:00 | 2021-03-03 18:15 | 2021-04-15 14:00 | CR0013266 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 32 | 32 | 95.9797 | 4 | 1 | 1 | 0.01 | 193525 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1452 | CR0013266 | CTASK0023581 | Closed | OPUS-BKG-EBKG | Vinh Tran | 16 | 16 | 2020-12-05 02:00 | 2020-11-30 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] [CLT Internal] eBKG - Add validation regarding to-be customer | 2020-12-10 11:29 | 2020-12-19 | 2020-12-18 13:31 | 2021-01-29 11:33 | 2021-02-09 09:55 |  | 2021-03-16 11:00 | 2021-03-16 11:00 | 2021-03-03 18:15 | 2021-04-15 14:00 | CR0013266 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 32 | 32 | 95.9797 | 4 | 1 | 1 | 0.01 | 193525 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1453 | CR0013266 | CTASK0023583 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-03-11 02:00 | 2021-03-08 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] [CLT Internal] eBKG - Add validation regarding to-be customer | 2020-12-10 11:29 | 2020-12-19 | 2020-12-18 13:31 | 2021-01-29 11:33 | 2021-02-09 09:55 |  | 2021-03-16 11:00 | 2021-03-16 11:00 | 2021-03-03 18:15 | 2021-04-15 14:00 | CR0013266 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W11 | 2021-03 | 32 | 32 | 95.9797 | 4 | 1 | 1 | 0.01 | 193525 | 1.5 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1454 | CR0012523 | CTASK0020282 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 8 | 8 | 2020-05-25 20:00 | 2020-05-25 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | General Full Container Release | [Estimation] FULREL (COREOR) Implementation with MYPKG Ports | 2020-06-09 11:54 | 2020-08-17 23:53 | 2020-08-14 18:11 | 2020-09-21 17:35 | 2020-09-23 17:08 |  | 2020-10-20 17:08 | 2020-10-20 17:38 | 2020-10-12 14:40 | 2020-11-20 14:00 | CR0012523 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseGeneral Full Container Release | OPUS-BKG-MFT-A | 2020-W43 | 2020-10 | 160 | 162 | 133.2184 | 4 | 2 | 1 | 0.05 | 173280 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 20 | 0 | 0.18519 | 2020-06 | 0 | 0
1455 | CR0012523 | CTASK0022821 | Closed | OPUS-BKG-IB | Thuc Tran | 32 | 32 | 2020-10-12 19:30 | 2020-10-01 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | General Full Container Release | [Deployment] FULREL (COREOR) Implementation with MYPKG Ports | 2020-06-09 11:54 | 2020-08-17 23:53 | 2020-08-14 18:11 | 2020-09-21 17:35 | 2020-09-23 17:08 |  | 2020-10-20 17:08 | 2020-10-20 17:38 | 2020-10-12 14:40 | 2020-11-20 14:00 | CR0012523 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseGeneral Full Container Release | OPUS-BKG-IB | 2020-W43 | 2020-10 | 160 | 162 | 133.2184 | 4 | 2 | 1 | 0.05 | 173280 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 20 | 0 | 0.18519 | 2020-06 | 0 | 0
1456 | CR0012523 | CTASK0022381 | Closed | OPUS-BKG-IB | Thuc Tran | 10 | 10 | 2020-09-09 19:30 | 2020-09-07 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | General Full Container Release | [Development + Testing + Deployment] FULREL (COREOR) Implementation with MYPKG Ports - Addition request | 2020-06-09 11:54 | 2020-08-17 23:53 | 2020-08-14 18:11 | 2020-09-21 17:35 | 2020-09-23 17:08 |  | 2020-10-20 17:08 | 2020-10-20 17:38 | 2020-10-12 14:40 | 2020-11-20 14:00 | CR0012523 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseGeneral Full Container Release | OPUS-BKG-IB | 2020-W43 | 2020-10 | 160 | 162 | 133.2184 | 4 | 2 | 1 | 0.05 | 173280 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 20 | 0 | 0.18519 | 2020-06 | 0 | 0
1457 | CR0012523 | CTASK0020607 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 110 | 112 | 2020-07-10 19:30 | 2020-06-10 11:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | General Full Container Release | [Development + Testing + Deployment] FULREL (COREOR) Implementation with MYPKG Ports | 2020-06-09 11:54 | 2020-08-17 23:53 | 2020-08-14 18:11 | 2020-09-21 17:35 | 2020-09-23 17:08 |  | 2020-10-20 17:08 | 2020-10-20 17:38 | 2020-10-12 14:40 | 2020-11-20 14:00 | CR0012523 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseGeneral Full Container Release | OPUS-BKG-MFT-A | 2020-W43 | 2020-10 | 160 | 162 | 133.2184 | 4 | 2 | 1 | 0.05 | 173280 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 20 | 0 | 0.18519 | 2020-06 | 0 | 0
1458 | CR0011735 | CTASK0016531 | Closed | OPUS-BKG-M | Vinh Tran | 8 | 8 | 2019-10-25 12:15 | 2019-10-21 12:15 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | NA *Standby* Make Tier/Role mandatory fields when booking agent escalates BKG/ leaves comment | 2019-10-18 17:19 | 2019-11-05 | 2019-10-25 13:45 | 2019-10-25 23:12 | 2019-10-28 14:31 | 2019-10-25 13:45 | 2019-11-05 14:32 | 2019-11-05 11:32 | 2019-10-28 23:02 | 2019-11-07 02:37 | CR0011735 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2019-W45 | 2019-11 | 8 | 8 | 17.8843 | 1 | 1 | 1 | 0.02 | 193525 | 0.4 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 7 | 0 | 0.45455 | 2019-10 | 0 | 0
1459 | CR0012918 | CTASK0022143 | Closed | OPUS-TRS | Giang Nguyen Hoang | 12 | 15 | 2020-08-31 14:06 | 2020-08-27 14:06 | Container | Service Management | Trans S/O |  |  |  | [CLT Internal] PARIS Phase 0 modification to prevent missing transaction type after BKG split. (2020/08) | 2020-08-20 10:08 | 2020-09-11 21:00 | 2020-09-04 16:09 | 2020-09-24 13:49 | 2020-09-24 14:08 |  | 2020-09-28 10:00 | 2020-10-06 11:57 | 2020-09-24 15:56 | 2020-11-05 14:00 | CR0012918 | Service ManagementTrans S/O | OPUS-TRS | 2020-W40 | 2020-09 | 27 | 30 | 38.9944 | 2 | 1 | 2 | 0.03 | 183440 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0 | 2020-08 | 0 | 0
1460 | CR0012918 | CTASK0022142 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 15 | 15 | 2020-08-31 14:05 | 2020-08-27 14:05 | Container | Service Management | Trans S/O |  |  |  | [CLT Internal] PARIS Phase 0 modification to prevent missing transaction type after BKG split. (2020/08) | 2020-08-20 10:08 | 2020-09-11 21:00 | 2020-09-04 16:09 | 2020-09-24 13:49 | 2020-09-24 14:08 |  | 2020-09-28 10:00 | 2020-10-06 11:57 | 2020-09-24 15:56 | 2020-11-05 14:00 | CR0012918 | Service ManagementTrans S/O | OPUS-TRS | 2020-W40 | 2020-09 | 27 | 30 | 38.9944 | 2 | 1 | 2 | 0.03 | 183432 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 36 | 0 | 0 | 2020-08 | 0 | 0
1461 | CR0011860 | CTASK0017922 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 52 | 52 | 2020-02-29 | 2020-02-17 09:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | Update P/Up CY(Empty container pickup CY) to OPUS (for customer : Samsung SDS) | 2020-02-13 13:55 | 2020-03-12 | 2020-03-11 17:19 | 2020-04-16 16:59 | 2020-09-29 13:03 |  | 2020-10-13 11:00 | 2020-10-13 11:00 | 2020-09-29 15:44 | 2020-11-13 14:00 | CR0011860 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W42 | 2020-10 | 67 | 52 | 242.8788 | 2 | 2 | 1 | 0.01 | 193488 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 20 | 0 | 2.1667 | 2020-02 | 0 | 0
1462 | CR0011860 | CTASK0017875 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 15 | 15 | 2020-01-16 15:10 | 2020-01-10 15:10 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Estimated]Update P/Up CY(Empty container pickup CY) to OPUS (for customer : Samsung SDS) | 2020-02-13 13:55 | 2020-03-12 | 2020-03-11 17:19 | 2020-04-16 16:59 | 2020-09-29 13:03 |  | 2020-10-13 11:00 | 2020-10-13 11:00 | 2020-09-29 15:44 | 2020-11-13 14:00 | CR0011860 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W42 | 2020-10 | 67 | 52 | 242.8788 | 2 | 2 | 1 | 0.01 | 193488 | 0.7 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 20 | 0 | 2.1667 | 2020-02 | 0 | 0
1463 | CR0013539 | CTASK0026200 | Closed | OPUS-TPB | Manh Nguyen | 44 | 44 | 2021-05-01 01:00 | 2021-04-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202104] TPB - Invoice Sender's email | 2021-03-31 16:18 | 2021-05-07 16:16 | 2021-05-07 11:15 | 2021-06-23 17:47 | 2021-06-24 08:39 |  | 2021-06-29 12:30 | 2021-06-29 11:43 | 2021-06-24 13:07 | 2021-07-29 14:00 | CR0013539 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2021-W26 | 2021-06 | 85 | 93 | 89.8419 | 4 | 1 | 1 | 0.04 | 153138 | 2.5 | 1 | 0 | 1 | 1 | 1 | 2 | 16 | 53 | 0.16667 | 0.16667 | 2021-03 | 1 | 1
1464 | CR0013539 | CTASK0026816 | Closed | OPUS-TPB | Manh Nguyen | 7 | 10 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202105] TPB - Invoice Sender's email | 2021-03-31 16:18 | 2021-05-07 16:16 | 2021-05-07 11:15 | 2021-06-23 17:47 | 2021-06-24 08:39 |  | 2021-06-29 12:30 | 2021-06-29 11:43 | 2021-06-24 13:07 | 2021-07-29 14:00 | CR0013539 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2021-W26 | 2021-06 | 85 | 93 | 89.8419 | 4 | 1 | 1 | 0.04 | 153138 | 2.5 | 1 | 0 | 1 | 1 | 1 | 2 | 16 | 53 | 0.16667 | 0.16667 | 2021-03 | 1 | 1
1465 | CR0013539 | CTASK0025759 | Closed | OPUS-TPB | Manh Nguyen | 10 | 14 | 2021-04-01 01:00 | 2021-03-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202103] TPB - Invoice Sender's email | 2021-03-31 16:18 | 2021-05-07 16:16 | 2021-05-07 11:15 | 2021-06-23 17:47 | 2021-06-24 08:39 |  | 2021-06-29 12:30 | 2021-06-29 11:43 | 2021-06-24 13:07 | 2021-07-29 14:00 | CR0013539 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2021-W26 | 2021-06 | 85 | 93 | 89.8419 | 4 | 1 | 1 | 0.04 | 153138 | 2.5 | 1 | 0 | 1 | 1 | 1 | 2 | 16 | 53 | 0.16667 | 0.16667 | 2021-03 | 1 | 1
1466 | CR0013539 | CTASK0027342 | Closed | OPUS-TPB | Manh Nguyen | 24 | 25 | 2021-07-01 01:00 | 2021-06-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202106] TPB - Invoice Sender's email | 2021-03-31 16:18 | 2021-05-07 16:16 | 2021-05-07 11:15 | 2021-06-23 17:47 | 2021-06-24 08:39 |  | 2021-06-29 12:30 | 2021-06-29 11:43 | 2021-06-24 13:07 | 2021-07-29 14:00 | CR0013539 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2021-W26 | 2021-06 | 85 | 93 | 89.8419 | 4 | 1 | 1 | 0.04 | 153138 | 2.5 | 1 | 0 | 1 | 1 | 1 | 2 | 16 | 53 | 0.16667 | 0.16667 | 2021-03 | 1 | 1
1467 | CR0011878 | CTASK0020652 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 52 | 52 | 2020-07-31 19:30 | 2020-07-06 11:00 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (US Office) | Manifest Transmit (MI) | [Development+ Testing+ Deployment][CLT Internal] NA - BKG - HBL was submitted to CBP even whe filer type is 2 | 2020-06-15 13:39 | 2020-11-01 |  | 2021-02-15 11:30 | 2021-03-10 13:08 |  | 2021-03-16 09:31 | 2021-03-16 09:53 | 2021-03-11 14:11 | 2021-04-15 14:00 | CR0011878 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (US Office)Manifest Transmit (MI) | OPUS-BKG-MFT-M | 2021-W11 | 2021-03 | 64 | 67 | 273.8277 | 3 | 2 | 1 | 0.01 | 193512 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 9 | 46 | 0.2963 | 0.5 | 2020-06 | 0 | 0
1468 | CR0011878 | CTASK0020584 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 7 | 10 | 2020-06-10 17:14 | 2020-06-09 17:14 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (US Office) | Manifest Transmit (MI) | [Estimation][CLT Internal] NA - BKG - HBL was submitted to CBP even whe filer type is 2 | 2020-06-15 13:39 | 2020-11-01 |  | 2021-02-15 11:30 | 2021-03-10 13:08 |  | 2021-03-16 09:31 | 2021-03-16 09:53 | 2021-03-11 14:11 | 2021-04-15 14:00 | CR0011878 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (US Office)Manifest Transmit (MI) | OPUS-BKG-MFT-M | 2021-W11 | 2021-03 | 64 | 67 | 273.8277 | 3 | 2 | 1 | 0.01 | 193512 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 9 | 46 | 0.2963 | 0.5 | 2020-06 | 0 | 0
1469 | CR0011878 | CTASK0025778 | Closed | OPUS-BKG-MFT-M | Nhut Nguyen Minh | 5 | 5 | 2021-03-16 15:14 | 2021-03-09 15:14 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (US Office) | Manifest Transmit (MI) | [Deployment][CLT Internal] NA - BKG - HBL was submitted to CBP even whe filer type is 2 | 2020-06-15 13:39 | 2020-11-01 |  | 2021-02-15 11:30 | 2021-03-10 13:08 |  | 2021-03-16 09:31 | 2021-03-16 09:53 | 2021-03-11 14:11 | 2021-04-15 14:00 | CR0011878 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (US Office)Manifest Transmit (MI) | OPUS-BKG-MFT-M | 2021-W11 | 2021-03 | 64 | 67 | 273.8277 | 3 | 2 | 1 | 0.01 | 193512 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 9 | 46 | 0.2963 | 0.5 | 2020-06 | 0 | 0
1470 | CR0010894 | CTASK0017811 | Closed | OPUS-CTM | Phu Nguyen Hoang | 32 | 32 | 2020-01-11 01:00 | 2020-01-08 00:30 | Container | Service Management | CNTR Movement |  |  |  | Fix source as user's request. | 2019-10-30 11:21 | 2019-11-30 | 2019-11-28 14:10 | 2020-03-09 23:59 | 2020-03-10 13:52 |  | 2020-03-17 10:00 | 2020-03-17 10:00 | 2020-03-10 18:03 | 2020-04-16 13:00 | CR0010894 | Service ManagementCNTR Movement | OPUS-CTM | 2020-W12 | 2020-03 | 67 | 0 | 138.944 | 2 | 1 | 2 | 0 | 193463 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 25 | 0 | 0 | 2019-10 | 0 | 0
1471 | CR0010894 | CTASK0018244 | Closed | OPUS-CTM | Tran Le | 35 | 35 |  |  | Container | Service Management | CNTR Movement |  |  |  | investigate to fix source to pass UAT | 2019-10-30 11:21 | 2019-11-30 | 2019-11-28 14:10 | 2020-03-09 23:59 | 2020-03-10 13:52 |  | 2020-03-17 10:00 | 2020-03-17 10:00 | 2020-03-10 18:03 | 2020-04-16 13:00 | CR0010894 | Service ManagementCNTR Movement | OPUS-CTM | 2020-W12 | 2020-03 | 67 | 0 | 138.944 | 2 | 1 | 2 | 0 | 193501 | 0.1 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 25 | 0 | 0 | 2019-10 | 0 | 0
1472 | CR0013586 | CTASK0025313 | Closed | OPUS-SPC | Toai Phan | 30 | 30 | 2021-03-31 11:42 | 2021-02-08 11:42 | Container | Sales Management | Space Control |  |  |  | Add 'Booking Via' filter in SPC UIs | 2021-02-18 12:52 | 2021-02-23 12:52 | 2021-02-23 08:57 | 2021-02-25 09:18 | 2021-02-25 10:07 |  | 2021-03-05 10:07 | 2021-03-02 09:24 | 2021-02-25 15:21 | 2021-03-15 09:25 | CR0013586 | Sales ManagementSpace Control | OPUS-SPC | 2021-W9 | 2021-03 | 30 | 30 | 14.8852 | 1 | 1 | 1 | 0.08 | 183427 | 2.2 | 0 | 0 | 0 | 1 | 1 | 1 | 13 | 46 | 0 | 0 | 2021-02 | 0 | 0
1473 | CR0010212 | CTASK0012189 | Closed | OPUS-BKG-M | Nam Nguyen | 86 | 16 | 2019-08-30 09:27 | 2019-08-26 09:20 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | BRN contents change request | 2019-04-17 10:05 | 2019-10-01 | 2019-09-30 17:47 | 2019-11-19 16:25 | 2019-11-20 17:18 |  | 2019-11-26 17:18 | 2019-11-26 11:51 | 2019-11-20 19:13 | 2019-12-09 14:20 | CR0010212 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2019-W48 | 2019-11 | 86 | 48 | 223.3004 | 2 | 1 | 1 | 0.01 | 123048 | 0.5 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 7 | 0 | 0.5 | 2019-04 | 0 | 0
1474 | CR0010212 | CTASK0016215 | Closed | OPUS-BKG-M | Nam Nguyen | 32 | 32 | 2019-09-20 11:05 | 2019-09-09 11:04 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | BRN contents change request | 2019-04-17 10:05 | 2019-10-01 | 2019-09-30 17:47 | 2019-11-19 16:25 | 2019-11-20 17:18 |  | 2019-11-26 17:18 | 2019-11-26 11:51 | 2019-11-20 19:13 | 2019-12-09 14:20 | CR0010212 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2019-W48 | 2019-11 | 86 | 48 | 223.3004 | 2 | 1 | 1 | 0.01 | 123048 | 0.5 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 7 | 0 | 0.5 | 2019-04 | 0 | 0
1475 | CR0012390 | CTASK0021093 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-08-31 18:50 | 2020-08-01 18:50 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI |  | [Development] Add "Contract Party name" and "Contract Number" in COPARN (310) - Only Flat File Change | 2020-08-11 08:48 | 2020-09-03 | 2020-08-27 14:33 | 2020-12-07 11:01 | 2020-12-08 09:47 |  | 2020-12-29 10:00 | 2020-12-29 10:00 | 2020-12-10 10:04 | 2021-01-28 14:00 | CR0012390 | Service ManagementBooking/DocumentationBookingFax/Email/EDI | OPUS-BKG-M | 2020-W53 | 2020-12 | 27 | 27 | 140.0502 | 5 | 1 | 1 | 0.01 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.28571 | 2020-08 | 0 | 0
1476 | CR0012390 | CTASK0022122 | Closed | OPUS-BKG-M | Loc Tran | 3 | 3 | 2020-08-31 19:37 | 2020-08-25 19:37 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI |  | [Testing] Add "Contract Party name" and "Contract Number" in COPARN (310) - Only Flat File Change | 2020-08-11 08:48 | 2020-09-03 | 2020-08-27 14:33 | 2020-12-07 11:01 | 2020-12-08 09:47 |  | 2020-12-29 10:00 | 2020-12-29 10:00 | 2020-12-10 10:04 | 2021-01-28 14:00 | CR0012390 | Service ManagementBooking/DocumentationBookingFax/Email/EDI | OPUS-BKG-M | 2020-W53 | 2020-12 | 27 | 27 | 140.0502 | 5 | 1 | 1 | 0.01 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.28571 | 2020-08 | 0 | 0
1477 | CR0012390 | CTASK0021096 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-08-31 18:50 | 2020-08-01 18:50 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI |  | [Testing] Add "Contract Party name" and "Contract Number" in COPARN (310) - Only Flat File Change | 2020-08-11 08:48 | 2020-09-03 | 2020-08-27 14:33 | 2020-12-07 11:01 | 2020-12-08 09:47 |  | 2020-12-29 10:00 | 2020-12-29 10:00 | 2020-12-10 10:04 | 2021-01-28 14:00 | CR0012390 | Service ManagementBooking/DocumentationBookingFax/Email/EDI | OPUS-BKG-M | 2020-W53 | 2020-12 | 27 | 27 | 140.0502 | 5 | 1 | 1 | 0.01 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.28571 | 2020-08 | 0 | 0
1478 | CR0012390 | CTASK0021063 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2020-07-09 02:00 | 2020-07-03 19:31 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI |  | [Design] Add "Contract Party name" and "Contract Number" in COPARN (310) - Only Flat File Change | 2020-08-11 08:48 | 2020-09-03 | 2020-08-27 14:33 | 2020-12-07 11:01 | 2020-12-08 09:47 |  | 2020-12-29 10:00 | 2020-12-29 10:00 | 2020-12-10 10:04 | 2021-01-28 14:00 | CR0012390 | Service ManagementBooking/DocumentationBookingFax/Email/EDI | OPUS-BKG-M | 2020-W53 | 2020-12 | 27 | 27 | 140.0502 | 5 | 1 | 1 | 0.01 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.28571 | 2020-08 | 0 | 0
1479 | CR0012390 | CTASK0021099 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2020-12-31 18:51 | 2020-12-01 18:51 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI |  | [Deployment] Add "Contract Party name" and "Contract Number" in COPARN (310) - Only Flat File Change | 2020-08-11 08:48 | 2020-09-03 | 2020-08-27 14:33 | 2020-12-07 11:01 | 2020-12-08 09:47 |  | 2020-12-29 10:00 | 2020-12-29 10:00 | 2020-12-10 10:04 | 2021-01-28 14:00 | CR0012390 | Service ManagementBooking/DocumentationBookingFax/Email/EDI | OPUS-BKG-M | 2020-W53 | 2020-12 | 27 | 27 | 140.0502 | 5 | 1 | 1 | 0.01 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 30 | 0 | 0.28571 | 2020-08 | 0 | 0
1480 | CR0011802 | CTASK0016727 | Closed | OPUS-BKG-M | Thien Lai | 10 | 10 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Estimated] NA *Standby* XXX guidance confusing to staff - Updated to XXX - No Constraint | 2019-10-28 16:14 | 2019-11-12 | 2019-11-06 10:30 | 2019-12-27 01:19 | 2020-01-06 12:16 | 2019-11-06 10:31 | 2020-01-14 12:16 | 2020-01-14 12:39 | 2020-01-07 04:59 | 2020-01-18 04:40 | CR0011802 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W3 | 2020-01 | 32 | 20 | 77.8352 | 2 | 1 | 2 | 0.01 | 193567 | 0.3 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 10 | 0 | 0.52941 | 2019-10 | 0 | 0
1481 | CR0011802 | CTASK0016738 | Closed | OPUS-BKG-M | Nam Nguyen | 22 | 20 | 2019-11-01 13:45 | 2019-10-28 13:45 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | NA *Standby* XXX guidance confusing to staff - Updated to XXX - No Constraint | 2019-10-28 16:14 | 2019-11-12 | 2019-11-06 10:30 | 2019-12-27 01:19 | 2020-01-06 12:16 | 2019-11-06 10:31 | 2020-01-14 12:16 | 2020-01-14 12:39 | 2020-01-07 04:59 | 2020-01-18 04:40 | CR0011802 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W3 | 2020-01 | 32 | 20 | 77.8352 | 2 | 1 | 2 | 0.01 | 123048 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 10 | 0 | 0.46154 | 2019-10 | 0 | 0
1482 | CR0013302 | CTASK0023952 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 31 | 30 | 2020-12-31 12:14 | 2020-12-11 12:13 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EUA - Add 'Partial Shipment' flag to EU Full Cntr Release | 2020-12-03 11:22 | 2020-12-31 23:21 | 2020-12-29 16:56 | 2020-12-31 10:18 | 2021-01-06 11:42 |  | 2021-01-12 11:41 | 2021-01-12 14:40 | 2021-01-07 16:10 | 2021-02-12 14:00 | CR0013302 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W2 | 2021-01 | 31 | 30 | 40.0136 | 1 | 1 | 1 | 0.03 | 193512 | 1.4 | 1 | 0 | 0 | 1 | 1 | 1 | 14 | 40 | 0.2963 | 0.3125 | 2020-12 | 0 | 0
1483 | CR0011620 | CTASK0017739 | Closed | OPUS-TRS | Giang Nguyen Hoang | 36 | 28 | 2020-02-14 18:00 | 2020-01-06 09:00 | Container | Service Management | Trans S/O | Service Order | Creation |  | TRS - Request to add validation logic to verify the 'amended' routes thru SO creation / correction screen exists in PRD with relevant trans mode | 2020-01-06 09:32 | 2020-02-29 18:00 | 2020-02-11 10:28 | 2020-05-16 06:40 | 2020-05-21 10:43 |  | 2020-06-09 11:00 | 2020-06-09 15:12 | 2020-05-21 12:23 | 2020-07-10 13:00 | CR0011620 | Service ManagementTrans S/OService OrderCreation | OPUS-TRS | 2020-W24 | 2020-06 | 72 | 56 | 155.0611 | 2 | 1 | 2 | 0.02 | 183440 | 0.8 | 0 | 0 | 0 | 1 | 1 | 3 | 5 | 29 | 0 | 0 | 2020-01 | 0 | 0
1484 | CR0011620 | CTASK0017738 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 36 | 28 | 2020-02-14 18:00 | 2020-01-06 09:00 | Container | Service Management | Trans S/O | Service Order | Creation |  | TRS - Request to add validation logic to verify the 'amended' routes thru SO creation / correction screen exists in PRD with relevant trans mode | 2020-01-06 09:32 | 2020-02-29 18:00 | 2020-02-11 10:28 | 2020-05-16 06:40 | 2020-05-21 10:43 |  | 2020-06-09 11:00 | 2020-06-09 15:12 | 2020-05-21 12:23 | 2020-07-10 13:00 | CR0011620 | Service ManagementTrans S/OService OrderCreation | OPUS-TRS | 2020-W24 | 2020-06 | 72 | 56 | 155.0611 | 2 | 1 | 2 | 0.02 | 183432 | 0.8 | 0 | 0 | 0 | 1 | 1 | 3 | 5 | 29 | 0 | 0 | 2020-01 | 0 | 0
1485 | CR0013433 | CTASK0025266 | Closed | OPUS-BKG-OB | Nam Nguyen | 23 | 26 | 2021-03-12 17:01 | 2021-03-05 17:01 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Development & Testing] Send BL image with filename based on customer request - Lotte Global Logis | 2021-02-09 16:45 | 2021-03-31 16:45 | 2021-03-30 09:39 | 2021-04-01 09:24 | 2021-04-07 15:17 |  | 2021-04-20 15:17 | 2021-04-20 10:42 | 2021-04-08 11:38 | 2021-05-20 14:00 | CR0013433 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W16 | 2021-04 | 27 | 34 | 69.9391 | 3 | 1 | 1 | 0.02 | 123048 | 2.4 | 2 | 0 | 0 | 1 | 1 | 2 | 5 | 27 | 0.22222 | 0.047619 | 2021-02 | 0 | 0
1486 | CR0013433 | CTASK0025270 | Closed | OPUS-BKG-OB | Nam Nguyen | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Deployment] Send BL image with filename based on customer request - Lotte Global Logis | 2021-02-09 16:45 | 2021-03-31 16:45 | 2021-03-30 09:39 | 2021-04-01 09:24 | 2021-04-07 15:17 |  | 2021-04-20 15:17 | 2021-04-20 10:42 | 2021-04-08 11:38 | 2021-05-20 14:00 | CR0013433 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W16 | 2021-04 | 27 | 34 | 69.9391 | 3 | 1 | 1 | 0.02 | 123048 | 2.4 | 2 | 0 | 0 | 1 | 1 | 2 | 5 | 27 | 0.22222 | 0.047619 | 2021-02 | 0 | 0
1487 | CR0013433 | CTASK0025267 | Closed | OPUS-BKG-OB | Nam Nguyen | 4 | 4 | 2021-02-26 17:14 | 2021-02-21 17:14 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Design] Send BL image with filename based on customer request - Lotte Global Logis | 2021-02-09 16:45 | 2021-03-31 16:45 | 2021-03-30 09:39 | 2021-04-01 09:24 | 2021-04-07 15:17 |  | 2021-04-20 15:17 | 2021-04-20 10:42 | 2021-04-08 11:38 | 2021-05-20 14:00 | CR0013433 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W16 | 2021-04 | 27 | 34 | 69.9391 | 3 | 1 | 1 | 0.02 | 123048 | 2.4 | 2 | 0 | 0 | 1 | 1 | 2 | 5 | 27 | 0.22222 | 0.047619 | 2021-02 | 0 | 0
1488 | CR0012645 | CTASK0020891 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 36 | 36 | 2020-07-17 19:30 | 2020-07-03 09:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Development Test Deployment] [LA ENHANCEMENT] Correct POD // according to the vessel // CLL | 2020-07-15 17:11 | 2020-07-23 | 2020-07-22 14:18 | 2020-08-21 15:01 | 2020-08-24 11:52 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-24 23:02 | 2020-10-01 13:00 | CR0012645 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W36 | 2020-09 | 50 | 50 | 47.7008 | 4 | 1 | 1 | 0.04 | 193506 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-07 | 0 | 0
1489 | CR0012645 | CTASK0022127 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 4 | 4 | 2020-09-01 13:00 | 2020-08-27 13:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Production] [LA ENHANCEMENT] Correct POD // according to the vessel // CLL | 2020-07-15 17:11 | 2020-07-23 | 2020-07-22 14:18 | 2020-08-21 15:01 | 2020-08-24 11:52 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-24 23:02 | 2020-10-01 13:00 | CR0012645 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W36 | 2020-09 | 50 | 50 | 47.7008 | 4 | 1 | 1 | 0.04 | 193506 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-07 | 0 | 0
1490 | CR0012645 | CTASK0021510 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 2 | 2 | 2020-07-28 13:00 | 2020-07-28 13:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Additional Development][LA ENHANCEMENT] Correct POD // according to the vessel // CLL (Add Requirment) | 2020-07-15 17:11 | 2020-07-23 | 2020-07-22 14:18 | 2020-08-21 15:01 | 2020-08-24 11:52 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-24 23:02 | 2020-10-01 13:00 | CR0012645 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W36 | 2020-09 | 50 | 50 | 47.7008 | 4 | 1 | 1 | 0.04 | 193506 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-07 | 0 | 0
1491 | CR0012645 | CTASK0020778 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 8 | 8 | 2020-06-23 15:48 | 2020-06-18 15:48 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Analytics] [LA ENHANCEMENT] Correct POD // according to the vessel // CLL | 2020-07-15 17:11 | 2020-07-23 | 2020-07-22 14:18 | 2020-08-21 15:01 | 2020-08-24 11:52 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-24 23:02 | 2020-10-01 13:00 | CR0012645 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W36 | 2020-09 | 50 | 50 | 47.7008 | 4 | 1 | 1 | 0.04 | 193506 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 1.25 | 2020-07 | 0 | 0
1492 | CR0012934 | CTASK0021889 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 9 | 8 | 2020-08-26 14:20 | 2020-08-20 14:20 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [CLT Internal] Change the mapping IBI_IB_BKG_IND of 301 EDI flat file more reasonable and simple. | 2020-08-24 13:45 | 2020-09-17 | 2020-09-09 14:13 | 2020-09-17 17:20 | 2020-09-21 08:58 |  | 2020-10-27 10:00 | 2020-10-27 10:00 | 2020-09-21 17:53 | 2020-11-27 14:00 | CR0012934 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2020-W44 | 2020-10 | 9 | 10 | 63.8438 | 2 | 1 | 1 | 0.01 | 193488 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 20 | 0 | 0.28125 | 2020-08 | 0 | 0
1493 | CR0012934 | CTASK0022074 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 2 | 2 |  |  | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Deployment][CLT Internal] Change the mapping IBI_IB_BKG_IND of 301 EDI flat file more reasonable and simple. | 2020-08-24 13:45 | 2020-09-17 | 2020-09-09 14:13 | 2020-09-17 17:20 | 2020-09-21 08:58 |  | 2020-10-27 10:00 | 2020-10-27 10:00 | 2020-09-21 17:53 | 2020-11-27 14:00 | CR0012934 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2020-W44 | 2020-10 | 9 | 10 | 63.8438 | 2 | 1 | 1 | 0.01 | 193488 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 20 | 0 | 0.28125 | 2020-08 | 0 | 0
1494 | CR0013832 | CTASK0026669 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-05-11 10:28 | 2021-05-10 10:28 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] Roll Over Function Enhancement | 2021-05-20 10:09 | 2021-06-08 22:08 | 2021-06-07 15:42 | 2021-06-09 09:50 | 2021-06-11 08:03 |  | 2021-06-22 10:03 | 2021-06-22 10:49 | 2021-06-11 16:37 | 2021-07-23 14:00 | CR0013832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W25 | 2021-06 | 46 | 46 | 32.9958 | 4 | 1 | 1 | 0.06 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.53659 | 0.28125 | 2021-05 | 0 | 0
1495 | CR0013832 | CTASK0026928 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-06-15 19:31 | 2021-06-14 11:31 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal] Roll Over Function Enhancement | 2021-05-20 10:09 | 2021-06-08 22:08 | 2021-06-07 15:42 | 2021-06-09 09:50 | 2021-06-11 08:03 |  | 2021-06-22 10:03 | 2021-06-22 10:49 | 2021-06-11 16:37 | 2021-07-23 14:00 | CR0013832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W25 | 2021-06 | 46 | 46 | 32.9958 | 4 | 1 | 1 | 0.06 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.53659 | 0.28125 | 2021-05 | 0 | 0
1496 | CR0013832 | CTASK0026927 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-06-05 02:00 | 2021-06-01 11:02 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] Roll Over Function Enhancement | 2021-05-20 10:09 | 2021-06-08 22:08 | 2021-06-07 15:42 | 2021-06-09 09:50 | 2021-06-11 08:03 |  | 2021-06-22 10:03 | 2021-06-22 10:49 | 2021-06-11 16:37 | 2021-07-23 14:00 | CR0013832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W25 | 2021-06 | 46 | 46 | 32.9958 | 4 | 1 | 1 | 0.06 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.53659 | 0.28125 | 2021-05 | 0 | 0
1497 | CR0013832 | CTASK0026926 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 28 | 28 | 2021-05-27 19:30 | 2021-05-19 11:20 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal] Roll Over Function Enhancement | 2021-05-20 10:09 | 2021-06-08 22:08 | 2021-06-07 15:42 | 2021-06-09 09:50 | 2021-06-11 08:03 |  | 2021-06-22 10:03 | 2021-06-22 10:49 | 2021-06-11 16:37 | 2021-07-23 14:00 | CR0013832 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W25 | 2021-06 | 46 | 46 | 32.9958 | 4 | 1 | 1 | 0.06 | 193488 | 1.9 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.53659 | 0.28125 | 2021-05 | 0 | 0
1498 | CR0013237 | CTASK0023315 | Closed | OPUS-BKG-M | Loc Tran | 11 | 16 | 2020-11-30 19:15 | 2020-11-02 19:15 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Design][CLT Internal] On Dock validation on all BKG UIs which can change booking route. | 2020-12-28 20:18 | 2021-02-11 02:00 | 2021-02-08 13:32 | 2021-02-10 15:40 | 2021-03-01 14:44 |  | 2021-03-16 10:00 | 2021-03-16 10:00 | 2021-03-02 13:38 | 2021-04-15 14:00 | CR0013237 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2021-W11 | 2021-03 | 59 | 58 | 77.571 | 4 | 1 | 1 | 0.03 | 193503 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.33333 | 0.28571 | 2020-12 | 0 | 0
1499 | CR0013237 | CTASK0023725 | Closed | OPUS-BKG-M | Loc Tran | 24 | 20 | 2020-12-31 19:30 | 2020-12-10 11:30 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Development][CLT Internal] On Dock validation on all BKG UIs which can change booking route. | 2020-12-28 20:18 | 2021-02-11 02:00 | 2021-02-08 13:32 | 2021-02-10 15:40 | 2021-03-01 14:44 |  | 2021-03-16 10:00 | 2021-03-16 10:00 | 2021-03-02 13:38 | 2021-04-15 14:00 | CR0013237 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2021-W11 | 2021-03 | 59 | 58 | 77.571 | 4 | 1 | 1 | 0.03 | 193503 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.33333 | 0.28571 | 2020-12 | 0 | 0
1500 | CR0013237 | CTASK0023729 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-03-16 16:33 | 2021-03-08 16:33 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Deployment][CLT Internal] On Dock validation on all BKG UIs which can change booking route. | 2020-12-28 20:18 | 2021-02-11 02:00 | 2021-02-08 13:32 | 2021-02-10 15:40 | 2021-03-01 14:44 |  | 2021-03-16 10:00 | 2021-03-16 10:00 | 2021-03-02 13:38 | 2021-04-15 14:00 | CR0013237 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2021-W11 | 2021-03 | 59 | 58 | 77.571 | 4 | 1 | 1 | 0.03 | 193503 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.33333 | 0.28571 | 2020-12 | 0 | 0
1501 | CR0013237 | CTASK0023727 | Closed | OPUS-BKG-M | Loc Tran | 20 | 18 | 2020-12-31 19:35 | 2020-12-14 19:35 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Testing][CLT Internal] On Dock validation on all BKG UIs which can change booking route. | 2020-12-28 20:18 | 2021-02-11 02:00 | 2021-02-08 13:32 | 2021-02-10 15:40 | 2021-03-01 14:44 |  | 2021-03-16 10:00 | 2021-03-16 10:00 | 2021-03-02 13:38 | 2021-04-15 14:00 | CR0013237 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2021-W11 | 2021-03 | 59 | 58 | 77.571 | 4 | 1 | 1 | 0.03 | 193503 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 9 | 46 | 0.33333 | 0.28571 | 2020-12 | 0 | 0
1502 | CR0012068 | CTASK0017565 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [CLT Internal] AS - OPUS CONTAINER - SHIPPER CODE POP UP ERROR | 2019-12-20 10:21 | 2019-12-24 10:21 | 2019-12-20 15:40 |  | 2019-12-20 15:41 |  | 2019-12-24 10:00 | 2019-12-25 12:36 | 2019-12-24 10:54 | 2020-01-18 23:13 | CR0012068 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2019-W52 | 2019-12 | 4 | 0 | 3.9856 | 1 | 1 | 1 | 0 | 193567 | 0.4 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 18 | 0 | 0.52941 | 2019-12 | 0 | 0
1503 | CR0012948 | CTASK0022693 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 17 | 17 | 2020-12-30 16:00 | 2020-12-01 16:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193488 | 1.3 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.53659 | 0.28125 | 2020-09 | 0 | 0
1504 | CR0012948 | CTASK0022678 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 18 | 18 | 2021-01-01 01:59 | 2020-12-23 10:30 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193470 | 1.5 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.36842 | 0.17391 | 2020-09 | 0 | 0
1505 | CR0012948 | CTASK0022602 | Closed | OPUS-BKG-M | Kieu Le | 14 | 14 | 2020-09-25 19:45 | 2020-09-21 02:45 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 153106 | 2 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.22951 | 0.4 | 2020-09 | 0 | 0
1506 | CR0012948 | CTASK0022689 | Closed | OPUS-BKG-M | Kieu Le | 28 | 28 | 2020-11-30 15:56 | 2020-11-01 15:56 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 153106 | 2 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.22951 | 0.4 | 2020-09 | 0 | 0
1507 | CR0012948 | CTASK0022596 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 | 2020-09-24 02:00 | 2020-09-21 10:30 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193470 | 1.5 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.36842 | 0.17391 | 2020-09 | 0 | 0
1508 | CR0012948 | CTASK0022676 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 20 | 20 | 2020-11-14 01:59 | 2020-10-26 10:30 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193470 | 1.5 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.36842 | 0.17391 | 2020-09 | 0 | 0
1509 | CR0012948 | CTASK0022675 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 57 | 86 | 2020-10-24 01:59 | 2020-09-28 10:30 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193470 | 1.5 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.36842 | 0.17391 | 2020-09 | 0 | 0
1510 | CR0012948 | CTASK0022692 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-12-31 15:59 | 2020-12-14 15:59 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 153106 | 2 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.22951 | 0.4 | 2020-09 | 0 | 0
1511 | CR0012948 | CTASK0022682 | Closed | OPUS-BKG-EBKG | Vinh Tran | 8 | 8 | 2020-12-02 02:00 | 2020-12-01 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193525 | 1.3 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.41667 | 0.47368 | 2020-09 | 0 | 0
1512 | CR0012948 | CTASK0022690 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 18 | 20 | 2020-11-16 15:57 | 2020-11-06 09:57 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193488 | 1.3 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.53659 | 0.28125 | 2020-09 | 0 | 0
1513 | CR0012948 | CTASK0022685 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 93 | 93 | 2020-10-31 01:52 | 2020-10-01 02:52 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193488 | 1.3 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.53659 | 0.28125 | 2020-09 | 0 | 0
1514 | CR0012948 | CTASK0022628 | Closed | OPUS-BKG-EBKG | Vinh Tran | 8 | 8 | 2020-09-24 02:00 | 2020-09-21 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193525 | 1.3 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.41667 | 0.47368 | 2020-09 | 0 | 0
1515 | CR0012948 | CTASK0022680 | Closed | OPUS-BKG-EBKG | Vinh Tran | 16 | 20 | 2020-11-14 02:00 | 2020-11-06 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193525 | 1.3 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.41667 | 0.47368 | 2020-09 | 0 | 0
1516 | CR0012948 | CTASK0022684 | Closed | OPUS-BKG-M | Kieu Le | 120 | 120 | 2020-10-31 01:51 | 2020-10-01 02:51 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 153106 | 2 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.22951 | 0.4 | 2020-09 | 0 | 0
1517 | CR0012948 | CTASK0022679 | Closed | OPUS-BKG-EBKG | Vinh Tran | 44 | 44 | 2020-10-24 02:00 | 2020-09-30 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] EUA - AUTO UPLOAD PROJECT EXTRA STATUS DRAFT (D) WHEN WEB BOOKING IS AUTO UPLOADED (RELATED TO CR0011418) | 2020-09-29 22:38 | 2020-11-12 02:00 | 2020-11-10 11:27 | 2020-12-21 17:23 | 2020-12-22 14:05 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-23 10:49 | 2021-02-04 14:00 | CR0012948 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W1 | 2021-01 | 469 | 512 | 97.4735 | 15 | 3 | 4 | 0.22 | 193525 | 1.3 | 1 | 0 | 0 | 4 | 2 | 2 | 5 | 40 | 0.41667 | 0.47368 | 2020-09 | 0 | 0
1518 | CR0012649 | CTASK0020831 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2020-09-30 18:48 | 2020-09-01 18:48 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Deployment] CA (Cool Atmosphere) & MA flag in reefer application to initiate a system rule that the CA & MA flag could not be activated by user | 2020-06-25 09:08 | 2020-07-23 | 2020-07-20 11:45 | 2020-08-13 15:34 | 2020-08-13 16:02 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-13 21:47 | 2020-10-01 13:00 | CR0012649 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W36 | 2020-09 | 32 | 32 | 68.0363 | 4 | 1 | 1 | 0.02 | 193567 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-06 | 0 | 0
1519 | CR0012649 | CTASK0020829 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-07-07 23:42 | 2020-07-01 09:42 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Testing] CA (Cool Atmosphere) & MA flag in reefer application to initiate a system rule that the CA & MA flag could not be activated by user | 2020-06-25 09:08 | 2020-07-23 | 2020-07-20 11:45 | 2020-08-13 15:34 | 2020-08-13 16:02 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-13 21:47 | 2020-10-01 13:00 | CR0012649 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W36 | 2020-09 | 32 | 32 | 68.0363 | 4 | 1 | 1 | 0.02 | 193567 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-06 | 0 | 0
1520 | CR0012649 | CTASK0020819 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2020-06-27 00:36 | 2020-06-22 09:36 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Design] CA (Cool Atmosphere) & MA flag in reefer application to initiate a system rule that the CA & MA flag could not be activated by user | 2020-06-25 09:08 | 2020-07-23 | 2020-07-20 11:45 | 2020-08-13 15:34 | 2020-08-13 16:02 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-13 21:47 | 2020-10-01 13:00 | CR0012649 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W36 | 2020-09 | 32 | 32 | 68.0363 | 4 | 1 | 1 | 0.02 | 193567 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-06 | 0 | 0
1521 | CR0012649 | CTASK0020827 | Closed | OPUS-BKG-M | Thien Lai | 12 | 12 | 2020-07-07 23:41 | 2020-07-01 09:41 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | RF Cargo Application | [Development] CA (Cool Atmosphere) & MA flag in reefer application to initiate a system rule that the CA & MA flag could not be activated by user | 2020-06-25 09:08 | 2020-07-23 | 2020-07-20 11:45 | 2020-08-13 15:34 | 2020-08-13 16:02 |  | 2020-09-01 10:00 | 2020-09-01 10:00 | 2020-08-13 21:47 | 2020-10-01 13:00 | CR0012649 | Service ManagementBooking/DocumentationBookingSpecial CargoRF Cargo Application | OPUS-BKG-M | 2020-W36 | 2020-09 | 32 | 32 | 68.0363 | 4 | 1 | 1 | 0.02 | 193567 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0.52941 | 2020-06 | 0 | 0
1522 | CR0011662 | CTASK0018255 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 28 | 28 | 2020-02-18 14:00 | 2020-02-07 14:00 | Container | Service Management | Booking/Documentation | Advance Manifest | EU ENS/EXS (EU Office) |  | (HBA) EUA EDI Auth - Change to the ENS Download and Transmit and ENS Report screens - Finland | 2019-09-04 15:55 | 2019-10-26 | 2019-10-25 10:42 | 2020-01-16 22:52 | 2020-01-30 12:01 |  | 2020-07-07 10:00 | 2020-07-07 09:30 | 2020-06-26 17:44 | 2020-08-09 13:00 | CR0011662 | Service ManagementBooking/DocumentationAdvance ManifestEU ENS/EXS (EU Office) | OPUS-BKG-MFT-E | 2020-W28 | 2020-07 | 28 | 28 | 306.7533 | 1 | 1 | 1 | 0 | 193506 | 0.3 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 27 | 0 | 0.85714 | 2019-09 | 0 | 0
1523 | CR0012976 | CTASK0022134 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-01-29 11:22 | 2021-01-01 11:22 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] ASIA - To add CM/TEU calculation based on EPP-B in Standby Booking Status Report | 2020-09-01 13:08 | 2020-10-01 | 2020-09-28 17:58 | 2021-01-22 14:37 | 2021-01-22 14:42 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-22 14:58 | 2021-03-04 14:00 | CR0012976 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W5 | 2021-02 | 53 | 54 | 153.8694 | 4 | 1 | 1 | 0.01 | 153106 | 1.9 | 1 | 0 | 0 | 1 | 1 | 3 | 8 | 21 | 0.22951 | 0.4 | 2020-09 | 0 | 0
1524 | CR0012976 | CTASK0022128 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2020-09-30 11:18 | 2020-09-01 11:17 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] ASIA - To add CM/TEU calculation based on EPP-B in Standby Booking Status Report | 2020-09-01 13:08 | 2020-10-01 | 2020-09-28 17:58 | 2021-01-22 14:37 | 2021-01-22 14:42 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-22 14:58 | 2021-03-04 14:00 | CR0012976 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W5 | 2021-02 | 53 | 54 | 153.8694 | 4 | 1 | 1 | 0.01 | 153106 | 1.9 | 1 | 0 | 0 | 1 | 1 | 3 | 8 | 21 | 0.22951 | 0.4 | 2020-09 | 0 | 0
1525 | CR0012976 | CTASK0022129 | Closed | OPUS-BKG-M | Kieu Le | 32 | 32 | 2020-09-30 11:18 | 2020-09-01 11:18 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] ASIA - To add CM/TEU calculation based on EPP-B in Standby Booking Status Report | 2020-09-01 13:08 | 2020-10-01 | 2020-09-28 17:58 | 2021-01-22 14:37 | 2021-01-22 14:42 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-22 14:58 | 2021-03-04 14:00 | CR0012976 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W5 | 2021-02 | 53 | 54 | 153.8694 | 4 | 1 | 1 | 0.01 | 153106 | 1.9 | 1 | 0 | 0 | 1 | 1 | 3 | 8 | 21 | 0.22951 | 0.4 | 2020-09 | 0 | 0
1526 | CR0012976 | CTASK0022132 | Closed | OPUS-BKG-M | Kieu Le | 11 | 12 | 2020-09-30 11:21 | 2020-09-01 11:21 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] ASIA - To add CM/TEU calculation based on EPP-B in Standby Booking Status Report | 2020-09-01 13:08 | 2020-10-01 | 2020-09-28 17:58 | 2021-01-22 14:37 | 2021-01-22 14:42 |  | 2021-02-02 10:00 | 2021-02-02 10:00 | 2021-01-22 14:58 | 2021-03-04 14:00 | CR0012976 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W5 | 2021-02 | 53 | 54 | 153.8694 | 4 | 1 | 1 | 0.01 | 153106 | 1.9 | 1 | 0 | 0 | 1 | 1 | 3 | 8 | 21 | 0.22951 | 0.4 | 2020-09 | 0 | 0
1527 | CR0012226 | CTASK0018210 | Closed | OPUS-SCO | Lien Le | 136 | 136 |  |  | Container | Statement Management | Statement Account Receivable |  |  |  | [Actual CLV] EUA - Enhancement and Modifications prepared for German launch of CLEAR | 2020-02-05 11:33 | 2020-02-18 11:32 | 2020-02-12 14:57 | 2020-02-14 17:38 | 2020-02-14 17:40 |  | 2020-02-18 17:39 | 2020-02-18 10:10 | 2020-02-17 17:12 | 2020-03-19 13:00 | CR0012226 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W8 | 2020-02 | 136 | 0 | 13.2547 | 1 | 1 | 1 | 0 | 193441 | 0.9 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 13 | 0 | 0 | 2020-02 | 0 | 0
1528 | CR0012581 | CTASK0020254 | Closed | OPUS-PRI | Nhien Nguyen | 60 | 60 | 2020-06-30 19:05 | 2020-05-26 19:05 | Container | Sales Management | Pricing | Code | MOT/SSE Filing Report | Filing List Inquiry | Auto filing generation in MOT module | 2020-05-25 10:55 | 2020-07-31 18:55 | 2020-07-06 09:07 | 2020-07-20 12:48 | 2020-07-20 13:10 |  | 2020-07-28 13:09 | 2020-07-28 13:11 | 2020-07-22 11:19 | 2020-08-19 17:17 | CR0012581 | Sales ManagementPricingCodeMOT/SSE Filing ReportFiling List Inquiry | OPUS-PRI | 2020-W31 | 2020-07 | 121 | 120 | 64.0933 | 3 | 1 | 3 | 0.08 | 183364 | 1.7 | 0 | 0 | 0 | 2 | 1 | 2 | 8 | 27 | 0 | 0 | 2020-05 | 0 | 0
1529 | CR0012581 | CTASK0020553 | Closed | OPUS-PRI | Ngan Nham | 30 | 30 | 2020-06-22 11:44 | 2020-06-08 11:44 | Container | Sales Management | Pricing | Code | MOT/SSE Filing Report | Filing List Inquiry | [Dev][Auto filing generation in MOT module][Divided from CTASK0020254] | 2020-05-25 10:55 | 2020-07-31 18:55 | 2020-07-06 09:07 | 2020-07-20 12:48 | 2020-07-20 13:10 |  | 2020-07-28 13:09 | 2020-07-28 13:11 | 2020-07-22 11:19 | 2020-08-19 17:17 | CR0012581 | Sales ManagementPricingCodeMOT/SSE Filing ReportFiling List Inquiry | OPUS-PRI | 2020-W31 | 2020-07 | 121 | 120 | 64.0933 | 3 | 1 | 3 | 0.08 | 193461 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 8 | 27 | 0 | 0.28571 | 2020-05 | 0 | 0
1530 | CR0012581 | CTASK0020552 | Closed | OPUS-PRI | Man Hoang | 31 | 30 | 2020-06-22 11:42 | 2020-06-08 11:42 | Container | Sales Management | Pricing | Code | MOT/SSE Filing Report | Filing List Inquiry | [Dev][Auto filing generation in MOT module][Divided from CTASK0020254] | 2020-05-25 10:55 | 2020-07-31 18:55 | 2020-07-06 09:07 | 2020-07-20 12:48 | 2020-07-20 13:10 |  | 2020-07-28 13:09 | 2020-07-28 13:11 | 2020-07-22 11:19 | 2020-08-19 17:17 | CR0012581 | Sales ManagementPricingCodeMOT/SSE Filing ReportFiling List Inquiry | OPUS-PRI | 2020-W31 | 2020-07 | 121 | 120 | 64.0933 | 3 | 1 | 3 | 0.08 | 183431 | 1.5 | 0 | 0 | 0 | 2 | 1 | 2 | 8 | 27 | 0 | 0.66667 | 2020-05 | 0 | 0
1531 | CR0010987 | CTASK0012820 | Closed | OPUS-PRI | Nhien Nguyen | 24 | 24 | 2019-04-26 10:57 | 2019-04-24 10:56 | Container | Sales Management | Pricing | Code | MOT/SSE Filing Report | Filing List Inquiry | [4/22~26] MOT filing request | 2019-02-20 17:56 | 2019-05-31 17:55 | 2019-03-29 17:40 | 2019-05-06 10:05 | 2019-05-07 10:34 |  | 2019-05-09 10:33 | 2019-05-09 10:02 | 2019-05-07 13:30 | 2019-06-09 13:02 | CR0010987 | Sales ManagementPricingCodeMOT/SSE Filing ReportFiling List Inquiry | OPUS-PRI | 2019-W19 | 2019-05 | 32 | 0 | 77.6924 | 2 | 1 | 1 | 0 | 183364 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 6 | 0 | 0 | 2019-02 | 0 | 0
1532 | CR0010987 | CTASK0012589 | Closed | OPUS-PRI | Nhien Nguyen | 8 | 8 | 2019-04-20 18:34 | 2019-04-15 18:34 | Container | Sales Management | Pricing | Code | MOT/SSE Filing Report | Filing List Inquiry | [4/15~19] MOT filing request | 2019-02-20 17:56 | 2019-05-31 17:55 | 2019-03-29 17:40 | 2019-05-06 10:05 | 2019-05-07 10:34 |  | 2019-05-09 10:33 | 2019-05-09 10:02 | 2019-05-07 13:30 | 2019-06-09 13:02 | CR0010987 | Sales ManagementPricingCodeMOT/SSE Filing ReportFiling List Inquiry | OPUS-PRI | 2019-W19 | 2019-05 | 32 | 0 | 77.6924 | 2 | 1 | 1 | 0 | 183364 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 6 | 0 | 0 | 2019-02 | 0 | 0
1533 | CR0010491 | CTASK0013996 | Closed | OPUS-BKG-MFT | Nhan Le | 20 | 20 |  |  | Container | Service Management | Booking/Documentation | Manifest | Argentina |  | [License Service] AR - CNTR Stay Days declaration // ARGENTINA Customs // related ECR0000212 | 2019-04-10 11:36 | 2019-06-14 11:31 | 2019-06-10 16:28 | 2019-06-19 01:48 | 2019-06-20 10:50 |  | 2019-06-25 09:30 | 2019-06-25 10:03 | 2019-06-21 22:56 | 2019-07-02 06:27 | CR0010491 | Service ManagementBooking/DocumentationManifestArgentina | OPUS-BKG-MFT-M | 2019-W26 | 2019-06 | 62 | 0 | 75.9123 | 5 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
1534 | CR0010491 | CTASK0014272 | Closed | OPUS-BKG-MFT | Nhan Le | 16 | 16 |  |  | Container | Service Management | Booking/Documentation | Manifest | Argentina |  | [License Service] AR - CNTR Stay Days declaration // ARGENTINA Customs // related ECR0000212 | 2019-04-10 11:36 | 2019-06-14 11:31 | 2019-06-10 16:28 | 2019-06-19 01:48 | 2019-06-20 10:50 |  | 2019-06-25 09:30 | 2019-06-25 10:03 | 2019-06-21 22:56 | 2019-07-02 06:27 | CR0010491 | Service ManagementBooking/DocumentationManifestArgentina | OPUS-BKG-MFT-M | 2019-W26 | 2019-06 | 62 | 0 | 75.9123 | 5 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
1535 | CR0010491 | CTASK0013653 | Closed | OPUS-BKG-MFT | Nhan Le | 12 | 12 |  |  | Container | Service Management | Booking/Documentation | Manifest | Argentina |  | [License Service] AR - CNTR Stay Days declaration // ARGENTINA Customs // related ECR0000212 | 2019-04-10 11:36 | 2019-06-14 11:31 | 2019-06-10 16:28 | 2019-06-19 01:48 | 2019-06-20 10:50 |  | 2019-06-25 09:30 | 2019-06-25 10:03 | 2019-06-21 22:56 | 2019-07-02 06:27 | CR0010491 | Service ManagementBooking/DocumentationManifestArgentina | OPUS-BKG-MFT-M | 2019-W26 | 2019-06 | 62 | 0 | 75.9123 | 5 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
1536 | CR0010491 | CTASK0014499 | Closed | OPUS-BKG-MFT | Nhan Le | 10 | 10 |  |  | Container | Service Management | Booking/Documentation | Manifest | Argentina |  | [License Service] AR - CNTR Stay Days declaration // ARGENTINA Customs // related ECR0000212 | 2019-04-10 11:36 | 2019-06-14 11:31 | 2019-06-10 16:28 | 2019-06-19 01:48 | 2019-06-20 10:50 |  | 2019-06-25 09:30 | 2019-06-25 10:03 | 2019-06-21 22:56 | 2019-07-02 06:27 | CR0010491 | Service ManagementBooking/DocumentationManifestArgentina | OPUS-BKG-MFT-M | 2019-W26 | 2019-06 | 62 | 0 | 75.9123 | 5 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
1537 | CR0010491 | CTASK0014840 | Closed | OPUS-BKG-MFT | Nhan Le | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Manifest | Argentina |  | [License Service] AR - CNTR Stay Days declaration // ARGENTINA Customs // related ECR0000212 | 2019-04-10 11:36 | 2019-06-14 11:31 | 2019-06-10 16:28 | 2019-06-19 01:48 | 2019-06-20 10:50 |  | 2019-06-25 09:30 | 2019-06-25 10:03 | 2019-06-21 22:56 | 2019-07-02 06:27 | CR0010491 | Service ManagementBooking/DocumentationManifestArgentina | OPUS-BKG-MFT-M | 2019-W26 | 2019-06 | 62 | 0 | 75.9123 | 5 | 1 | 1 | 0 | 183353 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 2019-04 | 0 | 0
1538 | CR0011548 | CTASK0020364 | Closed | OPUS-BKG-EBKG | Vinh Tran | 6 | 6 | 2020-05-30 02:00 | 2020-05-26 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] eComm - Change logic of sending "Internet Booking Request Accepted" for Special Cargo Booking | 2020-05-08 13:39 | 2020-06-11 | 2020-06-09 09:32 | 2020-10-05 13:35 | 2020-10-05 17:57 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-06 09:26 | 2020-11-19 14:00 | CR0011548 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W43 | 2020-10 | 44 | 48 | 164.8481 | 5 | 1 | 1 | 0.01 | 193525 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 20 | 0 | 0.45455 | 2020-05 | 0 | 0
1539 | CR0011548 | CTASK0019878 | Closed | OPUS-BKG-EBKG | Vinh Tran | 8 | 8 | 2020-05-12 02:00 | 2020-05-08 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] eComm - Change logic of sending "Internet Booking Request Accepted" for Special Cargo Booking | 2020-05-08 13:39 | 2020-06-11 | 2020-06-09 09:32 | 2020-10-05 13:35 | 2020-10-05 17:57 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-06 09:26 | 2020-11-19 14:00 | CR0011548 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W43 | 2020-10 | 44 | 48 | 164.8481 | 5 | 1 | 1 | 0.01 | 193525 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 20 | 0 | 0.45455 | 2020-05 | 0 | 0
1540 | CR0011548 | CTASK0019880 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2020-10-01 18:50 | 2020-10-01 18:50 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] eComm - Change logic of sending "Internet Booking Request Accepted" for Special Cargo Booking | 2020-05-08 13:39 | 2020-06-11 | 2020-06-09 09:32 | 2020-10-05 13:35 | 2020-10-05 17:57 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-06 09:26 | 2020-11-19 14:00 | CR0011548 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W43 | 2020-10 | 44 | 48 | 164.8481 | 5 | 1 | 1 | 0.01 | 193525 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 20 | 0 | 0.45455 | 2020-05 | 0 | 0
1541 | CR0011548 | CTASK0019876 | Closed | OPUS-BKG-EBKG | Vinh Tran | 10 | 10 | 2020-05-09 02:00 | 2020-05-07 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] eComm - Change logic of sending "Internet Booking Request Accepted" for Special Cargo Booking | 2020-05-08 13:39 | 2020-06-11 | 2020-06-09 09:32 | 2020-10-05 13:35 | 2020-10-05 17:57 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-06 09:26 | 2020-11-19 14:00 | CR0011548 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W43 | 2020-10 | 44 | 48 | 164.8481 | 5 | 1 | 1 | 0.01 | 193525 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 20 | 0 | 0.45455 | 2020-05 | 0 | 0
1542 | CR0011548 | CTASK0019281 | Closed | OPUS-BKG-EBKG | Vinh Tran | 20 | 20 | 2020-04-29 02:00 | 2020-03-30 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] eComm - Change logic of sending "Internet Booking Request Accepted" for Special Cargo Booking | 2020-05-08 13:39 | 2020-06-11 | 2020-06-09 09:32 | 2020-10-05 13:35 | 2020-10-05 17:57 |  | 2020-10-20 10:00 | 2020-10-20 10:00 | 2020-10-06 09:26 | 2020-11-19 14:00 | CR0011548 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W43 | 2020-10 | 44 | 48 | 164.8481 | 5 | 1 | 1 | 0.01 | 193525 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 6 | 20 | 0 | 0.45455 | 2020-05 | 0 | 0
1543 | CR0012885 | CTASK0022191 | Closed | OPUS-MDA | Cuong Nguyen | 2 | 4 | 2020-09-30 20:00 | 2020-09-07 08:00 | Container | Biz Common | Master Data | Admin | Process Status |  | [CTASK3] CLV_Pair Test | 2020-09-08 16:20 | 2020-09-25 20:00 | 2020-09-25 17:21 | 2020-10-31 21:00 | 2020-11-03 13:35 |  | 2020-11-10 10:00 | 2020-11-10 09:38 | 2020-11-06 10:35 | 2020-12-10 14:00 | CR0012885 | Biz CommonMaster DataAdminProcess Status | OPUS-MDA | 2020-W46 | 2020-11 | 20 | 44 | 62.7359 | 2 | 1 | 2 | 0.03 | 193529 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 16 | 0 | 0.058824 | 2020-09 | 0 | 0
1544 | CR0012885 | CTASK0022190 | Closed | OPUS-MDA | Tran Le | 18 | 40 | 2020-09-30 20:00 | 2020-09-07 08:00 | Container | Biz Common | Master Data | Admin | Process Status |  | [CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2020-09-08 16:20 | 2020-09-25 20:00 | 2020-09-25 17:21 | 2020-10-31 21:00 | 2020-11-03 13:35 |  | 2020-11-10 10:00 | 2020-11-10 09:38 | 2020-11-06 10:35 | 2020-12-10 14:00 | CR0012885 | Biz CommonMaster DataAdminProcess Status | OPUS-MDA | 2020-W46 | 2020-11 | 20 | 44 | 62.7359 | 2 | 1 | 2 | 0.03 | 193501 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 16 | 0 | 0 | 2020-09 | 0 | 0
1545 | CR0013801 | CTASK0026421 | Closed | OPUS-SCG | Trang Duy Thong | 8 | 8 | 2021-04-30 11:43 | 2021-04-01 11:43 | Container | Vessel Operation | Special Cargo | DG Restriction | Port Limit | DG Port/Terminal Limits – Creation | [CLT Internal] Remove alert for container number exceeds 13 char and other bug fixes - wrong container count in Email | 2021-04-12 09:06 | 2021-04-23 17:45 | 2021-04-22 12:59 | 2021-04-28 13:19 | 2021-04-28 14:59 |  | 2021-05-04 10:00 | 2021-05-04 10:46 | 2021-04-29 15:04 | 2021-06-03 14:00 | CR0013801 | Vessel OperationSpecial CargoDG RestrictionPort LimitDG Port/Terminal Limits – Creation | OPUS-SCG | 2021-W18 | 2021-05 | 8 | 8 | 22.0375 | 1 | 1 | 1 | 0.02 | 193511 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 28 | 0 | 0 | 2021-04 | 0 | 0
1546 | CR0010699 | CTASK0013312 | Closed | OPUS-BKG-OB | Kieu Le | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | Revenue Audit |  | [~2019-05-10] Revenue Audit Additional Column and link to RFA/SC using spyglass | 2018-12-07 16:39 | 2018-12-22 | 2018-12-20 18:01 | 2019-05-06 13:26 | 2019-05-10 08:54 |  | 2019-05-10 08:53 | 2019-05-10 10:00 | 2019-05-10 11:38 | 2019-05-14 11:37 | CR0010699 | Service ManagementBooking/DocumentationOutbound DocRevenue Audit | OPUS-BKG-CHG | 2019-W19 | 2019-05 | 18 | 10 | 153.6767 | 2 | 2 | 2 | 0 | 153106 | 0.2 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 6 | 0 | 0 | 2018-12 | 0 | 0
1547 | CR0010699 | CTASK0012486 | Closed | OPUS-PRI | Man Hoang | 10 | 10 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | Revenue Audit |  | [~2019/04/19] Revenue Audit Additional Column and link to RFA/SC using spyglass | 2018-12-07 16:39 | 2018-12-22 | 2018-12-20 18:01 | 2019-05-06 13:26 | 2019-05-10 08:54 |  | 2019-05-10 08:53 | 2019-05-10 10:00 | 2019-05-10 11:38 | 2019-05-14 11:37 | CR0010699 | Service ManagementBooking/DocumentationOutbound DocRevenue Audit | OPUS-BKG-CHG | 2019-W19 | 2019-05 | 18 | 10 | 153.6767 | 2 | 2 | 2 | 0 | 183431 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 6 | 0 | 0 | 2018-12 | 0 | 0
1548 | CR0012819 | CTASK0021405 | Closed | OPUS-TRS | Giang Nguyen Hoang | 18 | 20 |  |  | Container | Service Management | Trans S/O | Work Order | Issue |  | Allow user to manually input customer code in W/O issue - 3rd party Interface pop-up screen | 2020-09-23 15:48 | 2020-10-09 21:00 | 2020-10-06 18:05 | 2020-11-09 15:59 | 2020-11-09 16:05 |  | 2020-11-17 11:00 | 2020-11-17 08:59 | 2020-11-09 17:17 | 2020-12-27 14:00 | CR0012819 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2020-W47 | 2020-11 | 38 | 40 | 54.8001 | 2 | 1 | 2 | 0.03 | 183440 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0 | 2020-09 | 0 | 0
1549 | CR0012819 | CTASK0021404 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 20 | 20 |  |  | Container | Service Management | Trans S/O | Work Order | Issue |  | Allow user to manually input customer code in W/O issue - 3rd party Interface pop-up screen | 2020-09-23 15:48 | 2020-10-09 21:00 | 2020-10-06 18:05 | 2020-11-09 15:59 | 2020-11-09 16:05 |  | 2020-11-17 11:00 | 2020-11-17 08:59 | 2020-11-09 17:17 | 2020-12-27 14:00 | CR0012819 | Service ManagementTrans S/OWork OrderIssue | OPUS-TRS | 2020-W47 | 2020-11 | 38 | 40 | 54.8001 | 2 | 1 | 2 | 0.03 | 183432 | 1.5 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0 | 2020-09 | 0 | 0
1550 | CR0011993 | CTASK0017387 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 88 | 27 |  | 2019-12-04 13:00 | Container | Service Management | Booking/Documentation | Manifest | Panama | Panama Canal Authority | LA- SERVICES MANAGEMENT - PANAMA CANAL AUTHORITY MANIFEST | 2019-12-24 13:12 | 2020-02-28 15:33 | 2020-01-23 10:33 | 2020-01-28 06:13 | 2020-01-30 13:54 |  | 2020-02-04 10:00 | 2020-02-04 09:50 | 2020-02-03 22:52 | 2020-02-11 06:28 | CR0011993 | Service ManagementBooking/DocumentationManifestPanamaPanama Canal Authority | OPUS-BKG-MFT-M | 2020-W6 | 2020-02 | 88 | 27 | 41.8667 | 1 | 1 | 1 | 0.03 | 193506 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 13 | 0 | 0.85714 | 2019-12 | 0 | 0
1551 | CR0012447 | CTASK0019902 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 8 | 4 | 2020-04-28 18:29 | 2020-04-27 18:29 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [CLT Internal] enhancement to receive H.B/L with the max seq of doc_tp 'S' | 2020-03-31 09:36 | 2020-04-16 | 2020-04-06 13:05 | 2020-04-29 21:40 | 2020-05-07 10:00 |  | 2020-05-12 10:00 | 2020-05-19 10:31 | 2020-05-12 09:18 | 2020-06-01 11:33 | CR0012447 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W20 | 2020-05 | 8 | 4 | 42.0167 | 1 | 1 | 1 | 0 | 193488 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 26 | 0 | 2.1667 | 2020-03 | 0 | 0
1552 | CR0012195 | CTASK0018184 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 26 | 26 | 2020-03-13 17:27 | 2020-03-09 17:27 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | NA *DOC* - CHANGE CAED # INPUT REQUIREMENTS TO CERS # INPUT REQUIREMENTS (eComm - CR0012196) | 2020-02-05 16:52 | 2020-03-17 16:52 | 2020-03-16 09:59 | 2020-03-21 03:41 | 2020-03-23 08:30 |  | 2020-03-31 08:30 | 2020-03-31 10:00 | 2020-03-24 23:17 | 2020-04-30 13:00 | CR0012195 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2020-W14 | 2020-03 | 60 | 59 | 54.6515 | 3 | 2 | 3 | 0.04 | 193488 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 2.1667 | 2020-02 | 0 | 0
1553 | CR0012195 | CTASK0018281 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 12 | 12 | 2020-02-21 19:00 | 2020-02-10 12:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | NA *DOC* - CHANGE CAED # INPUT REQUIREMENTS TO CERS # INPUT REQUIREMENTS (eComm - CR0012196) | 2020-02-05 16:52 | 2020-03-17 16:52 | 2020-03-16 09:59 | 2020-03-21 03:41 | 2020-03-23 08:30 |  | 2020-03-31 08:30 | 2020-03-31 10:00 | 2020-03-24 23:17 | 2020-04-30 13:00 | CR0012195 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2020-W14 | 2020-03 | 60 | 59 | 54.6515 | 3 | 2 | 3 | 0.04 | 193512 | 0.6 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 0.5 | 2020-02 | 0 | 0
1554 | CR0012195 | CTASK0018126 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 22 | 21 | 2020-02-17 19:00 | 2020-01-30 15:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | NA *DOC* - CHANGE CAED # INPUT REQUIREMENTS TO CERS # INPUT REQUIREMENTS (eComm - CR0012196) | 2020-02-05 16:52 | 2020-03-17 16:52 | 2020-03-16 09:59 | 2020-03-21 03:41 | 2020-03-23 08:30 |  | 2020-03-31 08:30 | 2020-03-31 10:00 | 2020-03-24 23:17 | 2020-04-30 13:00 | CR0012195 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2020-W14 | 2020-03 | 60 | 59 | 54.6515 | 3 | 2 | 3 | 0.04 | 193470 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 25 | 0 | 1.3333 | 2020-02 | 0 | 0
1555 | CR0013193 | CTASK0023622 | Closed | OPUS-TRS | Giang Nguyen Hoang | 13 | 12 | 2020-11-27 11:20 | 2020-11-18 11:20 | Container | Service Management | Trans S/O |  |  |  | [202011] LA - OPS - Batch job (TRS File)//LDF "INT-INT"//Reference SR0102680 | 2020-11-18 11:18 | 2020-11-27 21:00 | 2020-11-23 16:43 | 2020-12-31 09:46 | 2021-01-04 10:07 |  | 2021-01-12 10:00 | 2021-01-12 10:00 | 2021-01-04 10:42 | 2021-01-28 00:31 | CR0013193 | Service ManagementTrans S/O | OPUS-TRS | 2021-W2 | 2021-01 | 22 | 24 | 54.9457 | 2 | 1 | 2 | 0.02 | 183440 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-11 | 0 | 0
1556 | CR0013193 | CTASK0023621 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 9 | 12 | 2020-11-27 11:20 | 2020-11-18 11:20 | Container | Service Management | Trans S/O |  |  |  | [202011] LA - OPS - Batch job (TRS File)//LDF "INT-INT"//Reference SR0102680 | 2020-11-18 11:18 | 2020-11-27 21:00 | 2020-11-23 16:43 | 2020-12-31 09:46 | 2021-01-04 10:07 |  | 2021-01-12 10:00 | 2021-01-12 10:00 | 2021-01-04 10:42 | 2021-01-28 00:31 | CR0013193 | Service ManagementTrans S/O | OPUS-TRS | 2021-W2 | 2021-01 | 22 | 24 | 54.9457 | 2 | 1 | 2 | 0.02 | 183432 | 1.7 | 0 | 0 | 0 | 1 | 1 | 2 | 14 | 40 | 0 | 0 | 2020-11 | 0 | 0
1557 | CR0012650 | CTASK0020603 | Closed | OPUS-APR | Chuong Ta | 80 | 78 | 2020-09-30 18:00 | 2020-06-10 16:19 | Container | Biz Common | Approval | Approval Confirm |  |  | [Actual][Chuong Ta]NA *BizCommon* Three (3) Additional CSR Approvers | 2020-06-17 13:06 | 2020-09-30 18:00 | 2020-08-05 14:52 | 2020-09-09 19:11 | 2020-09-09 19:52 |  | 2020-09-22 09:50 | 2020-09-22 10:00 | 2020-09-10 10:53 | 2020-10-22 13:00 | CR0012650 | Biz CommonApprovalApproval Confirm | OPUS-APR | 2020-W39 | 2020-09 | 80 | 78 | 96.8643 | 1 | 1 | 1 | 0.03 | 183379 | 1.3 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 36 | 0 | 0.38462 | 2020-06 | 0 | 0
1558 | CR0012884 | CTASK0021669 | Closed | OPUS-SCE | Son Nguyen The | 22 | 28 | 2020-08-21 11:02 | 2020-08-04 11:02 | Container | Service Management | SCEM | Visibility | Customer EDI Monitoring |  | [CLT Internal] OPUS service enhancement for triggering 315 Event. | 2020-08-04 11:01 | 2020-08-28 18:30 | 2020-08-24 08:54 |  | 2020-08-27 11:13 |  | 2020-09-01 12:00 | 2020-09-01 11:20 | 2020-08-27 11:13 | 2020-10-01 13:00 | CR0012884 | Service ManagementSCEMVisibilityCustomer EDI Monitoring | OPUS-SCE | 2020-W36 | 2020-09 | 22 | 28 | 28.0409 | 1 | 1 | 1 | 0.04 | 193531 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 36 | 0 | 0 | 2020-08 | 0 | 0
1559 | CR0012218 | CTASK0020157 | Closed | OPUS-DMT | Tran Le | 2 | 2 |  |  | Container | Service Management | Demurrage/Detention | Charge Generation | Charge Calculation |  | Testing | 2020-05-15 16:25 | 2020-05-22 20:00 | 2020-05-21 08:38 | 2020-06-25 21:04 | 2020-07-01 08:15 |  | 2020-11-10 10:00 | 2020-11-10 09:38 | 2020-07-02 16:00 | 2020-12-10 14:00 | CR0012218 | Service ManagementDemurrage/DetentionCharge GenerationCharge Calculation | OPUS-DMT | 2020-W46 | 2020-11 | 15 | 11 | 178.7324 | 2 | 1 | 2 | 0 | 193501 | 0.6 | 0 | 0 | 0 | 1 | 1 | 3 | 4 | 16 | 0 | 0 | 2020-05 | 0 | 0
1560 | CR0012218 | CTASK0019969 | Closed | OPUS-DMT | Cuong Nguyen | 13 | 11 | 2020-05-22 20:00 | 2020-05-01 08:00 | Container | Service Management | Demurrage/Detention | Charge Generation | Charge Calculation |  | [Change Task 2] GHQ - DMT - Create New OPUS DMT role to manage deletion of DMT charges in OPUS | 2020-05-15 16:25 | 2020-05-22 20:00 | 2020-05-21 08:38 | 2020-06-25 21:04 | 2020-07-01 08:15 |  | 2020-11-10 10:00 | 2020-11-10 09:38 | 2020-07-02 16:00 | 2020-12-10 14:00 | CR0012218 | Service ManagementDemurrage/DetentionCharge GenerationCharge Calculation | OPUS-DMT | 2020-W46 | 2020-11 | 15 | 11 | 178.7324 | 2 | 1 | 2 | 0 | 193529 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 4 | 16 | 0 | 0 | 2020-05 | 0 | 0
1561 | CR0012452 | CTASK0021020 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 15 | 13 | 2020-07-31 14:43 | 2020-07-01 14:43 | Container | Service Management | Domestic |  |  |  | (DOM)NA *DOM* Add functionality to process Street Turns through the DOM Portal with validations | 2020-06-03 16:12 | 2020-09-11 21:00 | 2020-09-11 13:32 | 2021-01-11 13:07 | 2021-01-12 16:46 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-13 15:28 | 2021-02-25 14:00 | CR0012452 | Service ManagementDomestic | OPUS-DOM | 2021-W4 | 2021-01 | 196 | 206 | 236.742 | 6 | 1 | 2 | 0.04 | 183432 | 1.2 | 0 | 0 | 0 | 3 | 1 | 3 | 12 | 40 | 0 | 0 | 2020-06 | 0 | 0
1562 | CR0012452 | CTASK0021676 | Closed | OPUS-DOM | Giang Nguyen Hoang | 16 | 24 | 2020-08-31 14:45 | 2020-08-01 14:45 | Container | Service Management | Domestic |  |  |  | (DOM)NA *DOM* Add functionality to process Street Turns through the DOM Portal with validations (2020/08) | 2020-06-03 16:12 | 2020-09-11 21:00 | 2020-09-11 13:32 | 2021-01-11 13:07 | 2021-01-12 16:46 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-13 15:28 | 2021-02-25 14:00 | CR0012452 | Service ManagementDomestic | OPUS-DOM | 2021-W4 | 2021-01 | 196 | 206 | 236.742 | 6 | 1 | 2 | 0.04 | 183440 | 1.2 | 0 | 0 | 0 | 3 | 1 | 3 | 12 | 40 | 0 | 0 | 2020-06 | 0 | 0
1563 | CR0012452 | CTASK0021677 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 55 | 59 | 2020-08-31 14:45 | 2020-08-01 14:45 | Container | Service Management | Domestic |  |  |  | (DOM)NA *DOM* Add functionality to process Street Turns through the DOM Portal with validations (2020/08) | 2020-06-03 16:12 | 2020-09-11 21:00 | 2020-09-11 13:32 | 2021-01-11 13:07 | 2021-01-12 16:46 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-13 15:28 | 2021-02-25 14:00 | CR0012452 | Service ManagementDomestic | OPUS-DOM | 2021-W4 | 2021-01 | 196 | 206 | 236.742 | 6 | 1 | 2 | 0.04 | 183432 | 1.2 | 0 | 0 | 0 | 3 | 1 | 3 | 12 | 40 | 0 | 0 | 2020-06 | 0 | 0
1564 | CR0012452 | CTASK0021019 | Closed | OPUS-DOM | Giang Nguyen Hoang | 26 | 26 | 2020-07-31 14:43 | 2020-07-01 14:42 | Container | Service Management | Domestic |  |  |  | (DOM)NA *DOM* Add functionality to process Street Turns through the DOM Portal with validations | 2020-06-03 16:12 | 2020-09-11 21:00 | 2020-09-11 13:32 | 2021-01-11 13:07 | 2021-01-12 16:46 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-13 15:28 | 2021-02-25 14:00 | CR0012452 | Service ManagementDomestic | OPUS-DOM | 2021-W4 | 2021-01 | 196 | 206 | 236.742 | 6 | 1 | 2 | 0.04 | 183440 | 1.2 | 0 | 0 | 0 | 3 | 1 | 3 | 12 | 40 | 0 | 0 | 2020-06 | 0 | 0
1565 | CR0012452 | CTASK0019423 | Closed | OPUS-DOM | Giang Nguyen Hoang | 52 | 52 |  |  | Container | Service Management | Domestic |  |  |  | (DOM)NA *DOM* Add functionality to process Street Turns through the DOM Portal with validations | 2020-06-03 16:12 | 2020-09-11 21:00 | 2020-09-11 13:32 | 2021-01-11 13:07 | 2021-01-12 16:46 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-13 15:28 | 2021-02-25 14:00 | CR0012452 | Service ManagementDomestic | OPUS-DOM | 2021-W4 | 2021-01 | 196 | 206 | 236.742 | 6 | 1 | 2 | 0.04 | 183440 | 1.2 | 0 | 0 | 0 | 3 | 1 | 3 | 12 | 40 | 0 | 0 | 2020-06 | 0 | 0
1566 | CR0012452 | CTASK0019422 | Closed | OPUS-DOM | Nhat Phan Dinh Minh | 32 | 32 |  |  | Container | Service Management | Domestic |  |  |  | NA *DOM* Add functionality to process Street Turns through the DOM Portal with validations | 2020-06-03 16:12 | 2020-09-11 21:00 | 2020-09-11 13:32 | 2021-01-11 13:07 | 2021-01-12 16:46 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-13 15:28 | 2021-02-25 14:00 | CR0012452 | Service ManagementDomestic | OPUS-DOM | 2021-W4 | 2021-01 | 196 | 206 | 236.742 | 6 | 1 | 2 | 0.04 | 183432 | 1.2 | 0 | 0 | 0 | 3 | 1 | 3 | 12 | 40 | 0 | 0 | 2020-06 | 0 | 0
1567 | CR0014002 | CTASK0027290 | Closed | OPUS-SCG | Trang Duy Thong | 3 | 3 |  |  | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [Documentation][Internal CR] Request SPCL CGO APVL/Inquiry for Partner Lines - Update - POL - POD & ETB - ETD | 2021-06-01 15:31 | 2021-06-04 15:30 | 2021-06-04 09:14 | 2021-06-09 13:25 | 2021-06-10 11:56 |  | 2021-06-22 11:56 | 2021-06-22 15:45 | 2021-06-11 16:39 | 2021-07-25 14:00 | CR0014002 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W25 | 2021-06 | 11 | 11 | 20.8506 | 2 | 1 | 1 | 0.02 | 193511 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.81818 | 0 | 2021-06 | 0 | 0
1568 | CR0014002 | CTASK0027301 | Closed | OPUS-SCG | Trang Duy Thong | 8 | 8 | 2021-06-04 13:48 | 2021-06-03 13:47 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [CLV][Internal CR] Request SPCL CGO APVL/Inquiry for Partner Lines - Update - POL - POD & ETB - ETD | 2021-06-01 15:31 | 2021-06-04 15:30 | 2021-06-04 09:14 | 2021-06-09 13:25 | 2021-06-10 11:56 |  | 2021-06-22 11:56 | 2021-06-22 15:45 | 2021-06-11 16:39 | 2021-07-25 14:00 | CR0014002 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W25 | 2021-06 | 11 | 11 | 20.8506 | 2 | 1 | 1 | 0.02 | 193511 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0.81818 | 0 | 2021-06 | 0 | 0
1569 | CR0013638 | CTASK0025492 | Closed | OPUS-SPC | Toai Phan | 34 | 35 | 2021-03-26 10:34 | 2021-02-22 10:34 | Container | Sales Management | Space Control |  |  |  | GHQ - Kontainer - Add 'Booking Via' filter in SPC UIs | 2021-02-25 10:33 | 2021-03-12 10:32 | 2021-03-12 08:02 | 2021-04-08 17:05 | 2021-04-09 10:57 |  | 2021-04-13 10:00 | 2021-04-13 11:37 | 2021-04-09 13:06 | 2021-05-15 14:00 | CR0013638 | Sales ManagementSpace Control | OPUS-SPC | 2021-W15 | 2021-04 | 34 | 35 | 46.9774 | 1 | 1 | 1 | 0.03 | 183427 | 2.2 | 0 | 0 | 0 | 1 | 1 | 1 | 7 | 27 | 0 | 0 | 2021-02 | 0 | 0
1570 | CR0012348 | CTASK0022273 | Closed | OPUS-TPB | Manh Nguyen | 110 | 150 | 2020-09-30 13:15 | 2020-09-01 13:15 | Container | Service Management | A/R Invoice | Invoice Inquiry |  |  | [TPB_Actual] Asia *AR Inv* New arrangement for Tax Invoice in India - from April 2020 (delayed to Oct 2020) | 2020-10-20 16:30 | 2020-11-20 16:29 | 2020-10-21 15:38 | 2020-10-23 13:40 | 2020-10-23 13:43 |  | 2020-10-27 10:00 | 2020-10-27 10:00 | 2020-10-23 14:38 | 2020-11-27 14:00 | CR0012348 | Service ManagementA/R InvoiceInvoice Inquiry | OPUS-INV | 2020-W44 | 2020-10 | 130 | 205 | 6.7294 | 3 | 2 | 3 | 1.27 | 153138 | 2.1 | 0 | 0 | 0 | 3 | 1 | 1 | 7 | 20 | 0 | 0.16667 | 2020-10 | 0 | 0
1571 | CR0012348 | CTASK0022274 | Closed | OPUS-TPB | Thai Nguyen | 5 | 40 | 2020-09-30 13:18 | 2020-09-01 13:18 | Container | Service Management | A/R Invoice | Invoice Inquiry |  |  | [TPB_Actual] Asia *AR Inv* New arrangement for Tax Invoice in India - from April 2020 (delayed to Oct 2020) | 2020-10-20 16:30 | 2020-11-20 16:29 | 2020-10-21 15:38 | 2020-10-23 13:40 | 2020-10-23 13:43 |  | 2020-10-27 10:00 | 2020-10-27 10:00 | 2020-10-23 14:38 | 2020-11-27 14:00 | CR0012348 | Service ManagementA/R InvoiceInvoice Inquiry | OPUS-INV | 2020-W44 | 2020-10 | 130 | 205 | 6.7294 | 3 | 2 | 3 | 1.27 | 173249 | 2.1 | 0 | 0 | 0 | 3 | 1 | 1 | 7 | 20 | 0 | 0.5 | 2020-10 | 0 | 0
1572 | CR0012348 | CTASK0022400 | Closed | OPUS-ACM | Huynh Tuan Khanh | 15 | 15 | 2020-09-30 11:04 | 2020-09-01 11:04 | Container | Service Management | A/R Invoice | Invoice Inquiry |  |  | [MDA] Asia *AR Inv* New arrangement for Tax Invoice in India - from April 2020 (delayed to Oct 2020) | 2020-10-20 16:30 | 2020-11-20 16:29 | 2020-10-21 15:38 | 2020-10-23 13:40 | 2020-10-23 13:43 |  | 2020-10-27 10:00 | 2020-10-27 10:00 | 2020-10-23 14:38 | 2020-11-27 14:00 | CR0012348 | Service ManagementA/R InvoiceInvoice Inquiry | OPUS-INV | 2020-W44 | 2020-10 | 130 | 205 | 6.7294 | 3 | 2 | 3 | 1.27 | 193499 | 1.4 | 0 | 0 | 0 | 3 | 1 | 1 | 7 | 20 | 0 | 0 | 2020-10 | 0 | 0
1573 | CR0011711 | CTASK0021015 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 26 | 26 | 2020-07-17 19:30 | 2020-07-06 11:00 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | [Development] (HBA) EUA EDI ¦ CUSTOMS MANIFEST for TNPA South Africa | 2019-11-01 08:26 | 2019-11-29 13:13 | 2019-11-14 16:47 | 2020-01-07 19:11 | 2020-07-23 09:03 |  | 2020-08-04 09:51 | 2020-08-04 09:30 | 2020-07-24 16:08 | 2020-09-04 13:00 | CR0011711 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W32 | 2020-08 | 85 | 77 | 277.0586 | 4 | 1 | 1 | 0.01 | 173280 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 9 | 30 | 0 | 0 | 2019-11 | 0 | 0
1574 | CR0011711 | CTASK0021891 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 11 | 11 | 2020-08-24 19:30 | 2020-08-18 11:00 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | [Development] (HBA) EUA EDI ¦ CUSTOMS MANIFEST for TNPA South Africa | 2019-11-01 08:26 | 2019-11-29 13:13 | 2019-11-14 16:47 | 2020-01-07 19:11 | 2020-07-23 09:03 |  | 2020-08-04 09:51 | 2020-08-04 09:30 | 2020-07-24 16:08 | 2020-09-04 13:00 | CR0011711 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W32 | 2020-08 | 85 | 77 | 277.0586 | 4 | 1 | 1 | 0.01 | 173280 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 9 | 30 | 0 | 0 | 2019-11 | 0 | 0
1575 | CR0011711 | CTASK0016932 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 28 | 20 | 2019-11-29 17:39 | 2019-10-28 17:39 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | (HBA) EUA EDI ¦ CUSTOMS MANIFEST for TNPA South Africa | 2019-11-01 08:26 | 2019-11-29 13:13 | 2019-11-14 16:47 | 2020-01-07 19:11 | 2020-07-23 09:03 |  | 2020-08-04 09:51 | 2020-08-04 09:30 | 2020-07-24 16:08 | 2020-09-04 13:00 | CR0011711 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W32 | 2020-08 | 85 | 77 | 277.0586 | 4 | 1 | 1 | 0.01 | 173280 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 9 | 30 | 0 | 0 | 2019-11 | 0 | 0
1576 | CR0011711 | CTASK0021437 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 20 | 20 | 2020-07-27 19:30 | 2020-07-20 11:00 | Container | Service Management | Booking/Documentation | Manifest | EU | Europe Customs EDI | [Deployment] (HBA) EUA EDI ¦ CUSTOMS MANIFEST for TNPA South Africa | 2019-11-01 08:26 | 2019-11-29 13:13 | 2019-11-14 16:47 | 2020-01-07 19:11 | 2020-07-23 09:03 |  | 2020-08-04 09:51 | 2020-08-04 09:30 | 2020-07-24 16:08 | 2020-09-04 13:00 | CR0011711 | Service ManagementBooking/DocumentationManifestEUEurope Customs EDI | OPUS-BKG-MFT-E | 2020-W32 | 2020-08 | 85 | 77 | 277.0586 | 4 | 1 | 1 | 0.01 | 173280 | 0.9 | 0 | 0 | 0 | 1 | 1 | 3 | 9 | 30 | 0 | 0 | 2019-11 | 0 | 0
1577 | CR0012936 | CTASK0022740 | Closed | OPUS-MGS | Tuyen Truong | 5 | 5 |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | NA *Opus F/F* Vendor- Please have configurable validation using a Hard code table in OPUS CTM module to identify GENSET or CHASSIS. | 2020-09-11 09:16 | 2020-09-30 | 2020-09-28 18:29 | 2021-01-07 09:59 | 2021-01-13 09:24 |  | 2021-01-19 10:00 | 2021-01-19 10:00 | 2021-01-14 09:52 | 2021-01-22 06:18 | CR0012936 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2021-W3 | 2021-01 | 5 | 0 | 130.0309 | 1 | 1 | 1 | 0 | 173255 | 1.9 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 40 | 0 | 0 | 2020-09 | 0 | 0
1578 | CR0012529 | CTASK0021295 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 6 | 6 | 2020-07-17 19:30 | 2020-07-15 11:00 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Deployment][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 173280 | 1.4 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 0.18519 | 2020-05 | 0 | 0
1579 | CR0012529 | CTASK0020069 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 3 | 3 | 2020-05-13 18:38 | 2020-05-11 10:38 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Estimation][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 193488 | 0.9 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 2.1667 | 2020-05 | 0 | 0
1580 | CR0012529 | CTASK0020060 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 1 | 1 | 2020-05-13 19:30 | 2020-05-12 11:00 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Estimation][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 173280 | 1.4 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 0.18519 | 2020-05 | 0 | 0
1581 | CR0012529 | CTASK0020352 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2020-05-30 01:36 | 2020-05-28 02:36 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Development][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 153106 | 1.7 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 0.4 | 2020-05 | 0 | 0
1582 | CR0012529 | CTASK0020111 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 19 | 18 | 2020-05-30 | 2020-05-25 09:00 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Development][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 173280 | 1.4 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 0.18519 | 2020-05 | 0 | 0
1583 | CR0012529 | CTASK0020110 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 22 | 22 | 2020-05-30 | 2020-05-25 09:00 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Development][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 193488 | 0.9 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 2.1667 | 2020-05 | 0 | 0
1584 | CR0012529 | CTASK0020353 | Closed | OPUS-BKG-M | Kieu Le | 7 | 8 | 2020-05-30 01:37 | 2020-05-28 10:37 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Testing][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 153106 | 1.7 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 0.4 | 2020-05 | 0 | 0
1585 | CR0012529 | CTASK0019511 | Closed | OPUS-BKG-OB | Nam Nguyen | 48 | 48 | 2020-05-22 | 2020-04-10 09:00 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Analysis][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 123048 | 1.7 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 0.46154 | 2020-05 | 0 | 0
1586 | CR0012529 | CTASK0020354 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2020-07-18 01:42 | 2020-07-16 02:42 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Deployment][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 153106 | 1.7 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 0.4 | 2020-05 | 0 | 0
1587 | CR0012529 | CTASK0020123 | Closed | OPUS-BKG-M | Kieu Le | 10 | 10 | 2020-05-23 01:36 | 2020-05-15 02:36 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Design] [CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 153106 | 1.7 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 0.4 | 2020-05 | 0 | 0
1588 | CR0012529 | CTASK0019903 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 26 | 26 | 2020-05-11 19:30 | 2020-04-28 16:00 | Container | Service Management | Booking/Documentation | Setup | Client Default for Booking |  | [Analysis][CLT Internal] (CSVC) OPUS System Error log Analysis and enhancement for defect prevention | 2020-05-25 17:44 | 2020-06-04 | 2020-06-03 16:35 | 2020-06-18 10:49 | 2020-06-25 08:59 |  | 2020-07-28 10:00 | 2020-07-28 10:00 | 2020-07-13 14:24 | 2020-08-27 13:00 | CR0012529 | Service ManagementBooking/DocumentationSetupClient Default for Booking | OPUS-BKG-M | 2020-W31 | 2020-07 | 150 | 150 | 63.6781 | 11 | 3 | 5 | 0.1 | 193470 | 1.2 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 27 | 0 | 0.17391 | 2020-05 | 0 | 0
1589 | CR0012311 | CTASK0021373 | Closed | OPUS-SCE | Son Nguyen The | 23 | 30 | 2020-07-31 11:39 | 2020-07-20 09:30 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | COP detail is not automatically updated to reflect actual yard when container movement occurs in yards outside same RCC. | 2020-07-07 11:40 | 2020-07-27 17:18 | 2020-07-27 16:19 | 2020-08-24 23:11 | 2020-08-25 11:45 |  | 2020-09-01 13:00 | 2020-09-01 11:18 | 2020-08-27 17:07 | 2020-10-01 13:00 | CR0012311 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2020-W36 | 2020-09 | 23 | 30 | 56.0556 | 1 | 1 | 1 | 0.02 | 193531 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 36 | 0 | 0 | 2020-07 | 0 | 0
1590 | CR0012910 | CTASK0022070 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-04-30 12:50 | 2021-04-01 02:50 | Container | Sales Management | Space Control | Standby Management |  |  | [Deployment] NA *Standby* Sequential Validation Logic Critical Enhancements | 2020-10-15 15:46 | 2020-11-26 | 2020-11-25 16:49 | 2021-04-07 09:02 | 2021-04-08 13:22 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-20 14:35 | 2021-05-27 14:00 | CR0012910 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2021-W17 | 2021-04 | 70 | 80 | 193.76 | 5 | 1 | 1 | 0.02 | 153106 | 2 | 1 | 0 | 0 | 1 | 1 | 3 | 12 | 27 | 0.22951 | 0.13043 | 2020-10 | 0 | 0
1591 | CR0012910 | CTASK0021799 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2020-08-15 01:16 | 2020-08-10 02:16 | Container | Sales Management | Space Control | Standby Management |  |  | [Design] NA *Standby* Sequential Validation Logic Critical Enhancements | 2020-10-15 15:46 | 2020-11-26 | 2020-11-25 16:49 | 2021-04-07 09:02 | 2021-04-08 13:22 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-20 14:35 | 2021-05-27 14:00 | CR0012910 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2021-W17 | 2021-04 | 70 | 80 | 193.76 | 5 | 1 | 1 | 0.02 | 153106 | 2 | 1 | 0 | 0 | 1 | 1 | 3 | 12 | 27 | 0.22951 | 0.13043 | 2020-10 | 0 | 0
1592 | CR0012910 | CTASK0023413 | Closed | OPUS-BKG-M | Kieu Le | 15 | 16 | 2020-11-13 13:51 | 2020-11-02 13:51 | Container | Sales Management | Space Control | Standby Management |  |  | [Development] NA *Standby* Sequential Validation Logic Critical Enhancements | 2020-10-15 15:46 | 2020-11-26 | 2020-11-25 16:49 | 2021-04-07 09:02 | 2021-04-08 13:22 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-20 14:35 | 2021-05-27 14:00 | CR0012910 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2021-W17 | 2021-04 | 70 | 80 | 193.76 | 5 | 1 | 1 | 0.02 | 153106 | 2 | 1 | 0 | 0 | 1 | 1 | 3 | 12 | 27 | 0.22951 | 0.13043 | 2020-10 | 0 | 0
1593 | CR0012910 | CTASK0022065 | Closed | OPUS-BKG-M | Kieu Le | 26 | 26 | 2020-10-30 12:45 | 2020-10-01 12:45 | Container | Sales Management | Space Control | Standby Management |  |  | [Development] NA *Standby* Sequential Validation Logic Critical Enhancements | 2020-10-15 15:46 | 2020-11-26 | 2020-11-25 16:49 | 2021-04-07 09:02 | 2021-04-08 13:22 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-20 14:35 | 2021-05-27 14:00 | CR0012910 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2021-W17 | 2021-04 | 70 | 80 | 193.76 | 5 | 1 | 1 | 0.02 | 153106 | 2 | 1 | 0 | 0 | 1 | 1 | 3 | 12 | 27 | 0.22951 | 0.13043 | 2020-10 | 0 | 0
1594 | CR0012910 | CTASK0022068 | Closed | OPUS-BKG-M | Kieu Le | 7 | 16 | 2020-11-30 12:48 | 2020-11-01 12:48 | Container | Sales Management | Space Control | Standby Management |  |  | [Testing] NA *Standby* Sequential Validation Logic Critical Enhancements | 2020-10-15 15:46 | 2020-11-26 | 2020-11-25 16:49 | 2021-04-07 09:02 | 2021-04-08 13:22 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-20 14:35 | 2021-05-27 14:00 | CR0012910 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2021-W17 | 2021-04 | 70 | 80 | 193.76 | 5 | 1 | 1 | 0.02 | 153106 | 2 | 1 | 0 | 0 | 1 | 1 | 3 | 12 | 27 | 0.22951 | 0.13043 | 2020-10 | 0 | 0
1595 | CR0013954 | CTASK0027179 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 14 | 10 | 2021-05-31 14:25 | 2021-05-25 14:25 | Container | Service Management | Trans S/O | CSR | CSR Creation |  | [202105] ONE DDE Project - PK logic Update for TRS | 2021-05-25 14:24 | 2021-06-11 21:00 | 2021-06-07 16:46 | 2021-06-09 09:52 | 2021-06-09 11:48 |  | 2021-06-15 10:00 | 2021-06-15 12:55 | 2021-06-09 13:41 | 2021-07-15 14:00 | CR0013954 | Service ManagementTrans S/OCSRCSR Creation | OPUS-TRS | 2021-W24 | 2021-06 | 29 | 20 | 20.817 | 2 | 1 | 2 | 0.04 | 183432 | 2.2 | 0 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0 | 0.22222 | 2021-05 | 0 | 0
1596 | CR0013954 | CTASK0027180 | Closed | OPUS-TRS | Giang Nguyen Hoang | 15 | 10 | 2021-05-31 14:25 | 2021-05-25 14:25 | Container | Service Management | Trans S/O | CSR | CSR Creation |  | [202105] ONE DDE Project - PK logic Update for TRS | 2021-05-25 14:24 | 2021-06-11 21:00 | 2021-06-07 16:46 | 2021-06-09 09:52 | 2021-06-09 11:48 |  | 2021-06-15 10:00 | 2021-06-15 12:55 | 2021-06-09 13:41 | 2021-07-15 14:00 | CR0013954 | Service ManagementTrans S/OCSRCSR Creation | OPUS-TRS | 2021-W24 | 2021-06 | 29 | 20 | 20.817 | 2 | 1 | 2 | 0.04 | 183440 | 2.2 | 0 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0 | 0 | 2021-05 | 0 | 0
1597 | CR0011038 | CTASK0020146 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 16 | 16 | 2020-06-30 16:35 | 2020-05-11 16:35 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Information | [PROD] Pickup CY/CFS in Arrival Information should reflect from DEL Yard but not POD Yard | 2019-11-19 13:45 | 2019-12-13 13:19 | 2019-12-13 13:56 | 2020-02-21 05:14 | 2020-05-13 13:12 |  | 2020-06-30 10:12 | 2020-06-30 11:29 | 2020-06-24 18:03 | 2020-07-30 13:00 | CR0011038 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Information | OPUS-BKG-IB | 2020-W27 | 2020-06 | 131 | 70 | 223.8519 | 2 | 1 | 1 | 0.01 | 193506 | 0.5 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 29 | 0 | 0.85714 | 2019-11 | 0 | 0
1598 | CR0011038 | CTASK0016958 | Closed | OPUS-BKG-MFT-A | Tan Nguyen | 115 | 54 | 2019-11-20 17:54 | 2019-10-31 17:54 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Information | Pickup CY/CFS in Arrival Information should reflect from DEL Yard but not POD Yard | 2019-11-19 13:45 | 2019-12-13 13:19 | 2019-12-13 13:56 | 2020-02-21 05:14 | 2020-05-13 13:12 |  | 2020-06-30 10:12 | 2020-06-30 11:29 | 2020-06-24 18:03 | 2020-07-30 13:00 | CR0011038 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Information | OPUS-BKG-IB | 2020-W27 | 2020-06 | 131 | 70 | 223.8519 | 2 | 1 | 1 | 0.01 | 193506 | 0.5 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 29 | 0 | 0.85714 | 2019-11 | 0 | 0
1599 | CR0012668 | CTASK0024643 | Closed | OPUS-PRI | Ngan Nham | 16 | 16 | 2021-01-30 01:00 | 2021-01-18 01:00 | Container | Sales Management | Pricing | Simulation | Verify Rate |  | [Development] EAS - PRI - Enhance Verify Rate in line with deployment of CR0011112 & CR0011141 | 2021-01-04 14:53 | 2021-01-30 00:30 | 2021-01-29 11:38 | 2021-05-06 09:12 | 2021-05-11 18:02 |  | 2021-05-18 11:00 | 2021-05-18 10:00 | 2021-05-13 16:54 | 2021-06-17 14:00 | CR0012668 | Sales ManagementPricingSimulationVerify Rate | OPUS-PRI | 2021-W20 | 2021-05 | 16 | 16 | 133.8384 | 1 | 1 | 1 | 0 | 193461 | 2.1 | 0 | 0 | 0 | 1 | 1 | 2 | 10 | 28 | 0 | 0 | 2021-01 | 0 | 0
1600 | CR0012025 | CTASK0018240 | Closed | OPUS-BKG-M | Vinh Tran | 16 | 16 | 2020-02-08 02:00 | 2020-02-04 02:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Test] Making MOT mandatory and auto-popup (OPUS part) | 2020-01-29 15:35 | 2020-02-11 | 2020-02-10 18:22 | 2020-05-14 12:20 | 2020-06-23 10:43 |  | 2020-06-23 10:00 | 2020-06-30 10:12 | 2020-06-23 19:31 | 2020-07-30 13:00 | CR0012025 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 30 | 15 | 145.7671 | 2 | 1 | 2 | 0 | 193525 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.45455 | 2020-01 | 0 | 0
1601 | CR0012025 | CTASK0018092 | Closed | OPUS-BKG-M | Loc Tran | 14 | 15 | 2020-01-16 19:00 | 2020-01-09 14:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Estimate] Making MOT mandatory and auto-popup (OPUS part) | 2020-01-29 15:35 | 2020-02-11 | 2020-02-10 18:22 | 2020-05-14 12:20 | 2020-06-23 10:43 |  | 2020-06-23 10:00 | 2020-06-30 10:12 | 2020-06-23 19:31 | 2020-07-30 13:00 | CR0012025 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W26 | 2020-06 | 30 | 15 | 145.7671 | 2 | 1 | 2 | 0 | 193503 | 0.5 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.36364 | 2020-01 | 0 | 0
1602 | CR0013572 | CTASK0025272 | Closed | OPUS-SCO | Lien Le | 42 | 40 | 2021-02-28 11:32 | 2021-02-09 11:32 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Feb2021][Lien][CLT internal] CLEAR enhancement regarding PRL] | 2021-02-22 09:29 | 2021-03-31 09:29 | 2021-04-01 17:59 | 2021-04-06 10:18 | 2021-05-04 10:39 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-05-05 22:59 | 2021-06-10 14:00 | CR0013572 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2021-W19 | 2021-05 | 118 | 110 | 78.0213 | 4 | 1 | 3 | 0.06 | 193441 | 2 | 2 | 2 | 0 | 2 | 1 | 2 | 6 | 28 | 0.42308 | 1.2222 | 2021-02 | 2 | 1
1603 | CR0013572 | CTASK0025273 | Closed | OPUS-SCO | Cuong Tran Hung | 10 | 10 | 2021-02-28 11:34 | 2021-02-09 11:34 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Feb2021][Cuong][CLT internal] CLEAR enhancement regarding PRL] | 2021-02-22 09:29 | 2021-03-31 09:29 | 2021-04-01 17:59 | 2021-04-06 10:18 | 2021-05-04 10:39 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-05-05 22:59 | 2021-06-10 14:00 | CR0013572 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2021-W19 | 2021-05 | 118 | 110 | 78.0213 | 4 | 1 | 3 | 0.06 | 193530 | 1.7 | 2 | 2 | 0 | 2 | 1 | 2 | 6 | 28 | 1.2308 | 1.2222 | 2021-02 | 2 | 1
1604 | CR0013572 | CTASK0025275 | Closed | OPUS-SCO | Nguyen Ha Vi | 10 | 10 | 2021-02-28 11:35 | 2021-02-01 11:35 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Feb2021][Vi Nguyen][CLT internal] CLEAR enhancement regarding PRL] | 2021-02-22 09:29 | 2021-03-31 09:29 | 2021-04-01 17:59 | 2021-04-06 10:18 | 2021-05-04 10:39 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-05-05 22:59 | 2021-06-10 14:00 | CR0013572 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2021-W19 | 2021-05 | 118 | 110 | 78.0213 | 4 | 1 | 3 | 0.06 | 203664 | 0.7 | 2 | 2 | 0 | 2 | 1 | 2 | 6 | 28 | 1.8182 | 1.2857 | 2021-02 | 2 | 1
1605 | CR0013572 | CTASK0025668 | Closed | OPUS-SCO | Nguyen Ha Vi | 56 | 50 | 2021-03-31 13:11 | 2021-03-01 13:11 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Mar2021][Vi Nguyen][CLT internal] CLEAR enhancement regarding PRL] | 2021-02-22 09:29 | 2021-03-31 09:29 | 2021-04-01 17:59 | 2021-04-06 10:18 | 2021-05-04 10:39 |  | 2021-05-11 10:00 | 2021-05-11 10:00 | 2021-05-05 22:59 | 2021-06-10 14:00 | CR0013572 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2021-W19 | 2021-05 | 118 | 110 | 78.0213 | 4 | 1 | 3 | 0.06 | 203664 | 0.7 | 2 | 2 | 0 | 2 | 1 | 2 | 6 | 28 | 1.8182 | 1.2857 | 2021-02 | 2 | 1
1606 | CR0011755 | CTASK0016751 | Closed | OPUS-BKG-M | Thien Lai | 7 | 7 |  |  | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Estimated] NA *BKG* Inquiry to understand if an Item label could be split to "Guide" and "Comment" in Booking history. | 2019-11-05 12:06 | 2019-11-26 | 2019-11-19 16:36 | 2020-01-31 00:36 | 2020-02-07 13:49 | 2019-11-19 16:36 | 2020-03-24 10:00 | 2020-03-24 10:00 | 2020-02-21 04:59 | 2020-04-23 13:00 | CR0011755 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W13 | 2020-03 | 64 | 56 | 139.9125 | 3 | 2 | 2 | 0.02 | 193567 | 0.3 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 25 | 0 | 0.52941 | 2019-11 | 0 | 0
1607 | CR0011755 | CTASK0016771 | Closed | OPUS-BKG-M | Nam Nguyen | 40 | 40 | 2019-11-15 19:10 | 2019-11-04 19:09 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | NA *BKG* Inquiry to understand if an Item label could be split to "Guide" and "Comment" in Booking history. | 2019-11-05 12:06 | 2019-11-26 | 2019-11-19 16:36 | 2020-01-31 00:36 | 2020-02-07 13:49 | 2019-11-19 16:36 | 2020-03-24 10:00 | 2020-03-24 10:00 | 2020-02-21 04:59 | 2020-04-23 13:00 | CR0011755 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W13 | 2020-03 | 64 | 56 | 139.9125 | 3 | 2 | 2 | 0.02 | 123048 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 25 | 0 | 0.46154 | 2019-11 | 0 | 0
1608 | CR0011755 | CTASK0018317 | Closed | OPUS-BKG-OB | Nam Nguyen | 17 | 16 | 2020-02-12 16:49 | 2020-02-11 16:49 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] NA *BKG* Inquiry to understand if an Item label could be split to "Guide" and "Comment" in Booking history. | 2019-11-05 12:06 | 2019-11-26 | 2019-11-19 16:36 | 2020-01-31 00:36 | 2020-02-07 13:49 | 2019-11-19 16:36 | 2020-03-24 10:00 | 2020-03-24 10:00 | 2020-02-21 04:59 | 2020-04-23 13:00 | CR0011755 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2020-W13 | 2020-03 | 64 | 56 | 139.9125 | 3 | 2 | 2 | 0.02 | 123048 | 1.1 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 25 | 0 | 0.46154 | 2019-11 | 0 | 0
1609 | CR0011332 | CTASK0016792 | Closed | OPUS-PRI | Man Hoang | 88 | 64 | 2019-11-29 15:42 | 2019-10-01 15:42 | Container | Sales Management | Pricing | Service Contract | S/C Inquiry | S/C Amendment History | NA *PRI* Amendment History not displaying edits to Standard Note (NA CAP) | 2019-10-29 15:40 | 2019-12-20 15:40 | 2019-11-15 17:13 | 2019-11-22 06:51 | 2020-01-02 09:54 |  | 2020-01-07 10:54 | 2020-01-07 10:12 | 2020-01-07 10:12 | 2020-01-08 01:23 | CR0011332 | Sales ManagementPricingService ContractS/C InquiryS/C Amendment History | OPUS-PRI | 2020-W2 | 2020-01 | 241 | 184 | 69.8012 | 3 | 1 | 3 | 0.11 | 183431 | 0.9 | 0 | 0 | 0 | 2 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-10 | 0 | 0
1610 | CR0011332 | CTASK0016790 | Closed | OPUS-PRI | Nhien Nguyen | 81 | 60 | 2019-11-29 15:45 | 2019-10-01 15:45 | Container | Sales Management | Pricing | Service Contract | S/C Inquiry | S/C Amendment History | NA *PRI* Amendment History not displaying edits to Standard Note (NA CAP) | 2019-10-29 15:40 | 2019-12-20 15:40 | 2019-11-15 17:13 | 2019-11-22 06:51 | 2020-01-02 09:54 |  | 2020-01-07 10:54 | 2020-01-07 10:12 | 2020-01-07 10:12 | 2020-01-08 01:23 | CR0011332 | Sales ManagementPricingService ContractS/C InquiryS/C Amendment History | OPUS-PRI | 2020-W2 | 2020-01 | 241 | 184 | 69.8012 | 3 | 1 | 3 | 0.11 | 183364 | 1.1 | 0 | 0 | 0 | 2 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-10 | 0 | 0
1611 | CR0011332 | CTASK0016791 | Closed | OPUS-PRI | Ngan Nham | 72 | 60 | 2019-11-29 15:43 | 2019-10-01 15:43 | Container | Sales Management | Pricing | Service Contract | S/C Inquiry | S/C Amendment History | NA *PRI* Amendment History not displaying edits to Standard Note (NA CAP) | 2019-10-29 15:40 | 2019-12-20 15:40 | 2019-11-15 17:13 | 2019-11-22 06:51 | 2020-01-02 09:54 |  | 2020-01-07 10:54 | 2020-01-07 10:12 | 2020-01-07 10:12 | 2020-01-08 01:23 | CR0011332 | Sales ManagementPricingService ContractS/C InquiryS/C Amendment History | OPUS-PRI | 2020-W2 | 2020-01 | 241 | 184 | 69.8012 | 3 | 1 | 3 | 0.11 | 193461 | 0.9 | 0 | 0 | 0 | 2 | 1 | 2 | 3 | 10 | 0 | 0 | 2019-10 | 0 | 0
1612 | CR0012217 | CTASK0022101 | Closed | OPUS-DMT | Cuong Nguyen | 80 | 78 | 2020-09-30 20:00 | 2020-09-01 08:00 | Container | Service Management | Demurrage/Detention | F/T Adjustment | DAR - After Booking |  | [Change Task 5] CLV_Development | 2020-08-26 08:23 | 2020-11-13 20:00 | 2020-11-13 17:11 | 2021-01-20 08:52 | 2021-01-21 15:41 |  | 2021-02-02 10:00 | 2021-02-02 10:12 | 2021-01-27 08:52 | 2021-02-02 23:08 | CR0012217 | Service ManagementDemurrage/DetentionF/T AdjustmentDAR - After Booking | OPUS-DMT | 2021-W5 | 2021-02 | 104 | 105 | 160.0677 | 2 | 1 | 1 | 0.03 | 193529 | 1.2 | 0 | 0 | 0 | 2 | 1 | 3 | 8 | 21 | 0 | 0.058824 | 2020-08 | 0 | 0
1613 | CR0012217 | CTASK0022102 | Closed | OPUS-DMT | Cuong Nguyen | 24 | 27 | 2020-10-30 20:00 | 2020-10-01 08:00 | Container | Service Management | Demurrage/Detention | F/T Adjustment | DAR - After Booking |  | [Change Task 6] CLV_Test_Deployment | 2020-08-26 08:23 | 2020-11-13 20:00 | 2020-11-13 17:11 | 2021-01-20 08:52 | 2021-01-21 15:41 |  | 2021-02-02 10:00 | 2021-02-02 10:12 | 2021-01-27 08:52 | 2021-02-02 23:08 | CR0012217 | Service ManagementDemurrage/DetentionF/T AdjustmentDAR - After Booking | OPUS-DMT | 2021-W5 | 2021-02 | 104 | 105 | 160.0677 | 2 | 1 | 1 | 0.03 | 193529 | 1.2 | 0 | 0 | 0 | 2 | 1 | 3 | 8 | 21 | 0 | 0.058824 | 2020-08 | 0 | 0
1614 | CR0013975 | CTASK0027285 | Closed | OPUS-TPB | Manh Nguyen | 28 | 30 | 2021-07-01 01:00 | 2021-06-01 01:00 | Container | Service Management | 3rd Party Billing | JO TPB | JO TPB Invoice Revise/Cancel |  | [202106][CLT Internal] AS - Opus Container - TPB - iNV amount changed | 2021-06-03 13:15 | 2021-07-30 22:38 | 2021-06-11 15:24 | 2021-06-15 13:34 | 2021-06-15 15:51 |  | 2021-06-22 12:30 | 2021-06-22 12:30 | 2021-06-16 09:09 | 2021-07-23 14:00 | CR0013975 | Service Management3rd Party BillingJO TPBJO TPB Invoice Revise/Cancel | OPUS-TPB | 2021-W25 | 2021-06 | 28 | 31 | 18.9686 | 2 | 1 | 1 | 0.07 | 153138 | 2.7 | 0 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0 | 0.16667 | 2021-06 | 0 | 0
1615 | CR0013975 | CTASK0027068 | Closed | OPUS-TPB | Manh Nguyen | 1 | 1 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | 3rd Party Billing | JO TPB | JO TPB Invoice Revise/Cancel |  | [202105][CLT Internal] AS - Opus Container - TPB - iNV amount changed | 2021-06-03 13:15 | 2021-07-30 22:38 | 2021-06-11 15:24 | 2021-06-15 13:34 | 2021-06-15 15:51 |  | 2021-06-22 12:30 | 2021-06-22 12:30 | 2021-06-16 09:09 | 2021-07-23 14:00 | CR0013975 | Service Management3rd Party BillingJO TPBJO TPB Invoice Revise/Cancel | OPUS-TPB | 2021-W25 | 2021-06 | 28 | 31 | 18.9686 | 2 | 1 | 1 | 0.07 | 153138 | 2.7 | 0 | 0 | 0 | 1 | 1 | 1 | 11 | 53 | 0 | 0.16667 | 2021-06 | 0 | 0
1616 | CR0012622 | CTASK0020133 | Closed | OPUS-SCO | Chuong Ta | 50 | 50 | 2020-06-01 11:28 | 2020-05-18 11:04 | Container | Statement Management | Statement Account Receivable |  |  |  | [CLV EFFORT][EUA - Structure change for SAR Customer Integration] Chuong Ta | 2020-06-25 10:19 | 2020-08-04 10:19 | 2020-07-03 15:51 | 2020-07-10 18:54 | 2020-07-10 18:56 |  | 2020-07-14 08:55 | 2020-07-21 10:19 | 2020-07-10 20:00 | 2020-08-20 13:00 | CR0012622 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W29 | 2020-07 | 462 | 424 | 18.9418 | 9 | 1 | 3 | 0.93 | 183379 | 1.3 | 0 | 0 | 0 | 4 | 1 | 1 | 9 | 27 | 0 | 0.38462 | 2020-06 | 0 | 0
1617 | CR0012622 | CTASK0020183 | Closed | OPUS-SCO | Mohamed Hary | 40 | 40 | 2020-05-30 16:30 | 2020-05-19 16:30 | Container | Statement Management | Statement Account Receivable |  |  |  | [CLV EFFORT] EUA - Structure change for SAR Customer Integration - Mohamed Hary | 2020-06-25 10:19 | 2020-08-04 10:19 | 2020-07-03 15:51 | 2020-07-10 18:54 | 2020-07-10 18:56 |  | 2020-07-14 08:55 | 2020-07-21 10:19 | 2020-07-10 20:00 | 2020-08-20 13:00 | CR0012622 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W29 | 2020-07 | 462 | 424 | 18.9418 | 9 | 1 | 3 | 0.93 | 193489 | 1.1 | 0 | 0 | 0 | 4 | 1 | 1 | 9 | 27 | 0 | 0.63636 | 2020-06 | 0 | 0
1618 | CR0012622 | CTASK0020476 | Closed | OPUS-SCO | Dinh Cong Tuan | 76 | 45 | 2020-06-30 17:20 | 2020-06-01 17:20 | Container | Statement Management | Statement Account Receivable |  |  |  | [CLV EFFORT][EUA - Structure change for SAR Customer Integration] on June - Dinh Cong Tuan | 2020-06-25 10:19 | 2020-08-04 10:19 | 2020-07-03 15:51 | 2020-07-10 18:54 | 2020-07-10 18:56 |  | 2020-07-14 08:55 | 2020-07-21 10:19 | 2020-07-10 20:00 | 2020-08-20 13:00 | CR0012622 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W29 | 2020-07 | 462 | 424 | 18.9418 | 9 | 1 | 3 | 0.93 | 193510 | 1.1 | 0 | 0 | 0 | 4 | 1 | 1 | 9 | 27 | 0 | 0 | 2020-06 | 0 | 0
1619 | CR0012622 | CTASK0020452 | Closed | OPUS-SCO | Chuong Ta | 70 | 62 | 2020-06-30 19:09 | 2020-06-01 19:09 | Container | Statement Management | Statement Account Receivable |  |  |  | [CLV EFFORT][EUA - Structure change for SAR Customer Integration] on June - Chuong Ta | 2020-06-25 10:19 | 2020-08-04 10:19 | 2020-07-03 15:51 | 2020-07-10 18:54 | 2020-07-10 18:56 |  | 2020-07-14 08:55 | 2020-07-21 10:19 | 2020-07-10 20:00 | 2020-08-20 13:00 | CR0012622 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W29 | 2020-07 | 462 | 424 | 18.9418 | 9 | 1 | 3 | 0.93 | 183379 | 1.3 | 0 | 0 | 0 | 4 | 1 | 1 | 9 | 27 | 0 | 0.38462 | 2020-06 | 0 | 0
1620 | CR0012622 | CTASK0020155 | Closed | OPUS-SCO | Dinh Cong Tuan | 51 | 50 | 2020-05-31 19:22 | 2020-05-18 19:22 | Container | Statement Management | Statement Account Receivable |  |  |  | EUA - Structure change for SAR Customer Integration - Dinh Cong Tuan | 2020-06-25 10:19 | 2020-08-04 10:19 | 2020-07-03 15:51 | 2020-07-10 18:54 | 2020-07-10 18:56 |  | 2020-07-14 08:55 | 2020-07-21 10:19 | 2020-07-10 20:00 | 2020-08-20 13:00 | CR0012622 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W29 | 2020-07 | 462 | 424 | 18.9418 | 9 | 1 | 3 | 0.93 | 193510 | 1.1 | 0 | 0 | 0 | 4 | 1 | 1 | 9 | 27 | 0 | 0 | 2020-06 | 0 | 0
1621 | CR0012622 | CTASK0021250 | Closed | OPUS-SCO | Dinh Cong Tuan | 40 | 40 | 2020-07-31 16:58 | 2020-07-01 16:58 | Container | Statement Management | Statement Account Receivable |  |  |  | [Tuan][July] additional modification | 2020-06-25 10:19 | 2020-08-04 10:19 | 2020-07-03 15:51 | 2020-07-10 18:54 | 2020-07-10 18:56 |  | 2020-07-14 08:55 | 2020-07-21 10:19 | 2020-07-10 20:00 | 2020-08-20 13:00 | CR0012622 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W29 | 2020-07 | 462 | 424 | 18.9418 | 9 | 1 | 3 | 0.93 | 193510 | 1.1 | 0 | 0 | 0 | 4 | 1 | 1 | 9 | 27 | 0 | 0 | 2020-06 | 0 | 0
1622 | CR0012622 | CTASK0020455 | Closed | OPUS-SCO | Mohamed Hary | 55 | 57 | 2020-06-30 19:42 | 2020-06-01 19:42 | Container | Statement Management | Statement Account Receivable |  |  |  | [CLV EFFORT] EUA - Structure change for SAR Customer Integration - Mohamed Hary | 2020-06-25 10:19 | 2020-08-04 10:19 | 2020-07-03 15:51 | 2020-07-10 18:54 | 2020-07-10 18:56 |  | 2020-07-14 08:55 | 2020-07-21 10:19 | 2020-07-10 20:00 | 2020-08-20 13:00 | CR0012622 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W29 | 2020-07 | 462 | 424 | 18.9418 | 9 | 1 | 3 | 0.93 | 193489 | 1.1 | 0 | 0 | 0 | 4 | 1 | 1 | 9 | 27 | 0 | 0.63636 | 2020-06 | 0 | 0
1623 | CR0012622 | CTASK0021208 | Closed | OPUS-SCO | Chuong Ta | 40 | 40 | 2020-07-31 08:51 | 2020-07-14 08:51 | Container | Statement Management | Statement Account Receivable |  |  |  | [Chuong][July] additional modification | 2020-06-25 10:19 | 2020-08-04 10:19 | 2020-07-03 15:51 | 2020-07-10 18:54 | 2020-07-10 18:56 |  | 2020-07-14 08:55 | 2020-07-21 10:19 | 2020-07-10 20:00 | 2020-08-20 13:00 | CR0012622 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W29 | 2020-07 | 462 | 424 | 18.9418 | 9 | 1 | 3 | 0.93 | 183379 | 1.3 | 0 | 0 | 0 | 4 | 1 | 1 | 9 | 27 | 0 | 0.38462 | 2020-06 | 0 | 0
1624 | CR0012622 | CTASK0021251 | Closed | OPUS-SCO | Mohamed Hary | 40 | 40 | 2020-07-31 16:59 | 2020-07-01 16:59 | Container | Statement Management | Statement Account Receivable |  |  |  | [Hary][July] additional modification | 2020-06-25 10:19 | 2020-08-04 10:19 | 2020-07-03 15:51 | 2020-07-10 18:54 | 2020-07-10 18:56 |  | 2020-07-14 08:55 | 2020-07-21 10:19 | 2020-07-10 20:00 | 2020-08-20 13:00 | CR0012622 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2020-W29 | 2020-07 | 462 | 424 | 18.9418 | 9 | 1 | 3 | 0.93 | 193489 | 1.1 | 0 | 0 | 0 | 4 | 1 | 1 | 9 | 27 | 0 | 0.63636 | 2020-06 | 0 | 0
1625 | CR0012977 | CTASK0026857 | Closed | OPUS-TES | Thai Nguyen | 1 | 1 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [202105] Freight C/A approval office setup needs to have option to select either country wise setup or AR office wise setup | 2020-12-15 17:26 | 2020-12-19 | 2020-12-18 11:09 | 2021-04-08 18:44 | 2021-04-15 13:59 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-20 16:43 | 2021-06-24 14:00 | CR0012977 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W21 | 2021-05 | 92 | 81 | 160.6903 | 5 | 2 | 2 | 0.02 | 173249 | 2.2 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0 | 0.5 | 2020-12 | 0 | 0
1626 | CR0012977 | CTASK0024089 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 24 | 24 | 2020-12-17 02:00 | 2020-12-08 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Develop+Test] Freight C/A approval office setup needs to have option to select either country wise setup or AR office wise setup | 2020-12-15 17:26 | 2020-12-19 | 2020-12-18 11:09 | 2021-04-08 18:44 | 2021-04-15 13:59 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-20 16:43 | 2021-06-24 14:00 | CR0012977 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W21 | 2021-05 | 92 | 81 | 160.6903 | 5 | 2 | 2 | 0.02 | 193470 | 1.7 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0 | 0.17391 | 2020-12 | 0 | 0
1627 | CR0012977 | CTASK0026961 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 14 | 14 | 2021-05-25 01:00 | 2021-05-11 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Deployment] Freight C/A approval office setup needs to have option to select either country wise setup or AR office wise setup | 2020-12-15 17:26 | 2020-12-19 | 2020-12-18 11:09 | 2021-04-08 18:44 | 2021-04-15 13:59 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-20 16:43 | 2021-06-24 14:00 | CR0012977 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W21 | 2021-05 | 92 | 81 | 160.6903 | 5 | 2 | 2 | 0.02 | 193470 | 1.7 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0 | 0.17391 | 2020-12 | 0 | 0
1628 | CR0012977 | CTASK0023463 | Closed | OPUS-TES | Thai Nguyen | 46 | 46 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | Freight C/A approval office setup needs to have option to select either country wise setup or AR office wise setup | 2020-12-15 17:26 | 2020-12-19 | 2020-12-18 11:09 | 2021-04-08 18:44 | 2021-04-15 13:59 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-20 16:43 | 2021-06-24 14:00 | CR0012977 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W21 | 2021-05 | 92 | 81 | 160.6903 | 5 | 2 | 2 | 0.02 | 173249 | 2.2 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0 | 0.5 | 2020-12 | 0 | 0
1629 | CR0012977 | CTASK0026491 | Closed | OPUS-TES | Thai Nguyen | 8 | 10 | 2021-05-01 01:00 | 2021-04-01 01:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [202104] Freight C/A approval office setup needs to have option to select either country wise setup or AR office wise setup | 2020-12-15 17:26 | 2020-12-19 | 2020-12-18 11:09 | 2021-04-08 18:44 | 2021-04-15 13:59 |  | 2021-05-25 10:00 | 2021-05-25 10:00 | 2021-05-20 16:43 | 2021-06-24 14:00 | CR0012977 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W21 | 2021-05 | 92 | 81 | 160.6903 | 5 | 2 | 2 | 0.02 | 173249 | 2.2 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 28 | 0 | 0.5 | 2020-12 | 0 | 0
1630 | CR0012487 | CTASK0019663 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2020-05-14 18:31 | 2020-05-11 10:03 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] ADDITIONAL REQUST IN RELATION TO BOOKING AUTO UPLOAD | 2020-04-28 16:19 | 2020-05-15 | 2020-05-13 17:13 | 2020-06-19 18:16 | 2020-06-24 13:46 |  | 2020-06-30 10:00 | 2020-06-30 10:13 | 2020-06-26 16:41 | 2020-07-30 13:00 | CR0012487 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 29 | 31 | 62.7371 | 4 | 1 | 2 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 2.1667 | 2020-04 | 0 | 0
1631 | CR0012487 | CTASK0019666 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 2 | 2 | 2020-06-12 18:00 | 2020-06-08 10:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] ADDITIONAL REQUST IN RELATION TO BOOKING AUTO UPLOAD | 2020-04-28 16:19 | 2020-05-15 | 2020-05-13 17:13 | 2020-06-19 18:16 | 2020-06-24 13:46 |  | 2020-06-30 10:00 | 2020-06-30 10:13 | 2020-06-26 16:41 | 2020-07-30 13:00 | CR0012487 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 29 | 31 | 62.7371 | 4 | 1 | 2 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 2.1667 | 2020-04 | 0 | 0
1632 | CR0012487 | CTASK0019661 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 15 | 15 | 2020-05-06 22:53 | 2020-04-29 10:52 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] ADDITIONAL REQUST IN RELATION TO BOOKING AUTO UPLOAD | 2020-04-28 16:19 | 2020-05-15 | 2020-05-13 17:13 | 2020-06-19 18:16 | 2020-06-24 13:46 |  | 2020-06-30 10:00 | 2020-06-30 10:13 | 2020-06-26 16:41 | 2020-07-30 13:00 | CR0012487 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 29 | 31 | 62.7371 | 4 | 1 | 2 | 0.02 | 193488 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 2.1667 | 2020-04 | 0 | 0
1633 | CR0012487 | CTASK0019646 | Closed | OPUS-BKG-M | Vinh Tran | 10 | 10 | 2020-04-16 02:00 | 2020-04-14 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] ADDITIONAL REQUST IN RELATION TO BOOKING AUTO UPLOAD | 2020-04-28 16:19 | 2020-05-15 | 2020-05-13 17:13 | 2020-06-19 18:16 | 2020-06-24 13:46 |  | 2020-06-30 10:00 | 2020-06-30 10:13 | 2020-06-26 16:41 | 2020-07-30 13:00 | CR0012487 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W27 | 2020-06 | 29 | 31 | 62.7371 | 4 | 1 | 2 | 0.02 | 193525 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 29 | 0 | 0.45455 | 2020-04 | 0 | 0
1634 | CR0011055 | CTASK0018211 | Closed | OPUS-SAP | Chuong Ta | 276 | 276 |  |  | Container | Statement Management | Statement Account Payable | Invoices |  |  | [Actual CLV] Account Code limitation in "Prepayment Invoice Entry Screen" | 2020-01-31 17:48 | 2020-02-25 17:48 | 2020-02-12 15:16 | 2020-03-18 10:16 | 2020-03-18 11:48 |  | 2020-03-24 11:47 | 2020-03-24 10:18 | 2020-03-18 11:51 | 2020-04-23 13:00 | CR0011055 | Statement ManagementStatement Account PayableInvoices | OPUS-SAP | 2020-W13 | 2020-03 | 276 | 0 | 52.7493 | 1 | 1 | 1 | 0 | 183379 | 0.9 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 25 | 0 | 0 | 2020-01 | 0 | 0
1635 | CR0011692 | CTASK0016838 | Closed | OPUS-BKG-M | Vinh Tran | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Estimated] Add "RD" (RAD) Indication in eBooking screen in Opus | 2019-12-06 16:29 | 2019-12-24 | 2019-12-19 16:14 | 2020-03-18 05:03 | 2020-03-20 14:49 |  | 2020-06-09 10:00 | 2020-06-09 13:22 | 2020-05-29 01:59 | 2020-07-10 13:00 | CR0011692 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W24 | 2020-06 | 24 | 20 | 185.7297 | 2 | 2 | 1 | 0 | 193525 | 0.5 | 0 | 0 | 0 | 1 | 1 | 3 | 5 | 29 | 0 | 0.45455 | 2019-12 | 0 | 0
1636 | CR0011692 | CTASK0016852 | Closed | OPUS-BKG-EBKG | Vinh Tran | 20 | 20 | 2019-12-13 19:01 | 2019-12-09 19:01 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | Add "RD" (RAD) Indication in eBooking screen in Opus | 2019-12-06 16:29 | 2019-12-24 | 2019-12-19 16:14 | 2020-03-18 05:03 | 2020-03-20 14:49 |  | 2020-06-09 10:00 | 2020-06-09 13:22 | 2020-05-29 01:59 | 2020-07-10 13:00 | CR0011692 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2020-W24 | 2020-06 | 24 | 20 | 185.7297 | 2 | 2 | 1 | 0 | 193525 | 0.5 | 0 | 0 | 0 | 1 | 1 | 3 | 5 | 29 | 0 | 0.45455 | 2019-12 | 0 | 0
1637 | CR0012640 | CTASK0021678 | Closed | OPUS-PRI | Nhien Nguyen | 49 | 50 | 2020-09-30 16:08 | 2020-07-27 16:08 | Container | Biz Common | Master Data | Partner | Customer Integration |  | Blacklist function to incorporate function to edit Parent & child blacklist settings too | 2020-08-31 15:57 | 2020-09-18 15:57 | 2020-09-16 13:37 | 2020-11-24 11:21 | 2020-11-26 15:21 |  | 2020-12-01 15:21 | 2020-12-01 11:52 | 2020-11-27 09:21 | 2021-01-03 14:00 | CR0012640 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2020-W49 | 2020-12 | 230 | 200 | 91.9744 | 4 | 2 | 4 | 0.09 | 183364 | 1.9 | 0 | 0 | 0 | 2 | 2 | 2 | 10 | 30 | 0 | 0 | 2020-08 | 0 | 0
1638 | CR0012640 | CTASK0021679 | Closed | OPUS-PRI | Ngan Nham | 131 | 95 | 2020-09-30 16:09 | 2020-07-31 07:09 | Container | Biz Common | Master Data | Partner | Customer Integration |  | Blacklist function to incorporate function to edit Parent & child blacklist settings too | 2020-08-31 15:57 | 2020-09-18 15:57 | 2020-09-16 13:37 | 2020-11-24 11:21 | 2020-11-26 15:21 |  | 2020-12-01 15:21 | 2020-12-01 11:52 | 2020-11-27 09:21 | 2021-01-03 14:00 | CR0012640 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2020-W49 | 2020-12 | 230 | 200 | 91.9744 | 4 | 2 | 4 | 0.09 | 193461 | 1.8 | 0 | 0 | 0 | 2 | 2 | 2 | 10 | 30 | 0 | 0.28571 | 2020-08 | 0 | 0
1639 | CR0012640 | CTASK0022063 | Closed | OPUS-ACM | Huynh Tuan Khanh | 15 | 20 | 2020-08-31 11:41 | 2020-07-27 11:41 | Container | Biz Common | Master Data | Partner | Customer Integration |  | Blacklist function to incorporate function to edit Parent & child blacklist settings too | 2020-08-31 15:57 | 2020-09-18 15:57 | 2020-09-16 13:37 | 2020-11-24 11:21 | 2020-11-26 15:21 |  | 2020-12-01 15:21 | 2020-12-01 11:52 | 2020-11-27 09:21 | 2021-01-03 14:00 | CR0012640 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2020-W49 | 2020-12 | 230 | 200 | 91.9744 | 4 | 2 | 4 | 0.09 | 193499 | 1.3 | 0 | 0 | 0 | 2 | 2 | 2 | 10 | 30 | 0 | 0 | 2020-08 | 0 | 0
1640 | CR0012640 | CTASK0022059 | Closed | OPUS-PRI | Man Hoang | 35 | 35 | 2020-08-31 11:19 | 2020-08-03 11:19 | Container | Biz Common | Master Data | Partner | Customer Integration |  | Blacklist function to incorporate function to edit Parent & child blacklist settings too | 2020-08-31 15:57 | 2020-09-18 15:57 | 2020-09-16 13:37 | 2020-11-24 11:21 | 2020-11-26 15:21 |  | 2020-12-01 15:21 | 2020-12-01 11:52 | 2020-11-27 09:21 | 2021-01-03 14:00 | CR0012640 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2020-W49 | 2020-12 | 230 | 200 | 91.9744 | 4 | 2 | 4 | 0.09 | 183431 | 1.8 | 0 | 0 | 0 | 2 | 2 | 2 | 10 | 30 | 0 | 0.66667 | 2020-08 | 0 | 0
1641 | CR0011526 | CTASK0017350 | Closed | OPUS-MNR | Tuyen Truong | 156 | 100 | 2020-03-31 09:12 | 2019-12-02 09:12 | Container | Equipment Management | M&R | Repair |  |  | NA * Corporate Accounting* Extract NA Specific M&R Expenses for Payment through Local ERP (F&A) | 2020-01-08 14:52 | 2020-03-06 19:51 | 2020-03-06 18:26 | 2020-03-19 10:16 | 2020-03-23 08:05 |  | 2020-03-31 18:04 | 2020-03-31 09:40 | 2020-03-25 22:26 | 2020-05-01 13:00 | CR0011526 | Equipment ManagementM&RRepair | OPUS-MNR | 2020-W14 | 2020-03 | 254 | 200 | 83.1333 | 2 | 1 | 2 | 0.1 | 173255 | 1.3 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 25 | 0 | 0 | 2020-01 | 0 | 0
1642 | CR0011526 | CTASK0017349 | Closed | OPUS-MNR | Tien Le | 98 | 100 | 2020-03-31 09:11 | 2019-12-02 09:10 | Container | Equipment Management | M&R | Repair |  |  | NA * Corporate Accounting* Extract NA Specific M&R Expenses for Payment through Local ERP (F&A) | 2020-01-08 14:52 | 2020-03-06 19:51 | 2020-03-06 18:26 | 2020-03-19 10:16 | 2020-03-23 08:05 |  | 2020-03-31 18:04 | 2020-03-31 09:40 | 2020-03-25 22:26 | 2020-05-01 13:00 | CR0011526 | Equipment ManagementM&RRepair | OPUS-MNR | 2020-W14 | 2020-03 | 254 | 200 | 83.1333 | 2 | 1 | 2 | 0.1 | 173286 | 1.3 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 25 | 0 | 0 | 2020-01 | 0 | 0
1643 | CR0012880 | CTASK0021671 | Closed | OPUS-SCE | Thanh Tran Ngoc | 30 | 30 |  |  | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [CLT Internal] OPUS service enhancement for COP actual mapping | 2020-08-04 11:56 | 2020-08-15 11:55 | 2020-08-14 16:45 |  | 2020-08-18 13:24 |  | 2020-08-26 01:00 | 2020-08-25 12:00 | 2020-08-21 11:09 | 2020-09-25 13:00 | CR0012880 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2020-W35 | 2020-08 | 30 | 30 | 21.5445 | 2 | 1 | 1 | 0.06 | 193478 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 12 | 30 | 0 | 0 | 2020-08 | 0 | 0
1644 | CR0012880 | CTASK0021396 | Closed | OPUS-SCE | Thanh Tran Ngoc | 1 | 1 |  |  | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [Documentation] [CLT Internal] OPUS service enhancement for COP actual mapping | 2020-08-04 11:56 | 2020-08-15 11:55 | 2020-08-14 16:45 |  | 2020-08-18 13:24 |  | 2020-08-26 01:00 | 2020-08-25 12:00 | 2020-08-21 11:09 | 2020-09-25 13:00 | CR0012880 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2020-W35 | 2020-08 | 30 | 30 | 21.5445 | 2 | 1 | 1 | 0.06 | 193478 | 0.8 | 0 | 0 | 0 | 1 | 1 | 1 | 12 | 30 | 0 | 0 | 2020-08 | 0 | 0
1645 | CR0013341 | CTASK0024180 | Closed | OPUS-TPB | Manh Nguyen | 117 | 50 | 2021-01-29 09:09 | 2020-12-16 09:09 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | EUA - additional enhancements to speed up the end-to-end TPB process | 2020-12-30 07:50 | 2021-02-25 07:49 | 2021-02-24 16:18 | 2021-04-28 16:04 | 2021-05-06 12:48 |  | 2021-05-11 12:00 | 2021-05-11 10:00 | 2021-05-06 17:05 | 2021-06-10 14:00 | CR0013341 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W19 | 2021-05 | 244 | 145 | 132.1734 | 7 | 2 | 3 | 0.05 | 153138 | 2.3 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 28 | 0 | 0.16667 | 2020-12 | 0 | 0
1646 | CR0013341 | CTASK0025620 | Closed | OPUS-TPB | Manh Nguyen | 38 | 40 | 2021-04-01 01:00 | 2021-03-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [202103] EUA - additional enhancements to speed up the end-to-end TPB process | 2020-12-30 07:50 | 2021-02-25 07:49 | 2021-02-24 16:18 | 2021-04-28 16:04 | 2021-05-06 12:48 |  | 2021-05-11 12:00 | 2021-05-11 10:00 | 2021-05-06 17:05 | 2021-06-10 14:00 | CR0013341 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W19 | 2021-05 | 244 | 145 | 132.1734 | 7 | 2 | 3 | 0.05 | 153138 | 2.3 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 28 | 0 | 0.16667 | 2020-12 | 0 | 0
1647 | CR0013341 | CTASK0026811 | Closed | OPUS-TPB | Manh Nguyen | 12 | 12 | 2021-06-01 01:00 | 2021-05-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [202105] EUA - additional enhancements to speed up the end-to-end TPB process | 2020-12-30 07:50 | 2021-02-25 07:49 | 2021-02-24 16:18 | 2021-04-28 16:04 | 2021-05-06 12:48 |  | 2021-05-11 12:00 | 2021-05-11 10:00 | 2021-05-06 17:05 | 2021-06-10 14:00 | CR0013341 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W19 | 2021-05 | 244 | 145 | 132.1734 | 7 | 2 | 3 | 0.05 | 153138 | 2.3 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 28 | 0 | 0.16667 | 2020-12 | 0 | 0
1648 | CR0013341 | CTASK0026751 | Closed | OPUS-TPB | Manh Nguyen | 1 | 1 | 2021-05-01 01:00 | 2021-04-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [202104] EUA - additional enhancements to speed up the end-to-end TPB process | 2020-12-30 07:50 | 2021-02-25 07:49 | 2021-02-24 16:18 | 2021-04-28 16:04 | 2021-05-06 12:48 |  | 2021-05-11 12:00 | 2021-05-11 10:00 | 2021-05-06 17:05 | 2021-06-10 14:00 | CR0013341 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W19 | 2021-05 | 244 | 145 | 132.1734 | 7 | 2 | 3 | 0.05 | 153138 | 2.3 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 28 | 0 | 0.16667 | 2020-12 | 0 | 0
1649 | CR0013341 | CTASK0024443 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 30 | 11 | 2021-01-31 17:16 | 2021-01-04 17:16 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [202101] EUA - additional enhancements to speed up the end-to-end TPB process (TRS) | 2020-12-30 07:50 | 2021-02-25 07:49 | 2021-02-24 16:18 | 2021-04-28 16:04 | 2021-05-06 12:48 |  | 2021-05-11 12:00 | 2021-05-11 10:00 | 2021-05-06 17:05 | 2021-06-10 14:00 | CR0013341 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W19 | 2021-05 | 244 | 145 | 132.1734 | 7 | 2 | 3 | 0.05 | 183432 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 28 | 0 | 0 | 2020-12 | 0 | 0
1650 | CR0013341 | CTASK0024444 | Closed | OPUS-TRS | Giang Nguyen Hoang | 23 | 11 | 2021-01-31 17:16 | 2021-01-04 17:16 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [202101] EUA - additional enhancements to speed up the end-to-end TPB process (TRS) | 2020-12-30 07:50 | 2021-02-25 07:49 | 2021-02-24 16:18 | 2021-04-28 16:04 | 2021-05-06 12:48 |  | 2021-05-11 12:00 | 2021-05-11 10:00 | 2021-05-06 17:05 | 2021-06-10 14:00 | CR0013341 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W19 | 2021-05 | 244 | 145 | 132.1734 | 7 | 2 | 3 | 0.05 | 183440 | 1.8 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 28 | 0 | 0 | 2020-12 | 0 | 0
1651 | CR0013341 | CTASK0025053 | Closed | OPUS-TPB | Manh Nguyen | 24 | 20 | 2021-02-27 01:00 | 2021-02-01 01:00 | Container | Service Management | 3rd Party Billing | TPB Process |  |  | [202102] EUA - additional enhancements to speed up the end-to-end TPB process | 2020-12-30 07:50 | 2021-02-25 07:49 | 2021-02-24 16:18 | 2021-04-28 16:04 | 2021-05-06 12:48 |  | 2021-05-11 12:00 | 2021-05-11 10:00 | 2021-05-06 17:05 | 2021-06-10 14:00 | CR0013341 | Service Management3rd Party BillingTPB Process | OPUS-TPB | 2021-W19 | 2021-05 | 244 | 145 | 132.1734 | 7 | 2 | 3 | 0.05 | 153138 | 2.3 | 0 | 0 | 0 | 2 | 1 | 2 | 6 | 28 | 0 | 0.16667 | 2020-12 | 0 | 0
1652 | CR0011703 | CTASK0019781 | Closed | OPUS-BKG-M | Kieu Le | 9 | 9 | 2020-04-30 02:00 | 2020-04-23 02:59 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Monitoring Report | [Development] Workload estimate of CMPB calculation for Standby Booking related screens in OPUS BKG Module | 2019-12-24 05:02 | 2020-02-11 | 2020-02-10 18:21 | 2020-08-06 05:54 | 2020-08-07 09:32 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-07 09:42 | 2020-09-24 13:00 | CR0011703 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Monitoring Report | OPUS-BKG-M | 2020-W35 | 2020-08 | 120 | 120 | 245.2067 | 3 | 1 | 1 | 0.02 | 153106 | 1.2 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 30 | 0 | 0.4 | 2019-12 | 0 | 0
1653 | CR0011703 | CTASK0016436 | Closed | OPUS-BKG-M | Kieu Le | 99 | 99 | 2020-01-17 10:56 | 2019-12-16 10:56 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Monitoring Report | Workload estimate of CMPB calculation for Standby Booking related screens in OPUS BKG Module | 2019-12-24 05:02 | 2020-02-11 | 2020-02-10 18:21 | 2020-08-06 05:54 | 2020-08-07 09:32 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-07 09:42 | 2020-09-24 13:00 | CR0011703 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Monitoring Report | OPUS-BKG-M | 2020-W35 | 2020-08 | 120 | 120 | 245.2067 | 3 | 1 | 1 | 0.02 | 153106 | 1.2 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 30 | 0 | 0.4 | 2019-12 | 0 | 0
1654 | CR0011703 | CTASK0021821 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 | 2020-08-21 20:30 | 2020-08-11 20:29 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Monitoring Report | [Deployment] Workload estimate of CMPB calculation for Standby Booking related screens in OPUS BKG Module | 2019-12-24 05:02 | 2020-02-11 | 2020-02-10 18:21 | 2020-08-06 05:54 | 2020-08-07 09:32 |  | 2020-08-25 10:00 | 2020-08-25 10:00 | 2020-08-07 09:42 | 2020-09-24 13:00 | CR0011703 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Monitoring Report | OPUS-BKG-M | 2020-W35 | 2020-08 | 120 | 120 | 245.2067 | 3 | 1 | 1 | 0.02 | 153106 | 1.2 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 30 | 0 | 0.4 | 2019-12 | 0 | 0
1655 | CR0012238 | CTASK0018739 | Closed | OPUS-CTM | Tran Le | 9 | 11 | 2020-04-11 | 2020-03-09 10:00 | Container | Service Management | CNTR Movement | Monitoring | EDI Error Report |  | [OPUS-CTM] Pair Test | 2020-03-09 08:32 | 2020-03-28 | 2020-03-26 16:37 | 2020-04-17 15:48 | 2020-04-20 08:12 |  | 2020-04-28 10:00 | 2020-04-28 09:37 | 2020-04-20 17:47 | 2020-04-28 13:35 | CR0012238 | Service ManagementCNTR MovementMonitoringEDI Error Report | OPUS-CTM | 2020-W18 | 2020-04 | 88 | 85 | 50.0612 | 2 | 1 | 2 | 0.07 | 193501 | 0.4 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0 | 2020-03 | 0 | 0
1656 | CR0012238 | CTASK0018542 | Closed | OPUS-CTM | Phu Nguyen Hoang | 79 | 74 | 2020-03-28 | 2020-03-09 10:00 | Container | Service Management | CNTR Movement | Monitoring | EDI Error Report |  | [OPUS-CTM] Enhance Monitoring UI | 2020-03-09 08:32 | 2020-03-28 | 2020-03-26 16:37 | 2020-04-17 15:48 | 2020-04-20 08:12 |  | 2020-04-28 10:00 | 2020-04-28 09:37 | 2020-04-20 17:47 | 2020-04-28 13:35 | CR0012238 | Service ManagementCNTR MovementMonitoringEDI Error Report | OPUS-CTM | 2020-W18 | 2020-04 | 88 | 85 | 50.0612 | 2 | 1 | 2 | 0.07 | 193463 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 0 | 0 | 2020-03 | 0 | 0
1657 | CR0013103 | CTASK0022778 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 42 | 40 | 2020-10-16 13:00 | 2020-10-01 13:00 | Container | Service Management | Booking/Documentation | Advance Manifest | EU ENS (Origin Office) |  | [Development-Testing] (HBA) EUA EDI AUTH¦ Inclusion of Cert. Reg No. in 347/ARNENT Flatfile for FI customs | 2020-10-12 09:37 | 2020-10-21 | 2020-10-19 18:36 | 2020-11-04 19:27 | 2020-11-06 13:49 |  | 2020-11-17 10:00 | 2020-11-17 09:30 | 2020-11-09 17:15 | 2020-12-17 14:00 | CR0013103 | Service ManagementBooking/DocumentationAdvance ManifestEU ENS (Origin Office) | OPUS-BKG-MFT-E | 2020-W47 | 2020-11 | 62 | 60 | 36.0158 | 3 | 1 | 1 | 0.07 | 193506 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 1.25 | 2020-10 | 0 | 0
1658 | CR0013103 | CTASK0022646 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 8 | 8 | 2020-09-25 13:00 | 2020-09-22 13:00 | Container | Service Management | Booking/Documentation | Advance Manifest | EU ENS (Origin Office) |  | [Estimate](HBA) EUA EDI AUTH¦ Inclusion of Cert. Reg No. in 347/ARNENT Flatfile for FI customs | 2020-10-12 09:37 | 2020-10-21 | 2020-10-19 18:36 | 2020-11-04 19:27 | 2020-11-06 13:49 |  | 2020-11-17 10:00 | 2020-11-17 09:30 | 2020-11-09 17:15 | 2020-12-17 14:00 | CR0013103 | Service ManagementBooking/DocumentationAdvance ManifestEU ENS (Origin Office) | OPUS-BKG-MFT-E | 2020-W47 | 2020-11 | 62 | 60 | 36.0158 | 3 | 1 | 1 | 0.07 | 193506 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 1.25 | 2020-10 | 0 | 0
1659 | CR0013103 | CTASK0023476 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 12 | 12 | 2020-11-17 02:00 | 2020-11-10 02:00 | Container | Service Management | Booking/Documentation | Advance Manifest | EU ENS (Origin Office) |  | [Deployment](HBA) EUA EDI AUTH¦ Inclusion of Cert. Reg No. in 347/ARNENT Flatfile for FI customs | 2020-10-12 09:37 | 2020-10-21 | 2020-10-19 18:36 | 2020-11-04 19:27 | 2020-11-06 13:49 |  | 2020-11-17 10:00 | 2020-11-17 09:30 | 2020-11-09 17:15 | 2020-12-17 14:00 | CR0013103 | Service ManagementBooking/DocumentationAdvance ManifestEU ENS (Origin Office) | OPUS-BKG-MFT-E | 2020-W47 | 2020-11 | 62 | 60 | 36.0158 | 3 | 1 | 1 | 0.07 | 193506 | 1.4 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 16 | 0 | 1.25 | 2020-10 | 0 | 0
1660 | CR0012342 | CTASK0020286 | Closed | OPUS-MNR | Tuyen Truong | 43 | 49 | 2020-07-01 01:59 | 2020-06-08 09:27 | Container | Equipment Management | M&R | Repair | Invoice |  | [Documentation] SAS - Request to add validation logic in MNR invoicing to verify for duplicated containers | 2020-06-08 17:03 | 2020-07-30 22:00 | 2020-07-28 19:01 | 2020-09-14 22:31 | 2020-10-14 15:26 |  | 2020-10-27 12:00 | 2020-10-27 11:00 | 2020-10-16 10:52 | 2020-11-23 16:51 | CR0012342 | Equipment ManagementM&RRepairInvoice | OPUS-MNR | 2020-W44 | 2020-10 | 192 | 168 | 140.7896 | 4 | 1 | 2 | 0.05 | 173255 | 1.7 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 20 | 0 | 0 | 2020-06 | 0 | 0
1661 | CR0012342 | CTASK0020297 | Closed | OPUS-MNR | Tuyen Truong | 93 | 55 | 2020-07-28 01:00 | 2020-07-01 11:02 | Container | Equipment Management | M&R | Repair | Invoice |  | SAS - Request to add validation logic in MNR invoicing to verify for duplicated containers | 2020-06-08 17:03 | 2020-07-30 22:00 | 2020-07-28 19:01 | 2020-09-14 22:31 | 2020-10-14 15:26 |  | 2020-10-27 12:00 | 2020-10-27 11:00 | 2020-10-16 10:52 | 2020-11-23 16:51 | CR0012342 | Equipment ManagementM&RRepairInvoice | OPUS-MNR | 2020-W44 | 2020-10 | 192 | 168 | 140.7896 | 4 | 1 | 2 | 0.05 | 173255 | 1.7 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 20 | 0 | 0 | 2020-06 | 0 | 0
1662 | CR0012342 | CTASK0020287 | Closed | OPUS-MNR | Tien Le | 8 | 12 | 2020-07-01 01:59 | 2020-06-08 09:33 | Container | Equipment Management | M&R | Repair | Invoice |  | SAS - Request to add validation logic in MNR invoicing to verify for duplicated containers | 2020-06-08 17:03 | 2020-07-30 22:00 | 2020-07-28 19:01 | 2020-09-14 22:31 | 2020-10-14 15:26 |  | 2020-10-27 12:00 | 2020-10-27 11:00 | 2020-10-16 10:52 | 2020-11-23 16:51 | CR0012342 | Equipment ManagementM&RRepairInvoice | OPUS-MNR | 2020-W44 | 2020-10 | 192 | 168 | 140.7896 | 4 | 1 | 2 | 0.05 | 173286 | 1.7 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 20 | 0 | 0 | 2020-06 | 0 | 0
1663 | CR0012342 | CTASK0020298 | Closed | OPUS-MNR | Tien Le | 48 | 52 | 2020-07-28 01:01 | 2020-07-01 11:06 | Container | Equipment Management | M&R | Repair | Invoice |  | SAS - Request to add validation logic in MNR invoicing to verify for duplicated containers | 2020-06-08 17:03 | 2020-07-30 22:00 | 2020-07-28 19:01 | 2020-09-14 22:31 | 2020-10-14 15:26 |  | 2020-10-27 12:00 | 2020-10-27 11:00 | 2020-10-16 10:52 | 2020-11-23 16:51 | CR0012342 | Equipment ManagementM&RRepairInvoice | OPUS-MNR | 2020-W44 | 2020-10 | 192 | 168 | 140.7896 | 4 | 1 | 2 | 0.05 | 173286 | 1.7 | 0 | 0 | 0 | 2 | 1 | 2 | 7 | 20 | 0 | 0 | 2020-06 | 0 | 0
1664 | CR0012964 | CTASK0022169 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2020-09-04 11:14 | 2020-08-31 11:14 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development] Apply AUTO EDI HOLD not removed when Booking becomes FIRM (EUA Logic) for AU, NZ, and KH | 2020-08-28 17:30 | 2020-09-17 | 2020-09-15 14:31 | 2020-10-05 08:57 | 2020-10-05 09:07 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-10-07 10:26 | 2020-11-12 14:00 | CR0012964 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2020-W42 | 2020-10 | 27 | 25 | 45.6873 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1665 | CR0012964 | CTASK0022172 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-09-04 19:49 | 2020-09-01 19:49 | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing] Apply AUTO EDI HOLD not removed when Booking becomes FIRM (EUA Logic) for AU, NZ, and KH | 2020-08-28 17:30 | 2020-09-17 | 2020-09-15 14:31 | 2020-10-05 08:57 | 2020-10-05 09:07 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-10-07 10:26 | 2020-11-12 14:00 | CR0012964 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2020-W42 | 2020-10 | 27 | 25 | 45.6873 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1666 | CR0012964 | CTASK0022174 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2020-10-31 17:57 | 2020-10-06 17:57 | Container | Service Management | Booking/Documentation | Booking |  |  | [Deployment] Apply AUTO EDI HOLD not removed when Booking becomes FIRM (EUA Logic) for AU, NZ, and KH | 2020-08-28 17:30 | 2020-09-17 | 2020-09-15 14:31 | 2020-10-05 08:57 | 2020-10-05 09:07 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-10-07 10:26 | 2020-11-12 14:00 | CR0012964 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2020-W42 | 2020-10 | 27 | 25 | 45.6873 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1667 | CR0012964 | CTASK0022454 | Closed | OPUS-BKG-M | Loc Tran | 3 | 1 |  |  | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing] Apply AUTO EDI HOLD not removed when Booking becomes FIRM (EUA Logic) for AU, NZ, and KH | 2020-08-28 17:30 | 2020-09-17 | 2020-09-15 14:31 | 2020-10-05 08:57 | 2020-10-05 09:07 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-10-07 10:26 | 2020-11-12 14:00 | CR0012964 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2020-W42 | 2020-10 | 27 | 25 | 45.6873 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1668 | CR0012964 | CTASK0022164 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-08-31 19:45 | 2020-08-26 19:45 | Container | Service Management | Booking/Documentation | Booking |  |  | [Design] Apply AUTO EDI HOLD not removed when Booking becomes FIRM (EUA Logic) for AU, NZ, and KH | 2020-08-28 17:30 | 2020-09-17 | 2020-09-15 14:31 | 2020-10-05 08:57 | 2020-10-05 09:07 |  | 2020-10-13 10:00 | 2020-10-13 10:00 | 2020-10-07 10:26 | 2020-11-12 14:00 | CR0012964 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2020-W42 | 2020-10 | 27 | 25 | 45.6873 | 5 | 1 | 1 | 0.02 | 193503 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 20 | 0 | 0.28571 | 2020-08 | 0 | 0
1669 | CR0012203 | CTASK0021684 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 20 | 20 | 2020-08-24 18:17 | 2020-08-04 09:17 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Analysis] EUA - PIN# Security - M/H Release - Make 'Not Visible' Full Cargo Release PIN# to anyone who has access to OPUS | 2020-08-27 13:21 | 2020-10-30 23:20 | 2020-10-30 19:27 | 2020-11-05 20:51 | 2020-11-10 10:59 |  | 2020-11-17 10:59 | 2020-11-17 11:30 | 2020-11-11 15:59 | 2020-12-17 14:00 | CR0012203 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W47 | 2020-11 | 253 | 253 | 81.9017 | 4 | 1 | 1 | 0.13 | 193512 | 1.2 | 0 | 0 | 0 | 3 | 1 | 2 | 6 | 16 | 0 | 0.3125 | 2020-08 | 0 | 0
1670 | CR0012203 | CTASK0021086 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 8 | 8 | 2020-07-31 19:06 | 2020-07-06 09:06 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Analysis] EUA - PIN# Security - M/H Release - Make 'Not Visible' Full Cargo Release PIN# to anyone who has access to OPUS | 2020-08-27 13:21 | 2020-10-30 23:20 | 2020-10-30 19:27 | 2020-11-05 20:51 | 2020-11-10 10:59 |  | 2020-11-17 10:59 | 2020-11-17 11:30 | 2020-11-11 15:59 | 2020-12-17 14:00 | CR0012203 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W47 | 2020-11 | 253 | 253 | 81.9017 | 4 | 1 | 1 | 0.13 | 193512 | 1.2 | 0 | 0 | 0 | 3 | 1 | 2 | 6 | 16 | 0 | 0.3125 | 2020-08 | 0 | 0
1671 | CR0012203 | CTASK0020122 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 4 | 4 | 2020-05-15 19:21 | 2020-05-14 19:21 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Estimation]EUA - PIN# Security - M/H Release - Make 'Not Visible' Full Cargo Release PIN# to anyone who has access to OPUS | 2020-08-27 13:21 | 2020-10-30 23:20 | 2020-10-30 19:27 | 2020-11-05 20:51 | 2020-11-10 10:59 |  | 2020-11-17 10:59 | 2020-11-17 11:30 | 2020-11-11 15:59 | 2020-12-17 14:00 | CR0012203 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W47 | 2020-11 | 253 | 253 | 81.9017 | 4 | 1 | 1 | 0.13 | 193512 | 1.2 | 0 | 0 | 0 | 3 | 1 | 2 | 6 | 16 | 0 | 0.3125 | 2020-08 | 0 | 0
1672 | CR0012203 | CTASK0022034 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 221 | 221 | 2020-10-30 13:43 | 2020-08-28 09:43 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Cargo Release (D/O) | [Development+ Testing+ Deployment] EUA - PIN# Security - M/H Release - Make 'Not Visible' Full Cargo Release PIN# to anyone who has access to OPUS | 2020-08-27 13:21 | 2020-10-30 23:20 | 2020-10-30 19:27 | 2020-11-05 20:51 | 2020-11-10 10:59 |  | 2020-11-17 10:59 | 2020-11-17 11:30 | 2020-11-11 15:59 | 2020-12-17 14:00 | CR0012203 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Cargo Release (D/O) | OPUS-BKG-IB | 2020-W47 | 2020-11 | 253 | 253 | 81.9017 | 4 | 1 | 1 | 0.13 | 193512 | 1.2 | 0 | 0 | 0 | 3 | 1 | 2 | 6 | 16 | 0 | 0.3125 | 2020-08 | 0 | 0
1673 | CR0012616 | CTASK0020727 | Closed | OPUS-DMT | Cuong Nguyen | 14 | 12 | 2020-07-10 20:00 | 2020-07-01 10:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK2] Design_Analysis_Development_Test_Deployment | 2020-06-25 11:14 | 2020-07-31 20:00 | 2020-07-22 14:45 | 2020-07-27 20:49 | 2020-08-03 14:52 |  | 2020-08-11 10:00 | 2020-08-11 09:39 | 2020-08-03 14:53 | 2020-08-11 10:19 | CR0012616 | Service ManagementDemurrage/Detention | OPUS-DMT | 2020-W33 | 2020-08 | 16 | 14 | 46.9486 | 2 | 1 | 2 | 0.01 | 193529 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 30 | 0 | 0.058824 | 2020-06 | 0 | 0
1674 | CR0012616 | CTASK0020728 | Closed | OPUS-DMT | Tran Le | 2 | 2 | 2020-07-10 20:00 | 2020-07-01 10:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK3] Pair Test | 2020-06-25 11:14 | 2020-07-31 20:00 | 2020-07-22 14:45 | 2020-07-27 20:49 | 2020-08-03 14:52 |  | 2020-08-11 10:00 | 2020-08-11 09:39 | 2020-08-03 14:53 | 2020-08-11 10:19 | CR0012616 | Service ManagementDemurrage/Detention | OPUS-DMT | 2020-W33 | 2020-08 | 16 | 14 | 46.9486 | 2 | 1 | 2 | 0.01 | 193501 | 0.7 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 30 | 0 | 0 | 2020-06 | 0 | 0
1675 | CR0010892 | CTASK0021935 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 12 | 10 | 2020-08-31 10:30 | 2020-08-24 10:30 | Container | Service Management | Trans S/O |  |  |  | [TRS] NA *MDA* Add "SB1402 Violation" Flag to Vendor screen (Legal) (2020/08) | 2020-08-21 09:07 | 2020-09-18 21:00 | 2020-09-17 17:08 | 2020-12-10 11:23 | 2020-12-10 13:51 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-07 10:32 | 2021-02-03 23:02 | CR0010892 | Service ManagementTrans S/O | OPUS-TRS | 2021-W4 | 2021-01 | 111 | 106 | 158.0368 | 6 | 2 | 4 | 0.03 | 183432 | 1.5 | 0 | 0 | 0 | 2 | 2 | 3 | 12 | 40 | 0 | 0 | 2020-08 | 0 | 0
1676 | CR0010892 | CTASK0024786 | Closed | OPUS-MDA | Tran Le | 5 | 5 |  |  | Container | Service Management | Trans S/O |  |  |  | [MDA-CLV] Implement to PROD | 2020-08-21 09:07 | 2020-09-18 21:00 | 2020-09-17 17:08 | 2020-12-10 11:23 | 2020-12-10 13:51 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-07 10:32 | 2021-02-03 23:02 | CR0010892 | Service ManagementTrans S/O | OPUS-TRS | 2021-W4 | 2021-01 | 111 | 106 | 158.0368 | 6 | 2 | 4 | 0.03 | 193501 | 0.9 | 0 | 0 | 0 | 2 | 2 | 3 | 12 | 40 | 0 | 0 | 2020-08 | 0 | 0
1677 | CR0010892 | CTASK0022056 | Closed | OPUS-MDA | Cuong Nguyen | 22 | 26 | 2020-09-11 20:00 | 2020-08-18 09:00 | Container | Service Management | Trans S/O |  |  |  | [MDA-CLV] Analysis + Development + Test | 2020-08-21 09:07 | 2020-09-18 21:00 | 2020-09-17 17:08 | 2020-12-10 11:23 | 2020-12-10 13:51 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-07 10:32 | 2021-02-03 23:02 | CR0010892 | Service ManagementTrans S/O | OPUS-TRS | 2021-W4 | 2021-01 | 111 | 106 | 158.0368 | 6 | 2 | 4 | 0.03 | 193529 | 1.2 | 0 | 0 | 0 | 2 | 2 | 3 | 12 | 40 | 0 | 0.058824 | 2020-08 | 0 | 0
1678 | CR0010892 | CTASK0021936 | Closed | OPUS-TRS | Giang Nguyen Hoang | 10 | 10 | 2020-08-31 10:31 | 2020-08-24 10:31 | Container | Service Management | Trans S/O |  |  |  | [TRS] NA *MDA* Add "SB1402 Violation" Flag to Vendor screen (Legal) (2020/08) | 2020-08-21 09:07 | 2020-09-18 21:00 | 2020-09-17 17:08 | 2020-12-10 11:23 | 2020-12-10 13:51 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-07 10:32 | 2021-02-03 23:02 | CR0010892 | Service ManagementTrans S/O | OPUS-TRS | 2021-W4 | 2021-01 | 111 | 106 | 158.0368 | 6 | 2 | 4 | 0.03 | 183440 | 1.5 | 0 | 0 | 0 | 2 | 2 | 3 | 12 | 40 | 0 | 0 | 2020-08 | 0 | 0
1679 | CR0010892 | CTASK0021938 | Closed | OPUS-TRS | Giang Nguyen Hoang | 29 | 30 | 2020-09-30 10:32 | 2020-09-01 10:32 | Container | Service Management | Trans S/O |  |  |  | [TRS] NA *MDA* Add "SB1402 Violation" Flag to Vendor screen (Legal) (2020/09) | 2020-08-21 09:07 | 2020-09-18 21:00 | 2020-09-17 17:08 | 2020-12-10 11:23 | 2020-12-10 13:51 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-07 10:32 | 2021-02-03 23:02 | CR0010892 | Service ManagementTrans S/O | OPUS-TRS | 2021-W4 | 2021-01 | 111 | 106 | 158.0368 | 6 | 2 | 4 | 0.03 | 183440 | 1.5 | 0 | 0 | 0 | 2 | 2 | 3 | 12 | 40 | 0 | 0 | 2020-08 | 0 | 0
1680 | CR0010892 | CTASK0021937 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 33 | 30 | 2020-09-30 10:31 | 2020-09-01 10:31 | Container | Service Management | Trans S/O |  |  |  | [TRS] NA *MDA* Add "SB1402 Violation" Flag to Vendor screen (Legal) (2020/09) | 2020-08-21 09:07 | 2020-09-18 21:00 | 2020-09-17 17:08 | 2020-12-10 11:23 | 2020-12-10 13:51 |  | 2021-01-26 10:00 | 2021-01-26 10:00 | 2021-01-07 10:32 | 2021-02-03 23:02 | CR0010892 | Service ManagementTrans S/O | OPUS-TRS | 2021-W4 | 2021-01 | 111 | 106 | 158.0368 | 6 | 2 | 4 | 0.03 | 183432 | 1.5 | 0 | 0 | 0 | 2 | 2 | 3 | 12 | 40 | 0 | 0 | 2020-08 | 0 | 0
1681 | CR0013651 | CTASK0025837 | Closed | OPUS-BKG-EBKG | Vinh Tran | 6 | 6 | 2021-03-13 02:00 | 2021-03-10 02:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Design] [CLT Internal] Enhancement to prevent unnecessary minor errors on e-booking | 2021-03-31 10:34 | 2021-04-27 | 2021-04-26 11:52 | 2021-06-11 08:58 | 2021-06-11 09:48 |  | 2021-06-15 09:00 | 2021-06-17 09:40 | 2021-06-16 09:07 | 2021-07-18 14:00 | CR0013651 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 54 | 80 | 75.9345 | 8 | 2 | 2 | 0.04 | 193525 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
1682 | CR0013651 | CTASK0025835 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 16 | 16 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Testing] [CLT Internal] Enhancement to prevent unnecessary minor errors on e-booking | 2021-03-31 10:34 | 2021-04-27 | 2021-04-26 11:52 | 2021-06-11 08:58 | 2021-06-11 09:48 |  | 2021-06-15 09:00 | 2021-06-17 09:40 | 2021-06-16 09:07 | 2021-07-18 14:00 | CR0013651 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 54 | 80 | 75.9345 | 8 | 2 | 2 | 0.04 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
1683 | CR0013651 | CTASK0025838 | Closed | OPUS-BKG-EBKG | Vinh Tran | 14 | 14 | 2021-04-08 02:00 | 2021-04-06 02:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Development] [CLT Internal] Enhancement to prevent unnecessary minor errors on e-booking | 2021-03-31 10:34 | 2021-04-27 | 2021-04-26 11:52 | 2021-06-11 08:58 | 2021-06-11 09:48 |  | 2021-06-15 09:00 | 2021-06-17 09:40 | 2021-06-16 09:07 | 2021-07-18 14:00 | CR0013651 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 54 | 80 | 75.9345 | 8 | 2 | 2 | 0.04 | 193525 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
1684 | CR0013651 | CTASK0025826 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-03-13 02:00 | 2021-03-09 11:25 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Design][CLT Internal] Enhancement to prevent unnecessary minor errors on e-booking | 2021-03-31 10:34 | 2021-04-27 | 2021-04-26 11:52 | 2021-06-11 08:58 | 2021-06-11 09:48 |  | 2021-06-15 09:00 | 2021-06-17 09:40 | 2021-06-16 09:07 | 2021-07-18 14:00 | CR0013651 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 54 | 80 | 75.9345 | 8 | 2 | 2 | 0.04 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
1685 | CR0013651 | CTASK0025839 | Closed | OPUS-BKG-EBKG | Vinh Tran | 10 | 16 | 2021-04-10 02:00 | 2021-04-08 02:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Testing] [CLT Internal] Enhancement to prevent unnecessary minor errors on e-booking | 2021-03-31 10:34 | 2021-04-27 | 2021-04-26 11:52 | 2021-06-11 08:58 | 2021-06-11 09:48 |  | 2021-06-15 09:00 | 2021-06-17 09:40 | 2021-06-16 09:07 | 2021-07-18 14:00 | CR0013651 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 54 | 80 | 75.9345 | 8 | 2 | 2 | 0.04 | 193525 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
1686 | CR0013651 | CTASK0025840 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-06-17 02:00 | 2021-06-15 02:00 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Deployment] [CLT Internal] Enhancement to prevent unnecessary minor errors on e-booking | 2021-03-31 10:34 | 2021-04-27 | 2021-04-26 11:52 | 2021-06-11 08:58 | 2021-06-11 09:48 |  | 2021-06-15 09:00 | 2021-06-17 09:40 | 2021-06-16 09:07 | 2021-07-18 14:00 | CR0013651 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 54 | 80 | 75.9345 | 8 | 2 | 2 | 0.04 | 193525 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.41667 | 0.47368 | 2021-03 | 0 | 0
1687 | CR0013651 | CTASK0025836 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Deployment] [CLT Internal] Enhancement to prevent unnecessary minor errors on e-booking | 2021-03-31 10:34 | 2021-04-27 | 2021-04-26 11:52 | 2021-06-11 08:58 | 2021-06-11 09:48 |  | 2021-06-15 09:00 | 2021-06-17 09:40 | 2021-06-16 09:07 | 2021-07-18 14:00 | CR0013651 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 54 | 80 | 75.9345 | 8 | 2 | 2 | 0.04 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
1688 | CR0013651 | CTASK0025834 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 16 | 16 | 2021-04-10 02:00 | 2021-04-05 11:20 | Container | Service Management | Booking/Documentation | Outbound Doc | e-Booking & S/I Process |  | [Development] [CLT Internal] Enhancement to prevent unnecessary minor errors on e-booking | 2021-03-31 10:34 | 2021-04-27 | 2021-04-26 11:52 | 2021-06-11 08:58 | 2021-06-11 09:48 |  | 2021-06-15 09:00 | 2021-06-17 09:40 | 2021-06-16 09:07 | 2021-07-18 14:00 | CR0013651 | Service ManagementBooking/DocumentationOutbound Doce-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W24 | 2021-06 | 54 | 80 | 75.9345 | 8 | 2 | 2 | 0.04 | 193488 | 1.8 | 1 | 0 | 0 | 1 | 1 | 2 | 11 | 53 | 0.53659 | 0.28125 | 2021-03 | 0 | 0
1689 | CR0014074 | CTASK0028077 | Closed | OPUS-SPC | Toai Phan | 6 | 6 |  |  | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [CLT Internal]Change average weight from average weight for customer total to average weight for single booking. | 2021-06-23 09:45 | 2021-07-03 | 2021-07-02 13:19 | 2021-07-07 17:11 | 2021-07-08 10:22 |  | 2021-07-13 10:00 | 2021-07-13 09:00 | 2021-07-08 13:18 | 2021-07-29 14:00 | CR0014074 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W28 | 2021-07 | 6 | 6 | 20.0102 | 1 | 1 | 1 | 0.01 | 183427 | 2.6 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 28 | 0 | 0 | 2021-06 | 0 | 0
1690 | CR0012757 | CTASK0021627 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 14 | 14 | 2021-03-23 01:00 | 2021-03-16 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Deployment] Include correct SWB in e-Subscription | 2020-08-03 09:37 | 2020-08-10 18:00 | 2020-08-10 15:46 | 2020-10-26 22:24 | 2021-03-15 14:58 |  | 2021-03-23 10:00 | 2021-03-23 10:00 | 2021-03-16 13:31 | 2021-04-22 14:00 | CR0012757 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W12 | 2021-03 | 42 | 42 | 232.016 | 3 | 1 | 1 | 0.01 | 193470 | 1.4 | 1 | 0 | 0 | 1 | 1 | 3 | 6 | 46 | 0.36842 | 0.17391 | 2020-08 | 0 | 0
1691 | CR0012757 | CTASK0021626 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 14 | 14 | 2020-08-08 01:00 | 2020-07-31 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Develop + Test] Include correct SWB in e-Subscription | 2020-08-03 09:37 | 2020-08-10 18:00 | 2020-08-10 15:46 | 2020-10-26 22:24 | 2021-03-15 14:58 |  | 2021-03-23 10:00 | 2021-03-23 10:00 | 2021-03-16 13:31 | 2021-04-22 14:00 | CR0012757 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W12 | 2021-03 | 42 | 42 | 232.016 | 3 | 1 | 1 | 0.01 | 193470 | 1.4 | 1 | 0 | 0 | 1 | 1 | 3 | 6 | 46 | 0.36842 | 0.17391 | 2020-08 | 0 | 0
1692 | CR0012757 | CTASK0021291 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 14 | 14 | 2020-07-22 01:00 | 2020-07-16 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Analysis & Estimation]Include correct SWB in e-Subscription | 2020-08-03 09:37 | 2020-08-10 18:00 | 2020-08-10 15:46 | 2020-10-26 22:24 | 2021-03-15 14:58 |  | 2021-03-23 10:00 | 2021-03-23 10:00 | 2021-03-16 13:31 | 2021-04-22 14:00 | CR0012757 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2021-W12 | 2021-03 | 42 | 42 | 232.016 | 3 | 1 | 1 | 0.01 | 193470 | 1.4 | 1 | 0 | 0 | 1 | 1 | 3 | 6 | 46 | 0.36842 | 0.17391 | 2020-08 | 0 | 0
1693 | CR0012384 | CTASK0019190 | Closed | OPUS-SCG | Tu Nguyen | 70 | 70 |  |  | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] SCG Enhancement for IMO Class 3 shipments. | 2020-03-27 09:14 | 2020-05-09 | 2020-04-22 17:55 | 2020-04-27 17:46 | 2020-04-27 18:02 |  | 2020-05-07 09:30 | 2020-05-07 09:30 | 2020-04-27 18:04 | 2020-06-06 13:00 | CR0012384 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W19 | 2020-05 | 70 | 70 | 41.0109 | 1 | 1 | 1 | 0.07 | 123045 | 1.5 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 26 | 0 | 0 | 2020-03 | 0 | 0
1694 | CR0013681 | CTASK0026033 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 15 | 15 | 2021-03-26 23:00 | 2021-03-22 10:30 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Design] Add Sensitive Cargo dropdown as filter criterial in several OPUS UIs for enhance search of these type of bookings | 2021-04-08 13:13 | 2021-05-22 | 2021-05-21 11:27 | 2021-07-15 16:18 | 2021-07-19 13:45 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-27 16:03 | 2021-08-17 14:00 | CR0013681 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W32 | 2021-08 | 159 | 186 | 123.8662 | 6 | 2 | 2 | 0.06 | 193470 | 2.1 | 1 | 0 | 0 | 2 | 1 | 2 | 10 | 22 | 0.36842 | 0.11111 | 2021-04 | 0 | 0
1695 | CR0013681 | CTASK0026010 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 4 | 4 | 2021-03-26 02:00 | 2021-03-22 02:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [EST]Add Sensitive Cargo dropdown as filter criterial in several OPUS UIs for enhance search of these type of bookings | 2021-04-08 13:13 | 2021-05-22 | 2021-05-21 11:27 | 2021-07-15 16:18 | 2021-07-19 13:45 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-27 16:03 | 2021-08-17 14:00 | CR0013681 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W32 | 2021-08 | 159 | 186 | 123.8662 | 6 | 2 | 2 | 0.06 | 193506 | 1.9 | 1 | 0 | 0 | 2 | 1 | 2 | 10 | 22 | 1.1212 | 1.25 | 2021-04 | 0 | 0
1696 | CR0013681 | CTASK0026037 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 45 | 45 | 2021-04-30 02:00 | 2021-04-01 02:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Dev-Deploy]Add Sensitive Cargo dropdown as filter criterial in several OPUS UIs for enhance search of these type of bookings | 2021-04-08 13:13 | 2021-05-22 | 2021-05-21 11:27 | 2021-07-15 16:18 | 2021-07-19 13:45 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-27 16:03 | 2021-08-17 14:00 | CR0013681 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W32 | 2021-08 | 159 | 186 | 123.8662 | 6 | 2 | 2 | 0.06 | 193506 | 1.9 | 1 | 0 | 0 | 2 | 1 | 2 | 10 | 22 | 1.1212 | 1.25 | 2021-04 | 0 | 0
1697 | CR0013681 | CTASK0026035 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 15 | 12 | 2021-08-10 19:30 | 2021-08-03 10:30 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Deployment] Add Sensitive Cargo dropdown as filter criterial in several OPUS UIs for enhance search of these type of bookings | 2021-04-08 13:13 | 2021-05-22 | 2021-05-21 11:27 | 2021-07-15 16:18 | 2021-07-19 13:45 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-27 16:03 | 2021-08-17 14:00 | CR0013681 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W32 | 2021-08 | 159 | 186 | 123.8662 | 6 | 2 | 2 | 0.06 | 193470 | 2.1 | 1 | 0 | 0 | 2 | 1 | 2 | 10 | 22 | 0.36842 | 0.11111 | 2021-04 | 0 | 0
1698 | CR0013681 | CTASK0026038 | Closed | OPUS-BKG-CLLCDL | Tan Nguyen | 16 | 16 | 2021-04-30 02:00 | 2021-04-16 02:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Test]Add Sensitive Cargo dropdown as filter criterial in several OPUS UIs for enhance search of these type of bookings | 2021-04-08 13:13 | 2021-05-22 | 2021-05-21 11:27 | 2021-07-15 16:18 | 2021-07-19 13:45 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-27 16:03 | 2021-08-17 14:00 | CR0013681 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W32 | 2021-08 | 159 | 186 | 123.8662 | 6 | 2 | 2 | 0.06 | 193506 | 1.9 | 1 | 0 | 0 | 2 | 1 | 2 | 10 | 22 | 1.1212 | 1.25 | 2021-04 | 0 | 0
1699 | CR0013681 | CTASK0026034 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 64 | 94 | 2021-05-07 23:00 | 2021-03-31 10:30 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Development + Testing] Add Sensitive Cargo dropdown as filter criterial in several OPUS UIs for enhance search of these type of bookings | 2021-04-08 13:13 | 2021-05-22 | 2021-05-21 11:27 | 2021-07-15 16:18 | 2021-07-19 13:45 |  | 2021-08-10 10:00 | 2021-08-10 10:00 | 2021-07-27 16:03 | 2021-08-17 14:00 | CR0013681 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2021-W32 | 2021-08 | 159 | 186 | 123.8662 | 6 | 2 | 2 | 0.06 | 193470 | 2.1 | 1 | 0 | 0 | 2 | 1 | 2 | 10 | 22 | 0.36842 | 0.11111 | 2021-04 | 0 | 0
1700 | CR0013887 | CTASK0026919 | Closed | OPUS-SPC | Toai Phan | 10 | 10 |  |  | Container | Sales Management | Space Control | Daily Forecast | Forecast Input |  | [CLT Internal]Deletes logic that OCN, IPC, and TS are active/inactive when VVD is blank and trade is entered. | 2021-05-11 10:55 | 2021-05-31 10:54 | 2021-05-27 15:27 | 2021-05-28 09:17 | 2021-06-29 14:18 |  | 2021-07-06 14:17 | 2021-07-06 10:25 | 2021-06-30 10:05 | 2021-07-29 14:00 | CR0013887 | Sales ManagementSpace ControlDaily ForecastForecast Input | OPUS-SPC | 2021-W27 | 2021-07 | 10 | 10 | 56.1406 | 1 | 1 | 1 | 0.01 | 183427 | 2.4 | 0 | 0 | 0 | 1 | 1 | 2 | 8 | 28 | 0 | 0 | 2021-05 | 0 | 0
1701 | CR0010567 | CTASK0016635 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 1 | 48 |  |  | Container | Service Management | Trans S/O |  |  |  | [Actual]Request to allow user to mass apply rates in 'Supplement SO ' creation | 2019-10-02 09:35 | 2019-10-31 18:00 | 2019-10-14 17:52 | 2019-10-24 14:36 | 2019-10-28 10:08 |  | 2019-11-12 10:00 | 2019-11-05 11:00 | 2020-03-23 11:03 | 2020-04-22 13:00 | CR0010567 | Service ManagementTrans S/O | OPUS-TRS | 2019-W46 | 2019-11 | 32 | 96 | 41.0176 | 2 | 1 | 2 | 0.1 | 183432 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 2019-10 | 0 | 0
1702 | CR0010567 | CTASK0016567 | Closed | OPUS-TRS | Hieu Tran | 31 | 48 |  |  | Container | Service Management | Trans S/O |  |  |  | [Actual]Request to allow user to mass apply rates in 'Supplement SO ' creation | 2019-10-02 09:35 | 2019-10-31 18:00 | 2019-10-14 17:52 | 2019-10-24 14:36 | 2019-10-28 10:08 |  | 2019-11-12 10:00 | 2019-11-05 11:00 | 2020-03-23 11:03 | 2020-04-22 13:00 | CR0010567 | Service ManagementTrans S/O | OPUS-TRS | 2019-W46 | 2019-11 | 32 | 96 | 41.0176 | 2 | 1 | 2 | 0.1 | 183400 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 2019-10 | 0 | 0
1703 | CR0013028 | CTASK0023119 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 55 | 55 | 2020-10-30 19:28 | 2020-10-21 07:28 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EUA CR : Regulatory Requirement - EU Full cntr Release via NXTPORT Secure Release Platform for BE customers | 2020-11-03 14:40 | 2020-12-31 14:35 | 2020-12-14 16:29 | 2020-12-16 19:47 | 2020-12-28 09:16 |  | 2021-01-12 09:16 | 2021-01-12 14:33 | 2020-12-28 15:19 | 2021-02-12 14:00 | CR0013028 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W2 | 2021-01 | 170 | 172 | 69.7755 | 3 | 1 | 1 | 0.1 | 193512 | 1.3 | 0 | 0 | 0 | 2 | 1 | 2 | 14 | 40 | 0 | 0.3125 | 2020-11 | 0 | 0
1704 | CR0013028 | CTASK0024395 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 8 | 10 | 2020-12-31 20:42 | 2020-12-25 09:42 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Deployment] EUA CR : Regulatory Requirement - EU Full cntr Release via NXTPORT Secure Release Platform for BE customers | 2020-11-03 14:40 | 2020-12-31 14:35 | 2020-12-14 16:29 | 2020-12-16 19:47 | 2020-12-28 09:16 |  | 2021-01-12 09:16 | 2021-01-12 14:33 | 2020-12-28 15:19 | 2021-02-12 14:00 | CR0013028 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W2 | 2021-01 | 170 | 172 | 69.7755 | 3 | 1 | 1 | 0.1 | 193512 | 1.3 | 0 | 0 | 0 | 2 | 1 | 2 | 14 | 40 | 0 | 0.3125 | 2020-11 | 0 | 0
1705 | CR0013028 | CTASK0023196 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 107 | 107 | 2020-11-27 12:26 | 2020-11-01 09:25 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EUA CR : Regulatory Requirement - EU Full cntr Release via NXTPORT Secure Release Platform for BE customers | 2020-11-03 14:40 | 2020-12-31 14:35 | 2020-12-14 16:29 | 2020-12-16 19:47 | 2020-12-28 09:16 |  | 2021-01-12 09:16 | 2021-01-12 14:33 | 2020-12-28 15:19 | 2021-02-12 14:00 | CR0013028 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W2 | 2021-01 | 170 | 172 | 69.7755 | 3 | 1 | 1 | 0.1 | 193512 | 1.3 | 0 | 0 | 0 | 2 | 1 | 2 | 14 | 40 | 0 | 0.3125 | 2020-11 | 0 | 0
1706 | CR0012301 | CTASK0021046 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 1 | 1 | 2020-07-01 19:00 | 2020-07-01 11:00 | [6 empty] | [CLT Internal][License Service] Chrome v80,81 & CLP(Common Library Patch) test, patch | 2020-02-26 08:58 | 2020-03-27 08:57 | 2020-03-17 09:13 |  | 2020-11-03 12:54 |  | 2020-05-17 12:54 | 2020-05-17 10:43 | 2020-11-03 16:06 | 2020-12-04 14:00 | CR0012301 |  | OPUS-BKG-OB | 2020-W20 | 2020-05 | 5 | 17 | 81.1641 | 2 | 2 | 2 | 0.01 | 193512 | 0.7 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.5 | 2020-02 | 0 | 0
1707 | CR0012301 | CTASK0018581 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 4 | 16 | 2020-02-27 19:30 | 2020-02-24 10:30 | [6 empty] | [CLT Internal][License Service] Chrome v80,81 & CLP(Common Library Patch) test, patch | 2020-02-26 08:58 | 2020-03-27 08:57 | 2020-03-17 09:13 |  | 2020-11-03 12:54 |  | 2020-05-17 12:54 | 2020-05-17 10:43 | 2020-11-03 16:06 | 2020-12-04 14:00 | CR0012301 |  | OPUS-BKG-MFT-A | 2020-W20 | 2020-05 | 5 | 17 | 81.1641 | 2 | 2 | 2 | 0.01 | 173280 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 26 | 0 | 0.18519 | 2020-02 | 0 | 0
1708 | CR0013455 | CTASK0024972 | Closed | OPUS-DMT | Cuong Nguyen | 2 | 2 | 2021-03-26 20:00 | 2021-03-01 08:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK3] CLV_Analysis_Pair Test | 2021-02-25 15:41 | 2021-03-12 20:00 | 2021-03-11 16:39 | 2021-03-16 09:17 | 2021-03-16 13:42 |  | 2021-03-23 10:00 | 2021-03-23 09:50 | 2021-03-18 09:46 | 2021-04-22 14:00 | CR0013455 | Service ManagementDemurrage/Detention | OPUS-DMT | 2021-W12 | 2021-03 | 0 | 2 | 25.7633 | 1 | 1 | 1 | 0 | 193529 | 1.7 | 1 | 0 | 0 | 1 | 1 | 1 | 6 | 46 | 0.11538 | 0.058824 | 2021-02 | 0 | 0
1709 | CR0011963 | CTASK0017188 | Closed | OPUS-PRI | Ngan Nham | 40 | 40 |  |  | Container | Sales Management | Pricing | Service Contract | S/C Creation | S/C Proposal & Amendment Creation | NA *NYSCHEX* *NACAP* Manual SC Naming Functionality | 2019-11-19 13:28 | 2019-11-26 13:27 | 2019-11-21 17:07 | 2019-11-21 19:37 | 2019-11-22 09:40 |  | 2019-11-26 10:40 | 2019-11-26 09:41 | 2019-11-26 10:23 | 2019-12-26 14:00 | CR0011963 | Sales ManagementPricingService ContractS/C CreationS/C Proposal & Amendment Creation | OPUS-PRI | 2019-W48 | 2019-11 | 40 | 40 | 6.8837 | 1 | 1 | 1 | 0.24 | 193461 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 7 | 0 | 0 | 2019-11 | 0 | 0
1710 | CR0011971 | CTASK0018733 | Closed | OPUS-SAP | Chuong Ta | 35 | 35 | 2020-03-31 11:34 | 2020-03-02 11:34 | Container | Statement Management | Statement Account Payable | Invoices | Invoices Entry |  | CSR Deletion Removes All Records in System | 2020-03-03 11:15 | 2020-04-14 11:15 | 2020-03-09 14:42 | 2020-04-08 02:18 | 2020-04-08 10:02 |  | 2020-04-14 10:02 | 2020-04-14 11:19 | 2020-04-09 01:23 | 2020-05-16 13:00 | CR0011971 | Statement ManagementStatement Account PayableInvoicesInvoices Entry | OPUS-SAP | 2020-W16 | 2020-04 | 35 | 0 | 41.9488 | 1 | 1 | 1 | 0 | 183379 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 16 | 0 | 0 | 2020-03 | 0 | 0
1711 | CR0011964 | CTASK0018634 | Closed | OPUS-BKG-CLLCDL | Thuc Tran | 16 | 16 | 2020-03-25 | 2020-03-02 09:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Development+Testing+Deployment] Add RFDRY_IND mapping in COPRAR EDI (ECR0011150) | 2020-02-28 09:51 | 2020-03-18 | 2020-03-17 14:35 | 2020-06-17 07:32 | 2020-06-17 15:41 |  | 2020-06-23 10:00 | 2020-06-23 10:00 | 2020-06-17 15:46 | 2020-07-23 13:00 | CR0011964 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W26 | 2020-06 | 31 | 31 | 116.0066 | 3 | 1 | 1 | 0.01 | 173280 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.18519 | 2020-02 | 0 | 0
1712 | CR0011964 | CTASK0020762 | Closed | OPUS-BKG-CLLCDL | Thuc Tran | 7 | 7 | 2020-06-22 19:30 | 2020-06-18 11:00 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Deployment] Add RFDRY_IND mapping in COPRAR EDI (ECR0011150) | 2020-02-28 09:51 | 2020-03-18 | 2020-03-17 14:35 | 2020-06-17 07:32 | 2020-06-17 15:41 |  | 2020-06-23 10:00 | 2020-06-23 10:00 | 2020-06-17 15:46 | 2020-07-23 13:00 | CR0011964 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W26 | 2020-06 | 31 | 31 | 116.0066 | 3 | 1 | 1 | 0.01 | 173280 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.18519 | 2020-02 | 0 | 0
1713 | CR0011964 | CTASK0018541 | Closed | OPUS-BKG-CLLCDL | Thuc Tran | 8 | 8 | 2020-02-24 19:30 | 2020-02-21 10:30 | Container | Service Management | Booking/Documentation | Operation | Loading/Discharging List | Container Loading List (CLL) | [Estimation] Add RFDRY_IND mapping in COPRAR EDI (ECR0011150) | 2020-02-28 09:51 | 2020-03-18 | 2020-03-17 14:35 | 2020-06-17 07:32 | 2020-06-17 15:41 |  | 2020-06-23 10:00 | 2020-06-23 10:00 | 2020-06-17 15:46 | 2020-07-23 13:00 | CR0011964 | Service ManagementBooking/DocumentationOperationLoading/Discharging ListContainer Loading List (CLL) | OPUS-BKG-MFT-E | 2020-W26 | 2020-06 | 31 | 31 | 116.0066 | 3 | 1 | 1 | 0.01 | 173280 | 1.2 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 29 | 0 | 0.18519 | 2020-02 | 0 | 0
1714 | CR0010998 | CTASK0016636 | Closed | OPUS-TRS | Giang Nguyen Hoang | 33 | 88 |  |  | Container | Service Management | Trans S/O | Agreement | Agreement Correction |  | [Actual]NA * TRS AGMT * Add transportation surcharge codes | 2019-10-08 10:55 | 2019-11-16 18:00 | 2019-10-30 14:34 | 2020-03-12 18:38 | 2020-03-17 16:57 |  | 2020-03-31 11:00 | 2020-03-31 11:00 | 2020-03-18 08:49 | 2020-04-30 13:00 | CR0010998 | Service ManagementTrans S/OAgreementAgreement Correction | OPUS-TRS | 2020-W14 | 2020-03 | 37 | 88 | 175.0032 | 2 | 1 | 2 | 0.02 | 183440 | 0.6 | 0 | 0 | 0 | 1 | 1 | 3 | 7 | 25 | 0 | 0 | 2019-10 | 0 | 0
1715 | CR0010998 | CTASK0016684 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 4 | 4 |  |  | Container | Service Management | Trans S/O | Agreement | Agreement Correction |  | [Actual]NA * TRS AGMT * Add transportation surcharge codes | 2019-10-08 10:55 | 2019-11-16 18:00 | 2019-10-30 14:34 | 2020-03-12 18:38 | 2020-03-17 16:57 |  | 2020-03-31 11:00 | 2020-03-31 11:00 | 2020-03-18 08:49 | 2020-04-30 13:00 | CR0010998 | Service ManagementTrans S/OAgreementAgreement Correction | OPUS-TRS | 2020-W14 | 2020-03 | 37 | 88 | 175.0032 | 2 | 1 | 2 | 0.02 | 183432 | 0.6 | 0 | 0 | 0 | 1 | 1 | 3 | 7 | 25 | 0 | 0 | 2019-10 | 0 | 0
1716 | CR0013412 | CTASK0024250 | Closed | OPUS-BKG-M | Vinh Tran | 8 | 8 | 2021-01-06 02:00 | 2021-01-04 02:00 | Container | Service Management | Booking/Documentation | Booking |  |  | [Deployment] (KONTAINERS) ADDITIONAL COLUMN "PREMIUM FLAG" TO BE ADDED IN OPUS | 2020-12-21 12:04 | 2021-01-01 | 2020-12-31 10:10 | 2021-01-12 14:28 | 2021-01-12 14:34 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-19 13:17 | 2021-01-28 17:40 | CR0013412 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W4 | 2021-01 | 119 | 118 | 35.9136 | 8 | 2 | 2 | 0.14 | 193525 | 1.6 | 1 | 0 | 0 | 2 | 1 | 1 | 12 | 40 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1717 | CR0013412 | CTASK0024246 | Closed | OPUS-BKG-M | Vinh Tran | 20 | 20 |  |  | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing] (KONTAINERS) ADDITIONAL COLUMN "PREMIUM FLAG" TO BE ADDED IN OPUS | 2020-12-21 12:04 | 2021-01-01 | 2020-12-31 10:10 | 2021-01-12 14:28 | 2021-01-12 14:34 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-19 13:17 | 2021-01-28 17:40 | CR0013412 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W4 | 2021-01 | 119 | 118 | 35.9136 | 8 | 2 | 2 | 0.14 | 193525 | 1.6 | 1 | 0 | 0 | 2 | 1 | 1 | 12 | 40 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1718 | CR0013412 | CTASK0024241 | Closed | OPUS-BKG-OB | Nam Nguyen | 8 | 8 | 2020-12-18 16:33 | 2020-12-16 16:33 | Container | Service Management | Booking/Documentation | Booking |  |  | [Design] (KONTAINERS) ADDITIONAL COLUMN "PREMIUM FLAG" TO BE ADDED IN OPUS | 2020-12-21 12:04 | 2021-01-01 | 2020-12-31 10:10 | 2021-01-12 14:28 | 2021-01-12 14:34 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-19 13:17 | 2021-01-28 17:40 | CR0013412 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W4 | 2021-01 | 119 | 118 | 35.9136 | 8 | 2 | 2 | 0.14 | 123048 | 2.2 | 1 | 0 | 0 | 2 | 1 | 1 | 12 | 40 | 0.22222 | 0.047619 | 2020-12 | 0 | 0
1719 | CR0013412 | CTASK0024245 | Closed | OPUS-BKG-OB | Nam Nguyen | 21 | 20 | 2021-01-01 12:16 | 2020-12-28 12:16 | Container | Service Management | Booking/Documentation | Booking |  |  | [Testing] (KONTAINERS) ADDITIONAL COLUMN "PREMIUM FLAG" TO BE ADDED IN OPUS | 2020-12-21 12:04 | 2021-01-01 | 2020-12-31 10:10 | 2021-01-12 14:28 | 2021-01-12 14:34 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-19 13:17 | 2021-01-28 17:40 | CR0013412 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W4 | 2021-01 | 119 | 118 | 35.9136 | 8 | 2 | 2 | 0.14 | 123048 | 2.2 | 1 | 0 | 0 | 2 | 1 | 1 | 12 | 40 | 0.22222 | 0.047619 | 2020-12 | 0 | 0
1720 | CR0013412 | CTASK0024244 | Closed | OPUS-BKG-OB | Nam Nguyen | 28 | 28 | 2020-12-25 14:46 | 2020-12-21 14:46 | Container | Service Management | Booking/Documentation | Booking |  |  | [Development] (KONTAINERS) ADDITIONAL COLUMN "PREMIUM FLAG" TO BE ADDED IN OPUS | 2020-12-21 12:04 | 2021-01-01 | 2020-12-31 10:10 | 2021-01-12 14:28 | 2021-01-12 14:34 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-19 13:17 | 2021-01-28 17:40 | CR0013412 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W4 | 2021-01 | 119 | 118 | 35.9136 | 8 | 2 | 2 | 0.14 | 123048 | 2.2 | 1 | 0 | 0 | 2 | 1 | 1 | 12 | 40 | 0.22222 | 0.047619 | 2020-12 | 0 | 0
1721 | CR0013412 | CTASK0024249 | Closed | OPUS-BKG-OB | Nam Nguyen | 8 | 8 | 2021-01-07 15:53 | 2021-01-05 15:53 | Container | Service Management | Booking/Documentation | Booking |  |  | [Deployment] (KONTAINERS) ADDITIONAL COLUMN "PREMIUM FLAG" TO BE ADDED IN OPUS | 2020-12-21 12:04 | 2021-01-01 | 2020-12-31 10:10 | 2021-01-12 14:28 | 2021-01-12 14:34 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-19 13:17 | 2021-01-28 17:40 | CR0013412 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W4 | 2021-01 | 119 | 118 | 35.9136 | 8 | 2 | 2 | 0.14 | 123048 | 2.2 | 1 | 0 | 0 | 2 | 1 | 1 | 12 | 40 | 0.22222 | 0.047619 | 2020-12 | 0 | 0
1722 | CR0013412 | CTASK0024240 | Closed | OPUS-BKG-M | Vinh Tran | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Booking |  |  | [Design] (KONTAINERS) ADDITIONAL COLUMN "PREMIUM FLAG" TO BE ADDED IN OPUS | 2020-12-21 12:04 | 2021-01-01 | 2020-12-31 10:10 | 2021-01-12 14:28 | 2021-01-12 14:34 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-19 13:17 | 2021-01-28 17:40 | CR0013412 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W4 | 2021-01 | 119 | 118 | 35.9136 | 8 | 2 | 2 | 0.14 | 193525 | 1.6 | 1 | 0 | 0 | 2 | 1 | 1 | 12 | 40 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1723 | CR0013412 | CTASK0024243 | Closed | OPUS-BKG-M | Vinh Tran | 18 | 18 |  |  | Container | Service Management | Booking/Documentation | Booking |  |  | [Development] (KONTAINERS) ADDITIONAL COLUMN "PREMIUM FLAG" TO BE ADDED IN OPUS | 2020-12-21 12:04 | 2021-01-01 | 2020-12-31 10:10 | 2021-01-12 14:28 | 2021-01-12 14:34 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2021-01-19 13:17 | 2021-01-28 17:40 | CR0013412 | Service ManagementBooking/DocumentationBooking | OPUS-BKG-M | 2021-W4 | 2021-01 | 119 | 118 | 35.9136 | 8 | 2 | 2 | 0.14 | 193525 | 1.6 | 1 | 0 | 0 | 2 | 1 | 1 | 12 | 40 | 0.41667 | 0.47368 | 2020-12 | 0 | 0
1724 | CR0012815 | CTASK0021025 | Closed | OPUS-PRI | Nhien Nguyen | 30 | 30 | 2020-07-31 16:37 | 2020-07-01 16:37 | Container | Sales Management | Pricing | Surcharge | Surcharge Location Group Creation |  | [CLT Internal] Surcharge Location Group validation | 2020-07-15 10:43 | 2020-07-31 10:42 | 2020-07-31 09:57 | 2020-08-05 12:38 | 2020-08-05 14:18 |  | 2020-08-11 14:18 | 2020-09-01 10:11 | 2020-08-27 14:44 | 2020-10-10 13:00 | CR0012815 | Sales ManagementPricingSurchargeSurcharge Location Group Creation | OPUS-PRI | 2020-W33 | 2020-08 | 30 | 30 | 27.1496 | 1 | 1 | 1 | 0.05 | 183364 | 1.8 | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 30 | 0 | 0 | 2020-07 | 0 | 0
1725 | CR0013946 | CTASK0027082 | Closed | OPUS-SCG | Tu Nguyen | 20 | 20 |  |  | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO Approved Details |  | [CLV] OPUS Enhancement Request - SPCL CGO Approved Details (VOP_SCG_0023) - CNTR No Field to be Added | 2021-06-02 11:08 | 2021-06-30 11:06 | 2021-06-29 11:43 | 2021-07-06 08:39 | 2021-07-06 13:52 |  | 2021-07-13 10:01 | 2021-07-13 09:49 | 2021-07-07 09:22 | 2021-07-29 14:00 | CR0013946 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO Approved Details | OPUS-SCG | 2021-W28 | 2021-07 | 20 | 20 | 40.9534 | 1 | 1 | 1 | 0.02 | 123045 | 2.7 | 1 | 0 | 0 | 1 | 1 | 1 | 9 | 28 | 0 | 0 | 2021-06 | 0 | 0
1726 | CR0013163 | CTASK0022887 | Closed | OPUS-PRI | Ngan Nham | 144 | 144 | 2020-11-11 14:00 | 2020-10-07 13:00 | Container | Sales Management |  |  |  |  | *API* Service Contract Filing in Support Of Kontainers Integration | 2020-10-23 09:19 | 2020-11-07 14:00 | 2020-12-14 09:29 |  | 2021-01-06 11:13 |  | 2021-01-07 11:13 | 2021-01-12 14:00 | 2021-01-07 10:34 | 2021-02-12 14:00 | CR0013163 | Sales Management | OPUS-PRI | 2021-W1 | 2021-01 | 254 | 254 | 76.0794 | 2 | 1 | 1 | 0.14 | 193461 | 1.9 | 0 | 0 | 0 | 3 | 1 | 2 | 5 | 40 | 0 | 0.28571 | 2020-10 | 0 | 0
1727 | CR0013163 | CTASK0023310 | Closed | OPUS-PRI | Ngan Nham | 110 | 110 | 2020-12-01 14:00 | 2020-11-02 14:00 | Container | Sales Management |  |  |  |  | *API* Service Contract Filing in Support Of Kontainers Integration | 2020-10-23 09:19 | 2020-11-07 14:00 | 2020-12-14 09:29 |  | 2021-01-06 11:13 |  | 2021-01-07 11:13 | 2021-01-12 14:00 | 2021-01-07 10:34 | 2021-02-12 14:00 | CR0013163 | Sales Management | OPUS-PRI | 2021-W1 | 2021-01 | 254 | 254 | 76.0794 | 2 | 1 | 1 | 0.14 | 193461 | 1.9 | 0 | 0 | 0 | 3 | 1 | 2 | 5 | 40 | 0 | 0.28571 | 2020-10 | 0 | 0
1728 | CR0013441 | CTASK0024328 | Closed | OPUS-SCG | Pham Khanh Van | 12 | 12 | 2021-01-04 16:14 | 2020-12-29 16:14 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV][CLT Internal] Prechecking alert, SS cargo approval duplication | 2020-12-28 11:25 | 2021-01-15 11:25 | 2021-01-15 09:48 | 2021-02-01 16:19 | 2021-02-04 16:40 |  | 2021-02-23 10:00 | 2021-02-23 12:49 | 2021-02-04 18:15 | 2021-03-26 14:00 | CR0013441 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2021-W8 | 2021-02 | 52 | 56 | 56.9411 | 3 | 1 | 3 | 0.04 | 193477 | 1.6 | 2 | 0 | 0 | 1 | 1 | 2 | 4 | 21 | 0 | 0 | 2020-12 | 0 | 0
1729 | CR0013441 | CTASK0024326 | Closed | OPUS-SCG | Trang Duy Thong | 12 | 16 | 2021-01-15 16:12 | 2020-12-24 16:12 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Documentation][CLT Internal] Prechecking alert, SS cargo approval duplication | 2020-12-28 11:25 | 2021-01-15 11:25 | 2021-01-15 09:48 | 2021-02-01 16:19 | 2021-02-04 16:40 |  | 2021-02-23 10:00 | 2021-02-23 12:49 | 2021-02-04 18:15 | 2021-03-26 14:00 | CR0013441 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2021-W8 | 2021-02 | 52 | 56 | 56.9411 | 3 | 1 | 3 | 0.04 | 193511 | 0.6 | 2 | 0 | 0 | 1 | 1 | 2 | 4 | 21 | 0.81818 | 0 | 2020-12 | 0 | 0
1730 | CR0013441 | CTASK0024327 | Closed | OPUS-SCG | Lanh Le | 28 | 28 | 2021-01-08 16:13 | 2020-12-29 16:13 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV][CLT Internal] Prechecking alert, SS cargo approval duplication | 2020-12-28 11:25 | 2021-01-15 11:25 | 2021-01-15 09:48 | 2021-02-01 16:19 | 2021-02-04 16:40 |  | 2021-02-23 10:00 | 2021-02-23 12:49 | 2021-02-04 18:15 | 2021-03-26 14:00 | CR0013441 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2021-W8 | 2021-02 | 52 | 56 | 56.9411 | 3 | 1 | 3 | 0.04 | 183422 | 2.1 | 2 | 0 | 0 | 1 | 1 | 2 | 4 | 21 | 0 | 0 | 2020-12 | 0 | 0
1731 | CR0013408 | CTASK0024319 | Closed | OPUS-SCG | Trang Duy Thong | 16 | 16 | 2021-01-15 10:57 | 2021-01-04 10:57 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Documentation] HLC MEGC Conversion type 48TG | 2021-01-06 13:50 | 2021-01-18 13:50 | 2021-01-18 13:18 | 2021-02-15 13:29 | 2021-02-15 13:36 |  | 2021-02-23 09:36 | 2021-02-23 12:47 | 2021-02-18 15:25 | 2021-03-26 14:00 | CR0013408 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2021-W8 | 2021-02 | 46 | 46 | 47.8232 | 2 | 1 | 2 | 0.04 | 193511 | 0.6 | 2 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0.81818 | 0 | 2021-01 | 0 | 0
1732 | CR0013408 | CTASK0024320 | Closed | OPUS-SCG | Tu Nguyen | 30 | 30 | 2021-01-15 10:58 | 2020-12-28 10:58 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | HLC MEGC Conversion type 48TG | 2021-01-06 13:50 | 2021-01-18 13:50 | 2021-01-18 13:18 | 2021-02-15 13:29 | 2021-02-15 13:36 |  | 2021-02-23 09:36 | 2021-02-23 12:47 | 2021-02-18 15:25 | 2021-03-26 14:00 | CR0013408 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2021-W8 | 2021-02 | 46 | 46 | 47.8232 | 2 | 1 | 2 | 0.04 | 123045 | 2.3 | 2 | 0 | 0 | 1 | 1 | 1 | 4 | 21 | 0 | 0 | 2021-01 | 0 | 0
1733 | CR0013119 | CTASK0022701 | Closed | OPUS-BKG-M | Loc Tran | 30 | 30 | 2020-10-28 18:45 | 2020-09-28 18:45 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [CLT Internal] Decommission of DG Constraint related logic in BKG | 2020-09-28 11:39 | 2020-12-03 02:00 | 2020-11-25 14:34 | 2020-11-27 16:31 | 2020-11-27 16:35 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2020-11-27 16:50 | 2021-02-25 14:00 | CR0013119 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W4 | 2021-01 | 52 | 60 | 119.9311 | 4 | 1 | 1 | 0.02 | 193503 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.33333 | 0.28571 | 2020-09 | 0 | 0
1734 | CR0013119 | CTASK0022700 | Closed | OPUS-BKG-M | Loc Tran | 6 | 6 | 2020-09-30 18:43 | 2020-09-23 18:43 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [CLT Internal] Decommission of DG Constraint related logic in BKG | 2020-09-28 11:39 | 2020-12-03 02:00 | 2020-11-25 14:34 | 2020-11-27 16:31 | 2020-11-27 16:35 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2020-11-27 16:50 | 2021-02-25 14:00 | CR0013119 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W4 | 2021-01 | 52 | 60 | 119.9311 | 4 | 1 | 1 | 0.02 | 193503 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.33333 | 0.28571 | 2020-09 | 0 | 0
1735 | CR0013119 | CTASK0022704 | Closed | OPUS-BKG-M | Loc Tran | 12 | 20 | 2020-11-25 19:12 | 2020-10-05 19:12 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [CLT Internal] Decommission of DG Constraint related logic in BKG | 2020-09-28 11:39 | 2020-12-03 02:00 | 2020-11-25 14:34 | 2020-11-27 16:31 | 2020-11-27 16:35 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2020-11-27 16:50 | 2021-02-25 14:00 | CR0013119 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W4 | 2021-01 | 52 | 60 | 119.9311 | 4 | 1 | 1 | 0.02 | 193503 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.33333 | 0.28571 | 2020-09 | 0 | 0
1736 | CR0013119 | CTASK0022706 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 | 2021-01-27 17:31 | 2021-01-19 17:31 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [CLT Internal] Decommission of DG Constraint related logic in BKG | 2020-09-28 11:39 | 2020-12-03 02:00 | 2020-11-25 14:34 | 2020-11-27 16:31 | 2020-11-27 16:35 |  | 2021-01-26 10:00 | 2021-01-26 11:00 | 2020-11-27 16:50 | 2021-02-25 14:00 | CR0013119 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W4 | 2021-01 | 52 | 60 | 119.9311 | 4 | 1 | 1 | 0.02 | 193503 | 1.2 | 1 | 0 | 0 | 1 | 1 | 2 | 12 | 40 | 0.33333 | 0.28571 | 2020-09 | 0 | 0
1737 | CR0010716 | CTASK0014986 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 147 | 99 | 2019-11-29 18:34 | 2019-10-23 09:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | NA *BKG* Add hover function to Booking creation module (CSVC/EXP BOOKING) | 2019-10-23 18:05 | 2019-12-24 | 2019-12-23 17:02 | 2020-02-10 06:25 | 2020-02-14 12:43 | 2019-12-23 17:02 | 2020-03-10 12:42 | 2020-03-10 10:00 | 2020-02-21 05:01 | 2020-04-09 13:00 | CR0010716 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W11 | 2020-03 | 169 | 99 | 138.7758 | 2 | 2 | 2 | 0.03 | 193470 | 0.6 | 0 | 0 | 1 | 1 | 1 | 2 | 7 | 25 | 0 | 1.3333 | 2019-10 | 1 | 1
1738 | CR0010716 | CTASK0014985 | Closed | OPUS-BKG-M | Nhan Le | 22 | 22 | 2019-12-13 18:33 | 2019-10-14 18:33 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | NA *BKG* Add hover function to Booking creation module (CSVC/EXP BOOKING) | 2019-10-23 18:05 | 2019-12-24 | 2019-12-23 17:02 | 2020-02-10 06:25 | 2020-02-14 12:43 | 2019-12-23 17:02 | 2020-03-10 12:42 | 2020-03-10 10:00 | 2020-02-21 05:01 | 2020-04-09 13:00 | CR0010716 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2020-W11 | 2020-03 | 169 | 99 | 138.7758 | 2 | 2 | 2 | 0.03 | 183353 | 1.1 | 0 | 0 | 1 | 1 | 1 | 2 | 7 | 25 | 0 | 0 | 2019-10 | 1 | 1
1739 | CR0013710 | CTASK0026257 | Implemented | OPUS-BKG-EBKG | Vinh Tran | 5 | 4 | 2021-08-04 02:00 | 2021-08-03 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] Removal of Auto Notification field and change of logic of Auto Notification defaulted across different eBooking channel | 2021-04-28 22:40 | 2021-05-29 | 2021-05-28 13:37 | 2021-07-15 16:13 | 2021-07-15 18:42 |  | 2021-08-10 11:00 | 2021-08-10 10:00 | 2021-08-03 11:39 |  | CR0013710 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W32 | 2021-08 | 61 | 60 | 103.5138 | 4 | 1 | 1 | 0.02 | 193525 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 10 | 22 | 0.41667 | 0.47368 | 2021-04 | 0 | 0
1740 | CR0013710 | CTASK0026255 | Implemented | OPUS-BKG-EBKG | Vinh Tran | 26 | 26 | 2021-05-14 02:00 | 2021-05-10 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development] Removal of Auto Notification field and change of logic of Auto Notification defaulted across different eBooking channel | 2021-04-28 22:40 | 2021-05-29 | 2021-05-28 13:37 | 2021-07-15 16:13 | 2021-07-15 18:42 |  | 2021-08-10 11:00 | 2021-08-10 10:00 | 2021-08-03 11:39 |  | CR0013710 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W32 | 2021-08 | 61 | 60 | 103.5138 | 4 | 1 | 1 | 0.02 | 193525 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 10 | 22 | 0.41667 | 0.47368 | 2021-04 | 0 | 0
1741 | CR0013710 | CTASK0026256 | Implemented | OPUS-BKG-EBKG | Vinh Tran | 20 | 20 | 2021-05-25 02:00 | 2021-05-17 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing] Removal of Auto Notification field and change of logic of Auto Notification defaulted across different eBooking channel | 2021-04-28 22:40 | 2021-05-29 | 2021-05-28 13:37 | 2021-07-15 16:13 | 2021-07-15 18:42 |  | 2021-08-10 11:00 | 2021-08-10 10:00 | 2021-08-03 11:39 |  | CR0013710 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W32 | 2021-08 | 61 | 60 | 103.5138 | 4 | 1 | 1 | 0.02 | 193525 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 10 | 22 | 0.41667 | 0.47368 | 2021-04 | 0 | 0
1742 | CR0013710 | CTASK0026254 | Implemented | OPUS-BKG-EBKG | Vinh Tran | 10 | 10 | 2021-04-07 02:00 | 2021-04-05 02:00 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] Removal of Auto Notification field and change of logic of Auto Notification defaulted across different eBooking channel | 2021-04-28 22:40 | 2021-05-29 | 2021-05-28 13:37 | 2021-07-15 16:13 | 2021-07-15 18:42 |  | 2021-08-10 11:00 | 2021-08-10 10:00 | 2021-08-03 11:39 |  | CR0013710 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W32 | 2021-08 | 61 | 60 | 103.5138 | 4 | 1 | 1 | 0.02 | 193525 | 1.9 | 1 | 0 | 0 | 1 | 1 | 2 | 10 | 22 | 0.41667 | 0.47368 | 2021-04 | 0 | 0
1743 | CR0012344 | CTASK0019324 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 | 2020-05-30 02:00 | 2020-05-11 16:12 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Testing] NA *Standby* Trunk-Loading next 5 VVD allocation inaccuracies - RICA19993900 | 2020-05-07 09:11 | 2020-06-27 | 2020-06-26 16:17 | 2020-07-15 00:12 | 2020-07-16 10:47 |  | 2020-07-21 10:00 | 2020-07-22 | 2020-07-17 04:24 | 2020-08-06 03:42 | CR0012344 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W30 | 2020-07 | 30 | 30 | 75.034 | 4 | 1 | 1 | 0.02 | 153106 | 1.6 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-05 | 0 | 0
1744 | CR0012344 | CTASK0019327 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2020-07-18 01:55 | 2020-07-14 02:54 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Deployment] NA *Standby* Trunk-Loading next 5 VVD allocation inaccuracies - RICA19993900 | 2020-05-07 09:11 | 2020-06-27 | 2020-06-26 16:17 | 2020-07-15 00:12 | 2020-07-16 10:47 |  | 2020-07-21 10:00 | 2020-07-22 | 2020-07-17 04:24 | 2020-08-06 03:42 | CR0012344 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W30 | 2020-07 | 30 | 30 | 75.034 | 4 | 1 | 1 | 0.02 | 153106 | 1.6 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-05 | 0 | 0
1745 | CR0012344 | CTASK0019323 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2020-05-08 16:11 | 2020-05-04 16:11 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Development] NA *Standby* Trunk-Loading next 5 VVD allocation inaccuracies - RICA19993900 | 2020-05-07 09:11 | 2020-06-27 | 2020-06-26 16:17 | 2020-07-15 00:12 | 2020-07-16 10:47 |  | 2020-07-21 10:00 | 2020-07-22 | 2020-07-17 04:24 | 2020-08-06 03:42 | CR0012344 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W30 | 2020-07 | 30 | 30 | 75.034 | 4 | 1 | 1 | 0.02 | 153106 | 1.6 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-05 | 0 | 0
1746 | CR0012344 | CTASK0019254 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2020-03-31 01:08 | 2020-03-26 02:08 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Design] NA *Standby* Trunk-Loading next 5 VVD allocation inaccuracies - RICA19993900 | 2020-05-07 09:11 | 2020-06-27 | 2020-06-26 16:17 | 2020-07-15 00:12 | 2020-07-16 10:47 |  | 2020-07-21 10:00 | 2020-07-22 | 2020-07-17 04:24 | 2020-08-06 03:42 | CR0012344 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2020-W30 | 2020-07 | 30 | 30 | 75.034 | 4 | 1 | 1 | 0.02 | 153106 | 1.6 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 27 | 0 | 0.4 | 2020-05 | 0 | 0
1747 | CR0013962 | CTASK0026990 | Closed | OPUS-SCO | Lien Le | 15 | 14 | 2021-05-31 10:52 | 2021-05-13 10:52 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Management By EMail |  | [May 2021][Lien Le][CLT Internal] Prevention of OOME from Collection Management by Email screen | 2021-05-18 09:03 | 2021-07-15 09:03 | 2021-05-31 11:42 | 2021-06-02 10:55 | 2021-06-02 13:31 |  | 2021-06-08 10:00 | 2021-06-08 10:00 | 2021-06-03 11:46 | 2021-07-08 14:00 | CR0013962 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Management By EMail | OPUS-SAR | 2021-W23 | 2021-06 | 27 | 26 | 21.0395 | 2 | 1 | 2 | 0.05 | 193441 | 2.2 | 2 | 0 | 0 | 1 | 1 | 1 | 9 | 53 | 0.42308 | 0 | 2021-05 | 0 | 0
1748 | CR0013962 | CTASK0026989 | Closed | OPUS-SCO | Cuong Tran Hung | 12 | 12 | 2021-05-31 10:51 | 2021-05-13 10:51 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Management By EMail |  | [May 2021][Cuong Tran][CLT Internal] Prevention of OOME from Collection Management by Email screen | 2021-05-18 09:03 | 2021-07-15 09:03 | 2021-05-31 11:42 | 2021-06-02 10:55 | 2021-06-02 13:31 |  | 2021-06-08 10:00 | 2021-06-08 10:00 | 2021-06-03 11:46 | 2021-07-08 14:00 | CR0013962 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Management By EMail | OPUS-SAR | 2021-W23 | 2021-06 | 27 | 26 | 21.0395 | 2 | 1 | 2 | 0.05 | 193530 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 9 | 53 | 1.2308 | 1.2222 | 2021-05 | 0 | 0
1749 | CR0013561 | CTASK0025022 | Closed | OPUS-BKG-M | Kieu Le | 15 | 16 | 2021-02-26 16:41 | 2021-02-01 02:41 | Container | Sales Management | Space Control | Standby Management |  |  | [Development] Asia - Standby Master Constraint Table UI - Add new filters | 2021-02-02 17:53 | 2021-02-25 | 2021-02-23 13:26 | 2021-02-24 09:35 | 2021-02-24 09:45 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-25 09:48 | 2021-04-01 14:00 | CR0013561 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2021-W9 | 2021-03 | 28 | 32 | 27.6713 | 4 | 1 | 1 | 0.05 | 153106 | 2.3 | 0 | 0 | 0 | 1 | 1 | 1 | 13 | 46 | 0.22951 | 0.13043 | 2021-02 | 0 | 0
1750 | CR0013561 | CTASK0025026 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-03-31 16:45 | 2021-03-01 16:45 | Container | Sales Management | Space Control | Standby Management |  |  | [Deployment] Asia - Standby Master Constraint Table UI - Add new filters | 2021-02-02 17:53 | 2021-02-25 | 2021-02-23 13:26 | 2021-02-24 09:35 | 2021-02-24 09:45 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-25 09:48 | 2021-04-01 14:00 | CR0013561 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2021-W9 | 2021-03 | 28 | 32 | 27.6713 | 4 | 1 | 1 | 0.05 | 153106 | 2.3 | 0 | 0 | 0 | 1 | 1 | 1 | 13 | 46 | 0.22951 | 0.13043 | 2021-02 | 0 | 0
1751 | CR0013561 | CTASK0025021 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-02-26 16:40 | 2021-02-01 02:40 | Container | Sales Management | Space Control | Standby Management |  |  | [Design] Asia - Standby Master Constraint Table UI - Add new filters | 2021-02-02 17:53 | 2021-02-25 | 2021-02-23 13:26 | 2021-02-24 09:35 | 2021-02-24 09:45 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-25 09:48 | 2021-04-01 14:00 | CR0013561 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2021-W9 | 2021-03 | 28 | 32 | 27.6713 | 4 | 1 | 1 | 0.05 | 153106 | 2.3 | 0 | 0 | 0 | 1 | 1 | 1 | 13 | 46 | 0.22951 | 0.13043 | 2021-02 | 0 | 0
1752 | CR0013561 | CTASK0025024 | Closed | OPUS-BKG-M | Kieu Le | 9 | 12 | 2021-02-26 16:44 | 2021-02-01 16:44 | Container | Sales Management | Space Control | Standby Management |  |  | [Testing] Asia - Standby Master Constraint Table UI - Add new filters | 2021-02-02 17:53 | 2021-02-25 | 2021-02-23 13:26 | 2021-02-24 09:35 | 2021-02-24 09:45 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-02-25 09:48 | 2021-04-01 14:00 | CR0013561 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2021-W9 | 2021-03 | 28 | 32 | 27.6713 | 4 | 1 | 1 | 0.05 | 153106 | 2.3 | 0 | 0 | 0 | 1 | 1 | 1 | 13 | 46 | 0.22951 | 0.13043 | 2021-02 | 0 | 0
1753 | CR0012761 | CTASK0020804 | Closed | OPUS-SCG | Pham Khanh Van | 35 | 35 | 2020-07-17 15:59 | 2020-06-23 15:58 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV][Documentation] Change the logic of MSC's route information | 2020-06-26 16:13 | 2020-07-17 16:13 | 2020-07-16 17:17 | 2020-07-30 00:35 | 2020-07-30 16:36 |  | 2020-08-04 10:01 | 2020-08-04 11:41 | 2020-07-31 14:48 | 2020-09-03 13:00 | CR0012761 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W32 | 2020-08 | 65 | 65 | 38.7412 | 2 | 1 | 1 | 0.07 | 193477 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 30 | 0 | 0 | 2020-06 | 0 | 0
1754 | CR0012761 | CTASK0020815 | Closed | OPUS-SCG | Pham Khanh Van | 30 | 30 |  |  | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] Change the logic of MSC's route information | 2020-06-26 16:13 | 2020-07-17 16:13 | 2020-07-16 17:17 | 2020-07-30 00:35 | 2020-07-30 16:36 |  | 2020-08-04 10:01 | 2020-08-04 11:41 | 2020-07-31 14:48 | 2020-09-03 13:00 | CR0012761 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2020-W32 | 2020-08 | 65 | 65 | 38.7412 | 2 | 1 | 1 | 0.07 | 193477 | 1.1 | 0 | 0 | 0 | 1 | 1 | 1 | 9 | 30 | 0 | 0 | 2020-06 | 0 | 0
1755 | CR0013206 | CTASK0023280 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-01-26 12:31 | 2021-01-21 11:31 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing][CLT Internal] Enable to change the pre/post code of the booking VVD. | 2020-11-13 09:44 | 2021-02-04 | 2021-01-29 14:06 | 2021-01-29 15:51 | 2021-01-29 16:09 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 16:13 | 2021-04-01 14:00 | CR0013206 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W9 | 2021-03 | 36 | 36 | 109.0112 | 3 | 1 | 1 | 0.01 | 193488 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.53659 | 0.28125 | 2020-11 | 0 | 0
1756 | CR0013206 | CTASK0023281 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-02-25 02:00 | 2021-02-22 10:56 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment][CLT Internal] Enable to change the pre/post code of the booking VVD. | 2020-11-13 09:44 | 2021-02-04 | 2021-01-29 14:06 | 2021-01-29 15:51 | 2021-01-29 16:09 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 16:13 | 2021-04-01 14:00 | CR0013206 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W9 | 2021-03 | 36 | 36 | 109.0112 | 3 | 1 | 1 | 0.01 | 193488 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.53659 | 0.28125 | 2020-11 | 0 | 0
1757 | CR0013206 | CTASK0023279 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 24 | 24 | 2020-12-11 19:32 | 2020-12-01 10:32 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development][CLT Internal] Enable to change the pre/post code of the booking VVD. | 2020-11-13 09:44 | 2021-02-04 | 2021-01-29 14:06 | 2021-01-29 15:51 | 2021-01-29 16:09 |  | 2021-03-02 10:00 | 2021-03-02 10:00 | 2021-01-29 16:13 | 2021-04-01 14:00 | CR0013206 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W9 | 2021-03 | 36 | 36 | 109.0112 | 3 | 1 | 1 | 0.01 | 193488 | 1.4 | 1 | 0 | 0 | 1 | 1 | 2 | 13 | 46 | 0.53659 | 0.28125 | 2020-11 | 0 | 0
1758 | CR0012642 | CTASK0020214 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 | 2020-05-22 19:30 | 2020-05-20 15:00 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | B/L Issue [Alt+8] | [Analysis]OBDOC- Amend RPA BL Release (in CR0012085) to extract BLs by booking office | 2020-05-25 13:46 | 2020-06-03 | 2020-05-29 17:00 | 2020-06-03 13:35 | 2020-06-04 10:23 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-06-04 16:54 | 2020-07-09 13:00 | CR0012642 | Service ManagementBooking/DocumentationOutbound DocB/L CreationB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W24 | 2020-06 | 28 | 34 | 14.8429 | 2 | 1 | 1 | 0.1 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 29 | 0 | 0.17391 | 2020-05 | 0 | 0
1759 | CR0012642 | CTASK0020316 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 20 | 26 | 2020-06-05 19:30 | 2020-05-26 10:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | B/L Issue [Alt+8] | [Development + Testing + Deploy] OBDOC- Amend RPA BL Release (in CR0012085) to extract BLs by booking office | 2020-05-25 13:46 | 2020-06-03 | 2020-05-29 17:00 | 2020-06-03 13:35 | 2020-06-04 10:23 |  | 2020-06-09 10:00 | 2020-06-09 10:00 | 2020-06-04 16:54 | 2020-07-09 13:00 | CR0012642 | Service ManagementBooking/DocumentationOutbound DocB/L CreationB/L Issue [Alt+8] | OPUS-BKG-OB | 2020-W24 | 2020-06 | 28 | 34 | 14.8429 | 2 | 1 | 1 | 0.1 | 193470 | 1.2 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 29 | 0 | 0.17391 | 2020-05 | 0 | 0
1760 | CR0012630 | CTASK0020894 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 38 | 28 | 2020-08-31 14:45 | 2020-08-01 14:45 | Container | Service Management | Trans S/O | USA/CA Rail |  |  | NA *Opus FF* VENDOR- Please update logic to capture Packaging details from OPUS in RAILBILL F/F | 2020-07-28 11:25 | 2020-09-30 21:00 | 2020-09-16 09:10 | 2020-12-08 15:03 | 2020-12-15 09:36 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-17 17:32 | 2021-01-13 06:12 | CR0012630 | Service ManagementTrans S/OUSA/CA Rail | OPUS-TRS | 2021-W1 | 2021-01 | 62 | 56 | 160.9411 | 2 | 1 | 2 | 0.01 | 183432 | 1.4 | 0 | 0 | 0 | 1 | 1 | 3 | 5 | 40 | 0 | 0 | 2020-07 | 0 | 0
1761 | CR0012630 | CTASK0020971 | Closed | OPUS-TRS | Giang Nguyen Hoang | 24 | 28 | 2020-08-31 14:45 | 2020-08-01 14:45 | Container | Service Management | Trans S/O | USA/CA Rail |  |  | NA *Opus FF* VENDOR- Please update logic to capture Packaging details from OPUS in RAILBILL F/F | 2020-07-28 11:25 | 2020-09-30 21:00 | 2020-09-16 09:10 | 2020-12-08 15:03 | 2020-12-15 09:36 |  | 2021-01-05 10:00 | 2021-01-05 10:00 | 2020-12-17 17:32 | 2021-01-13 06:12 | CR0012630 | Service ManagementTrans S/OUSA/CA Rail | OPUS-TRS | 2021-W1 | 2021-01 | 62 | 56 | 160.9411 | 2 | 1 | 2 | 0.01 | 183440 | 1.4 | 0 | 0 | 0 | 1 | 1 | 3 | 5 | 40 | 0 | 0 | 2020-07 | 0 | 0
1762 | CR0012810 | CTASK0023373 | Closed | OPUS-PRD | VInh Bui | 36 | 40 | 2020-11-30 14:35 | 2020-11-01 14:35 | Container | Service Management | Product Catalog |  |  |  | GHQ - Add Cnee field into Network Constraint - NOV | 2020-09-17 14:54 | 2020-12-31 20:00 | 2020-11-24 09:46 | 2021-04-14 08:59 | 2021-04-15 09:36 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-19 16:27 | 2021-05-29 14:00 | CR0012810 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W17 | 2021-04 | 134 | 148 | 221.7956 | 4 | 1 | 1 | 0.03 | 193469 | 0.9 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 27 | 0 | 0 | 2020-09 | 0 | 0
1763 | CR0012810 | CTASK0022643 | Closed | OPUS-PRD | VInh Bui | 20 | 20 | 2020-09-30 12:02 | 2020-09-23 12:02 | Container | Service Management | Product Catalog |  |  |  | GHQ - Add Cnee field into Network Constraint - SEP | 2020-09-17 14:54 | 2020-12-31 20:00 | 2020-11-24 09:46 | 2021-04-14 08:59 | 2021-04-15 09:36 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-19 16:27 | 2021-05-29 14:00 | CR0012810 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W17 | 2021-04 | 134 | 148 | 221.7956 | 4 | 1 | 1 | 0.03 | 193469 | 0.9 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 27 | 0 | 0 | 2020-09 | 0 | 0
1764 | CR0012810 | CTASK0026510 | Closed | OPUS-PRD | VInh Bui | 4 | 8 | 2021-04-30 09:38 | 2021-04-15 09:38 | Container | Service Management | Product Catalog |  |  |  | GHQ - Add Cnee field into Network Constraint-APR | 2020-09-17 14:54 | 2020-12-31 20:00 | 2020-11-24 09:46 | 2021-04-14 08:59 | 2021-04-15 09:36 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-19 16:27 | 2021-05-29 14:00 | CR0012810 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W17 | 2021-04 | 134 | 148 | 221.7956 | 4 | 1 | 1 | 0.03 | 193469 | 0.9 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 27 | 0 | 0 | 2020-09 | 0 | 0
1765 | CR0012810 | CTASK0022644 | Closed | OPUS-PRD | VInh Bui | 74 | 80 | 2020-10-31 18:00 | 2020-10-01 08:00 | Container | Service Management | Product Catalog |  |  |  | GHQ - Add Cnee field into Network Constraint - OCT | 2020-09-17 14:54 | 2020-12-31 20:00 | 2020-11-24 09:46 | 2021-04-14 08:59 | 2021-04-15 09:36 |  | 2021-04-27 10:00 | 2021-04-27 10:00 | 2021-04-19 16:27 | 2021-05-29 14:00 | CR0012810 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W17 | 2021-04 | 134 | 148 | 221.7956 | 4 | 1 | 1 | 0.03 | 193469 | 0.9 | 0 | 0 | 0 | 2 | 1 | 3 | 12 | 27 | 0 | 0 | 2020-09 | 0 | 0
1766 | CR0013483 | CTASK0026075 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 12 | 12 | 2021-03-26 02:00 | 2021-03-26 02:00 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare |  | [Dev-Test Feedback][CLT Internal] EU DG EDI Transmit Screen - Unable to delete data in EU DG EDI Transmit Screen | 2021-02-15 18:00 | 2021-03-06 | 2021-02-19 14:43 | 2021-07-05 13:10 | 2021-07-06 11:29 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-12 17:08 | 2021-07-29 14:00 | CR0013483 | Service ManagementBooking/DocumentationOperationEU DG Declare | OPUS-BKG-MFT | 2021-W28 | 2021-07 | 64 | 70 | 147.6667 | 7 | 1 | 2 | 0.02 | 193506 | 1.7 | 3 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 1.1212 | 1.25 | 2021-02 | 0 | 0
1767 | CR0013483 | CTASK0026375 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 8 | 8 | 2021-04-30 02:00 | 2021-04-08 02:00 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare |  | [Dev-Test Feedback][CLT Internal] EU DG EDI Transmit Screen - Unable to delete data in EU DG EDI Transmit Screen | 2021-02-15 18:00 | 2021-03-06 | 2021-02-19 14:43 | 2021-07-05 13:10 | 2021-07-06 11:29 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-12 17:08 | 2021-07-29 14:00 | CR0013483 | Service ManagementBooking/DocumentationOperationEU DG Declare | OPUS-BKG-MFT | 2021-W28 | 2021-07 | 64 | 70 | 147.6667 | 7 | 1 | 2 | 0.02 | 193506 | 1.7 | 3 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 1.1212 | 1.25 | 2021-02 | 0 | 0
1768 | CR0013483 | CTASK0027969 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 20 | 24 | 2021-07-20 23:38 | 2021-07-01 23:38 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare |  | [PROD][CLT Internal] EU DG EDI Transmit Screen - Unable to delete data in EU DG EDI Transmit Screen | 2021-02-15 18:00 | 2021-03-06 | 2021-02-19 14:43 | 2021-07-05 13:10 | 2021-07-06 11:29 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-12 17:08 | 2021-07-29 14:00 | CR0013483 | Service ManagementBooking/DocumentationOperationEU DG Declare | OPUS-BKG-MFT | 2021-W28 | 2021-07 | 64 | 70 | 147.6667 | 7 | 1 | 2 | 0.02 | 193606 | 1.3 | 3 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 4.25 | 2.25 | 2021-02 | 0 | 0
1769 | CR0013483 | CTASK0025239 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 6 | 6 | 2021-03-12 02:00 | 2021-03-01 02:00 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare |  | [Dev][CLT Internal] EU DG EDI Transmit Screen - Unable to delete data in EU DG EDI Transmit Screen | 2021-02-15 18:00 | 2021-03-06 | 2021-02-19 14:43 | 2021-07-05 13:10 | 2021-07-06 11:29 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-12 17:08 | 2021-07-29 14:00 | CR0013483 | Service ManagementBooking/DocumentationOperationEU DG Declare | OPUS-BKG-MFT | 2021-W28 | 2021-07 | 64 | 70 | 147.6667 | 7 | 1 | 2 | 0.02 | 193506 | 1.7 | 3 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 1.1212 | 1.25 | 2021-02 | 0 | 0
1770 | CR0013483 | CTASK0025238 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 2 | 2 | 2021-02-09 02:00 | 2021-02-09 02:00 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare |  | [Analytics][CLT Internal] EU DG EDI Transmit Screen - Unable to delete data in EU DG EDI Transmit Screen | 2021-02-15 18:00 | 2021-03-06 | 2021-02-19 14:43 | 2021-07-05 13:10 | 2021-07-06 11:29 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-12 17:08 | 2021-07-29 14:00 | CR0013483 | Service ManagementBooking/DocumentationOperationEU DG Declare | OPUS-BKG-MFT | 2021-W28 | 2021-07 | 64 | 70 | 147.6667 | 7 | 1 | 2 | 0.02 | 193506 | 1.7 | 3 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 1.1212 | 1.25 | 2021-02 | 0 | 0
1771 | CR0013483 | CTASK0025240 | Closed | OPUS-BKG-MFT-E | Tan Nguyen | 16 | 16 | 2021-03-12 02:00 | 2021-03-01 02:00 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare |  | [Test][CLT Internal] EU DG EDI Transmit Screen - Unable to delete data in EU DG EDI Transmit Screen | 2021-02-15 18:00 | 2021-03-06 | 2021-02-19 14:43 | 2021-07-05 13:10 | 2021-07-06 11:29 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-12 17:08 | 2021-07-29 14:00 | CR0013483 | Service ManagementBooking/DocumentationOperationEU DG Declare | OPUS-BKG-MFT | 2021-W28 | 2021-07 | 64 | 70 | 147.6667 | 7 | 1 | 2 | 0.02 | 193506 | 1.7 | 3 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 1.1212 | 1.25 | 2021-02 | 0 | 0
1772 | CR0013483 | CTASK0027473 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 2 | 2 | 2021-06-30 17:42 | 2021-06-08 17:42 | Container | Service Management | Booking/Documentation | Operation | EU DG Declare |  | [Fix Issue] [CLT Internal] EU DG EDI Transmit Screen - Unable to delete data in EU DG EDI Transmit Screen | 2021-02-15 18:00 | 2021-03-06 | 2021-02-19 14:43 | 2021-07-05 13:10 | 2021-07-06 11:29 |  | 2021-07-13 10:00 | 2021-07-13 10:00 | 2021-07-12 17:08 | 2021-07-29 14:00 | CR0013483 | Service ManagementBooking/DocumentationOperationEU DG Declare | OPUS-BKG-MFT | 2021-W28 | 2021-07 | 64 | 70 | 147.6667 | 7 | 1 | 2 | 0.02 | 193606 | 1.3 | 3 | 0 | 0 | 1 | 1 | 2 | 9 | 28 | 4.25 | 2.25 | 2021-02 | 0 | 0
1773 | CR0011127 | CTASK0012531 | Closed | OPUS-MNR | Tuyen Truong | 32 | 32 | 2019-05-31 08:18 | 2019-04-22 08:17 | Container | Equipment Management | M&R |  |  |  | Disposal invoice settled status not revert to 'Not settled' when the Disposal invoice is cancelled | 2019-04-30 17:22 | 2019-05-17 17:21 | 2019-05-09 12:24 | 2019-05-21 13:20 | 2019-05-22 10:25 |  | 2019-05-28 10:25 | 2019-05-28 13:00 | 2019-06-18 11:47 | 2019-06-18 16:14 | CR0011127 | Equipment ManagementM&R | OPUS-MNR | 2019-W22 | 2019-05 | 36 | 32 | 27.7104 | 5 | 2 | 2 | 0.05 | 173255 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 6 | 0 | 0 | 2019-04 | 0 | 0
1774 | CR0011127 | CTASK0013176 | Closed | OPUS-MGS | Tuyen Truong | 4 | 4 | 2019-05-10 18:06 | 2019-05-06 18:06 | Container | Equipment Management | M&R |  |  |  | [actual]Disposal invoice settled status not revert to 'Not settled' when the Disposal invoice is cancelled | 2019-04-30 17:22 | 2019-05-17 17:21 | 2019-05-09 12:24 | 2019-05-21 13:20 | 2019-05-22 10:25 |  | 2019-05-28 10:25 | 2019-05-28 13:00 | 2019-06-18 11:47 | 2019-06-18 16:14 | CR0011127 | Equipment ManagementM&R | OPUS-MNR | 2019-W22 | 2019-05 | 36 | 32 | 27.7104 | 5 | 2 | 2 | 0.05 | 173255 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 6 | 0 | 0 | 2019-04 | 0 | 0
1775 | CR0011127 | CTASK0013175 | Closed | OPUS-MNR | Tien Le | 1 | 1 |  |  | Container | Equipment Management | M&R |  |  |  | [actual]Disposal invoice settled status not revert to 'Not settled' when the Disposal invoice is cancelled | 2019-04-30 17:22 | 2019-05-17 17:21 | 2019-05-09 12:24 | 2019-05-21 13:20 | 2019-05-22 10:25 |  | 2019-05-28 10:25 | 2019-05-28 13:00 | 2019-06-18 11:47 | 2019-06-18 16:14 | CR0011127 | Equipment ManagementM&R | OPUS-MNR | 2019-W22 | 2019-05 | 36 | 32 | 27.7104 | 5 | 2 | 2 | 0.05 | 173286 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 6 | 0 | 0 | 2019-04 | 0 | 0
1776 | CR0011127 | CTASK0012898 | Closed | OPUS-MNR | Tien Le | 20 | 20 |  |  | Container | Equipment Management | M&R |  |  |  | [actual]Disposal invoice settled status not revert to 'Not settled' when the Disposal invoice is cancelled | 2019-04-30 17:22 | 2019-05-17 17:21 | 2019-05-09 12:24 | 2019-05-21 13:20 | 2019-05-22 10:25 |  | 2019-05-28 10:25 | 2019-05-28 13:00 | 2019-06-18 11:47 | 2019-06-18 16:14 | CR0011127 | Equipment ManagementM&R | OPUS-MNR | 2019-W22 | 2019-05 | 36 | 32 | 27.7104 | 5 | 2 | 2 | 0.05 | 173286 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 6 | 0 | 0 | 2019-04 | 0 | 0
1777 | CR0011127 | CTASK0012897 | Closed | OPUS-MNR | Tuyen Truong | 12 | 12 |  |  | Container | Equipment Management | M&R |  |  |  | [actual]Disposal invoice settled status not revert to 'Not settled' when the Disposal invoice is cancelled | 2019-04-30 17:22 | 2019-05-17 17:21 | 2019-05-09 12:24 | 2019-05-21 13:20 | 2019-05-22 10:25 |  | 2019-05-28 10:25 | 2019-05-28 13:00 | 2019-06-18 11:47 | 2019-06-18 16:14 | CR0011127 | Equipment ManagementM&R | OPUS-MNR | 2019-W22 | 2019-05 | 36 | 32 | 27.7104 | 5 | 2 | 2 | 0.05 | 173255 | 0.6 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 6 | 0 | 0 | 2019-04 | 0 | 0
1778 | CR0014608 | CTASK0031760 | Closed | OPUS-SPC | Linh Nguyen | 12 | 12 | 2022-01-22 22:25 | 2022-01-01 22:25 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | Include POR into Standby MCT Feeder Tab | 2022-01-03 13:01 | 2022-01-14 13:00 | 2022-01-13 07:52 | 2022-02-14 20:18 | 2022-02-16 08:33 |  | 2022-02-23 08:32 | 2022-02-23 09:39 | 2022-02-17 12:27 | 2022-03-02 12:00 | CR0014608 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W8 | 2022-02 | 30 | 30 | 50.8136 | 2 | 1 | 2 | 0.02 | 193464 | 2.8 | 0 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 1.5 | 2022-01 | 0 | 0
1779 | CR0014608 | CTASK0031692 | Closed | OPUS-SPC | Toai Phan | 18 | 18 |  |  | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | Include POR into Standby MCT Feeder Tab | 2022-01-03 13:01 | 2022-01-14 13:00 | 2022-01-13 07:52 | 2022-02-14 20:18 | 2022-02-16 08:33 |  | 2022-02-23 08:32 | 2022-02-23 09:39 | 2022-02-17 12:27 | 2022-03-02 12:00 | CR0014608 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W8 | 2022-02 | 30 | 30 | 50.8136 | 2 | 1 | 2 | 0.02 | 183427 | 3.1 | 0 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2022-01 | 0 | 0
1780 | CR0014664 | CTASK0031064 | Closed | OPUS-BKG-M | Trang Le Minh | 12 | 12 | 2021-12-31 21:03 | 2021-12-01 15:02 | Container | Service Management | Booking/Documentation |  |  |  | [Design] Global *EDI* - INTTRA/IFTMBC - Add SPLIT booking fields to Booking Confirmation Flat File | 2021-12-21 09:14 | 2022-01-20 | 2022-01-19 08:59 | 2022-02-17 08:47 | 2022-02-17 08:53 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-17 12:25 | 2022-03-15 12:00 | CR0014664 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 91 | 90 | 76.9487 | 4 | 1 | 1 | 0.05 | 193594 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0 | 0 | 2021-12 | 0 | 0
1781 | CR0014664 | CTASK0031101 | Closed | OPUS-BKG-M | Trang Le Minh | 10 | 10 | 2022-03-02 21:45 | 2022-03-01 06:45 | Container | Service Management | Booking/Documentation |  |  |  | [Deployment] Global *EDI* - INTTRA/IFTMBC - Add SPLIT booking fields to Booking Confirmation Flat File | 2021-12-21 09:14 | 2022-01-20 | 2022-01-19 08:59 | 2022-02-17 08:47 | 2022-02-17 08:53 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-17 12:25 | 2022-03-15 12:00 | CR0014664 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 91 | 90 | 76.9487 | 4 | 1 | 1 | 0.05 | 193594 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0 | 0 | 2021-12 | 0 | 0
1782 | CR0014664 | CTASK0031098 | Closed | OPUS-BKG-M | Trang Le Minh | 52 | 52 | 2021-12-31 21:55 | 2021-12-20 08:55 | Container | Service Management | Booking/Documentation |  |  |  | [Development] Global *EDI* - INTTRA/IFTMBC - Add SPLIT booking fields to Booking Confirmation Flat File | 2021-12-21 09:14 | 2022-01-20 | 2022-01-19 08:59 | 2022-02-17 08:47 | 2022-02-17 08:53 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-17 12:25 | 2022-03-15 12:00 | CR0014664 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 91 | 90 | 76.9487 | 4 | 1 | 1 | 0.05 | 193594 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0 | 0 | 2021-12 | 0 | 0
1783 | CR0014664 | CTASK0031099 | Closed | OPUS-BKG-M | Trang Le Minh | 17 | 16 | 2022-01-28 21:56 | 2022-01-01 08:56 | Container | Service Management | Booking/Documentation |  |  |  | [Test] Global *EDI* - INTTRA/IFTMBC - Add SPLIT booking fields to Booking Confirmation Flat File | 2021-12-21 09:14 | 2022-01-20 | 2022-01-19 08:59 | 2022-02-17 08:47 | 2022-02-17 08:53 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-17 12:25 | 2022-03-15 12:00 | CR0014664 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 91 | 90 | 76.9487 | 4 | 1 | 1 | 0.05 | 193594 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0 | 0 | 2021-12 | 0 | 0
1784 | CR0014253 | CTASK0029396 | Closed | OPUS-SPC | Toai Phan | 16 | 12 |  |  | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | Asia - BKG VIA & Premium Flag field in Standby Module - Further Enhancement | 2021-09-02 07:01 | 2021-09-30 22:00 | 2021-09-24 14:22 | 2021-09-27 08:56 | 2021-09-28 11:31 |  | 2021-10-05 11:30 | 2021-10-05 08:04 | 2021-09-28 14:52 | 2021-10-12 12:00 | CR0014253 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W40 | 2021-10 | 16 | 12 | 33.187 | 1 | 1 | 1 | 0.02 | 183427 | 2.8 | 0 | 0 | 0 | 1 |  | 1 | 5 | 26 | 0 | 0 | 2021-09 | 0 | 0
1785 | CR0014819 | CTASK0033135 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 8 | 8 | 2022-03-25 13:10 | 2022-03-21 13:10 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Deployment] EUA - Cancel Release in EU Full Cntr Release - M/H | 2022-01-25 09:17 | 2022-02-25 21:14 | 2022-02-24 16:18 | 2022-03-02 11:19 | 2022-03-21 11:39 |  | 2022-03-29 08:00 | 2022-03-29 08:00 | 2022-03-23 16:35 | 2022-04-06 12:00 | CR0014819 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2022-W13 | 2022-03 | 43 | 39 | 62.9465 | 2 | 1 | 1 | 0.03 | 193512 | 2.6 | 2 | 0 | 0 | 1 |  | 2 | 6 | 38 | 0.2963 | 0 | 2022-01 | 0 | 0
1786 | CR0014819 | CTASK0031911 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 35 | 31 | 2022-02-18 13:24 | 2022-01-21 13:24 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EUA - Cancel Release in EU Full Cntr Release - M/H | 2022-01-25 09:17 | 2022-02-25 21:14 | 2022-02-24 16:18 | 2022-03-02 11:19 | 2022-03-21 11:39 |  | 2022-03-29 08:00 | 2022-03-29 08:00 | 2022-03-23 16:35 | 2022-04-06 12:00 | CR0014819 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2022-W13 | 2022-03 | 43 | 39 | 62.9465 | 2 | 1 | 1 | 0.03 | 193512 | 2.6 | 2 | 0 | 0 | 1 |  | 2 | 6 | 38 | 0.2963 | 0 | 2022-01 | 0 | 0
1787 | CR0012337 | CTASK0027730 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 12 | 12 | 2021-06-30 12:26 | 2021-06-23 12:26 | Container | Service Management | Trans S/O |  |  |  | [202106] PARIS Phase Zero Roll out to Spain & Portugal | 2021-06-23 08:56 | 2021-07-16 19:00 | 2021-07-08 13:10 | 2021-08-23 07:21 | 2021-10-28 08:56 |  | 2021-11-03 21:56 | 2021-11-03 09:16 | 2021-10-29 08:39 | 2021-11-10 12:00 | CR0012337 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 62 | 64 | 133.5412 | 4 | 1 | 2 | 0.02 | 183432 | 2.3 | 0 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.043478 | 0.22222 | 2021-06 | 0 | 0
1788 | CR0012337 | CTASK0027731 | Closed | OPUS-TRS | Giang Nguyen Hoang | 19 | 19 | 2021-06-30 12:27 | 2021-06-23 12:27 | Container | Service Management | Trans S/O |  |  |  | [202106] PARIS Phase Zero Roll out to Spain & Portugal | 2021-06-23 08:56 | 2021-07-16 19:00 | 2021-07-08 13:10 | 2021-08-23 07:21 | 2021-10-28 08:56 |  | 2021-11-03 21:56 | 2021-11-03 09:16 | 2021-10-29 08:39 | 2021-11-10 12:00 | CR0012337 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 62 | 64 | 133.5412 | 4 | 1 | 2 | 0.02 | 183440 | 2.3 | 0 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0 | 0 | 2021-06 | 0 | 0
1789 | CR0012337 | CTASK0027876 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 18 | 20 | 2021-07-31 07:52 | 2021-07-02 07:52 | Container | Service Management | Trans S/O |  |  |  | [202107] PARIS Phase Zero Roll out to Spain & Portugal | 2021-06-23 08:56 | 2021-07-16 19:00 | 2021-07-08 13:10 | 2021-08-23 07:21 | 2021-10-28 08:56 |  | 2021-11-03 21:56 | 2021-11-03 09:16 | 2021-10-29 08:39 | 2021-11-10 12:00 | CR0012337 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 62 | 64 | 133.5412 | 4 | 1 | 2 | 0.02 | 183432 | 2.3 | 0 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.043478 | 0.22222 | 2021-06 | 0 | 0
1790 | CR0012337 | CTASK0027877 | Closed | OPUS-TRS | Giang Nguyen Hoang | 13 | 13 | 2021-07-31 07:52 | 2021-07-02 07:52 | Container | Service Management | Trans S/O |  |  |  | [202107] PARIS Phase Zero Roll out to Spain & Portugal | 2021-06-23 08:56 | 2021-07-16 19:00 | 2021-07-08 13:10 | 2021-08-23 07:21 | 2021-10-28 08:56 |  | 2021-11-03 21:56 | 2021-11-03 09:16 | 2021-10-29 08:39 | 2021-11-10 12:00 | CR0012337 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 62 | 64 | 133.5412 | 4 | 1 | 2 | 0.02 | 183440 | 2.3 | 0 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0 | 0 | 2021-06 | 0 | 0
1791 | CR0013247 | CTASK0024899 | Closed | OPUS-PRI | Nhien Nguyen | 31 | 50 | 2021-04-30 08:37 | 2021-04-01 08:37 | Container | Biz Common | Master Data | Partner | Customer Integration |  | GHQ - MDA - Customer Code Creation Duplication check Logic | 2021-01-26 09:11 | 2021-03-31 09:11 | 2021-03-31 09:15 | 2022-03-15 07:12 | 2022-03-24 11:35 |  | 2022-04-05 11:34 | 2022-04-05 13:49 | 2022-03-24 14:17 | 2022-04-21 12:00 | CR0013247 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W14 | 2022-04 | 171 | 150 | 434.0988 | 2 | 2 | 2 | 0.01 | 183364 | 2.3 | 2 | 0 | 0 | 2 |  | 4 | 6 | 18 | 0.54545 | 1.2 | 2021-01 | 0 | 0
1792 | CR0013247 | CTASK0024898 | Closed | OPUS-ACM | Huynh Tuan Khanh | 140 | 100 | 2021-11-15 16:00 | 2021-02-01 08:36 | Container | Biz Common | Master Data | Partner | Customer Integration |  | GHQ - MDA - Customer Code Creation Duplication check Logic | 2021-01-26 09:11 | 2021-03-31 09:11 | 2021-03-31 09:15 | 2022-03-15 07:12 | 2022-03-24 11:35 |  | 2022-04-05 11:34 | 2022-04-05 13:49 | 2022-03-24 14:17 | 2022-04-21 12:00 | CR0013247 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W14 | 2022-04 | 171 | 150 | 434.0988 | 2 | 2 | 2 | 0.01 | 193499 | 1.7 | 2 | 0 | 0 | 2 |  | 4 | 6 | 18 | 0 | 0 | 2021-01 | 0 | 0
1793 | CR0014389 | CTASK0029067 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-09-17 20:39 | 2021-09-01 14:39 | Container | Service Management | Booking/Documentation | Operation | Transshipment |  | [Development][CLT Internal] IB Service Mode Code Missing Update In Transshipment Management Part | 2021-09-07 13:49 | 2021-09-29 22:00 | 2021-09-27 06:43 | 2021-10-12 08:06 | 2021-10-12 12:22 |  | 2021-10-26 08:00 | 2021-10-26 08:00 | 2021-10-12 14:47 | 2021-10-26 08:40 | CR0014389 | Service ManagementBooking/DocumentationOperationTransshipment | OPUS-BKG-M | 2021-W43 | 2021-10 | 40 | 40 | 48.7579 | 4 | 1 | 1 | 0.03 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0.22951 | 0.13043 | 2021-09 | 0 | 0
1794 | CR0014389 | CTASK0029068 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 | 2021-09-24 20:42 | 2021-09-20 00:41 | Container | Service Management | Booking/Documentation | Operation | Transshipment |  | [Testing][CLT Internal] IB Service Mode Code Missing Update In Transshipment Management Part | 2021-09-07 13:49 | 2021-09-29 22:00 | 2021-09-27 06:43 | 2021-10-12 08:06 | 2021-10-12 12:22 |  | 2021-10-26 08:00 | 2021-10-26 08:00 | 2021-10-12 14:47 | 2021-10-26 08:40 | CR0014389 | Service ManagementBooking/DocumentationOperationTransshipment | OPUS-BKG-M | 2021-W43 | 2021-10 | 40 | 40 | 48.7579 | 4 | 1 | 1 | 0.03 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0.22951 | 0.13043 | 2021-09 | 0 | 0
1795 | CR0014389 | CTASK0029066 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-09-17 14:37 | 2021-09-01 14:37 | Container | Service Management | Booking/Documentation | Operation | Transshipment |  | [Design] [CLT Internal] IB Service Mode Code Missing Update In Transshipment Management Part | 2021-09-07 13:49 | 2021-09-29 22:00 | 2021-09-27 06:43 | 2021-10-12 08:06 | 2021-10-12 12:22 |  | 2021-10-26 08:00 | 2021-10-26 08:00 | 2021-10-12 14:47 | 2021-10-26 08:40 | CR0014389 | Service ManagementBooking/DocumentationOperationTransshipment | OPUS-BKG-M | 2021-W43 | 2021-10 | 40 | 40 | 48.7579 | 4 | 1 | 1 | 0.03 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0.22951 | 0.13043 | 2021-09 | 0 | 0
1796 | CR0014389 | CTASK0029070 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-10-29 14:43 | 2021-10-01 14:43 | Container | Service Management | Booking/Documentation | Operation | Transshipment |  | [Deployment][CLT Internal] IB Service Mode Code Missing Update In Transshipment Management Part | 2021-09-07 13:49 | 2021-09-29 22:00 | 2021-09-27 06:43 | 2021-10-12 08:06 | 2021-10-12 12:22 |  | 2021-10-26 08:00 | 2021-10-26 08:00 | 2021-10-12 14:47 | 2021-10-26 08:40 | CR0014389 | Service ManagementBooking/DocumentationOperationTransshipment | OPUS-BKG-M | 2021-W43 | 2021-10 | 40 | 40 | 48.7579 | 4 | 1 | 1 | 0.03 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0.22951 | 0.13043 | 2021-09 | 0 | 0
1797 | CR0014782 | CTASK0031423 | Closed | OPUS-TES | Thai Nguyen | 8 | 10 | 2022-01-31 20:00 | 2022-01-03 06:00 | Container | Service Management | TML INV |  |  |  | [202201] Expand current MT and TM logic to CGCU, TPND, SVSS | 2021-12-13 12:12 | 2021-12-31 20:00 | 2021-12-29 11:23 | 2022-03-04 11:50 | 2022-03-08 09:31 |  | 2022-03-15 09:30 | 2022-03-15 09:21 | 2022-03-10 08:11 | 2022-03-22 12:00 | CR0014782 | Service ManagementTML INV | OPUS-TES | 2022-W11 | 2022-03 | 68 | 69 | 91.8874 | 5 | 1 | 1 | 0.03 | 173249 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0.89474 | 0 | 2021-12 | 0 | 0
1798 | CR0014782 | CTASK0032800 | Closed | OPUS-TES | Thai Nguyen | 5 | 5 | 2022-03-31 09:50 | 2022-03-01 09:50 | Container | Service Management | TML INV |  |  |  | [202203] Expand current MT and TM logic to CGCU, TPND, SVSS | 2021-12-13 12:12 | 2021-12-31 20:00 | 2021-12-29 11:23 | 2022-03-04 11:50 | 2022-03-08 09:31 |  | 2022-03-15 09:30 | 2022-03-15 09:21 | 2022-03-10 08:11 | 2022-03-22 12:00 | CR0014782 | Service ManagementTML INV | OPUS-TES | 2022-W11 | 2022-03 | 68 | 69 | 91.8874 | 5 | 1 | 1 | 0.03 | 173249 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0.89474 | 0 | 2021-12 | 0 | 0
1799 | CR0014782 | CTASK0030770 | Closed | OPUS-TES | Thai Nguyen | 4 | 4 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Service Management | TML INV |  |  |  | [202111] Expand current MT and TM logic to CGCU, TPND, SVSS | 2021-12-13 12:12 | 2021-12-31 20:00 | 2021-12-29 11:23 | 2022-03-04 11:50 | 2022-03-08 09:31 |  | 2022-03-15 09:30 | 2022-03-15 09:21 | 2022-03-10 08:11 | 2022-03-22 12:00 | CR0014782 | Service ManagementTML INV | OPUS-TES | 2022-W11 | 2022-03 | 68 | 69 | 91.8874 | 5 | 1 | 1 | 0.03 | 173249 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0.89474 | 0 | 2021-12 | 0 | 0
1800 | CR0014782 | CTASK0032070 | Closed | OPUS-TES | Thai Nguyen | 10 | 10 | 2022-02-28 19:00 | 2022-02-03 06:00 | Container | Service Management | TML INV |  |  |  | [202202] Expand current MT and TM logic to CGCU, TPND, SVSS | 2021-12-13 12:12 | 2021-12-31 20:00 | 2021-12-29 11:23 | 2022-03-04 11:50 | 2022-03-08 09:31 |  | 2022-03-15 09:30 | 2022-03-15 09:21 | 2022-03-10 08:11 | 2022-03-22 12:00 | CR0014782 | Service ManagementTML INV | OPUS-TES | 2022-W11 | 2022-03 | 68 | 69 | 91.8874 | 5 | 1 | 1 | 0.03 | 173249 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0.89474 | 0 | 2021-12 | 0 | 0
1801 | CR0014782 | CTASK0030898 | Closed | OPUS-TES | Thai Nguyen | 41 | 40 | 2021-12-31 20:00 | 2021-12-01 06:00 | Container | Service Management | TML INV |  |  |  | [202112] Expand current MT and TM logic to CGCU, TPND, SVSS | 2021-12-13 12:12 | 2021-12-31 20:00 | 2021-12-29 11:23 | 2022-03-04 11:50 | 2022-03-08 09:31 |  | 2022-03-15 09:30 | 2022-03-15 09:21 | 2022-03-10 08:11 | 2022-03-22 12:00 | CR0014782 | Service ManagementTML INV | OPUS-TES | 2022-W11 | 2022-03 | 68 | 69 | 91.8874 | 5 | 1 | 1 | 0.03 | 173249 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0.89474 | 0 | 2021-12 | 0 | 0
1802 | CR0014262 | CTASK0028900 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-12-24 17:28 | 2021-12-20 09:28 | Container | Service Management | Product Catalog |  |  |  | [Deployment]Reproduction of CR0012810(GHQ - Add Cnee field into Network Constraint) | 2021-08-31 08:34 | 2021-09-24 18:00 | 2021-09-16 14:56 | 2021-11-29 12:36 | 2021-12-16 07:30 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-23 09:28 | 2022-01-04 12:00 | CR0014262 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W52 | 2021-12 | 44 | 50 | 118.9761 | 6 | 2 | 2 | 0.02 | 193488 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1803 | CR0014262 | CTASK0028899 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-09-22 20:15 | 2021-09-16 09:15 | Container | Service Management | Product Catalog |  |  |  | [Testing]Reproduction of CR0012810(GHQ - Add Cnee field into Network Constraint) | 2021-08-31 08:34 | 2021-09-24 18:00 | 2021-09-16 14:56 | 2021-11-29 12:36 | 2021-12-16 07:30 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-23 09:28 | 2022-01-04 12:00 | CR0014262 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W52 | 2021-12 | 44 | 50 | 118.9761 | 6 | 2 | 2 | 0.02 | 193488 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1804 | CR0014262 | CTASK0031286 | Closed | OPUS-PRD | VInh Bui | 12 | 6 | 2021-12-31 15:29 | 2021-12-01 15:29 | Container | Service Management | Product Catalog |  |  |  | Reproduction of CR0012810(GHQ - Add Cnee field into Network Constraint) [PRD/DEC] | 2021-08-31 08:34 | 2021-09-24 18:00 | 2021-09-16 14:56 | 2021-11-29 12:36 | 2021-12-16 07:30 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-23 09:28 | 2022-01-04 12:00 | CR0014262 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W52 | 2021-12 | 44 | 50 | 118.9761 | 6 | 2 | 2 | 0.02 | 193469 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0 | 0 | 2021-08 | 0 | 0
1805 | CR0014262 | CTASK0028901 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-08-18 14:58 | 2021-08-11 08:57 | Container | Service Management | Product Catalog |  |  |  | [Design] Reproduction of CR0012810(GHQ - Add Cnee field into Network Constraint) | 2021-08-31 08:34 | 2021-09-24 18:00 | 2021-09-16 14:56 | 2021-11-29 12:36 | 2021-12-16 07:30 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-23 09:28 | 2022-01-04 12:00 | CR0014262 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W52 | 2021-12 | 44 | 50 | 118.9761 | 6 | 2 | 2 | 0.02 | 193488 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1806 | CR0014262 | CTASK0028898 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 16 | 16 | 2021-09-08 09:24 | 2021-08-30 09:23 | Container | Service Management | Product Catalog |  |  |  | [Development]Reproduction of CR0012810(GHQ - Add Cnee field into Network Constraint) | 2021-08-31 08:34 | 2021-09-24 18:00 | 2021-09-16 14:56 | 2021-11-29 12:36 | 2021-12-16 07:30 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-23 09:28 | 2022-01-04 12:00 | CR0014262 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W52 | 2021-12 | 44 | 50 | 118.9761 | 6 | 2 | 2 | 0.02 | 193488 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1807 | CR0014262 | CTASK0029409 | Closed | OPUS-PRD | VInh Bui | 12 | 12 | 2021-09-30 06:25 | 2021-09-01 06:25 | Container | Service Management | Product Catalog |  |  |  | Reproduction of CR0012810(GHQ - Add Cnee field into Network Constraint) [PRD/SEP] | 2021-08-31 08:34 | 2021-09-24 18:00 | 2021-09-16 14:56 | 2021-11-29 12:36 | 2021-12-16 07:30 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-23 09:28 | 2022-01-04 12:00 | CR0014262 | Service ManagementProduct Catalog | OPUS-PRD | 2021-W52 | 2021-12 | 44 | 50 | 118.9761 | 6 | 2 | 2 | 0.02 | 193469 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0 | 0 | 2021-08 | 0 | 0
1808 | CR0014241 | CTASK0028362 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-08-05 17:30 | 2021-08-04 09:14 | Container | Service Management | Booking/Documentation | Booking | Booking |  | [Testing]Retrigger of BKGs 301 F/F files to EDIAPI in support of MOBILE APP | 2021-07-27 07:24 | 2021-08-07 | 2021-08-05 14:41 | 2021-10-07 07:40 | 2021-10-07 07:54 |  | 2021-10-19 08:00 | 2021-10-19 08:00 | 2021-10-12 14:49 | 2021-10-26 12:00 | CR0014241 | Service ManagementBooking/DocumentationBookingBooking | OPUS-BKG-M | 2021-W42 | 2021-10 | 54 | 70 | 84.0251 | 4 | 1 | 1 | 0.03 | 193488 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-07 | 0 | 0
1809 | CR0014241 | CTASK0028363 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-10-13 19:27 | 2021-10-11 09:27 | Container | Service Management | Booking/Documentation | Booking | Booking |  | [Deployment]Retrigger of BKGs 301 F/F files to EDIAPI in support of MOBILE APP | 2021-07-27 07:24 | 2021-08-07 | 2021-08-05 14:41 | 2021-10-07 07:40 | 2021-10-07 07:54 |  | 2021-10-19 08:00 | 2021-10-19 08:00 | 2021-10-12 14:49 | 2021-10-26 12:00 | CR0014241 | Service ManagementBooking/DocumentationBookingBooking | OPUS-BKG-M | 2021-W42 | 2021-10 | 54 | 70 | 84.0251 | 4 | 1 | 1 | 0.03 | 193488 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-07 | 0 | 0
1810 | CR0014241 | CTASK0028361 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 30 | 46 | 2021-07-30 19:25 | 2021-07-26 09:25 | Container | Service Management | Booking/Documentation | Booking | Booking |  | [Development]Retrigger of BKGs 301 F/F files to EDIAPI in support of MOBILE APP | 2021-07-27 07:24 | 2021-08-07 | 2021-08-05 14:41 | 2021-10-07 07:40 | 2021-10-07 07:54 |  | 2021-10-19 08:00 | 2021-10-19 08:00 | 2021-10-12 14:49 | 2021-10-26 12:00 | CR0014241 | Service ManagementBooking/DocumentationBookingBooking | OPUS-BKG-M | 2021-W42 | 2021-10 | 54 | 70 | 84.0251 | 4 | 1 | 1 | 0.03 | 193488 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-07 | 0 | 0
1811 | CR0014241 | CTASK0028364 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-07-26 17:30 | 2021-07-22 09:14 | Container | Service Management | Booking/Documentation | Booking | Booking |  | [Design] Retrigger of BKGs 301 F/F files to EDIAPI in support of MOBILE APP | 2021-07-27 07:24 | 2021-08-07 | 2021-08-05 14:41 | 2021-10-07 07:40 | 2021-10-07 07:54 |  | 2021-10-19 08:00 | 2021-10-19 08:00 | 2021-10-12 14:49 | 2021-10-26 12:00 | CR0014241 | Service ManagementBooking/DocumentationBookingBooking | OPUS-BKG-M | 2021-W42 | 2021-10 | 54 | 70 | 84.0251 | 4 | 1 | 1 | 0.03 | 193488 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-07 | 0 | 0
1812 | CR0014557 | CTASK0029789 | Closed | OPUS-PRI | Ngan Nham | 1 | 1 | 2021-10-29 23:00 | 2021-10-28 23:00 | Container | Sales Management | Pricing |  |  |  | [Develop][Kontainers] RFA contract duration | 2021-10-08 14:46 | 2021-12-10 23:00 | 2021-11-04 12:25 | 2021-11-08 13:08 | 2021-11-09 12:21 |  | 2021-11-16 10:00 | 2021-11-16 09:00 | 2021-11-11 08:01 | 2021-11-23 12:01 | CR0014557 | Sales ManagementPricing | OPUS-PRI | 2021-W46 | 2021-11 | 0 | 0 | 38.8014 | 1 | 1 | 1 | 0 | 193461 | 2.9 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0 | 2021-10 | 0 | 0
1813 | CR0014722 | CTASK0030683 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 8 | 8 | 2021-12-31 18:04 | 2021-12-01 18:04 | Container | Service Management | Booking/Documentation | Manifest | Rotterdam (ROCS) | CRN Create | [TEST]ROCS transmission - Change CRN functionality enhancement | 2021-12-13 09:48 | 2021-12-14 22:00 | 2021-12-14 14:03 | 2022-01-10 07:34 | 2022-01-11 15:26 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-20 14:56 | 2022-02-01 12:00 | CR0014722 | Service ManagementBooking/DocumentationManifestRotterdam (ROCS)CRN Create | OPUS-BKG-MFT-E | 2022-W4 | 2022-01 | 35 | 36 | 42.9251 | 4 | 2 | 2 | 0.03 | 193512 | 2.5 | 1 | 2 | 0 | 1 |  | 1 | 9 | 33 | 0.2963 | 0 | 2021-12 | 2 | 1
1814 | CR0014722 | CTASK0030684 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 4 | 4 | 2021-12-31 17:53 | 2021-12-01 17:53 | Container | Service Management | Booking/Documentation | Manifest | Rotterdam (ROCS) | CRN Create | [DEPLOY]ROCS transmission - Change CRN functionality enhancement | 2021-12-13 09:48 | 2021-12-14 22:00 | 2021-12-14 14:03 | 2022-01-10 07:34 | 2022-01-11 15:26 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-20 14:56 | 2022-02-01 12:00 | CR0014722 | Service ManagementBooking/DocumentationManifestRotterdam (ROCS)CRN Create | OPUS-BKG-MFT-E | 2022-W4 | 2022-01 | 35 | 36 | 42.9251 | 4 | 2 | 2 | 0.03 | 193512 | 2.5 | 1 | 2 | 0 | 1 |  | 1 | 9 | 33 | 0.2963 | 0 | 2021-12 | 2 | 1
1815 | CR0014722 | CTASK0030681 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 7 | 8 | 2021-12-31 17:20 | 2021-12-01 17:20 | Container | Service Management | Booking/Documentation | Manifest | Rotterdam (ROCS) | CRN Create | [EST] ROCS transmission - Change CRN functionality enhancement | 2021-12-13 09:48 | 2021-12-14 22:00 | 2021-12-14 14:03 | 2022-01-10 07:34 | 2022-01-11 15:26 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-20 14:56 | 2022-02-01 12:00 | CR0014722 | Service ManagementBooking/DocumentationManifestRotterdam (ROCS)CRN Create | OPUS-BKG-MFT-E | 2022-W4 | 2022-01 | 35 | 36 | 42.9251 | 4 | 2 | 2 | 0.03 | 193606 | 2.1 | 1 | 2 | 0 | 1 |  | 1 | 9 | 33 | 4.25 | 0 | 2021-12 | 2 | 1
1816 | CR0014722 | CTASK0030682 | Closed | OPUS-BKG-MFT-E | Nhut Nguyen Minh | 16 | 16 | 2021-12-31 18:19 | 2021-12-01 18:19 | Container | Service Management | Booking/Documentation | Manifest | Rotterdam (ROCS) | CRN Create | [DEV]ROCS transmission - Change CRN functionality enhancement | 2021-12-13 09:48 | 2021-12-14 22:00 | 2021-12-14 14:03 | 2022-01-10 07:34 | 2022-01-11 15:26 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-20 14:56 | 2022-02-01 12:00 | CR0014722 | Service ManagementBooking/DocumentationManifestRotterdam (ROCS)CRN Create | OPUS-BKG-MFT-E | 2022-W4 | 2022-01 | 35 | 36 | 42.9251 | 4 | 2 | 2 | 0.03 | 193512 | 2.5 | 1 | 2 | 0 | 1 |  | 1 | 9 | 33 | 0.2963 | 0 | 2021-12 | 2 | 1
1817 | CR0014012 | CTASK0027769 | Closed | OPUS-SCG | Trang Duy Thong | 85 | 85 | 2021-07-16 14:37 | 2021-06-01 14:36 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval |  |  | OPUS Enhancement Request - Autogenerated Report for Partner Container Update Weekly Performance Report | 2021-06-07 11:30 | 2021-07-02 22:00 | 2021-07-02 13:15 | 2021-10-20 15:58 | 2021-10-21 08:51 |  | 2021-10-26 08:00 | 2021-10-26 13:14 | 2021-10-21 12:47 | 2021-11-03 12:00 | CR0014012 | Vessel OperationSpecial CargoSPCL CGO Approval | OPUS-SCG | 2021-W43 | 2021-10 | 120 | 120 | 140.854 | 2 | 1 | 1 | 0.04 | 193511 | 1 | 2 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0.81818 | 0 | 2021-06 | 0 | 0
1818 | CR0014012 | CTASK0027365 | Closed | OPUS-SCG | Trang Duy Thong | 35 | 35 |  |  | Container | Vessel Operation | Special Cargo | SPCL CGO Approval |  |  | [Document] OPUS Enhancement Request - Autogenerated Report for Partner Container Update Weekly Performance Report | 2021-06-07 11:30 | 2021-07-02 22:00 | 2021-07-02 13:15 | 2021-10-20 15:58 | 2021-10-21 08:51 |  | 2021-10-26 08:00 | 2021-10-26 13:14 | 2021-10-21 12:47 | 2021-11-03 12:00 | CR0014012 | Vessel OperationSpecial CargoSPCL CGO Approval | OPUS-SCG | 2021-W43 | 2021-10 | 120 | 120 | 140.854 | 2 | 1 | 1 | 0.04 | 193511 | 1 | 2 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0.81818 | 0 | 2021-06 | 0 | 0
1819 | CR0014784 | CTASK0032464 | Closed | OPUS-SPC | Linh Nguyen | 16 | 20 | 2022-03-25 06:24 | 2022-02-14 06:24 | Container | Sales Management | Space Control | Standby Management |  |  | [CLV-SPC] Create Separate Sequential Validation Logic for SINHQ | 2022-01-28 11:31 | 2022-02-18 11:31 | 2022-02-17 06:22 | 2022-03-14 19:17 | 2022-03-16 11:22 |  | 2022-03-25 11:21 | 2022-03-22 09:51 | 2022-03-17 14:31 | 2022-03-29 12:00 | CR0014784 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2022-W12 | 2022-03 | 35 | 30 | 55.9928 | 2 | 1 | 2 | 0.02 | 193464 | 2.9 | 0 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0 | 1.5 | 2022-01 | 0 | 0
1820 | CR0014784 | CTASK0032646 | Closed | OPUS-SPC | Toai Phan | 19 | 10 | 2022-03-25 08:56 | 2022-02-14 08:55 | Container | Sales Management | Space Control | Standby Management |  |  | [CLV-SPC] Create Separate Sequential Validation Logic for SINHQ | 2022-01-28 11:31 | 2022-02-18 11:31 | 2022-02-17 06:22 | 2022-03-14 19:17 | 2022-03-16 11:22 |  | 2022-03-25 11:21 | 2022-03-22 09:51 | 2022-03-17 14:31 | 2022-03-29 12:00 | CR0014784 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2022-W12 | 2022-03 | 35 | 30 | 55.9928 | 2 | 1 | 2 | 0.02 | 183427 | 3.2 | 0 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0 | 0 | 2022-01 | 0 | 0
1821 | CR0013398 | CTASK0028934 | Closed | OPUS-SCE | VInh Bui | 23 | 30 | 2021-08-31 20:38 | 2021-08-01 20:38 | Container | Service Management | SCEM | Customer Order Plan | COP Inquiry |  | [CLT Internal] The value of Master column that is being hard coded as Master in Master/Slave Screen(Aug) | 2021-04-08 16:21 | 2021-08-31 16:21 | 2021-08-27 15:45 | 2021-08-30 07:39 | 2021-10-22 09:59 |  | 2021-11-09 09:00 | 2021-11-09 07:00 | 2021-10-25 15:22 | 2021-11-16 12:00 | CR0013398 | Service ManagementSCEMCustomer Order PlanCOP Inquiry | OPUS-SCE | 2021-W45 | 2021-11 | 88 | 140 | 214.6935 | 6 | 1 | 1 | 0.03 | 193469 | 1.5 | 1 | 0 | 0 | 2 |  | 3 | 9 | 38 | 0 | 0 | 2021-04 | 0 | 0
1822 | CR0013398 | CTASK0024146 | Closed | OPUS-SCE | VInh Bui | 1 | 1 |  |  | Container | Service Management | SCEM | Customer Order Plan | COP Inquiry |  | [Documentation][CLT Internal] The value of Master column that is being hard coded as Master in Master/Slave Screen | 2021-04-08 16:21 | 2021-08-31 16:21 | 2021-08-27 15:45 | 2021-08-30 07:39 | 2021-10-22 09:59 |  | 2021-11-09 09:00 | 2021-11-09 07:00 | 2021-10-25 15:22 | 2021-11-16 12:00 | CR0013398 | Service ManagementSCEMCustomer Order PlanCOP Inquiry | OPUS-SCE | 2021-W45 | 2021-11 | 88 | 140 | 214.6935 | 6 | 1 | 1 | 0.03 | 193469 | 1.5 | 1 | 0 | 0 | 2 |  | 3 | 9 | 38 | 0 | 0 | 2021-04 | 0 | 0
1823 | CR0013398 | CTASK0029342 | Closed | OPUS-SCE | VInh Bui | 11 | 30 | 2021-09-30 08:20 | 2021-09-01 08:20 | Container | Service Management | SCEM | Customer Order Plan | COP Inquiry |  | [CLT Internal] The value of Master column that is being hard coded as Master in Master/Slave Screen(Sep) | 2021-04-08 16:21 | 2021-08-31 16:21 | 2021-08-27 15:45 | 2021-08-30 07:39 | 2021-10-22 09:59 |  | 2021-11-09 09:00 | 2021-11-09 07:00 | 2021-10-25 15:22 | 2021-11-16 12:00 | CR0013398 | Service ManagementSCEMCustomer Order PlanCOP Inquiry | OPUS-SCE | 2021-W45 | 2021-11 | 88 | 140 | 214.6935 | 6 | 1 | 1 | 0.03 | 193469 | 1.5 | 1 | 0 | 0 | 2 |  | 3 | 9 | 38 | 0 | 0 | 2021-04 | 0 | 0
1824 | CR0013398 | CTASK0029854 | Closed | OPUS-SCE | VInh Bui | 8 | 30 | 2021-10-31 18:44 | 2021-10-01 18:43 | Container | Service Management | SCEM | Customer Order Plan | COP Inquiry |  | [CLT Internal] The value of Master column that is being hard coded as Master in Master/Slave Screen(Oct) | 2021-04-08 16:21 | 2021-08-31 16:21 | 2021-08-27 15:45 | 2021-08-30 07:39 | 2021-10-22 09:59 |  | 2021-11-09 09:00 | 2021-11-09 07:00 | 2021-10-25 15:22 | 2021-11-16 12:00 | CR0013398 | Service ManagementSCEMCustomer Order PlanCOP Inquiry | OPUS-SCE | 2021-W45 | 2021-11 | 88 | 140 | 214.6935 | 6 | 1 | 1 | 0.03 | 193469 | 1.5 | 1 | 0 | 0 | 2 |  | 3 | 9 | 38 | 0 | 0 | 2021-04 | 0 | 0
1825 | CR0013398 | CTASK0024154 | Closed | OPUS-SCE | VInh Bui | 29 | 30 | 2020-12-31 13:42 | 2020-12-01 13:42 | Container | Service Management | SCEM | Customer Order Plan | COP Inquiry |  | [CLT Internal] The value of Master column that is being hard coded as Master in Master/Slave Screen | 2021-04-08 16:21 | 2021-08-31 16:21 | 2021-08-27 15:45 | 2021-08-30 07:39 | 2021-10-22 09:59 |  | 2021-11-09 09:00 | 2021-11-09 07:00 | 2021-10-25 15:22 | 2021-11-16 12:00 | CR0013398 | Service ManagementSCEMCustomer Order PlanCOP Inquiry | OPUS-SCE | 2021-W45 | 2021-11 | 88 | 140 | 214.6935 | 6 | 1 | 1 | 0.03 | 193469 | 1.5 | 1 | 0 | 0 | 2 |  | 3 | 9 | 38 | 0 | 0 | 2021-04 | 0 | 0
1826 | CR0013398 | CTASK0028349 | Closed | OPUS-SCE | VInh Bui | 17 | 20 | 2021-07-31 20:53 | 2021-07-01 20:53 | Container | Service Management | SCEM | Customer Order Plan | COP Inquiry |  | [CLT Internal] The value of Master column that is being hard coded as Master in Master/Slave Screen(Jul) | 2021-04-08 16:21 | 2021-08-31 16:21 | 2021-08-27 15:45 | 2021-08-30 07:39 | 2021-10-22 09:59 |  | 2021-11-09 09:00 | 2021-11-09 07:00 | 2021-10-25 15:22 | 2021-11-16 12:00 | CR0013398 | Service ManagementSCEMCustomer Order PlanCOP Inquiry | OPUS-SCE | 2021-W45 | 2021-11 | 88 | 140 | 214.6935 | 6 | 1 | 1 | 0.03 | 193469 | 1.5 | 1 | 0 | 0 | 2 |  | 3 | 9 | 38 | 0 | 0 | 2021-04 | 0 | 0
1827 | CR0014416 | CTASK0029968 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing][CLT Internal] KHIB09580600 - Auto Upload BKG Status N and Auto Upload Remark "This booking has been already created" | 2021-10-01 10:02 | 2021-11-26 22:00 | 2021-10-19 14:39 | 2021-11-09 08:33 | 2021-11-09 13:31 |  | 2021-11-16 09:00 | 2021-11-16 09:00 | 2021-11-11 08:18 | 2021-11-23 12:01 | CR0014416 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W46 | 2021-11 | 4 | 4 | 45.957 | 1 | 1 | 1 | 0 | 193525 | 2.3 | 1 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0.41667 | 0.16667 | 2021-10 | 0 | 0
1828 | CR0014752 | CTASK0032245 | Closed | OPUS-TES | Thai Nguyen | 14 | 14 | 2022-02-28 10:36 | 2022-02-07 10:36 | Container | Service Management | TML INV | Agreement | AGMT Creation |  | [202202][CLT Internal] NA * TML INV * Why did chassis rates disappear when new version was created? LGB05069 | 2022-01-04 07:35 | 2022-01-31 20:00 | 2022-01-27 09:16 | 2022-02-21 13:46 | 2022-02-21 14:27 |  | 2022-03-08 09:30 | 2022-03-08 09:21 | 2022-03-03 13:11 | 2022-03-15 12:00 | CR0014752 | Service ManagementTML INVAgreementAGMT Creation | OPUS-TES | 2022-W10 | 2022-03 | 65 | 72 | 63.0796 | 4 | 1 | 1 | 0.05 | 173249 | 3.3 | 1 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0.89474 | 0 | 2022-01 | 0 | 0
1829 | CR0014752 | CTASK0031421 | Closed | OPUS-TES | Thai Nguyen | 46 | 45 | 2022-01-31 20:00 | 2022-01-03 06:00 | Container | Service Management | TML INV | Agreement | AGMT Creation |  | [202201][CLT Internal] NA * TML INV * Why did chassis rates disappear when new version was created? LGB05069 | 2022-01-04 07:35 | 2022-01-31 20:00 | 2022-01-27 09:16 | 2022-02-21 13:46 | 2022-02-21 14:27 |  | 2022-03-08 09:30 | 2022-03-08 09:21 | 2022-03-03 13:11 | 2022-03-15 12:00 | CR0014752 | Service ManagementTML INVAgreementAGMT Creation | OPUS-TES | 2022-W10 | 2022-03 | 65 | 72 | 63.0796 | 4 | 1 | 1 | 0.05 | 173249 | 3.3 | 1 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0.89474 | 0 | 2022-01 | 0 | 0
1830 | CR0014752 | CTASK0030446 | Closed | OPUS-TES | Thai Nguyen | 5 | 5 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Service Management | TML INV | Agreement | AGMT Creation |  | [202111][CLT Internal] NA * TML INV * Why did chassis rates disappear when new version was created? LGB05069 | 2022-01-04 07:35 | 2022-01-31 20:00 | 2022-01-27 09:16 | 2022-02-21 13:46 | 2022-02-21 14:27 |  | 2022-03-08 09:30 | 2022-03-08 09:21 | 2022-03-03 13:11 | 2022-03-15 12:00 | CR0014752 | Service ManagementTML INVAgreementAGMT Creation | OPUS-TES | 2022-W10 | 2022-03 | 65 | 72 | 63.0796 | 4 | 1 | 1 | 0.05 | 173249 | 3.3 | 1 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0.89474 | 0 | 2022-01 | 0 | 0
1831 | CR0014752 | CTASK0032769 | Closed | OPUS-TES | Thai Nguyen | 8 | 8 | 2022-03-31 14:08 | 2022-03-01 14:08 | Container | Service Management | TML INV | Agreement | AGMT Creation |  | [202203][CLT Internal] NA * TML INV * Why did chassis rates disappear when new version was created? LGB05069 | 2022-01-04 07:35 | 2022-01-31 20:00 | 2022-01-27 09:16 | 2022-02-21 13:46 | 2022-02-21 14:27 |  | 2022-03-08 09:30 | 2022-03-08 09:21 | 2022-03-03 13:11 | 2022-03-15 12:00 | CR0014752 | Service ManagementTML INVAgreementAGMT Creation | OPUS-TES | 2022-W10 | 2022-03 | 65 | 72 | 63.0796 | 4 | 1 | 1 | 0.05 | 173249 | 3.3 | 1 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0.89474 | 0 | 2022-01 | 0 | 0
1832 | CR0014964 | CTASK0032072 | Closed | OPUS-TES | Thai Nguyen | 40 | 40 | 2022-02-28 19:00 | 2022-02-03 06:00 | Container | Service Management | TML INV |  |  |  | [202202] Change of the location reference upon TES AP I/F to ERP | 2022-01-27 09:22 | 2022-02-16 09:21 | 2022-02-15 15:15 | 2022-02-21 13:50 | 2022-02-21 14:29 |  | 2022-03-02 09:30 | 2022-03-02 09:12 | 2022-02-22 15:30 | 2022-03-09 12:00 | CR0014964 | Service ManagementTML INV | OPUS-TES | 2022-W9 | 2022-03 | 46 | 46 | 34.0057 | 2 | 1 | 1 | 0.06 | 173249 | 3.3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.89474 | 0 | 2022-01 | 0 | 0
1833 | CR0014964 | CTASK0031850 | Closed | OPUS-TES | Thai Nguyen | 6 | 6 | 2022-01-31 15:07 | 2022-01-03 15:07 | Container | Service Management | TML INV |  |  |  | [202201] Change of the location reference upon TES AP I/F to ERP | 2022-01-27 09:22 | 2022-02-16 09:21 | 2022-02-15 15:15 | 2022-02-21 13:50 | 2022-02-21 14:29 |  | 2022-03-02 09:30 | 2022-03-02 09:12 | 2022-02-22 15:30 | 2022-03-09 12:00 | CR0014964 | Service ManagementTML INV | OPUS-TES | 2022-W9 | 2022-03 | 46 | 46 | 34.0057 | 2 | 1 | 1 | 0.06 | 173249 | 3.3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.89474 | 0 | 2022-01 | 0 | 0
1834 | CR0013505 | CTASK0026346 | Closed | OPUS-BKG-IB | Thuc Tran | 28 | 28 | 2021-04-23 17:30 | 2021-04-05 09:00 | Container | Service Management | Booking/Documentation | Inbound Doc |  |  | [Development+Testing+Deployment] Add new ID in Hard Coding Setup (User) | 2021-06-02 08:25 | 2021-06-30 21:24 | 2021-06-25 13:29 | 2022-03-22 09:53 | 2022-04-07 11:43 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-04-07 16:34 | 2022-06-07 12:00 | CR0013505 | Service ManagementBooking/DocumentationInbound Doc | OPUS-BKG-IB | 2022-W22 | 2022-05 | 32 | 32 | 362.9829 | 2 | 1 | 1 | 0 | 173280 | 2.5 | 1 | 0 | 0 | 1 |  | 4 | 7 | 26 | 0.375 | 1 | 2021-06 | 0 | 0
1835 | CR0013505 | CTASK0025983 | Closed | OPUS-BKG-IB | Thuc Tran | 4 | 4 | 2021-03-22 17:30 | 2021-03-17 09:00 | Container | Service Management | Booking/Documentation | Inbound Doc |  |  | [Estimation] Add new ID in Hard Coding Setup (User) | 2021-06-02 08:25 | 2021-06-30 21:24 | 2021-06-25 13:29 | 2022-03-22 09:53 | 2022-04-07 11:43 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-04-07 16:34 | 2022-06-07 12:00 | CR0013505 | Service ManagementBooking/DocumentationInbound Doc | OPUS-BKG-IB | 2022-W22 | 2022-05 | 32 | 32 | 362.9829 | 2 | 1 | 1 | 0 | 173280 | 2.5 | 1 | 0 | 0 | 1 |  | 4 | 7 | 26 | 0.375 | 1 | 2021-06 | 0 | 0
1836 | CR0014344 | CTASK0028816 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-08-20 20:51 | 2021-08-17 00:51 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Design][CLT Internal] Group VVD/Port Assign screen can't update the route | 2021-09-07 13:47 | 2021-09-16 | 2021-09-13 15:42 | 2021-09-28 12:43 | 2021-09-28 12:46 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-09-28 14:53 | 2021-10-12 08:24 | CR0014344 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2021-W41 | 2021-10 | 30 | 30 | 34.7589 | 4 | 1 | 1 | 0.04 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 9 | 26 | 0.22951 | 0.13043 | 2021-09 | 0 | 0
1837 | CR0014344 | CTASK0028820 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-10-29 20:56 | 2021-10-01 00:56 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Deployment][CLT Internal] Group VVD/Port Assign screen can't update the route | 2021-09-07 13:47 | 2021-09-16 | 2021-09-13 15:42 | 2021-09-28 12:43 | 2021-09-28 12:46 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-09-28 14:53 | 2021-10-12 08:24 | CR0014344 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2021-W41 | 2021-10 | 30 | 30 | 34.7589 | 4 | 1 | 1 | 0.04 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 9 | 26 | 0.22951 | 0.13043 | 2021-09 | 0 | 0
1838 | CR0014344 | CTASK0028817 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-08-27 20:53 | 2021-08-23 00:53 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Development][CLT Internal] Group VVD/Port Assign screen can't update the route | 2021-09-07 13:47 | 2021-09-16 | 2021-09-13 15:42 | 2021-09-28 12:43 | 2021-09-28 12:46 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-09-28 14:53 | 2021-10-12 08:24 | CR0014344 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2021-W41 | 2021-10 | 30 | 30 | 34.7589 | 4 | 1 | 1 | 0.04 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 9 | 26 | 0.22951 | 0.13043 | 2021-09 | 0 | 0
1839 | CR0014344 | CTASK0028818 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-09-15 22:54 | 2021-09-06 00:54 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Testing][CLT Internal] Group VVD/Port Assign screen can't update the route | 2021-09-07 13:47 | 2021-09-16 | 2021-09-13 15:42 | 2021-09-28 12:43 | 2021-09-28 12:46 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-09-28 14:53 | 2021-10-12 08:24 | CR0014344 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2021-W41 | 2021-10 | 30 | 30 | 34.7589 | 4 | 1 | 1 | 0.04 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 9 | 26 | 0.22951 | 0.13043 | 2021-09 | 0 | 0
1840 | CR0013674 | CTASK0027030 | Closed | OPUS-VSK | Linh Nguyen | 70 | 70 | 2021-07-30 16:00 | 2021-05-24 07:00 | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Creation |  | [VSK-CLV] Validation and processing of incoming EDI for ATA/ATB/ATD to actualised OPUS Costal Schedule | 2021-05-31 10:14 | 2021-07-30 16:00 | 2021-07-30 07:57 |  | 2022-11-17 12:21 |  | 2022-03-01 12:20 | 2022-01-20 12:30 | 2022-12-07 12:41 | 2022-12-20 12:00 | CR0013674 | Vessel OperationVessel ScheduleActual SKDActual SKD Creation | OPUS-VSK | 2022-W9 | 2022-03 | 198 | 198 | 274.0875 | 5 | 1 | 2 | 0.03 | 193464 | 2.2 | 6 | 6 | 0 | 2 |  | 3 | 7 | 38 | 0.375 | 1.5 | 2021-05 | 6 | 1
1841 | CR0013674 | CTASK0032026 | Closed | OPUS-VSK | Linh Nguyen | 24 | 24 |  |  | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Creation |  | [CLV-VSK][Validation and processing of incoming EDI for ATA/ATB/ATD to actualised OPUS Costal Schedule] | 2021-05-31 10:14 | 2021-07-30 16:00 | 2021-07-30 07:57 |  | 2022-11-17 12:21 |  | 2022-03-01 12:20 | 2022-01-20 12:30 | 2022-12-07 12:41 | 2022-12-20 12:00 | CR0013674 | Vessel OperationVessel ScheduleActual SKDActual SKD Creation | OPUS-VSK | 2022-W9 | 2022-03 | 198 | 198 | 274.0875 | 5 | 1 | 2 | 0.03 | 193464 | 2.2 | 6 | 6 | 0 | 2 |  | 3 | 7 | 38 | 0.375 | 1.5 | 2021-05 | 6 | 1
1842 | CR0013674 | CTASK0027029 | Closed | OPUS-VSK | Thuan Tran | 70 | 70 | 2021-07-30 16:00 | 2021-05-24 07:00 | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Creation |  | [VSK-CLV] Validation and processing of incoming EDI for ATA/ATB/ATD to actualised OPUS Costal Schedule | 2021-05-31 10:14 | 2021-07-30 16:00 | 2021-07-30 07:57 |  | 2022-11-17 12:21 |  | 2022-03-01 12:20 | 2022-01-20 12:30 | 2022-12-07 12:41 | 2022-12-20 12:00 | CR0013674 | Vessel OperationVessel ScheduleActual SKDActual SKD Creation | OPUS-VSK | 2022-W9 | 2022-03 | 198 | 198 | 274.0875 | 5 | 1 | 2 | 0.03 | 183423 | 2.5 | 6 | 6 | 0 | 2 |  | 3 | 7 | 38 | 0 | 0 | 2021-05 | 6 | 1
1843 | CR0013674 | CTASK0029931 | Closed | OPUS-VSK | Linh Nguyen | 14 | 14 |  |  | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Creation |  | [CLV-VSK]Validation and processing of incoming EDI for ATA/ATB/ATD to actualised OPUS Costal Schedule | 2021-05-31 10:14 | 2021-07-30 16:00 | 2021-07-30 07:57 |  | 2022-11-17 12:21 |  | 2022-03-01 12:20 | 2022-01-20 12:30 | 2022-12-07 12:41 | 2022-12-20 12:00 | CR0013674 | Vessel OperationVessel ScheduleActual SKDActual SKD Creation | OPUS-VSK | 2022-W9 | 2022-03 | 198 | 198 | 274.0875 | 5 | 1 | 2 | 0.03 | 193464 | 2.2 | 6 | 6 | 0 | 2 |  | 3 | 7 | 38 | 0.375 | 1.5 | 2021-05 | 6 | 1
1844 | CR0013674 | CTASK0031554 | Closed | OPUS-VSK | Linh Nguyen | 20 | 20 | 2022-01-31 10:11 | 2022-01-01 10:11 | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Creation |  | [CLV-VSK][Validation and processing of incoming EDI for ATA/ATB/ATD to actualised OPUS Costal Schedule] | 2021-05-31 10:14 | 2021-07-30 16:00 | 2021-07-30 07:57 |  | 2022-11-17 12:21 |  | 2022-03-01 12:20 | 2022-01-20 12:30 | 2022-12-07 12:41 | 2022-12-20 12:00 | CR0013674 | Vessel OperationVessel ScheduleActual SKDActual SKD Creation | OPUS-VSK | 2022-W9 | 2022-03 | 198 | 198 | 274.0875 | 5 | 1 | 2 | 0.03 | 193464 | 2.2 | 6 | 6 | 0 | 2 |  | 3 | 7 | 38 | 0.375 | 1.5 | 2021-05 | 6 | 1
1845 | CR0014111 | CTASK0028275 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 1 | 1 |  |  | Container | Service Management | Booking/Documentation |  |  |  | [Document]Hard Coding required for SOC Sanctioned CTNRs (base on Prefix) | 2021-08-04 14:49 | 2021-09-08 14:49 | 2021-09-03 11:36 | 2021-12-01 13:12 | 2021-12-02 06:11 |  | 2021-12-14 08:11 | 2021-12-14 08:16 | 2021-12-09 11:20 | 2021-12-22 12:00 | CR0014111 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W50 | 2021-12 | 119 | 118 | 131.7236 | 8 | 2 | 3 | 0.04 | 193488 | 2.1 | 1 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1846 | CR0014111 | CTASK0028415 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 10 | 10 | 2021-12-10 22:15 | 2021-12-06 09:15 | Container | Service Management | Booking/Documentation |  |  |  | [Deployment]Hard Coding required for SOC Sanctioned CTNRs (base on Prefix) | 2021-08-04 14:49 | 2021-09-08 14:49 | 2021-09-03 11:36 | 2021-12-01 13:12 | 2021-12-02 06:11 |  | 2021-12-14 08:11 | 2021-12-14 08:16 | 2021-12-09 11:20 | 2021-12-22 12:00 | CR0014111 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W50 | 2021-12 | 119 | 118 | 131.7236 | 8 | 2 | 3 | 0.04 | 193488 | 2.1 | 1 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1847 | CR0014111 | CTASK0030025 | Closed | OPUS-TRS | Giang Nguyen Hoang | 20 | 15 |  |  | Container | Service Management | Booking/Documentation |  |  |  | [202110] Hard Coding required for SOC Sanctioned CTNRs (base on Prefix) | 2021-08-04 14:49 | 2021-09-08 14:49 | 2021-09-03 11:36 | 2021-12-01 13:12 | 2021-12-02 06:11 |  | 2021-12-14 08:11 | 2021-12-14 08:16 | 2021-12-09 11:20 | 2021-12-22 12:00 | CR0014111 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W50 | 2021-12 | 119 | 118 | 131.7236 | 8 | 2 | 3 | 0.04 | 183440 | 2.4 | 1 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0 | 0 | 2021-08 | 0 | 0
1848 | CR0014111 | CTASK0028414 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 12 | 12 | 2021-09-08 09:50 | 2021-08-30 09:50 | Container | Service Management | Booking/Documentation |  |  |  | [Testing]Hard Coding required for SOC Sanctioned CTNRs (base on Prefix) | 2021-08-04 14:49 | 2021-09-08 14:49 | 2021-09-03 11:36 | 2021-12-01 13:12 | 2021-12-02 06:11 |  | 2021-12-14 08:11 | 2021-12-14 08:16 | 2021-12-09 11:20 | 2021-12-22 12:00 | CR0014111 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W50 | 2021-12 | 119 | 118 | 131.7236 | 8 | 2 | 3 | 0.04 | 193488 | 2.1 | 1 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1849 | CR0014111 | CTASK0028312 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 12 | 12 | 2021-07-21 17:31 | 2021-07-19 09:24 | Container | Service Management | Booking/Documentation |  |  |  | [Design] Hard Coding required for SOC Sanctioned CTNRs (base on Prefix) | 2021-08-04 14:49 | 2021-09-08 14:49 | 2021-09-03 11:36 | 2021-12-01 13:12 | 2021-12-02 06:11 |  | 2021-12-14 08:11 | 2021-12-14 08:16 | 2021-12-09 11:20 | 2021-12-22 12:00 | CR0014111 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W50 | 2021-12 | 119 | 118 | 131.7236 | 8 | 2 | 3 | 0.04 | 193488 | 2.1 | 1 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1850 | CR0014111 | CTASK0030014 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 11 | 15 |  |  | Container | Service Management | Booking/Documentation |  |  |  | [202110] Hard Coding required for SOC Sanctioned CTNRs (base on Prefix) | 2021-08-04 14:49 | 2021-09-08 14:49 | 2021-09-03 11:36 | 2021-12-01 13:12 | 2021-12-02 06:11 |  | 2021-12-14 08:11 | 2021-12-14 08:16 | 2021-12-09 11:20 | 2021-12-22 12:00 | CR0014111 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W50 | 2021-12 | 119 | 118 | 131.7236 | 8 | 2 | 3 | 0.04 | 183432 | 2.4 | 1 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0.043478 | 0.22222 | 2021-08 | 0 | 0
1851 | CR0014111 | CTASK0028413 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 49 | 49 | 2021-08-20 19:18 | 2021-08-09 09:18 | Container | Service Management | Booking/Documentation |  |  |  | [Development]Hard Coding required for SOC Sanctioned CTNRs (base on Prefix) | 2021-08-04 14:49 | 2021-09-08 14:49 | 2021-09-03 11:36 | 2021-12-01 13:12 | 2021-12-02 06:11 |  | 2021-12-14 08:11 | 2021-12-14 08:16 | 2021-12-09 11:20 | 2021-12-22 12:00 | CR0014111 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W50 | 2021-12 | 119 | 118 | 131.7236 | 8 | 2 | 3 | 0.04 | 193488 | 2.1 | 1 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1852 | CR0014111 | CTASK0030436 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 5 | 5 | 2021-11-19 22:21 | 2021-11-09 22:21 | Container | Service Management | Booking/Documentation |  |  |  | [Development]Hard Coding required for SOC Sanctioned CTNRs (base on Prefix) | 2021-08-04 14:49 | 2021-09-08 14:49 | 2021-09-03 11:36 | 2021-12-01 13:12 | 2021-12-02 06:11 |  | 2021-12-14 08:11 | 2021-12-14 08:16 | 2021-12-09 11:20 | 2021-12-22 12:00 | CR0014111 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W50 | 2021-12 | 119 | 118 | 131.7236 | 8 | 2 | 3 | 0.04 | 193488 | 2.1 | 1 | 0 | 0 | 2 |  | 2 | 6 | 26 | 0.53659 | 0 | 2021-08 | 0 | 0
1853 | CR0014635 | CTASK0030547 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2022-02-16 | 2022-02-09 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | [Deployment] EUA Regulatory- Egypt ACI New category " Egypt ACID Confirmation" in the attachment dropdown list to be added | 2021-11-30 06:56 | 2021-12-24 22:00 | 2021-12-22 08:17 | 2022-02-08 07:23 | 2022-02-10 08:59 |  | 2022-02-15 09:00 | 2022-02-15 08:00 | 2022-02-11 05:30 | 2022-02-22 12:00 | CR0014635 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2022-W7 | 2022-02 | 20 | 20 | 77.086 | 3 | 1 | 1 | 0.01 | 193525 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 10 | 30 | 0.41667 | 0.16667 | 2021-11 | 0 | 0
1854 | CR0014635 | CTASK0030545 | Closed | OPUS-BKG-EBKG | Vinh Tran | 6 | 6 | 2021-11-16 | 2021-11-15 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | [Design] EUA Regulatory- Egypt ACI New category " Egypt ACID Confirmation" in the attachment dropdown list to be added | 2021-11-30 06:56 | 2021-12-24 22:00 | 2021-12-22 08:17 | 2022-02-08 07:23 | 2022-02-10 08:59 |  | 2022-02-15 09:00 | 2022-02-15 08:00 | 2022-02-11 05:30 | 2022-02-22 12:00 | CR0014635 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2022-W7 | 2022-02 | 20 | 20 | 77.086 | 3 | 1 | 1 | 0.01 | 193525 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 10 | 30 | 0.41667 | 0.16667 | 2021-11 | 0 | 0
1855 | CR0014635 | CTASK0030546 | Closed | OPUS-BKG-EBKG | Vinh Tran | 10 | 10 | 2021-12-18 | 2021-12-06 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | [Development+Testing] EUA Regulatory- Egypt ACI New category " Egypt ACID Confirmation" in the attachment dropdown list to be added | 2021-11-30 06:56 | 2021-12-24 22:00 | 2021-12-22 08:17 | 2022-02-08 07:23 | 2022-02-10 08:59 |  | 2022-02-15 09:00 | 2022-02-15 08:00 | 2022-02-11 05:30 | 2022-02-22 12:00 | CR0014635 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2022-W7 | 2022-02 | 20 | 20 | 77.086 | 3 | 1 | 1 | 0.01 | 193525 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 10 | 30 | 0.41667 | 0.16667 | 2021-11 | 0 | 0
1856 | CR0014216 | CTASK0030108 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 74 | 70 | 2021-11-30 14:20 | 2021-10-22 14:20 | Container | Service Management | Booking/Documentation | Inbound Doc | Pick-Up Notice | Pick-Up Notice Send | [Development+ Testing+ Deployment] NA * CTM * Supplemental CR to CR0010761 revising mask pickup logic to include equalized yards | 2021-11-01 17:28 | 2021-12-10 21:56 | 2021-12-10 15:12 | 2022-02-17 17:06 | 2022-02-24 15:35 |  | 2022-03-08 08:00 | 2022-03-08 07:30 | 2022-02-28 15:02 | 2022-03-15 12:00 | CR0014216 | Service ManagementBooking/DocumentationInbound DocPick-Up NoticePick-Up Notice Send | OPUS-BKG-IB | 2022-W10 | 2022-03 | 74 | 70 | 126.6058 | 1 | 1 | 1 | 0.02 | 193512 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0.2963 | 0 | 2021-11 | 0 | 0
1857 | CR0015087 | CTASK0032207 | Closed | OPUS-SCO | Chuong Ta | 75 | 70 | 2022-02-28 16:50 | 2022-02-07 16:50 | Container | Statement Management | Statement Account Receivable |  |  |  | [Feb-2022] OPUS Source Code Clean Up - ACCT | 2022-02-10 11:21 | 2022-02-28 11:20 | 2022-02-17 15:52 |  | 2022-02-17 16:04 |  | 2022-02-22 10:00 | 2022-02-22 10:00 | 2022-02-18 12:06 | 2022-03-02 07:30 | CR0015087 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W8 | 2022-02 | 75 | 70 | 11.9439 | 1 | 1 | 1 | 0.24 | 183379 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 14 | 30 | 0.32 | 0.375 | 2022-02 | 0 | 0
1858 | CR0013380 | CTASK0024118 | Closed | OPUS-VSK | Linh Nguyen | 15 | 13 | 2021-01-20 09:04 | 2020-12-14 09:04 | Container | Vessel Operation | Vessel Schedule | Feeder SKD |  |  | [CLV][CLT Internal] Feeder SKD reverse call enhancement | 2020-12-17 08:17 | 2021-01-30 08:16 | 2021-01-13 08:52 | 2021-10-07 12:28 | 2021-10-08 07:40 |  | 2021-10-19 08:00 | 2021-10-19 10:38 | 2021-10-12 14:53 | 2021-10-27 12:00 | CR0013380 | Vessel OperationVessel ScheduleFeeder SKD | OPUS-VSK | 2021-W42 | 2021-10 | 15 | 13 | 305.9885 | 2 | 1 | 1 | 0 | 193464 | 1.8 | 1 | 0 | 0 | 1 |  | 4 | 6 | 26 | 0.375 | 0 | 2020-12 | 0 | 0
1859 | CR0013380 | CTASK0024117 | Closed | OPUS-VSK | Linh Nguyen | 1 | 1 |  |  | Container | Vessel Operation | Vessel Schedule | Feeder SKD |  |  | [Documentation][CLT Internal] Feeder SKD reverse call enhancement | 2020-12-17 08:17 | 2021-01-30 08:16 | 2021-01-13 08:52 | 2021-10-07 12:28 | 2021-10-08 07:40 |  | 2021-10-19 08:00 | 2021-10-19 10:38 | 2021-10-12 14:53 | 2021-10-27 12:00 | CR0013380 | Vessel OperationVessel ScheduleFeeder SKD | OPUS-VSK | 2021-W42 | 2021-10 | 15 | 13 | 305.9885 | 2 | 1 | 1 | 0 | 193464 | 1.8 | 1 | 0 | 0 | 1 |  | 4 | 6 | 26 | 0.375 | 0 | 2020-12 | 0 | 0
1860 | CR0014428 | CTASK0029943 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 8 | 8 | 2021-12-31 17:23 | 2021-12-01 17:23 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [EST]ROOT Project Squad 16 - Booking Reconciliation Process - SAF Filling | 2021-10-21 14:25 | 2021-12-17 22:00 | 2021-12-17 13:22 | 2022-02-17 16:54 | 2022-02-22 14:38 |  | 2022-03-08 08:37 | 2022-03-08 08:03 | 2022-02-22 15:28 | 2022-03-17 12:00 | CR0014428 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 123 | 128 | 137.7587 | 4 | 1 | 2 | 0.04 | 193606 | 2 | 1 | 1 | 0 | 2 |  | 2 | 8 | 38 | 4.25 | 0 | 2021-10 | 1 | 1
1861 | CR0014428 | CTASK0029946 | Closed | OPUS-BKG-MFT-E | Nhut Nguyen Minh | 21 | 24 | 2021-12-31 09:50 | 2021-12-01 09:50 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [TEST]ROOT Project Squad 16 - Booking Reconciliation Process - SAF Filling | 2021-10-21 14:25 | 2021-12-17 22:00 | 2021-12-17 13:22 | 2022-02-17 16:54 | 2022-02-22 14:38 |  | 2022-03-08 08:37 | 2022-03-08 08:03 | 2022-02-22 15:28 | 2022-03-17 12:00 | CR0014428 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 123 | 128 | 137.7587 | 4 | 1 | 2 | 0.04 | 193512 | 2.3 | 1 | 1 | 0 | 2 |  | 2 | 8 | 38 | 0.2963 | 0 | 2021-10 | 1 | 1
1862 | CR0014428 | CTASK0029945 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 87 | 88 | 2021-12-31 21:56 | 2021-12-01 21:56 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [DEV]ROOT Project Squad 16 - Booking Reconciliation Process - SAF Filling | 2021-10-21 14:25 | 2021-12-17 22:00 | 2021-12-17 13:22 | 2022-02-17 16:54 | 2022-02-22 14:38 |  | 2022-03-08 08:37 | 2022-03-08 08:03 | 2022-02-22 15:28 | 2022-03-17 12:00 | CR0014428 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 123 | 128 | 137.7587 | 4 | 1 | 2 | 0.04 | 193606 | 2 | 1 | 1 | 0 | 2 |  | 2 | 8 | 38 | 4.25 | 0 | 2021-10 | 1 | 1
1863 | CR0014428 | CTASK0029947 | Closed | OPUS-BKG-MFT-E | Nhut Nguyen Minh | 7 | 8 | 2021-12-31 09:54 | 2021-12-01 09:54 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Deploy]ROOT Project Squad 16 - Booking Reconciliation Process - SAF Filling | 2021-10-21 14:25 | 2021-12-17 22:00 | 2021-12-17 13:22 | 2022-02-17 16:54 | 2022-02-22 14:38 |  | 2022-03-08 08:37 | 2022-03-08 08:03 | 2022-02-22 15:28 | 2022-03-17 12:00 | CR0014428 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 123 | 128 | 137.7587 | 4 | 1 | 2 | 0.04 | 193512 | 2.3 | 1 | 1 | 0 | 2 |  | 2 | 8 | 38 | 0.2963 | 0 | 2021-10 | 1 | 1
1864 | CR0014386 | CTASK0029358 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 32 | 32 | 2021-11-30 19:41 | 2021-11-01 19:41 | Container | Service Management | Booking/Documentation | Manifest | UAE Customs EDI (Import) |  | [Test + Deploy] A new report to generate "Export Load List" as per UAE port & Customs requirement | 2021-10-20 09:43 | 2021-12-23 22:00 | 2021-12-23 12:55 | 2022-03-02 07:11 | 2022-03-07 15:03 |  | 2022-03-22 08:03 | 2022-03-22 08:57 | 2022-03-10 08:14 | 2022-03-29 12:00 | CR0014386 | Service ManagementBooking/DocumentationManifestUAE Customs EDI (Import) | OPUS-BKG-MFT-A | 2022-W12 | 2022-03 | 87 | 88 | 152.9303 | 3 | 1 | 1 | 0.02 | 193606 | 2 | 1 | 0 | 0 | 1 |  | 3 | 7 | 38 | 4.25 | 0 | 2021-10 | 0 | 0
1865 | CR0014386 | CTASK0029357 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 48 | 48 | 2021-10-15 18:59 | 2021-09-23 18:58 | Container | Service Management | Booking/Documentation | Manifest | UAE Customs EDI (Import) |  | [Develop] A new report to generate "Export Load List" as per UAE port & Customs requirement | 2021-10-20 09:43 | 2021-12-23 22:00 | 2021-12-23 12:55 | 2022-03-02 07:11 | 2022-03-07 15:03 |  | 2022-03-22 08:03 | 2022-03-22 08:57 | 2022-03-10 08:14 | 2022-03-29 12:00 | CR0014386 | Service ManagementBooking/DocumentationManifestUAE Customs EDI (Import) | OPUS-BKG-MFT-A | 2022-W12 | 2022-03 | 87 | 88 | 152.9303 | 3 | 1 | 1 | 0.02 | 193606 | 2 | 1 | 0 | 0 | 1 |  | 3 | 7 | 38 | 4.25 | 0 | 2021-10 | 0 | 0
1866 | CR0014386 | CTASK0029309 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 7 | 8 | 2021-09-15 13:20 | 2021-09-08 13:20 | Container | Service Management | Booking/Documentation | Manifest | UAE Customs EDI (Import) |  | [Estimate] A new report to generate "Export Load List" as per UAE port & Customs requirement | 2021-10-20 09:43 | 2021-12-23 22:00 | 2021-12-23 12:55 | 2022-03-02 07:11 | 2022-03-07 15:03 |  | 2022-03-22 08:03 | 2022-03-22 08:57 | 2022-03-10 08:14 | 2022-03-29 12:00 | CR0014386 | Service ManagementBooking/DocumentationManifestUAE Customs EDI (Import) | OPUS-BKG-MFT-A | 2022-W12 | 2022-03 | 87 | 88 | 152.9303 | 3 | 1 | 1 | 0.02 | 193606 | 2 | 1 | 0 | 0 | 1 |  | 3 | 7 | 38 | 4.25 | 0 | 2021-10 | 0 | 0
1867 | CR0014667 | CTASK0030894 | Closed | OPUS-TES | Thai Nguyen | 32 | 35 | 2021-12-31 20:00 | 2021-12-01 06:00 | Container | Service Management | TML INV | Invoice | Invoice Inquiry | Invoice Summary | [202112][CLT Internal] AS - TES invoice - VSH1SY210334 (Pay days) | 2021-11-12 12:03 | 2021-12-10 20:00 | 2021-12-09 08:40 | 2022-02-10 14:16 | 2022-02-10 15:29 |  | 2022-02-22 09:30 | 2022-02-22 09:00 | 2022-02-11 16:02 | 2022-03-02 12:00 | CR0014667 | Service ManagementTML INVInvoiceInvoice InquiryInvoice Summary | OPUS-TES | 2022-W8 | 2022-02 | 50 | 53 | 101.8934 | 3 | 1 | 1 | 0.02 | 173249 | 3.1 | 2 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0.89474 | 0 | 2021-11 | 0 | 0
1868 | CR0014667 | CTASK0030223 | Closed | OPUS-TES | Thai Nguyen | 13 | 13 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Service Management | TML INV | Invoice | Invoice Inquiry | Invoice Summary | [202111][CLT Internal] AS - TES invoice - VSH1SY210334 | 2021-11-12 12:03 | 2021-12-10 20:00 | 2021-12-09 08:40 | 2022-02-10 14:16 | 2022-02-10 15:29 |  | 2022-02-22 09:30 | 2022-02-22 09:00 | 2022-02-11 16:02 | 2022-03-02 12:00 | CR0014667 | Service ManagementTML INVInvoiceInvoice InquiryInvoice Summary | OPUS-TES | 2022-W8 | 2022-02 | 50 | 53 | 101.8934 | 3 | 1 | 1 | 0.02 | 173249 | 3.1 | 2 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0.89474 | 0 | 2021-11 | 0 | 0
1869 | CR0014667 | CTASK0032200 | Closed | OPUS-TES | Thai Nguyen | 5 | 5 | 2022-02-28 15:32 | 2022-02-03 15:32 | Container | Service Management | TML INV | Invoice | Invoice Inquiry | Invoice Summary | [202202][CLT Internal] AS - TES invoice - VSH1SY210334 (Pay days) | 2021-11-12 12:03 | 2021-12-10 20:00 | 2021-12-09 08:40 | 2022-02-10 14:16 | 2022-02-10 15:29 |  | 2022-02-22 09:30 | 2022-02-22 09:00 | 2022-02-11 16:02 | 2022-03-02 12:00 | CR0014667 | Service ManagementTML INVInvoiceInvoice InquiryInvoice Summary | OPUS-TES | 2022-W8 | 2022-02 | 50 | 53 | 101.8934 | 3 | 1 | 1 | 0.02 | 173249 | 3.1 | 2 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0.89474 | 0 | 2021-11 | 0 | 0
1870 | CR0014625 | CTASK0030461 | Closed | OPUS-SPC | Toai Phan | 84 | 57 | 2021-12-17 12:05 | 2021-11-11 12:04 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [CLV-SPC] [Add Validation Error pop-out to Master Constraint Table (Customer Tab) for AP upload] | 2021-11-11 12:09 | 2021-12-17 20:00 | 2022-01-05 09:38 | 2022-02-07 06:58 | 2022-02-16 09:49 |  | 2022-02-22 09:49 | 2022-02-23 09:15 | 2022-02-17 12:28 | 2022-03-02 12:00 | CR0014625 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W8 | 2022-02 | 84 | 57 | 102.9029 | 1 | 1 | 1 | 0.02 | 183427 | 2.9 | 3 | 2 | 0 | 1 |  | 2 | 14 | 30 | 0.44444 | 0 | 2021-11 | 2 | 1
1871 | CR0015132 | CTASK0033221 | Closed | OPUS-SPC | Toai Phan | 14 | 12 | 2022-03-30 15:45 | 2022-03-28 15:45 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [SPC-Internal] add logic to filter booking by Loading Country Code | 2022-03-02 06:29 | 2022-04-04 06:29 | 2022-04-01 13:17 | 2022-04-11 07:27 | 2022-04-18 13:48 |  | 2022-04-26 13:47 | 2022-04-26 06:17 | 2022-04-21 13:30 | 2022-05-05 12:00 | CR0015132 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W17 | 2022-04 | 14 | 12 | 55.3042 | 1 | 1 | 1 | 0.01 | 183427 | 3.3 | 0 | 0 | 0 | 1 |  | 2 | 6 | 18 | 0 | 0 | 2022-03 | 0 | 0
1872 | CR0015226 | CTASK0033021 | Closed | OPUS-VSK | Huy Vu | 16 | 16 | 2022-03-29 23:00 | 2022-03-20 23:00 | Container | Vessel Operation | Vessel Schedule |  |  |  | [CLV-VSK][CLT Internal]VVD Inquiry UI doesn't showing the full schedule | 2022-03-18 17:46 | 2022-03-25 20:00 | 2022-03-25 06:59 | 2022-04-13 07:45 | 2022-04-13 07:58 |  | 2022-04-19 09:00 | 2022-04-19 07:00 | 2022-04-13 15:50 | 2022-04-26 12:00 | CR0015226 | Vessel OperationVessel Schedule | OPUS-VSK | 2022-W16 | 2022-04 | 21 | 20 | 31.6344 | 3 | 1 | 2 | 0.03 | 193618 | 2.1 | 0 | 0 | 0 | 1 |  | 1 | 4 | 18 | 0 | 0 | 2022-03 | 0 | 0
1873 | CR0015226 | CTASK0032985 | Closed | OPUS-VSK | Huy Vu | 1 | 1 | 2022-03-31 23:28 | 2022-03-18 23:28 | Container | Vessel Operation | Vessel Schedule |  |  |  | [Document][[CLT Internal]VVD Inquiry UI doesn't showing the full schedule] | 2022-03-18 17:46 | 2022-03-25 20:00 | 2022-03-25 06:59 | 2022-04-13 07:45 | 2022-04-13 07:58 |  | 2022-04-19 09:00 | 2022-04-19 07:00 | 2022-04-13 15:50 | 2022-04-26 12:00 | CR0015226 | Vessel OperationVessel Schedule | OPUS-VSK | 2022-W16 | 2022-04 | 21 | 20 | 31.6344 | 3 | 1 | 2 | 0.03 | 193618 | 2.1 | 0 | 0 | 0 | 1 |  | 1 | 4 | 18 | 0 | 0 | 2022-03 | 0 | 0
1874 | CR0015226 | CTASK0033022 | Closed | OPUS-VSK | Linh Nguyen | 5 | 4 | 2022-03-31 23:29 | 2022-03-21 | Container | Vessel Operation | Vessel Schedule |  |  |  | [CLV-VSK][CLT Internal]VVD Inquiry UI doesn't showing the full schedule | 2022-03-18 17:46 | 2022-03-25 20:00 | 2022-03-25 06:59 | 2022-04-13 07:45 | 2022-04-13 07:58 |  | 2022-04-19 09:00 | 2022-04-19 07:00 | 2022-04-13 15:50 | 2022-04-26 12:00 | CR0015226 | Vessel OperationVessel Schedule | OPUS-VSK | 2022-W16 | 2022-04 | 21 | 20 | 31.6344 | 3 | 1 | 2 | 0.03 | 193464 | 3 | 0 | 0 | 0 | 1 |  | 1 | 4 | 18 | 0 | 0 | 2022-03 | 0 | 0
1875 | CR0014565 | CTASK0030837 | Closed | OPUS-BKG-M | Quy Truong | 4 | 4 | 2021-12-24 14:52 | 2021-12-20 14:52 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Relay Vessel Group Assign by Relay Port | [Testing] Add search filter and full name of vessel into module "Service Management > Booking Documentation > Operation > Transshipment > Relay Vessel Group Assign by Relay Port" | 2021-12-07 16:50 | 2021-12-30 | 2021-12-28 07:15 | 2022-03-02 12:31 | 2022-03-02 14:04 |  | 2022-03-15 08:00 | 2022-03-15 08:00 | 2022-03-03 13:07 | 2022-03-22 12:00 | CR0014565 | Service ManagementBooking/DocumentationOperationTransshipmentRelay Vessel Group Assign by Relay Port | OPUS-BKG-M | 2022-W11 | 2022-03 | 30 | 28 | 97.632 | 4 | 1 | 1 | 0.01 | 203791 | 1.1 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2021-12 | 0 | 0
1876 | CR0014565 | CTASK0030823 | Closed | OPUS-BKG-M | Quy Truong | 8 | 8 | 2021-12-01 15:06 | 2021-11-30 15:06 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Relay Vessel Group Assign by Relay Port | [Design] Add search filter and full name of vessel into module "Service Management > Booking Documentation > Operation > Transshipment > Relay Vessel Group Assign by Relay Port" | 2021-12-07 16:50 | 2021-12-30 | 2021-12-28 07:15 | 2022-03-02 12:31 | 2022-03-02 14:04 |  | 2022-03-15 08:00 | 2022-03-15 08:00 | 2022-03-03 13:07 | 2022-03-22 12:00 | CR0014565 | Service ManagementBooking/DocumentationOperationTransshipmentRelay Vessel Group Assign by Relay Port | OPUS-BKG-M | 2022-W11 | 2022-03 | 30 | 28 | 97.632 | 4 | 1 | 1 | 0.01 | 203791 | 1.1 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2021-12 | 0 | 0
1877 | CR0014565 | CTASK0030838 | Closed | OPUS-BKG-M | Quy Truong | 2 | 2 |  |  | Container | Service Management | Booking/Documentation | Operation | Transshipment | Relay Vessel Group Assign by Relay Port | [Deployment] Add search filter and full name of vessel into module "Service Management > Booking Documentation > Operation > Transshipment > Relay Vessel Group Assign by Relay Port" | 2021-12-07 16:50 | 2021-12-30 | 2021-12-28 07:15 | 2022-03-02 12:31 | 2022-03-02 14:04 |  | 2022-03-15 08:00 | 2022-03-15 08:00 | 2022-03-03 13:07 | 2022-03-22 12:00 | CR0014565 | Service ManagementBooking/DocumentationOperationTransshipmentRelay Vessel Group Assign by Relay Port | OPUS-BKG-M | 2022-W11 | 2022-03 | 30 | 28 | 97.632 | 4 | 1 | 1 | 0.01 | 203791 | 1.1 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2021-12 | 0 | 0
1878 | CR0014565 | CTASK0030836 | Closed | OPUS-BKG-M | Quy Truong | 16 | 16 | 2021-12-10 16:18 | 2021-12-06 16:18 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Relay Vessel Group Assign by Relay Port | [Development] Add search filter and full name of vessel into module "Service Management > Booking Documentation > Operation > Transshipment > Relay Vessel Group Assign by Relay Port" | 2021-12-07 16:50 | 2021-12-30 | 2021-12-28 07:15 | 2022-03-02 12:31 | 2022-03-02 14:04 |  | 2022-03-15 08:00 | 2022-03-15 08:00 | 2022-03-03 13:07 | 2022-03-22 12:00 | CR0014565 | Service ManagementBooking/DocumentationOperationTransshipmentRelay Vessel Group Assign by Relay Port | OPUS-BKG-M | 2022-W11 | 2022-03 | 30 | 28 | 97.632 | 4 | 1 | 1 | 0.01 | 203791 | 1.1 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2021-12 | 0 | 0
1879 | CR0014610 | CTASK0030147 | Closed | OPUS-SCE | VInh Bui | 1 | 1 | 2021-11-12 16:23 | 2021-10-27 16:23 | Container | Service Management | SCEM | Visibility | Vessel Schedule EDI Management |  | [Documentation][Kontainers] Feeder_Double calling service | 2021-10-28 13:19 | 2021-11-12 13:18 | 2021-11-03 15:20 | 2021-11-05 09:23 | 2021-11-09 15:39 |  | 2021-11-16 09:00 | 2021-11-16 09:00 | 2021-11-11 09:48 | 2021-11-23 12:01 | CR0014610 | Service ManagementSCEMVisibilityVessel Schedule EDI Management | OPUS-SCE | 2021-W46 | 2021-11 | 24 | 25 | 18.8204 | 3 | 1 | 1 | 0.06 | 193469 | 2.1 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0 | 2021-10 | 0 | 0
1880 | CR0014610 | CTASK0030152 | Closed | OPUS-SCE | VInh Bui | 9 | 10 | 2021-10-31 16:35 | 2021-10-27 16:35 | Container | Service Management | SCEM | Visibility | Vessel Schedule EDI Management |  | [Kontainers] Feeder_Double calling service (Oct) | 2021-10-28 13:19 | 2021-11-12 13:18 | 2021-11-03 15:20 | 2021-11-05 09:23 | 2021-11-09 15:39 |  | 2021-11-16 09:00 | 2021-11-16 09:00 | 2021-11-11 09:48 | 2021-11-23 12:01 | CR0014610 | Service ManagementSCEMVisibilityVessel Schedule EDI Management | OPUS-SCE | 2021-W46 | 2021-11 | 24 | 25 | 18.8204 | 3 | 1 | 1 | 0.06 | 193469 | 2.1 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0 | 2021-10 | 0 | 0
1881 | CR0014610 | CTASK0030382 | Closed | OPUS-SCE | VInh Bui | 15 | 15 | 2021-11-30 20:41 | 2021-11-01 20:41 | Container | Service Management | SCEM | Visibility | Vessel Schedule EDI Management |  | [Kontainers] Feeder_Double calling service (Nov) | 2021-10-28 13:19 | 2021-11-12 13:18 | 2021-11-03 15:20 | 2021-11-05 09:23 | 2021-11-09 15:39 |  | 2021-11-16 09:00 | 2021-11-16 09:00 | 2021-11-11 09:48 | 2021-11-23 12:01 | CR0014610 | Service ManagementSCEMVisibilityVessel Schedule EDI Management | OPUS-SCE | 2021-W46 | 2021-11 | 24 | 25 | 18.8204 | 3 | 1 | 1 | 0.06 | 193469 | 2.1 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0 | 2021-10 | 0 | 0
1882 | CR0013872 | CTASK0026851 | Closed | OPUS-JOO | Huy Vu | 13 | 13 |  |  | Container | Support & Admin | Joint Operation |  |  |  | [CLV][CLT Internal] - Modify according to RD-related internal regulations (Enhancement RD in JOO to bind variable from literal SQL) | 2021-07-26 08:18 | 2021-08-20 08:17 | 2021-08-06 09:48 | 2021-12-21 14:14 | 2021-12-28 14:47 |  | 2022-01-11 17:00 | 2022-01-11 08:00 | 2021-12-28 15:34 | 2022-01-19 12:00 | CR0013872 | Support & AdminJoint Operation | OPUS-JOO | 2022-W2 | 2022-01 | 13 | 13 | 169.3627 | 2 | 1 | 1 | 0 | 193618 | 1.5 | 2 | 0 | 0 | 1 |  | 3 | 7 | 33 | 0 | 0 | 2021-07 | 0 | 0
1883 | CR0013872 | CTASK0026810 | Closed | OPUS-JOO | Huy Vu | 1 | 1 |  |  | Container | Support & Admin | Joint Operation |  |  |  | [Document][CLT Internal] - Modify according to RD-related internal regulations (Enhancement RD in JOO to bind variable from literal SQL) | 2021-07-26 08:18 | 2021-08-20 08:17 | 2021-08-06 09:48 | 2021-12-21 14:14 | 2021-12-28 14:47 |  | 2022-01-11 17:00 | 2022-01-11 08:00 | 2021-12-28 15:34 | 2022-01-19 12:00 | CR0013872 | Support & AdminJoint Operation | OPUS-JOO | 2022-W2 | 2022-01 | 13 | 13 | 169.3627 | 2 | 1 | 1 | 0 | 193618 | 1.5 | 2 | 0 | 0 | 1 |  | 3 | 7 | 33 | 0 | 0 | 2021-07 | 0 | 0
1884 | CR0014268 | CTASK0028522 | Closed | OPUS-SCE | Son Nguyen The | 18 | 20 | 2021-08-31 14:17 | 2021-08-01 14:17 | Container | Service Management | SCEM |  |  |  | Mobile APP alignment - Revising VE and VBE trigger logic - AUG | 2021-08-09 11:01 | 2021-09-01 17:00 | 2021-08-31 15:38 | 2022-03-04 08:48 | 2022-03-09 23:26 |  | 2022-03-15 17:00 | 2022-03-14 23:26 | 2022-03-10 08:12 | 2022-03-16 14:56 | CR0014268 | Service ManagementSCEM | OPUS-SCE | 2022-W11 | 2022-03 | 21 | 45 | 218.2497 | 3 | 1 | 2 | 0.01 | 193531 | 1.8 | 1 | 0 | 0 | 1 |  | 3 | 10 | 38 | 0 | 0 | 2021-08 | 0 | 0
1885 | CR0014268 | CTASK0028521 | Closed | OPUS-SCE | Son Nguyen The | 20 | 20 |  |  | Container | Service Management | SCEM |  |  |  | [Documentation] Mobile APP alignment - Revising VE and VBE trigger logic | 2021-08-09 11:01 | 2021-09-01 17:00 | 2021-08-31 15:38 | 2022-03-04 08:48 | 2022-03-09 23:26 |  | 2022-03-15 17:00 | 2022-03-14 23:26 | 2022-03-10 08:12 | 2022-03-16 14:56 | CR0014268 | Service ManagementSCEM | OPUS-SCE | 2022-W11 | 2022-03 | 21 | 45 | 218.2497 | 3 | 1 | 2 | 0.01 | 193531 | 1.8 | 1 | 0 | 0 | 1 |  | 3 | 10 | 38 | 0 | 0 | 2021-08 | 0 | 0
1886 | CR0014268 | CTASK0031395 | Closed | OPUS-SCE | VInh Bui | 3 | 5 | 2021-12-31 16:46 | 2021-12-01 16:46 | Container | Service Management | SCEM |  |  |  | Mobile APP alignment - Revising VE and VBE trigger logic (DEC) | 2021-08-09 11:01 | 2021-09-01 17:00 | 2021-08-31 15:38 | 2022-03-04 08:48 | 2022-03-09 23:26 |  | 2022-03-15 17:00 | 2022-03-14 23:26 | 2022-03-10 08:12 | 2022-03-16 14:56 | CR0014268 | Service ManagementSCEM | OPUS-SCE | 2022-W11 | 2022-03 | 21 | 45 | 218.2497 | 3 | 1 | 2 | 0.01 | 193469 | 1.8 | 1 | 0 | 0 | 1 |  | 3 | 10 | 38 | 0 | 0 | 2021-08 | 0 | 0
1887 | CR0014288 | CTASK0028685 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-08-20 20:18 | 2021-08-16 00:18 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development][CLT Internal] Portcast Result Enhancement with Sequential Validation | 2021-08-17 08:43 | 2021-09-09 | 2021-09-02 11:08 | 2021-09-07 09:10 | 2021-09-07 09:19 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-08 14:48 | 2021-10-06 12:00 | CR0014288 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W39 | 2021-09 | 32 | 32 | 41.9702 | 4 | 1 | 1 | 0.03 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 0.22951 | 0.13043 | 2021-08 | 0 | 0
1888 | CR0014288 | CTASK0028686 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-08-31 20:20 | 2021-08-30 00:19 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing][CLT Internal] Portcast Result Enhancement with Sequential Validation | 2021-08-17 08:43 | 2021-09-09 | 2021-09-02 11:08 | 2021-09-07 09:10 | 2021-09-07 09:19 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-08 14:48 | 2021-10-06 12:00 | CR0014288 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W39 | 2021-09 | 32 | 32 | 41.9702 | 4 | 1 | 1 | 0.03 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 0.22951 | 0.13043 | 2021-08 | 0 | 0
1889 | CR0014288 | CTASK0028684 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-08-13 18:17 | 2021-08-09 00:17 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design][CLT Internal] Portcast Result Enhancement with Sequential Validation | 2021-08-17 08:43 | 2021-09-09 | 2021-09-02 11:08 | 2021-09-07 09:10 | 2021-09-07 09:19 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-08 14:48 | 2021-10-06 12:00 | CR0014288 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W39 | 2021-09 | 32 | 32 | 41.9702 | 4 | 1 | 1 | 0.03 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 0.22951 | 0.13043 | 2021-08 | 0 | 0
1890 | CR0014288 | CTASK0028688 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-09-30 20:21 | 2021-09-01 00:21 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment][CLT Internal] Portcast Result Enhancement with Sequential Validation | 2021-08-17 08:43 | 2021-09-09 | 2021-09-02 11:08 | 2021-09-07 09:10 | 2021-09-07 09:19 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-08 14:48 | 2021-10-06 12:00 | CR0014288 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W39 | 2021-09 | 32 | 32 | 41.9702 | 4 | 1 | 1 | 0.03 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 0.22951 | 0.13043 | 2021-08 | 0 | 0
1891 | CR0014906 | CTASK0031378 | Closed | OPUS-BKG-CHG | Nam Nguyen | 14 | 14 | 2021-12-31 08:43 | 2021-12-20 08:43 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Design][CLT Internal] to prevent the missing container in container rate for flex height case | 2022-01-12 15:13 | 2022-02-11 09:42 | 2022-02-10 10:00 | 2022-02-16 11:50 | 2022-02-18 09:19 |  | 2022-03-02 08:00 | 2022-03-02 07:50 | 2022-02-18 12:09 | 2022-03-09 12:00 | CR0014906 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W9 | 2022-03 | 62 | 62 | 48.6991 | 4 | 2 | 2 | 0.05 | 123048 | 3.3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.22222 | 0 | 2022-01 | 0 | 0
1892 | CR0014906 | CTASK0031380 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 16 | 16 | 2022-02-28 21:00 | 2022-02-21 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Testing][CLT Internal] to prevent the missing container in container rate for flex height case | 2022-01-12 15:13 | 2022-02-11 09:42 | 2022-02-10 10:00 | 2022-02-16 11:50 | 2022-02-18 09:19 |  | 2022-03-02 08:00 | 2022-03-02 07:50 | 2022-02-18 12:09 | 2022-03-09 12:00 | CR0014906 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W9 | 2022-03 | 62 | 62 | 48.6991 | 4 | 2 | 2 | 0.05 | 193470 | 2.8 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.36842 | 0.11111 | 2022-01 | 0 | 0
1893 | CR0014906 | CTASK0031379 | Closed | OPUS-BKG-CHG | Nam Nguyen | 23 | 24 | 2022-01-30 09:05 | 2022-01-03 09:05 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Development][CLT Internal] to prevent the missing container in container rate for flex height case | 2022-01-12 15:13 | 2022-02-11 09:42 | 2022-02-10 10:00 | 2022-02-16 11:50 | 2022-02-18 09:19 |  | 2022-03-02 08:00 | 2022-03-02 07:50 | 2022-02-18 12:09 | 2022-03-09 12:00 | CR0014906 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W9 | 2022-03 | 62 | 62 | 48.6991 | 4 | 2 | 2 | 0.05 | 123048 | 3.3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.22222 | 0 | 2022-01 | 0 | 0
1894 | CR0014906 | CTASK0031381 | Closed | OPUS-BKG-CHG | Nam Nguyen | 9 | 8 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Deployment][CLT Internal] to prevent the missing container in container rate for flex height case | 2022-01-12 15:13 | 2022-02-11 09:42 | 2022-02-10 10:00 | 2022-02-16 11:50 | 2022-02-18 09:19 |  | 2022-03-02 08:00 | 2022-03-02 07:50 | 2022-02-18 12:09 | 2022-03-09 12:00 | CR0014906 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W9 | 2022-03 | 62 | 62 | 48.6991 | 4 | 2 | 2 | 0.05 | 123048 | 3.3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.22222 | 0 | 2022-01 | 0 | 0
1895 | CR0015328 | CTASK0033375 | Closed | OPUS-VSK | Linh Nguyen | 1 | 1 |  |  | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Input Ratio Report |  | [Document][AIS Data EDI Update - Vessel Schedules for ATA Detection] | 2022-04-08 08:27 | 2022-05-09 20:00 | 2022-05-03 09:17 | 2022-05-19 15:39 | 2022-05-24 16:38 |  | 2022-06-01 | 2022-05-31 09:51 | 2022-05-31 09:49 | 2022-06-07 12:00 | CR0015328 | Vessel OperationVessel ScheduleActual SKDActual SKD Input Ratio Report | OPUS-VSK | 2022-W22 | 2022-05 | 62 | 68 | 53.6482 | 6 | 1 | 1 | 0.05 | 193464 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.375 | 0 | 2022-04 | 0 | 0
1896 | CR0015328 | CTASK0033435 | Closed | OPUS-VSK | Linh Nguyen | 10 | 10 | 2022-04-30 22:22 | 2022-04-25 22:22 | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Input Ratio Report |  | [Test][AIS Data EDI Update - Vessel Schedules for ATA Detection] | 2022-04-08 08:27 | 2022-05-09 20:00 | 2022-05-03 09:17 | 2022-05-19 15:39 | 2022-05-24 16:38 |  | 2022-06-01 | 2022-05-31 09:51 | 2022-05-31 09:49 | 2022-06-07 12:00 | CR0015328 | Vessel OperationVessel ScheduleActual SKDActual SKD Input Ratio Report | OPUS-VSK | 2022-W22 | 2022-05 | 62 | 68 | 53.6482 | 6 | 1 | 1 | 0.05 | 193464 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.375 | 0 | 2022-04 | 0 | 0
1897 | CR0015328 | CTASK0033432 | Closed | OPUS-VSK | Linh Nguyen | 6 | 6 | 2022-04-20 22:21 | 2022-04-04 22:20 | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Input Ratio Report |  | [Design][AIS Data EDI Update - Vessel Schedules for ATA Detection] | 2022-04-08 08:27 | 2022-05-09 20:00 | 2022-05-03 09:17 | 2022-05-19 15:39 | 2022-05-24 16:38 |  | 2022-06-01 | 2022-05-31 09:51 | 2022-05-31 09:49 | 2022-06-07 12:00 | CR0015328 | Vessel OperationVessel ScheduleActual SKDActual SKD Input Ratio Report | OPUS-VSK | 2022-W22 | 2022-05 | 62 | 68 | 53.6482 | 6 | 1 | 1 | 0.05 | 193464 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.375 | 0 | 2022-04 | 0 | 0
1898 | CR0015328 | CTASK0033436 | Closed | OPUS-VSK | Linh Nguyen | 4 | 4 |  |  | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Input Ratio Report |  | [Deployment][AIS Data EDI Update - Vessel Schedules for ATA Detection] | 2022-04-08 08:27 | 2022-05-09 20:00 | 2022-05-03 09:17 | 2022-05-19 15:39 | 2022-05-24 16:38 |  | 2022-06-01 | 2022-05-31 09:51 | 2022-05-31 09:49 | 2022-06-07 12:00 | CR0015328 | Vessel OperationVessel ScheduleActual SKDActual SKD Input Ratio Report | OPUS-VSK | 2022-W22 | 2022-05 | 62 | 68 | 53.6482 | 6 | 1 | 1 | 0.05 | 193464 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.375 | 0 | 2022-04 | 0 | 0
1899 | CR0015328 | CTASK0033429 | Closed | OPUS-VSK | Linh Nguyen | 8 | 8 | 2022-04-15 22:19 | 2022-04-04 22:19 | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Input Ratio Report |  | [Analysis][AIS Data EDI Update - Vessel Schedules for ATA Detection] | 2022-04-08 08:27 | 2022-05-09 20:00 | 2022-05-03 09:17 | 2022-05-19 15:39 | 2022-05-24 16:38 |  | 2022-06-01 | 2022-05-31 09:51 | 2022-05-31 09:49 | 2022-06-07 12:00 | CR0015328 | Vessel OperationVessel ScheduleActual SKDActual SKD Input Ratio Report | OPUS-VSK | 2022-W22 | 2022-05 | 62 | 68 | 53.6482 | 6 | 1 | 1 | 0.05 | 193464 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.375 | 0 | 2022-04 | 0 | 0
1900 | CR0015328 | CTASK0033433 | Closed | OPUS-VSK | Linh Nguyen | 40 | 40 | 2022-04-30 22:21 | 2022-04-11 22:21 | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Input Ratio Report |  | [Development][AIS Data EDI Update - Vessel Schedules for ATA Detection] | 2022-04-08 08:27 | 2022-05-09 20:00 | 2022-05-03 09:17 | 2022-05-19 15:39 | 2022-05-24 16:38 |  | 2022-06-01 | 2022-05-31 09:51 | 2022-05-31 09:49 | 2022-06-07 12:00 | CR0015328 | Vessel OperationVessel ScheduleActual SKDActual SKD Input Ratio Report | OPUS-VSK | 2022-W22 | 2022-05 | 62 | 68 | 53.6482 | 6 | 1 | 1 | 0.05 | 193464 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.375 | 0 | 2022-04 | 0 | 0
1901 | CR0014162 | CTASK0028334 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 4 | 8 |  |  | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Deploy] IFCSUM Not displaying the correct Equipment Status for Tranship containers - ECR0013285 | 2021-08-18 19:39 | 2021-08-24 22:00 | 2021-08-23 09:39 | 2021-09-07 16:02 | 2021-09-08 09:36 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-17 08:25 | 2021-10-06 12:00 | CR0014162 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2021-W39 | 2021-09 | 51 | 60 | 40.5147 | 5 | 1 | 1 | 0.06 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 4.25 | 2.25 | 2021-08 | 0 | 0
1902 | CR0014162 | CTASK0029549 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 13 | 16 | 2021-09-30 18:11 | 2021-09-23 18:11 | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [PROD] IFCSUM Not displaying the correct Equipment Status for Tranship containers - ECR0013285 | 2021-08-18 19:39 | 2021-08-24 22:00 | 2021-08-23 09:39 | 2021-09-07 16:02 | 2021-09-08 09:36 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-17 08:25 | 2021-10-06 12:00 | CR0014162 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2021-W39 | 2021-09 | 51 | 60 | 40.5147 | 5 | 1 | 1 | 0.06 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 4.25 | 2.25 | 2021-08 | 0 | 0
1903 | CR0014162 | CTASK0028331 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 4 | 4 | 2021-07-23 11:40 | 2021-07-20 11:40 | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Estimate] IFCSUM Not displaying the correct Equipment Status for Tranship containers - ECR0013285 | 2021-08-18 19:39 | 2021-08-24 22:00 | 2021-08-23 09:39 | 2021-09-07 16:02 | 2021-09-08 09:36 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-17 08:25 | 2021-10-06 12:00 | CR0014162 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2021-W39 | 2021-09 | 51 | 60 | 40.5147 | 5 | 1 | 1 | 0.06 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 4.25 | 2.25 | 2021-08 | 0 | 0
1904 | CR0014162 | CTASK0028333 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 14 | 16 |  |  | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Test] IFCSUM Not displaying the correct Equipment Status for Tranship containers - ECR0013285 | 2021-08-18 19:39 | 2021-08-24 22:00 | 2021-08-23 09:39 | 2021-09-07 16:02 | 2021-09-08 09:36 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-17 08:25 | 2021-10-06 12:00 | CR0014162 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2021-W39 | 2021-09 | 51 | 60 | 40.5147 | 5 | 1 | 1 | 0.06 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 4.25 | 2.25 | 2021-08 | 0 | 0
1905 | CR0014162 | CTASK0028332 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 16 | 16 |  |  | Container | Service Management | Booking/Documentation | Manifest | Australia |  | [Develop] IFCSUM Not displaying the correct Equipment Status for Tranship containers - ECR0013285 | 2021-08-18 19:39 | 2021-08-24 22:00 | 2021-08-23 09:39 | 2021-09-07 16:02 | 2021-09-08 09:36 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-17 08:25 | 2021-10-06 12:00 | CR0014162 | Service ManagementBooking/DocumentationManifestAustralia | OPUS-BKG-MFT-A | 2021-W39 | 2021-09 | 51 | 60 | 40.5147 | 5 | 1 | 1 | 0.06 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 4.25 | 2.25 | 2021-08 | 0 | 0
1906 | CR0014120 | CTASK0027808 | Closed | OPUS-DMT | Cuong Nguyen | 22 | 26 | 2021-11-12 18:00 | 2021-06-25 06:00 | Container | Service Management | Demurrage/Detention | Billing |  |  | [CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2021-07-21 07:11 | 2021-07-30 18:00 | 2021-07-30 13:44 | 2021-09-08 14:52 | 2021-11-09 06:58 |  | 2021-11-16 08:01 | 2021-11-16 08:01 | 2021-11-09 07:14 | 2021-11-23 12:01 | CR0014120 | Service ManagementDemurrage/DetentionBilling | OPUS-DMT | 2021-W46 | 2021-11 | 22 | 26 | 118.035 | 1 | 1 | 1 | 0.01 | 193529 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.11538 | 0.22222 | 2021-07 | 0 | 0
1907 | CR0013062 | CTASK0026450 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2022-04-30 11:54 | 2022-04-01 11:54 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [Deployment] NA *PRD* Additional Data Points in Constraint Management | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193567 | 2.3 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.5625 | 0 | 2021-11 | 0 | 0
1908 | CR0013062 | CTASK0032744 | Closed | OPUS-PRD | VInh Bui | 3 | 3 | 2022-03-31 13:48 | 2022-03-01 13:48 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | NA *PRD* Additional Data Points in Constraint Management - MAR | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193469 | 2.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0 | 0 | 2021-11 | 0 | 0
1909 | CR0013062 | CTASK0032483 | Closed | OPUS-PRD | Tran Le | 5 | 5 |  |  | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | NA *PRD* Additional Data Points in Constraint Management - FEB | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193501 | 2.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.052632 | 0 | 2021-11 | 0 | 0
1910 | CR0013062 | CTASK0030395 | Closed | OPUS-PRD | Tran Le | 59 | 35 | 2021-12-31 10:01 | 2021-12-01 10:01 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | NA *PRD* Additional Data Points in Constraint Management - DEC | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193501 | 2.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.052632 | 0 | 2021-11 | 0 | 0
1911 | CR0013062 | CTASK0031092 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-12-31 14:54 | 2021-12-20 14:53 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [Testing] NA *PRD* Additional Data Points in Constraint Management | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 153106 | 3.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.22951 | 0 | 2021-11 | 0 | 0
1912 | CR0013062 | CTASK0026449 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-12-31 13:29 | 2021-12-27 13:29 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [Test] NA *PRD* Additional Data Points in Constraint Management | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193567 | 2.3 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.5625 | 0 | 2021-11 | 0 | 0
1913 | CR0013062 | CTASK0034048 | Closed | OPUS-PRD | VInh Bui | 21 | 21 | 2022-05-31 09:59 | 2022-05-01 09:59 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [DEPLOYMENT] NA *PRD* Additional Data Points in Constraint Management-MAY | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193469 | 2.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0 | 0 | 2021-11 | 0 | 0
1914 | CR0013062 | CTASK0030396 | Closed | OPUS-PRD | VInh Bui | 65 | 35 | 2021-12-31 10:01 | 2021-12-01 10:01 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | NA *PRD* Additional Data Points in Constraint Management - DEC | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193469 | 2.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0 | 0 | 2021-11 | 0 | 0
1915 | CR0013062 | CTASK0031199 | Closed | OPUS-BKG-M | Thien Lai | 32 | 32 | 2021-12-17 16:17 | 2021-12-13 10:16 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [Development] NA *PRD* Additional Data Points in Constraint Management | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193567 | 2.3 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.5625 | 0 | 2021-11 | 0 | 0
1916 | CR0013062 | CTASK0031049 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-12-10 20:04 | 2021-12-06 00:04 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [Design] NA *PRD* Additional Data Points in Constraint Management | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 153106 | 3.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.22951 | 0 | 2021-11 | 0 | 0
1917 | CR0013062 | CTASK0034049 | Closed | OPUS-PRD | Tran Le | 4 | 4 | 2022-05-31 10:00 | 2022-05-01 10:00 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [DEPLOYMENT] NA *PRD* Additional Data Points in Constraint Management-MAY | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193501 | 2.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.052632 | 0 | 2021-11 | 0 | 0
1918 | CR0013062 | CTASK0031090 | Closed | OPUS-BKG-M | Kieu Le | 44 | 44 | 2021-12-31 20:52 | 2021-12-13 00:52 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [Development] NA *PRD* Additional Data Points in Constraint Management | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 153106 | 3.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.22951 | 0 | 2021-11 | 0 | 0
1919 | CR0013062 | CTASK0030392 | Closed | OPUS-PRD | Tran Le | 47 | 50 | 2021-11-30 09:58 | 2021-11-01 09:58 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | NA *PRD* Additional Data Points in Constraint Management - NOV | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193501 | 2.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.052632 | 0 | 2021-11 | 0 | 0
1920 | CR0013062 | CTASK0031119 | Closed | OPUS-BKG-M | Trang Le Minh | 20 | 20 | 2021-12-17 20:54 | 2021-12-13 00:54 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [Development] NA *PRD* Additional Data Points in Constraint Management | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193594 | 2.2 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0 | 0 | 2021-11 | 0 | 0
1921 | CR0013062 | CTASK0031095 | Closed | OPUS-BKG-M | Khoi Bui | 7 | 8 | 2022-05-31 14:55 | 2022-05-04 14:55 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [Deployment] NA *PRD* Additional Data Points in Constraint Management | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 203713 | 0.9 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0 | 0 | 2021-11 | 0 | 0
1922 | CR0013062 | CTASK0026447 | Closed | OPUS-BKG-M | Thien Lai | 24 | 24 | 2021-12-17 13:29 | 2021-12-09 13:29 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | [Development] NA *PRD* Additional Data Points in Constraint Management | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193567 | 2.3 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0.5625 | 0 | 2021-11 | 0 | 0
1923 | CR0013062 | CTASK0030393 | Closed | OPUS-PRD | VInh Bui | 50 | 50 | 2021-11-30 09:59 | 2021-11-01 09:59 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | NA *PRD* Additional Data Points in Constraint Management - NOV | 2021-11-08 08:27 | 2022-01-07 18:00 | 2022-01-06 07:34 | 2022-04-25 11:46 | 2022-05-04 11:53 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:00 | 2022-05-24 12:00 | CR0013062 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 389 | 370 | 189.9813 | 17 | 2 | 6 | 0.08 | 193469 | 2.1 | 3 | 0 | 0 | 4 |  | 3 | 8 | 26 | 0 | 0 | 2021-11 | 0 | 0
1924 | CR0014245 | CTASK0030030 | Closed | OPUS-BKG-M | Trang Le Minh | 5 | 5 | 2021-10-29 13:38 | 2021-10-11 13:38 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Design] GHQ - CSVC/EDI - To capture BRN information sent via EDI | 2021-10-25 08:09 | 2021-11-17 22:00 | 2021-11-15 13:23 | 2022-01-14 16:02 | 2022-01-17 07:19 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-17 12:55 | 2022-02-02 12:00 | CR0014245 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W4 | 2022-01 | 15 | 15 | 91.994 | 4 | 1 | 1 | 0.01 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 9 | 33 | 0 | 0 | 2021-10 | 0 | 0
1925 | CR0014245 | CTASK0030031 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2021-10-29 21:20 | 2021-10-25 08:20 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Development] GHQ - CSVC/EDI - To capture BRN information sent via EDI | 2021-10-25 08:09 | 2021-11-17 22:00 | 2021-11-15 13:23 | 2022-01-14 16:02 | 2022-01-17 07:19 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-17 12:55 | 2022-02-02 12:00 | CR0014245 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W4 | 2022-01 | 15 | 15 | 91.994 | 4 | 1 | 1 | 0.01 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 9 | 33 | 0 | 0 | 2021-10 | 0 | 0
1926 | CR0014245 | CTASK0030035 | Closed | OPUS-BKG-M | Trang Le Minh | 2 | 2 | 2022-01-25 14:03 | 2022-01-17 14:03 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Deployment] GHQ - CSVC/EDI - To capture BRN information sent via EDI | 2021-10-25 08:09 | 2021-11-17 22:00 | 2021-11-15 13:23 | 2022-01-14 16:02 | 2022-01-17 07:19 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-17 12:55 | 2022-02-02 12:00 | CR0014245 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W4 | 2022-01 | 15 | 15 | 91.994 | 4 | 1 | 1 | 0.01 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 9 | 33 | 0 | 0 | 2021-10 | 0 | 0
1927 | CR0014245 | CTASK0030032 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2021-11-12 21:21 | 2021-11-08 08:21 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Testing] GHQ - CSVC/EDI - To capture BRN information sent via EDI | 2021-10-25 08:09 | 2021-11-17 22:00 | 2021-11-15 13:23 | 2022-01-14 16:02 | 2022-01-17 07:19 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-17 12:55 | 2022-02-02 12:00 | CR0014245 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W4 | 2022-01 | 15 | 15 | 91.994 | 4 | 1 | 1 | 0.01 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 9 | 33 | 0 | 0 | 2021-10 | 0 | 0
1928 | CR0014506 | CTASK0031852 | Closed | OPUS-SCE | Phu Nguyen Hoang | 11 | 30 |  |  | Container | Service Management | Trans S/O | Service Order |  |  | [SCE] EUA - PARIS Phase 1 project - allow BKG container swap for outbound jobs after OP (outbound empty pick-up) event occured without the need to cancel or frustrate Service Order. | 2021-12-07 08:30 | 2022-01-21 22:00 | 2022-01-14 15:49 | 2022-03-17 22:04 | 2022-04-06 14:23 |  | 2022-04-12 14:23 | 2022-04-12 08:46 | 2022-04-06 15:37 | 2022-04-19 12:00 | CR0014506 | Service ManagementTrans S/OService Order | OPUS-TRS | 2022-W15 | 2022-04 | 32 | 68 | 126.2447 | 3 | 2 | 3 | 0.02 | 193463 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 2 | 18 | 0.16667 | 0 | 2021-12 | 0 | 0
1929 | CR0014506 | CTASK0031827 | Closed | OPUS-SCE | Tran Le | 7 | 30 |  |  | Container | Service Management | Trans S/O | Service Order |  |  | [SCE] EUA - PARIS Phase 1 project - allow BKG container swap for outbound jobs after OP (outbound empty pick-up) event occured without the need to cancel or frustrate Service Order. | 2021-12-07 08:30 | 2022-01-21 22:00 | 2022-01-14 15:49 | 2022-03-17 22:04 | 2022-04-06 14:23 |  | 2022-04-12 14:23 | 2022-04-12 08:46 | 2022-04-06 15:37 | 2022-04-19 12:00 | CR0014506 | Service ManagementTrans S/OService Order | OPUS-TRS | 2022-W15 | 2022-04 | 32 | 68 | 126.2447 | 3 | 2 | 3 | 0.02 | 193501 | 2.2 | 2 | 0 | 0 | 1 |  | 2 | 2 | 18 | 0.052632 | 0 | 2021-12 | 0 | 0
1930 | CR0014506 | CTASK0031977 | Closed | OPUS-BKG-M | Quy Truong | 14 | 8 | 2022-01-24 13:25 | 2022-01-21 13:25 | Container | Service Management | Trans S/O | Service Order |  |  | [BKG-Main] EUA - PARIS Phase 1 project - allow BKG container swap for outbound jobs after OP (outbound empty pick-up) event occured without the need to cancel or frustrate Service Order. | 2021-12-07 08:30 | 2022-01-21 22:00 | 2022-01-14 15:49 | 2022-03-17 22:04 | 2022-04-06 14:23 |  | 2022-04-12 14:23 | 2022-04-12 08:46 | 2022-04-06 15:37 | 2022-04-19 12:00 | CR0014506 | Service ManagementTrans S/OService Order | OPUS-TRS | 2022-W15 | 2022-04 | 32 | 68 | 126.2447 | 3 | 2 | 3 | 0.02 | 203791 | 1.1 | 2 | 0 | 0 | 1 |  | 2 | 2 | 18 | 0 | 0 | 2021-12 | 0 | 0
1931 | CR0014807 | CTASK0034373 | Closed | OPUS-BKG-MFT-M | Linh Dinh Bo | 6 | 6 | 2022-05-31 18:34 | 2022-05-23 18:34 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 193522 | 2.7 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0 | 0 | 2022-02 | 0 | 0
1932 | CR0014807 | CTASK0032746 | Closed | OPUS-BKG-MFT-M | Linh Dinh Bo | 4 | 4 | 2022-03-04 14:04 | 2022-02-28 14:04 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 193522 | 2.7 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0 | 0 | 2022-02 | 0 | 0
1933 | CR0014807 | CTASK0031775 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2022-01-19 17:30 | 2022-01-17 08:30 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 193470 | 2.9 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0.36842 | 0.11111 | 2022-02 | 0 | 0
1934 | CR0014807 | CTASK0031888 | Closed | OPUS-BKG-M | Quy Truong | 8 | 8 | 2022-03-12 | 2022-03-09 08:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deloyment] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 203791 | 1.3 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0 | 0 | 2022-02 | 0 | 0
1935 | CR0014807 | CTASK0031875 | Closed | OPUS-BKG-MFT-M | Linh Dinh Bo | 11 | 10 | 2022-01-31 13:40 | 2022-01-01 13:40 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 193522 | 2.7 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0 | 0 | 2022-02 | 0 | 0
1936 | CR0014807 | CTASK0031776 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 12 | 12 | 2022-02-25 21:00 | 2022-02-14 08:30 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Dev + Test] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 193470 | 2.9 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0.36842 | 0.11111 | 2022-02 | 0 | 0
1937 | CR0014807 | CTASK0031891 | Closed | OPUS-BKG-M | Quy Truong | 8 | 8 | 2022-03-10 | 2022-02-28 08:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [TG]EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 203791 | 1.3 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0 | 0 | 2022-02 | 0 | 0
1938 | CR0014807 | CTASK0031886 | Closed | OPUS-BKG-M | Quy Truong | 58 | 52 | 2022-03-09 21:52 | 2022-02-07 21:52 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 203791 | 1.3 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0 | 0 | 2022-02 | 0 | 0
1939 | CR0014807 | CTASK0031777 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 4 | 2022-05-27 15:22 | 2022-05-23 15:22 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 193470 | 2.9 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0.36842 | 0.11111 | 2022-02 | 0 | 0
1940 | CR0014807 | CTASK0031887 | Closed | OPUS-BKG-M | Quy Truong | 8 | 8 | 2022-03-04 09:00 | 2022-03-01 09:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 203791 | 1.3 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0 | 0 | 2022-02 | 0 | 0
1941 | CR0014807 | CTASK0031708 | Closed | OPUS-BKG-M | Quy Truong | 26 | 26 | 2022-01-18 08:49 | 2022-01-04 08:49 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] EUA SYM / RPM request - To expand C/A reason list | 2022-02-07 07:10 | 2022-03-09 22:00 | 2022-03-08 14:54 | 2022-05-16 06:17 | 2022-05-16 08:22 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:56 | 2022-06-07 12:00 | CR0014807 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 137 | 142 | 113.0345 | 11 | 3 | 3 | 0.05 | 203791 | 1.3 | 2 | 0 | 0 | 2 |  | 2 | 7 | 26 | 0 | 0 | 2022-02 | 0 | 0
1942 | CR0014165 | CTASK0029057 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2022-02-28 11:51 | 2022-02-07 11:50 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] Standby - 10 days Rule and Revalidation items logic changes | 2021-10-07 13:45 | 2021-10-28 | 2021-10-19 08:05 | 2022-02-15 07:26 | 2022-02-15 08:06 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-17 12:23 | 2022-03-10 12:00 | CR0014165 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2022-W9 | 2022-03 | 14 | 18 | 145.7605 | 5 | 1 | 2 | 0.01 | 153106 | 3 | 2 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.22951 | 0 | 2021-10 | 0 | 0
1943 | CR0014165 | CTASK0029054 | Closed | OPUS-BKG-M | Trang Le Minh | 8 | 8 | 2021-10-29 20:48 | 2021-10-01 11:48 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] Standby - 10 days Rule and Revalidation items logic changes | 2021-10-07 13:45 | 2021-10-28 | 2021-10-19 08:05 | 2022-02-15 07:26 | 2022-02-15 08:06 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-17 12:23 | 2022-03-10 12:00 | CR0014165 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2022-W9 | 2022-03 | 14 | 18 | 145.7605 | 5 | 1 | 2 | 0.01 | 193594 | 2.1 | 2 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0 | 0 | 2021-10 | 0 | 0
1944 | CR0014165 | CTASK0029056 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-11-30 11:50 | 2021-11-01 11:50 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [TG] Standby - 10 days Rule and Revalidation items logic changes | 2021-10-07 13:45 | 2021-10-28 | 2021-10-19 08:05 | 2022-02-15 07:26 | 2022-02-15 08:06 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-17 12:23 | 2022-03-10 12:00 | CR0014165 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2022-W9 | 2022-03 | 14 | 18 | 145.7605 | 5 | 1 | 2 | 0.01 | 153106 | 3 | 2 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.22951 | 0 | 2021-10 | 0 | 0
1945 | CR0014165 | CTASK0029052 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-09-17 11:46 | 2021-09-01 11:46 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] Standby - 10 days Rule and Revalidation items logic changes | 2021-10-07 13:45 | 2021-10-28 | 2021-10-19 08:05 | 2022-02-15 07:26 | 2022-02-15 08:06 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-17 12:23 | 2022-03-10 12:00 | CR0014165 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2022-W9 | 2022-03 | 14 | 18 | 145.7605 | 5 | 1 | 2 | 0.01 | 153106 | 3 | 2 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.22951 | 0 | 2021-10 | 0 | 0
1946 | CR0014165 | CTASK0029053 | Closed | OPUS-BKG-M | Kieu Le | 2 | 4 | 2021-10-29 20:47 | 2021-10-01 00:47 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] Standby - 10 days Rule and Revalidation items logic changes | 2021-10-07 13:45 | 2021-10-28 | 2021-10-19 08:05 | 2022-02-15 07:26 | 2022-02-15 08:06 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-17 12:23 | 2022-03-10 12:00 | CR0014165 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2022-W9 | 2022-03 | 14 | 18 | 145.7605 | 5 | 1 | 2 | 0.01 | 153106 | 3 | 2 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.22951 | 0 | 2021-10 | 0 | 0
1947 | CR0014277 | CTASK0031340 | Closed | OPUS-SCE | Tran Le | 2 | 2 |  |  | eCommerce | Track & Trace | Visibility Service | Event Notification |  |  | [SCE]3CA Proactive Notification Phase 2- Container Event-Manage effort | 2021-09-27 09:10 | 2021-10-26 21:00 | 2021-10-26 16:06 | 2022-01-07 12:04 | 2022-01-10 11:14 |  | 2022-01-18 08:00 | 2022-01-18 07:30 | 2022-01-10 13:36 | 2022-01-26 12:00 | CR0014277 | Track & TraceVisibility ServiceEvent Notification | OPUS-SCE | 2022-W3 | 2022-01 | 2 | 0 | 112.9516 | 1 | 1 | 1 | 0 | 193501 | 2 | 0 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0 | 0.076923 | 2021-09 | 0 | 0
1948 | CR0014799 | CTASK0033430 | Closed | OPUS-BKG-EBKG | Le Nguyen | 4 | 4 | 2022-04-13 08:01 | 2022-04-07 08:01 | Container | Service Management | OCPS |  |  |  | [Development] SHINE - OPUS : Change the logic when uploading PO & Invoice Number to OPUS | 2022-01-05 06:13 | 2022-01-07 22:00 | 2022-01-06 14:41 | 2022-02-22 11:32 | 2022-02-24 09:59 |  | 2022-03-30 09:00 | 2022-04-12 08:00 | 2022-04-04 07:45 | 2022-04-19 12:00 | CR0014799 | Service ManagementOCPS | OPUS-OCPS | 2022-W13 | 2022-03 | 12 | 12 | 84.1157 | 2 | 2 | 2 | 0.01 | 203686 | 1.4 | 2 | 0 | 0 | 1 |  | 2 | 6 | 38 | 0 | 0 | 2022-01 | 0 | 0
1949 | CR0014799 | CTASK0031337 | Closed | OPUS-OCPS | Vinh Tran | 8 | 8 | 2022-01-01 | 2021-12-20 | Container | Service Management | OCPS |  |  |  | [Development/Testing] SHINE - OPUS : Change the logic when uploading PO & Invoice Number to OPUS | 2022-01-05 06:13 | 2022-01-07 22:00 | 2022-01-06 14:41 | 2022-02-22 11:32 | 2022-02-24 09:59 |  | 2022-03-30 09:00 | 2022-04-12 08:00 | 2022-04-04 07:45 | 2022-04-19 12:00 | CR0014799 | Service ManagementOCPS | OPUS-OCPS | 2022-W13 | 2022-03 | 12 | 12 | 84.1157 | 2 | 2 | 2 | 0.01 | 193525 | 2.6 | 2 | 0 | 0 | 1 |  | 2 | 6 | 38 | 0.41667 | 0.16667 | 2022-01 | 0 | 0
1950 | CR0014458 | CTASK0030040 | Closed | OPUS-BKG-M | Kieu Le | 11 | 10 | 2021-11-19 14:43 | 2021-11-01 14:43 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Development] ASIA - SPC - Allocation Type option between Total & Booking under EQ Restriction Tab | 2021-11-10 07:17 | 2021-11-25 | 2021-11-24 10:09 | 2022-01-04 08:28 | 2022-01-04 08:47 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:05 | 2022-01-25 12:00 | CR0014458 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W3 | 2022-01 | 31 | 30 | 69.0301 | 5 | 1 | 3 | 0.02 | 153106 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0.22951 | 0 | 2021-11 | 0 | 0
1951 | CR0014458 | CTASK0030041 | Closed | OPUS-BKG-M | Quy Truong | 4 | 8 | 2021-11-19 20:44 | 2021-11-15 00:44 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Testing] ASIA - SPC - Allocation Type option between Total & Booking under EQ Restriction Tab | 2021-11-10 07:17 | 2021-11-25 | 2021-11-24 10:09 | 2022-01-04 08:28 | 2022-01-04 08:47 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:05 | 2022-01-25 12:00 | CR0014458 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W3 | 2022-01 | 31 | 30 | 69.0301 | 5 | 1 | 3 | 0.02 | 203791 | 1.1 | 1 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
1952 | CR0014458 | CTASK0030043 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2022-01-31 14:47 | 2022-01-04 14:47 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Deployment] ASIA - SPC - Allocation Type option between Total & Booking under EQ Restriction Tab | 2021-11-10 07:17 | 2021-11-25 | 2021-11-24 10:09 | 2022-01-04 08:28 | 2022-01-04 08:47 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:05 | 2022-01-25 12:00 | CR0014458 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W3 | 2022-01 | 31 | 30 | 69.0301 | 5 | 1 | 3 | 0.02 | 153106 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0.22951 | 0 | 2021-11 | 0 | 0
1953 | CR0014458 | CTASK0030045 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2021-10-29 14:51 | 2021-10-20 14:51 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Development][DB] ASIA - SPC - Allocation Type option between Total & Booking under EQ Restriction Tab | 2021-11-10 07:17 | 2021-11-25 | 2021-11-24 10:09 | 2022-01-04 08:28 | 2022-01-04 08:47 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:05 | 2022-01-25 12:00 | CR0014458 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W3 | 2022-01 | 31 | 30 | 69.0301 | 5 | 1 | 3 | 0.02 | 193594 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
1954 | CR0014458 | CTASK0030039 | Closed | OPUS-BKG-M | Quy Truong | 8 | 4 | 2021-11-19 14:42 | 2021-11-01 14:42 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Design] ASIA - SPC - Allocation Type option between Total & Booking under EQ Restriction Tab | 2021-11-10 07:17 | 2021-11-25 | 2021-11-24 10:09 | 2022-01-04 08:28 | 2022-01-04 08:47 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:05 | 2022-01-25 12:00 | CR0014458 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W3 | 2022-01 | 31 | 30 | 69.0301 | 5 | 1 | 3 | 0.02 | 203791 | 1.1 | 1 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
1955 | CR0013025 | CTASK0023749 | Closed | OPUS-BKG-M | Kieu Le | 24 | 24 | 2020-12-31 08:58 | 2020-12-01 08:58 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] NA *Standby* Issue with 'Guided' return results in the Standby Booking Status Report | 2020-12-23 08:34 | 2021-01-14 | 2021-01-12 13:15 | 2021-09-23 13:23 | 2021-09-23 13:55 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-24 08:45 | 2021-10-13 12:00 | CR0013025 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W40 | 2021-10 | 48 | 48 | 285.9766 | 4 | 1 | 1 | 0.01 | 153106 | 2.2 | 2 | 0 | 0 | 1 |  | 3 | 5 | 26 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
1956 | CR0013025 | CTASK0023747 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2020-11-27 08:55 | 2020-11-23 08:54 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] NA *Standby* Issue with 'Guided' return results in the Standby Booking Status Report | 2020-12-23 08:34 | 2021-01-14 | 2021-01-12 13:15 | 2021-09-23 13:23 | 2021-09-23 13:55 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-24 08:45 | 2021-10-13 12:00 | CR0013025 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W40 | 2021-10 | 48 | 48 | 285.9766 | 4 | 1 | 1 | 0.01 | 153106 | 2.2 | 2 | 0 | 0 | 1 |  | 3 | 5 | 26 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
1957 | CR0013025 | CTASK0023752 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-01-29 09:01 | 2021-01-01 09:01 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] NA *Standby* Issue with 'Guided' return results in the Standby Booking Status Report | 2020-12-23 08:34 | 2021-01-14 | 2021-01-12 13:15 | 2021-09-23 13:23 | 2021-09-23 13:55 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-24 08:45 | 2021-10-13 12:00 | CR0013025 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W40 | 2021-10 | 48 | 48 | 285.9766 | 4 | 1 | 1 | 0.01 | 153106 | 2.2 | 2 | 0 | 0 | 1 |  | 3 | 5 | 26 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
1958 | CR0013025 | CTASK0023753 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-09-30 09:02 | 2021-09-27 00:02 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] NA *Standby* Issue with 'Guided' return results in the Standby Booking Status Report | 2020-12-23 08:34 | 2021-01-14 | 2021-01-12 13:15 | 2021-09-23 13:23 | 2021-09-23 13:55 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-24 08:45 | 2021-10-13 12:00 | CR0013025 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W40 | 2021-10 | 48 | 48 | 285.9766 | 4 | 1 | 1 | 0.01 | 153106 | 2.2 | 2 | 0 | 0 | 1 |  | 3 | 5 | 26 | 0.22951 | 0.13043 | 2020-12 | 0 | 0
1959 | CR0014677 | CTASK0030855 | Closed | OPUS-BKG-MFT-E | Nhut Nguyen Minh | 4 | 4 | 2021-12-31 18:08 | 2021-12-01 18:08 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [DEPLOY](HBA) EUA AUTH ¦ Including Place of Delivery as search and selection criteria for EUA Customs EDI for EG POD | 2021-12-16 16:09 | 2022-01-18 09:24 | 2022-01-18 08:21 | 2022-01-19 15:54 | 2022-01-20 09:48 |  | 2022-02-08 08:00 | 2022-02-08 08:00 | 2022-01-20 15:42 | 2022-02-15 12:00 | CR0014677 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W6 | 2022-02 | 24 | 24 | 53.6608 | 4 | 1 | 2 | 0.02 | 193512 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 6 | 30 | 0.2963 | 0 | 2021-12 | 0 | 0
1960 | CR0014677 | CTASK0030852 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 4 | 4 | 2021-12-31 17:15 | 2021-12-01 17:15 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [EST](HBA) EUA AUTH ¦ Including Place of Delivery as search and selection criteria for EUA Customs EDI for EG POD | 2021-12-16 16:09 | 2022-01-18 09:24 | 2022-01-18 08:21 | 2022-01-19 15:54 | 2022-01-20 09:48 |  | 2022-02-08 08:00 | 2022-02-08 08:00 | 2022-01-20 15:42 | 2022-02-15 12:00 | CR0014677 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W6 | 2022-02 | 24 | 24 | 53.6608 | 4 | 1 | 2 | 0.02 | 193606 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 6 | 30 | 4.25 | 0 | 2021-12 | 0 | 0
1961 | CR0014677 | CTASK0030854 | Closed | OPUS-BKG-MFT-E | Nhut Nguyen Minh | 8 | 8 | 2021-12-31 17:48 | 2021-12-01 17:48 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [TEST](HBA) EUA AUTH ¦ Including Place of Delivery as search and selection criteria for EUA Customs EDI for EG POD | 2021-12-16 16:09 | 2022-01-18 09:24 | 2022-01-18 08:21 | 2022-01-19 15:54 | 2022-01-20 09:48 |  | 2022-02-08 08:00 | 2022-02-08 08:00 | 2022-01-20 15:42 | 2022-02-15 12:00 | CR0014677 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W6 | 2022-02 | 24 | 24 | 53.6608 | 4 | 1 | 2 | 0.02 | 193512 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 6 | 30 | 0.2963 | 0 | 2021-12 | 0 | 0
1962 | CR0014677 | CTASK0030853 | Closed | OPUS-BKG-MFT-E | Nhut Nguyen Minh | 8 | 8 | 2021-12-31 22:07 | 2021-12-01 22:07 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [DEV](HBA) EUA AUTH ¦ Including Place of Delivery as search and selection criteria for EUA Customs EDI for EG POD | 2021-12-16 16:09 | 2022-01-18 09:24 | 2022-01-18 08:21 | 2022-01-19 15:54 | 2022-01-20 09:48 |  | 2022-02-08 08:00 | 2022-02-08 08:00 | 2022-01-20 15:42 | 2022-02-15 12:00 | CR0014677 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W6 | 2022-02 | 24 | 24 | 53.6608 | 4 | 1 | 2 | 0.02 | 193512 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 6 | 30 | 0.2963 | 0 | 2021-12 | 0 | 0
1963 | CR0014387 | CTASK0031497 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 15 | 15 | 2022-01-31 17:12 | 2022-01-01 17:12 | Container | Biz Common | Approval | Approval Confirm |  |  | [Jan 2022][Internal] Validation to avoid CSR approve & cancel at the same time | 2021-12-14 15:56 | 2022-01-28 15:56 | 2022-01-27 15:38 | 2022-02-14 11:07 | 2022-02-14 14:10 |  | 2022-02-22 10:00 | 2022-02-22 09:00 | 2022-02-14 14:27 | 2022-03-02 12:00 | CR0014387 | Biz CommonApprovalApproval Confirm | OPUS-APR | 2022-W8 | 2022-02 | 172 | 162 | 69.7526 | 6 | 2 | 4 | 0.1 | 203704 | 1.3 | 2 | 0 | 0 | 2 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
1964 | CR0014387 | CTASK0031239 | Closed | OPUS-SAP | Lien Le | 22 | 20 | 2021-12-31 15:05 | 2021-12-14 15:05 | Container | Biz Common | Approval | Approval Confirm |  |  | [DEC] Validation to avoid CSR approve & cancel at the same time | 2021-12-14 15:56 | 2022-01-28 15:56 | 2022-01-27 15:38 | 2022-02-14 11:07 | 2022-02-14 14:10 |  | 2022-02-22 10:00 | 2022-02-22 09:00 | 2022-02-14 14:27 | 2022-03-02 12:00 | CR0014387 | Biz CommonApprovalApproval Confirm | OPUS-APR | 2022-W8 | 2022-02 | 172 | 162 | 69.7526 | 6 | 2 | 4 | 0.1 | 193441 | 2.8 | 2 | 0 | 0 | 2 |  | 2 | 14 | 30 | 0.42308 | 0 | 2021-12 | 0 | 0
1965 | CR0014387 | CTASK0031240 | Closed | OPUS-SCO | Mohamed Hary | 20 | 20 | 2021-12-31 15:06 | 2021-12-14 15:05 | Container | Biz Common | Approval | Approval Confirm |  |  | [DEC] Validation to avoid CSR approve & cancel at the same time | 2021-12-14 15:56 | 2022-01-28 15:56 | 2022-01-27 15:38 | 2022-02-14 11:07 | 2022-02-14 14:10 |  | 2022-02-22 10:00 | 2022-02-22 09:00 | 2022-02-14 14:27 | 2022-03-02 12:00 | CR0014387 | Biz CommonApprovalApproval Confirm | OPUS-APR | 2022-W8 | 2022-02 | 172 | 162 | 69.7526 | 6 | 2 | 4 | 0.1 | 193489 | 2.5 | 2 | 0 | 0 | 2 |  | 2 | 14 | 30 | 0.72727 | 0 | 2021-12 | 0 | 0
1966 | CR0014387 | CTASK0031238 | Closed | OPUS-SAP | Chuong Ta | 55 | 50 | 2021-12-31 15:03 | 2021-12-14 15:03 | Container | Biz Common | Approval | Approval Confirm |  |  | [DEC] Validation to avoid CSR approve & cancel at the same time | 2021-12-14 15:56 | 2022-01-28 15:56 | 2022-01-27 15:38 | 2022-02-14 11:07 | 2022-02-14 14:10 |  | 2022-02-22 10:00 | 2022-02-22 09:00 | 2022-02-14 14:27 | 2022-03-02 12:00 | CR0014387 | Biz CommonApprovalApproval Confirm | OPUS-APR | 2022-W8 | 2022-02 | 172 | 162 | 69.7526 | 6 | 2 | 4 | 0.1 | 183379 | 2.8 | 2 | 0 | 0 | 2 |  | 2 | 14 | 30 | 0.32 | 0.375 | 2021-12 | 0 | 0
1967 | CR0014387 | CTASK0031496 | Closed | OPUS-SCO | Chuong Ta | 40 | 37 | 2022-01-31 17:11 | 2022-01-01 17:11 | Container | Biz Common | Approval | Approval Confirm |  |  | [Jan 2022] [Internal] Validation to avoid CSR approve & cancel at the same time | 2021-12-14 15:56 | 2022-01-28 15:56 | 2022-01-27 15:38 | 2022-02-14 11:07 | 2022-02-14 14:10 |  | 2022-02-22 10:00 | 2022-02-22 09:00 | 2022-02-14 14:27 | 2022-03-02 12:00 | CR0014387 | Biz CommonApprovalApproval Confirm | OPUS-APR | 2022-W8 | 2022-02 | 172 | 162 | 69.7526 | 6 | 2 | 4 | 0.1 | 183379 | 2.8 | 2 | 0 | 0 | 2 |  | 2 | 14 | 30 | 0.32 | 0.375 | 2021-12 | 0 | 0
1968 | CR0014387 | CTASK0031241 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 20 | 20 | 2021-12-31 15:06 | 2021-12-14 15:06 | Container | Biz Common | Approval | Approval Confirm |  |  | [DEC] Validation to avoid CSR approve & cancel at the same time | 2021-12-14 15:56 | 2022-01-28 15:56 | 2022-01-27 15:38 | 2022-02-14 11:07 | 2022-02-14 14:10 |  | 2022-02-22 10:00 | 2022-02-22 09:00 | 2022-02-14 14:27 | 2022-03-02 12:00 | CR0014387 | Biz CommonApprovalApproval Confirm | OPUS-APR | 2022-W8 | 2022-02 | 172 | 162 | 69.7526 | 6 | 2 | 4 | 0.1 | 203704 | 1.3 | 2 | 0 | 0 | 2 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
1969 | CR0015289 | CTASK0033966 | Closed | OPUS-TPB | Manh Nguyen | 33 | 35 | 2022-05-31 13:45 | 2022-05-03 13:45 | Container | Service Management | 3rd Party Billing | TPB Process | TPB Manual Registration |  | [All] EUA - make booking number a non mandatory field in TPB for MNR expense type. | 2022-04-27 08:21 | 2022-05-13 20:21 | 2022-05-13 07:58 | 2022-05-24 09:03 | 2022-05-24 09:26 |  | 2022-05-31 09:30 | 2022-05-31 09:00 | 2022-05-26 12:31 | 2022-06-07 12:00 | CR0015289 | Service Management3rd Party BillingTPB ProcessTPB Manual Registration | OPUS-TPB | 2022-W22 | 2022-05 | 33 | 40 | 34.0477 | 2 | 1 | 1 | 0.05 | 153138 | 3.6 | 1 | 0 | 0 | 1 |  | 1 | 7 | 26 | 0.16667 | 0 | 2022-04 | 0 | 0
1970 | CR0015289 | CTASK0033287 | Closed | OPUS-TPB | Manh Nguyen | 5 | 5 | 2022-04-29 15:38 | 2022-04-01 15:38 | Container | Service Management | 3rd Party Billing | TPB Process | TPB Manual Registration |  | [Analysis] EUA - make booking number a non mandatory field in TPB for MNR expense type. | 2022-04-27 08:21 | 2022-05-13 20:21 | 2022-05-13 07:58 | 2022-05-24 09:03 | 2022-05-24 09:26 |  | 2022-05-31 09:30 | 2022-05-31 09:00 | 2022-05-26 12:31 | 2022-06-07 12:00 | CR0015289 | Service Management3rd Party BillingTPB ProcessTPB Manual Registration | OPUS-TPB | 2022-W22 | 2022-05 | 33 | 40 | 34.0477 | 2 | 1 | 1 | 0.05 | 153138 | 3.6 | 1 | 0 | 0 | 1 |  | 1 | 7 | 26 | 0.16667 | 0 | 2022-04 | 0 | 0
1971 | CR0014717 | CTASK0030308 | Closed | OPUS-CTM | Phu Nguyen Hoang | 20 | 23 |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | [Documentation][CLT Internal] Adding validation for delete CHS/MGS error case | 2021-11-08 10:46 | 2021-11-17 16:30 | 2021-11-17 14:29 | 2021-11-29 11:46 | 2021-12-01 08:56 |  | 2021-12-07 08:55 | 2021-12-07 09:34 | 2021-12-02 13:08 | 2021-12-14 12:01 | CR0014717 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2021-W49 | 2021-12 | 20 | 23 | 28.923 | 1 | 1 | 1 | 0.03 | 193463 | 2.7 | 1 | 0 | 0 | 1 |  | 1 | 10 | 26 | 0.16667 | 0 | 2021-11 | 0 | 0
1972 | CR0012586 | CTASK0024760 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-01-31 13:36 | 2021-01-18 13:36 | Container | Service Management | Booking/Documentation |  |  |  | [Design] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 193567 | 1.7 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.5625 | 0.53333 | 2021-04 | 4 | 1
1973 | CR0012586 | CTASK0024844 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 48 | 46 | 2021-06-19 | 2021-06-01 09:01 | Container | Service Management | Booking/Documentation |  |  |  | [Development] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 193488 | 1.8 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.53659 | 0.28125 | 2021-04 | 4 | 1
1974 | CR0012586 | CTASK0024837 | Closed | OPUS-BKG-M | Thien Lai | 24 | 24 | 2021-06-30 17:04 | 2021-06-01 17:04 | Container | Service Management | Booking/Documentation |  |  |  | [Testing] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 193567 | 1.7 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.5625 | 0.53333 | 2021-04 | 4 | 1
1975 | CR0012586 | CTASK0027151 | Closed | OPUS-BKG-M | Kieu Le | 20 | 20 | 2021-06-11 19:48 | 2021-06-01 00:48 | Container | Service Management | Booking/Documentation |  |  |  | [Development] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 153106 | 2.5 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.22951 | 0.13043 | 2021-04 | 4 | 1
1976 | CR0012586 | CTASK0024560 | Closed | OPUS-BKG-M | Kieu Le | 32 | 32 | 2021-01-29 15:02 | 2021-01-04 15:02 | Container | Service Management | Booking/Documentation |  |  |  | [Design] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 153106 | 2.5 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.22951 | 0.13043 | 2021-04 | 4 | 1
1977 | CR0012586 | CTASK0024846 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 10 | 8 | 2022-02-25 10:23 | 2022-02-21 10:22 | Container | Service Management | Booking/Documentation |  |  |  | [Deployment] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 193488 | 1.8 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.53659 | 0.28125 | 2021-04 | 4 | 1
1978 | CR0012586 | CTASK0024125 | Closed | OPUS-BKG-M | Kieu Le | 3 | 3 | 2020-12-31 15:01 | 2020-12-01 15:00 | Container | Service Management | Booking/Documentation |  |  |  | [Design] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 153106 | 2.5 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.22951 | 0.13043 | 2021-04 | 4 | 1
1979 | CR0012586 | CTASK0024839 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2022-02-25 18:45 | 2022-02-21 08:44 | Container | Service Management | Booking/Documentation |  |  |  | [Deployment] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 193567 | 1.7 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.5625 | 0.53333 | 2021-04 | 4 | 1
1980 | CR0012586 | CTASK0024845 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-07-23 13:40 | 2021-07-12 13:40 | Container | Service Management | Booking/Documentation |  |  |  | [Testing] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 193488 | 1.8 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.53659 | 0.28125 | 2021-04 | 4 | 1
1981 | CR0012586 | CTASK0024835 | Closed | OPUS-BKG-M | Thien Lai | 40 | 40 | 2021-06-30 17:04 | 2021-06-01 17:04 | Container | Service Management | Booking/Documentation |  |  |  | [Development] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 193567 | 1.7 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.5625 | 0.53333 | 2021-04 | 4 | 1
1982 | CR0012586 | CTASK0024736 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 21 | 21 | 2021-01-20 07:27 | 2021-01-14 23:27 | Container | Service Management | Booking/Documentation |  |  |  | [Design] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 193488 | 1.8 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.53659 | 0.28125 | 2021-04 | 4 | 1
1983 | CR0012586 | CTASK0024834 | Closed | OPUS-BKG-M | Kieu Le | 92 | 92 | 2021-05-31 09:05 | 2021-05-10 00:04 | Container | Service Management | Booking/Documentation |  |  |  | [Development] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 153106 | 2.5 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.22951 | 0.13043 | 2021-04 | 4 | 1
1984 | CR0012586 | CTASK0024838 | Closed | OPUS-BKG-M | Kieu Le | 24 | 24 | 2021-06-25 09:06 | 2021-06-01 09:06 | Container | Service Management | Booking/Documentation |  |  |  | [Testing] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 153106 | 2.5 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.22951 | 0.13043 | 2021-04 | 4 | 1
1985 | CR0012586 | CTASK0024840 | Closed | OPUS-BKG-M | Kieu Le | 23 | 23 | 2022-02-28 09:07 | 2022-02-07 09:07 | Container | Service Management | Booking/Documentation |  |  |  | [Deployment] NA *BKG* Broken Routes Update New UI | 2021-04-12 09:47 | 2021-07-28 22:00 | 2021-07-28 15:23 | 2022-01-28 07:03 | 2022-01-28 08:58 |  | 2022-03-08 08:00 | 2022-03-08 08:00 | 2022-02-21 08:05 | 2022-03-15 12:00 | CR0012586 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 361 | 357 | 329.9256 | 14 | 1 | 3 | 0.05 | 153106 | 2.5 | 5 | 4 | 0 | 4 |  | 4 | 8 | 38 | 0.22951 | 0.13043 | 2021-04 | 4 | 1
1986 | CR0014621 | CTASK0030112 | Closed | OPUS-PRI | Ngan Nham | 33 | 33 | 2021-10-29 23:00 | 2021-10-24 23:00 | Container | Biz Common | Master Data | Partner |  |  | [Develop] [Oct] Additional indicator to be added in both Customer Integration and Group Customer Code | 2021-10-28 06:34 | 2021-11-19 23:00 | 2021-11-15 09:01 | 2022-01-06 16:13 | 2022-01-11 13:46 |  | 2022-01-18 10:00 | 2022-01-18 10:50 | 2022-01-14 08:48 | 2022-01-25 12:00 | CR0014621 | Biz CommonMaster DataPartner | OPUS-PRI | 2022-W3 | 2022-01 | 33 | 33 | 82.1428 | 1 | 1 | 1 | 0.02 | 193461 | 2.9 | 1 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0.125 | 0 | 2021-10 | 0 | 0
1987 | CR0014882 | CTASK0031144 | Closed | OPUS-SCG | Tu Nguyen | 30 | 30 | 2021-12-31 16:00 | 2021-12-14 15:59 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] [CLT Internal] Fix issues related to Pre-Checking. | 2021-12-16 14:55 | 2021-12-21 14:54 | 2021-12-20 14:37 | 2021-12-28 07:22 | 2021-12-28 10:44 |  | 2022-01-11 08:00 | 2022-01-11 08:00 | 2021-12-28 15:34 | 2022-01-18 12:01 | CR0014882 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W2 | 2022-01 | 80 | 80 | 25.712 | 3 | 1 | 2 | 0.13 | 123045 | 3.2 | 0 | 0 | 0 | 1 |  | 1 | 7 | 33 | 0 | 0 | 2021-12 | 0 | 0
1988 | CR0014882 | CTASK0031141 | Closed | OPUS-SCG | Thuan Tran | 1 | 1 | 2021-12-31 15:52 | 2021-12-14 15:52 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Documentation] [CLT Internal] Fix issues related to Pre-Checking. | 2021-12-16 14:55 | 2021-12-21 14:54 | 2021-12-20 14:37 | 2021-12-28 07:22 | 2021-12-28 10:44 |  | 2022-01-11 08:00 | 2022-01-11 08:00 | 2021-12-28 15:34 | 2022-01-18 12:01 | CR0014882 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W2 | 2022-01 | 80 | 80 | 25.712 | 3 | 1 | 2 | 0.13 | 183423 | 3.1 | 0 | 0 | 0 | 1 |  | 1 | 7 | 33 | 0 | 0 | 2021-12 | 0 | 0
1989 | CR0014882 | CTASK0031143 | Closed | OPUS-SCG | Thuan Tran | 50 | 50 | 2021-12-31 15:59 | 2021-12-14 15:59 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] [CLT Internal] Fix issues related to Pre-Checking. | 2021-12-16 14:55 | 2021-12-21 14:54 | 2021-12-20 14:37 | 2021-12-28 07:22 | 2021-12-28 10:44 |  | 2022-01-11 08:00 | 2022-01-11 08:00 | 2021-12-28 15:34 | 2022-01-18 12:01 | CR0014882 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W2 | 2022-01 | 80 | 80 | 25.712 | 3 | 1 | 2 | 0.13 | 183423 | 3.1 | 0 | 0 | 0 | 1 |  | 1 | 7 | 33 | 0 | 0 | 2021-12 | 0 | 0
1990 | CR0014591 | CTASK0029916 | Closed | OPUS-VSK | Linh Nguyen | 1 | 1 |  |  | Container | Vessel Operation | Vessel Schedule | VSL SKD | VSL SKD Inquiry |  | [Documentation]VVD CNFT0002E - CNNGB07 not in search result of VSL SKD Inquiry by Port | 2021-10-14 17:56 | 2021-11-02 17:55 | 2021-10-27 14:06 | 2021-10-28 08:37 | 2021-11-01 08:35 |  | 2021-11-09 20:33 | 2021-11-09 07:43 | 2021-11-02 14:38 | 2021-11-17 12:00 | CR0014591 | Vessel OperationVessel ScheduleVSL SKDVSL SKD Inquiry | OPUS-VSK | 2021-W45 | 2021-11 | 17 | 17 | 26.1094 | 2 | 1 | 1 | 0.03 | 193464 | 2.6 | 2 | 2 | 0 | 1 |  | 1 | 9 | 38 | 0.375 | 1.5 | 2021-10 | 2 | 1
1991 | CR0014591 | CTASK0029918 | Closed | OPUS-VSK | Linh Nguyen | 17 | 17 |  |  | Container | Vessel Operation | Vessel Schedule | VSL SKD | VSL SKD Inquiry |  | [CLV-VSK]VVD CNFT0002E - CNNGB07 not in search result of VSL SKD Inquiry by Port | 2021-10-14 17:56 | 2021-11-02 17:55 | 2021-10-27 14:06 | 2021-10-28 08:37 | 2021-11-01 08:35 |  | 2021-11-09 20:33 | 2021-11-09 07:43 | 2021-11-02 14:38 | 2021-11-17 12:00 | CR0014591 | Vessel OperationVessel ScheduleVSL SKDVSL SKD Inquiry | OPUS-VSK | 2021-W45 | 2021-11 | 17 | 17 | 26.1094 | 2 | 1 | 1 | 0.03 | 193464 | 2.6 | 2 | 2 | 0 | 1 |  | 1 | 9 | 38 | 0.375 | 1.5 | 2021-10 | 2 | 1
1992 | CR0014097 | CTASK0027955 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-10-08 21:53 | 2021-10-04 08:52 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing]*ESA-JPN* Hide/Mask Vessel name and/or Teminal Name on BRN when Hide/Mask Flag = Y in VSK UIs | 2021-10-05 06:56 | 2021-10-13 22:00 | 2021-10-12 07:25 | 2022-02-21 15:02 | 2022-02-21 15:24 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-22 14:50 | 2022-03-10 12:00 | CR0014097 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W9 | 2022-03 | 42 | 42 | 148.0442 | 4 | 1 | 1 | 0.01 | 193488 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.53659 | 0 | 2021-10 | 0 | 0
1993 | CR0014097 | CTASK0027866 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2021-07-07 | 2021-07-01 09:33 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] *ESA-JPN* Hide/Mask Vessel name and/or Teminal Name on BRN when Hide/Mask Flag = Y in VSK UIs | 2021-10-05 06:56 | 2021-10-13 22:00 | 2021-10-12 07:25 | 2022-02-21 15:02 | 2022-02-21 15:24 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-22 14:50 | 2022-03-10 12:00 | CR0014097 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W9 | 2022-03 | 42 | 42 | 148.0442 | 4 | 1 | 1 | 0.01 | 193488 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.53659 | 0 | 2021-10 | 0 | 0
1994 | CR0014097 | CTASK0027954 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 24 | 24 | 2021-09-24 20:10 | 2021-09-20 09:10 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] *ESA-JPN* Hide/Mask Vessel name and/or Teminal Name on BRN when Hide/Mask Flag = Y in VSK UIs | 2021-10-05 06:56 | 2021-10-13 22:00 | 2021-10-12 07:25 | 2022-02-21 15:02 | 2022-02-21 15:24 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-22 14:50 | 2022-03-10 12:00 | CR0014097 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W9 | 2022-03 | 42 | 42 | 148.0442 | 4 | 1 | 1 | 0.01 | 193488 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.53659 | 0 | 2021-10 | 0 | 0
1995 | CR0014097 | CTASK0027956 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2022-02-25 15:13 | 2022-02-21 15:13 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment]*ESA-JPN* Hide/Mask Vessel name and/or Teminal Name on BRN when Hide/Mask Flag = Y in VSK UIs | 2021-10-05 06:56 | 2021-10-13 22:00 | 2021-10-12 07:25 | 2022-02-21 15:02 | 2022-02-21 15:24 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-22 14:50 | 2022-03-10 12:00 | CR0014097 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W9 | 2022-03 | 42 | 42 | 148.0442 | 4 | 1 | 1 | 0.01 | 193488 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.53659 | 0 | 2021-10 | 0 | 0
1996 | CR0015071 | CTASK0032118 | Closed | OPUS-SCG | Trang Duy Thong | 74 | 74 | 2022-03-11 10:05 | 2022-02-14 10:04 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV][CLT Internal] Enhancement - Send Normal IFTMBF EDI using Back End Job | 2022-02-08 09:28 | 2022-03-25 09:27 | 2022-03-23 09:48 | 2022-04-13 15:49 | 2022-04-18 09:09 |  | 2022-04-26 09:00 | 2022-04-26 09:59 | 2022-04-21 09:26 | 2022-05-03 12:00 | CR0015071 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W17 | 2022-04 | 96 | 98 | 76.9807 | 2 | 1 | 1 | 0.05 | 193511 | 1.7 | 1 | 7 | 0 | 1 |  | 2 | 6 | 18 | 0.81818 | 2.6667 | 2022-02 | 7 | 1
1997 | CR0015071 | CTASK0032034 | Closed | OPUS-SCG | Trang Duy Thong | 22 | 24 | 2022-03-25 09:54 | 2022-01-27 09:54 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Documentation][CLT Internal] Enhancement - Send Normal IFTMBF EDI using Back End Job | 2022-02-08 09:28 | 2022-03-25 09:27 | 2022-03-23 09:48 | 2022-04-13 15:49 | 2022-04-18 09:09 |  | 2022-04-26 09:00 | 2022-04-26 09:59 | 2022-04-21 09:26 | 2022-05-03 12:00 | CR0015071 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W17 | 2022-04 | 96 | 98 | 76.9807 | 2 | 1 | 1 | 0.05 | 193511 | 1.7 | 1 | 7 | 0 | 1 |  | 2 | 6 | 18 | 0.81818 | 2.6667 | 2022-02 | 7 | 1
1998 | CR0014258 | CTASK0031604 | Closed | OPUS-SCO | Cuong Tran Hung | 16 | 18 | 2022-01-31 18:22 | 2022-01-01 18:22 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Jan 2022] change to CLEAR logic for BATCH Promise fulfill and BATCH Case Close | 2021-11-03 11:03 | 2022-01-14 11:03 | 2022-01-13 09:47 | 2022-04-06 12:57 | 2022-04-07 08:39 |  | 2022-04-12 10:00 | 2022-04-12 16:07 | 2022-04-08 13:38 | 2022-04-20 12:00 | CR0014258 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2022-W15 | 2022-04 | 265 | 252 | 159.9562 | 7 | 1 | 6 | 0.07 | 193530 | 2.4 | 1 | 1 | 0 | 3 |  | 3 | 2 | 18 | 1.2308 | 1.25 | 2021-11 | 1 | 1
1999 | CR0014258 | CTASK0030333 | Closed | OPUS-SCO | Nguyen Ha Vi | 63 | 60 | 2021-11-30 09:52 | 2021-11-01 09:52 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Nov 2021] change to CLEAR logic for BATCH Promise fulfill and BATCH Case Close | 2021-11-03 11:03 | 2022-01-14 11:03 | 2022-01-13 09:47 | 2022-04-06 12:57 | 2022-04-07 08:39 |  | 2022-04-12 10:00 | 2022-04-12 16:07 | 2022-04-08 13:38 | 2022-04-20 12:00 | CR0014258 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2022-W15 | 2022-04 | 265 | 252 | 159.9562 | 7 | 1 | 6 | 0.07 | 203664 | 1.4 | 1 | 1 | 0 | 3 |  | 3 | 2 | 18 | 1.8182 | 2.5 | 2021-11 | 1 | 1
2000 | CR0014258 | CTASK0030336 | Closed | OPUS-SCO | Chuong Ta | 22 | 20 | 2021-11-30 09:58 | 2021-11-01 09:58 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Nov 2021] change to CLEAR logic for BATCH Promise fulfill and BATCH Case Close | 2021-11-03 11:03 | 2022-01-14 11:03 | 2022-01-13 09:47 | 2022-04-06 12:57 | 2022-04-07 08:39 |  | 2022-04-12 10:00 | 2022-04-12 16:07 | 2022-04-08 13:38 | 2022-04-20 12:00 | CR0014258 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2022-W15 | 2022-04 | 265 | 252 | 159.9562 | 7 | 1 | 6 | 0.07 | 183379 | 2.7 | 1 | 1 | 0 | 3 |  | 3 | 2 | 18 | 0.32 | 0.375 | 2021-11 | 1 | 1
2001 | CR0014258 | CTASK0030335 | Closed | OPUS-SCO | Mohamed Hary | 40 | 40 | 2021-11-30 09:56 | 2021-11-01 09:56 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Nov 2021] change to CLEAR logic for BATCH Promise fulfill and BATCH Case Close | 2021-11-03 11:03 | 2022-01-14 11:03 | 2022-01-13 09:47 | 2022-04-06 12:57 | 2022-04-07 08:39 |  | 2022-04-12 10:00 | 2022-04-12 16:07 | 2022-04-08 13:38 | 2022-04-20 12:00 | CR0014258 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2022-W15 | 2022-04 | 265 | 252 | 159.9562 | 7 | 1 | 6 | 0.07 | 193489 | 2.4 | 1 | 1 | 0 | 3 |  | 3 | 2 | 18 | 0.72727 | 0 | 2021-11 | 1 | 1
2002 | CR0014258 | CTASK0030332 | Closed | OPUS-SCO | Lien Le | 66 | 60 | 2021-11-30 09:51 | 2021-11-01 09:51 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Nov 2021] change to CLEAR logic for BATCH Promise fulfill and BATCH Case Close | 2021-11-03 11:03 | 2022-01-14 11:03 | 2022-01-13 09:47 | 2022-04-06 12:57 | 2022-04-07 08:39 |  | 2022-04-12 10:00 | 2022-04-12 16:07 | 2022-04-08 13:38 | 2022-04-20 12:00 | CR0014258 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2022-W15 | 2022-04 | 265 | 252 | 159.9562 | 7 | 1 | 6 | 0.07 | 193441 | 2.7 | 1 | 1 | 0 | 3 |  | 3 | 2 | 18 | 0.42308 | 0 | 2021-11 | 1 | 1
2003 | CR0014258 | CTASK0030334 | Closed | OPUS-SCO | Cuong Tran Hung | 33 | 30 | 2021-11-30 09:53 | 2021-11-01 09:53 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Nov 2021] change to CLEAR logic for BATCH Promise fulfill and BATCH Case Close | 2021-11-03 11:03 | 2022-01-14 11:03 | 2022-01-13 09:47 | 2022-04-06 12:57 | 2022-04-07 08:39 |  | 2022-04-12 10:00 | 2022-04-12 16:07 | 2022-04-08 13:38 | 2022-04-20 12:00 | CR0014258 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2022-W15 | 2022-04 | 265 | 252 | 159.9562 | 7 | 1 | 6 | 0.07 | 193530 | 2.4 | 1 | 1 | 0 | 3 |  | 3 | 2 | 18 | 1.2308 | 1.25 | 2021-11 | 1 | 1
2004 | CR0014258 | CTASK0030337 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 25 | 24 | 2021-11-30 10:01 | 2021-11-01 10:01 | Container | Statement Management | Statement Account Receivable | Collection Manager |  |  | [Nov 2021] change to CLEAR logic for BATCH Promise fulfill and BATCH Case Close | 2021-11-03 11:03 | 2022-01-14 11:03 | 2022-01-13 09:47 | 2022-04-06 12:57 | 2022-04-07 08:39 |  | 2022-04-12 10:00 | 2022-04-12 16:07 | 2022-04-08 13:38 | 2022-04-20 12:00 | CR0014258 | Statement ManagementStatement Account ReceivableCollection Manager | OPUS-SAR | 2022-W15 | 2022-04 | 265 | 252 | 159.9562 | 7 | 1 | 6 | 0.07 | 203704 | 1.2 | 1 | 1 | 0 | 3 |  | 3 | 2 | 18 | 0 | 0 | 2021-11 | 1 | 1
2005 | CR0014117 | CTASK0028383 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 20 | 16 | 2021-08-31 11:23 | 2021-08-01 11:23 | Container | Equipment Management | CNTR Master |  |  |  | [202108] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes). | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 183432 | 2.4 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.043478 | 0.22222 | 2021-07 | 1 | 1
2006 | CR0014117 | CTASK0028385 | Closed | OPUS-TRS | Giang Nguyen Hoang | 16 | 16 | 2021-08-31 11:24 | 2021-08-01 11:24 | Container | Equipment Management | CNTR Master |  |  |  | [202108] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes). | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 183440 | 2.4 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0 | 0 | 2021-07 | 1 | 1
2007 | CR0014117 | CTASK0028381 | Closed | OPUS-TRS | Giang Nguyen Hoang | 16 | 16 | 2021-07-31 11:22 | 2021-07-27 11:22 | Container | Equipment Management | CNTR Master |  |  |  | [202107] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes). | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 183440 | 2.4 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0 | 0 | 2021-07 | 1 | 1
2008 | CR0014117 | CTASK0029126 | Closed | OPUS-TES | Thai Nguyen | 100 | 100 | 2021-09-30 22:00 | 2021-09-01 | Container | Equipment Management | CNTR Master |  |  |  | [202109] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes) | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 173249 | 2.8 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.89474 | 0.5 | 2021-07 | 1 | 1
2009 | CR0014117 | CTASK0030231 | Closed | OPUS-TES | Thai Nguyen | 1 | 1 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Equipment Management | CNTR Master |  |  |  | [202111] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes) | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 173249 | 2.8 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.89474 | 0.5 | 2021-07 | 1 | 1
2010 | CR0014117 | CTASK0029689 | Closed | OPUS-TES | Thai Nguyen | 81 | 80 | 2021-10-29 20:00 | 2021-10-01 04:00 | Container | Equipment Management | CNTR Master |  |  |  | [202110] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes) | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 173249 | 2.8 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.89474 | 0.5 | 2021-07 | 1 | 1
2011 | CR0014117 | CTASK0027985 | Closed | OPUS-BKG-RPT | Nam Nguyen | 53 | 60 | 2021-08-30 21:19 | 2021-08-02 21:19 | Container | Equipment Management | CNTR Master |  |  |  | [Development & Testing] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes). | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 123048 | 2.8 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.22222 | 0.047619 | 2021-07 | 1 | 1
2012 | CR0014117 | CTASK0028380 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 13 | 16 | 2021-07-31 11:22 | 2021-07-27 11:22 | Container | Equipment Management | CNTR Master |  |  |  | [202107] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes). | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 183432 | 2.4 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.043478 | 0.22222 | 2021-07 | 1 | 1
2013 | CR0014117 | CTASK0027986 | Closed | OPUS-BKG-RPT | Nam Nguyen | 12 | 16 | 2021-12-10 21:58 | 2021-12-01 21:57 | Container | Equipment Management | CNTR Master |  |  |  | [Deployment] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes). | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 123048 | 2.8 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.22222 | 0.047619 | 2021-07 | 1 | 1
2014 | CR0014117 | CTASK0027921 | Closed | OPUS-TES | Thai Nguyen | 22 | 25 | 2021-07-30 20:00 | 2021-07-01 | Container | Equipment Management | CNTR Master |  |  |  | [202107] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes) | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 173249 | 2.8 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.89474 | 0.5 | 2021-07 | 1 | 1
2015 | CR0014117 | CTASK0031044 | Closed | OPUS-TES | Thai Nguyen | 5 | 5 | 2021-12-31 20:00 | 2021-12-01 06:00 | Container | Equipment Management | CNTR Master |  |  |  | [202112] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes) | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 173249 | 2.8 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.89474 | 0.5 | 2021-07 | 1 | 1
2016 | CR0014117 | CTASK0028481 | Closed | OPUS-TES | Thai Nguyen | 1 | 1 | 2021-08-31 22:00 | 2021-08-01 | Container | Equipment Management | CNTR Master |  |  |  | [202108] Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes) | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 173249 | 2.8 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.89474 | 0.5 | 2021-07 | 1 | 1
2017 | CR0014117 | CTASK0027971 | Closed | OPUS-BKG-RPT | Nam Nguyen | 8 | 8 | 2021-08-31 21:58 | 2021-08-22 21:58 | Container | Equipment Management | CNTR Master |  |  |  | [Design]Creation of new O5 Ty/Sz in OPUS to handle the increasing number of O5 (40' Open Top High Cubes). | 2021-07-26 13:32 | 2021-10-15 18:00 | 2021-10-14 11:57 | 2021-12-03 13:55 | 2021-12-08 07:38 |  | 2021-12-14 08:30 | 2021-12-14 10:00 | 2021-12-08 15:52 | 2021-12-22 12:00 | CR0014117 | Equipment ManagementCNTR Master | OPUS-MST | 2021-W50 | 2021-12 | 338 | 359 | 140.79 | 13 | 3 | 4 | 0.11 | 123048 | 2.8 | 5 | 0 | 1 | 4 |  | 2 | 6 | 26 | 0.22222 | 0.047619 | 2021-07 | 1 | 1
2018 | CR0014613 | CTASK0030175 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 5 | 10 |  |  | Container | Service Management | Trans S/O |  |  |  | [202110][EUA – Extend auto S/O deletion logic for EUA region to delete S/O without W/O after 90 days] | 2021-10-27 13:05 | 2021-11-05 22:00 | 2021-11-01 17:20 | 2021-11-10 07:59 | 2021-11-11 11:22 |  | 2021-11-16 11:24 | 2021-11-03 18:58 | 2021-11-12 11:30 | 2021-11-24 12:00 | CR0014613 | Service ManagementTrans S/O | OPUS-TRS | 2021-W46 | 2021-11 | 29 | 34 | 19.9299 | 3 | 1 | 2 | 0.07 | 183432 | 2.6 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0.22222 | 2021-10 | 0 | 0
2019 | CR0014613 | CTASK0030024 | Closed | OPUS-TRS | Giang Nguyen Hoang | 20 | 20 |  |  | Container | Service Management | Trans S/O |  |  |  | [202110][EUA – Extend auto S/O deletion logic for EUA region to delete S/O without W/O after 90 days] | 2021-10-27 13:05 | 2021-11-05 22:00 | 2021-11-01 17:20 | 2021-11-10 07:59 | 2021-11-11 11:22 |  | 2021-11-16 11:24 | 2021-11-03 18:58 | 2021-11-12 11:30 | 2021-11-24 12:00 | CR0014613 | Service ManagementTrans S/O | OPUS-TRS | 2021-W46 | 2021-11 | 29 | 34 | 19.9299 | 3 | 1 | 2 | 0.07 | 183440 | 2.6 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0 | 2021-10 | 0 | 0
2020 | CR0014613 | CTASK0030518 | Closed | OPUS-TRS | Giang Nguyen Hoang | 4 | 4 |  |  | Container | Service Management | Trans S/O |  |  |  | [202111][EUA – Extend auto S/O deletion logic for EUA region to delete S/O without W/O after 90 days] | 2021-10-27 13:05 | 2021-11-05 22:00 | 2021-11-01 17:20 | 2021-11-10 07:59 | 2021-11-11 11:22 |  | 2021-11-16 11:24 | 2021-11-03 18:58 | 2021-11-12 11:30 | 2021-11-24 12:00 | CR0014613 | Service ManagementTrans S/O | OPUS-TRS | 2021-W46 | 2021-11 | 29 | 34 | 19.9299 | 3 | 1 | 2 | 0.07 | 183440 | 2.6 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0 | 2021-10 | 0 | 0
2021 | CR0014831 | CTASK0030977 | Closed | OPUS-SCG | Trang Duy Thong | 18 | 18 | 2022-01-28 14:03 | 2021-12-08 14:03 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval |  |  | [CLV] OPUS Enhancement Request - Adding New Column in Auto Generated Partner CNTR Update Report (%Checked) | 2021-12-13 16:19 | 2022-01-14 16:19 | 2022-01-13 09:31 | 2022-01-29 07:22 | 2022-02-08 14:02 |  | 2022-02-15 14:00 | 2022-02-15 08:58 | 2022-02-11 16:04 | 2022-02-22 12:00 | CR0014831 | Vessel OperationSpecial CargoSPCL CGO Approval | OPUS-SCG | 2022-W7 | 2022-02 | 36 | 36 | 63.9035 | 2 | 1 | 1 | 0.02 | 193511 | 1.5 | 2 | 4 | 0 | 1 |  | 2 | 10 | 30 | 0.81818 | 2.6667 | 2021-12 | 4 | 1
2022 | CR0014831 | CTASK0030976 | Closed | OPUS-SCG | Trang Duy Thong | 18 | 18 | 2022-01-28 14:02 | 2021-12-08 14:02 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval |  |  | [Documentation] OPUS Enhancement Request - Adding New Column in Auto Generated Partner CNTR Update Report (%Checked) | 2021-12-13 16:19 | 2022-01-14 16:19 | 2022-01-13 09:31 | 2022-01-29 07:22 | 2022-02-08 14:02 |  | 2022-02-15 14:00 | 2022-02-15 08:58 | 2022-02-11 16:04 | 2022-02-22 12:00 | CR0014831 | Vessel OperationSpecial CargoSPCL CGO Approval | OPUS-SCG | 2022-W7 | 2022-02 | 36 | 36 | 63.9035 | 2 | 1 | 1 | 0.02 | 193511 | 1.5 | 2 | 4 | 0 | 1 |  | 2 | 10 | 30 | 0.81818 | 2.6667 | 2021-12 | 4 | 1
2023 | CR0014247 | CTASK0029128 | Closed | OPUS-TES | Thai Nguyen | 20 | 20 | 2021-09-30 22:00 | 2021-09-01 | Container | Service Management | TML INV |  |  |  | [202109] GHQ - Add new TES Cost Code(SVXXJP) | 2021-08-27 09:07 | 2021-09-24 21:06 | 2021-09-24 08:53 | 2021-10-18 11:16 | 2021-10-18 13:46 |  | 2021-10-26 09:30 | 2021-10-26 07:52 | 2021-10-20 15:59 | 2021-11-02 12:00 | CR0014247 | Service ManagementTML INV | OPUS-TES | 2021-W43 | 2021-10 | 43 | 42 | 60.0158 | 3 | 1 | 1 | 0.03 | 173249 | 2.9 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.89474 | 0.5 | 2021-08 | 0 | 0
2024 | CR0014247 | CTASK0028867 | Closed | OPUS-TES | Thai Nguyen | 17 | 17 | 2021-08-31 22:00 | 2021-08-01 | Container | Service Management | TML INV |  |  |  | [202108] GHQ - Add new TES Cost Code(SVXXJP) | 2021-08-27 09:07 | 2021-09-24 21:06 | 2021-09-24 08:53 | 2021-10-18 11:16 | 2021-10-18 13:46 |  | 2021-10-26 09:30 | 2021-10-26 07:52 | 2021-10-20 15:59 | 2021-11-02 12:00 | CR0014247 | Service ManagementTML INV | OPUS-TES | 2021-W43 | 2021-10 | 43 | 42 | 60.0158 | 3 | 1 | 1 | 0.03 | 173249 | 2.9 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.89474 | 0.5 | 2021-08 | 0 | 0
2025 | CR0014247 | CTASK0029691 | Closed | OPUS-TES | Thai Nguyen | 6 | 5 | 2021-10-29 20:00 | 2021-10-01 04:00 | Container | Service Management | TML INV |  |  |  | [202110] GHQ - Add new TES Cost Code(SVXXJP) | 2021-08-27 09:07 | 2021-09-24 21:06 | 2021-09-24 08:53 | 2021-10-18 11:16 | 2021-10-18 13:46 |  | 2021-10-26 09:30 | 2021-10-26 07:52 | 2021-10-20 15:59 | 2021-11-02 12:00 | CR0014247 | Service ManagementTML INV | OPUS-TES | 2021-W43 | 2021-10 | 43 | 42 | 60.0158 | 3 | 1 | 1 | 0.03 | 173249 | 2.9 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.89474 | 0.5 | 2021-08 | 0 | 0
2026 | CR0014436 | CTASK0029575 | Closed | OPUS-BKG-MFT-E | Linh Dinh Bo | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [Documentation]EUA Egypt ACI regulatory - EUA Customs EDI to have ACI references | 2021-10-14 08:00 | 2021-10-31 22:00 |  | 2021-11-03 17:24 | 2021-11-04 07:09 |  | 2021-11-09 08:09 | 2021-11-09 08:00 | 2021-11-04 07:19 | 2021-11-16 12:00 | CR0014436 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2021-W45 | 2021-11 | 65 | 50 | 26.0062 | 4 | 2 | 2 | 0.08 | 193522 | 2.4 | 1 | 2 | 0 | 1 |  | 1 | 9 | 38 | 0 | 0 | 2021-10 | 2 | 1
2027 | CR0014436 | CTASK0030018 | Closed | OPUS-BKG-MFT-A | Linh Dinh Bo | 10 | 10 | 2021-10-27 21:38 | 2021-10-10 21:38 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [Development+Testing+Deployment] EUA Egypt ACI regulatory - EUA Customs EDI to have ACI references | 2021-10-14 08:00 | 2021-10-31 22:00 |  | 2021-11-03 17:24 | 2021-11-04 07:09 |  | 2021-11-09 08:09 | 2021-11-09 08:00 | 2021-11-04 07:19 | 2021-11-16 12:00 | CR0014436 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2021-W45 | 2021-11 | 65 | 50 | 26.0062 | 4 | 2 | 2 | 0.08 | 193522 | 2.4 | 1 | 2 | 0 | 1 |  | 1 | 9 | 38 | 0 | 0 | 2021-10 | 2 | 1
2028 | CR0014436 | CTASK0029586 | Closed | OPUS-BKG-MFT-E | Linh Dinh Bo | 45 | 30 | 2021-10-16 17:30 | 2021-09-20 09:00 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [Development+Testing+Deployment] EUA Egypt ACI regulatory - EUA Customs EDI to have ACI references | 2021-10-14 08:00 | 2021-10-31 22:00 |  | 2021-11-03 17:24 | 2021-11-04 07:09 |  | 2021-11-09 08:09 | 2021-11-09 08:00 | 2021-11-04 07:19 | 2021-11-16 12:00 | CR0014436 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2021-W45 | 2021-11 | 65 | 50 | 26.0062 | 4 | 2 | 2 | 0.08 | 193522 | 2.4 | 1 | 2 | 0 | 1 |  | 1 | 9 | 38 | 0 | 0 | 2021-10 | 2 | 1
2029 | CR0014436 | CTASK0029463 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 10 | 10 | 2021-09-24 17:30 | 2021-09-13 09:00 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [Estimation] EUA Egypt ACI regulatory - EUA Customs EDI to have ACI references | 2021-10-14 08:00 | 2021-10-31 22:00 |  | 2021-11-03 17:24 | 2021-11-04 07:09 |  | 2021-11-09 08:09 | 2021-11-09 08:00 | 2021-11-04 07:19 | 2021-11-16 12:00 | CR0014436 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2021-W45 | 2021-11 | 65 | 50 | 26.0062 | 4 | 2 | 2 | 0.08 | 173280 | 2.8 | 1 | 2 | 0 | 1 |  | 1 | 9 | 38 | 0.375 | 1 | 2021-10 | 2 | 1
2030 | CR0014291 | CTASK0030236 | Closed | OPUS-TPB | Manh Nguyen | 61 | 61 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Service Management | 3rd Party Billing | TPB Process | TPB Handling |  | [202111] TPB Invoices to Apply Credit Terms | 2021-11-16 11:27 | 2022-01-14 20:00 | 2022-01-14 08:23 | 2022-02-16 12:12 | 2022-02-16 15:01 |  | 2022-03-08 09:30 | 2022-03-08 09:15 | 2022-03-02 12:16 | 2022-03-15 12:00 | CR0014291 | Service Management3rd Party BillingTPB ProcessTPB Handling | OPUS-TPB | 2022-W10 | 2022-03 | 199 | 222 | 111.9185 | 6 | 1 | 1 | 0.08 | 153138 | 3.1 | 1 | 2 | 0 | 3 |  | 2 | 8 | 38 | 0.16667 | 0 | 2021-11 | 2 | 1
2031 | CR0014291 | CTASK0029120 | Closed | OPUS-TPB | Manh Nguyen | 1 | 1 | 2021-09-30 22:00 | 2021-09-01 | Container | Service Management | 3rd Party Billing | TPB Process | TPB Handling |  | [202109] TPB Invoices to Apply Credit Terms | 2021-11-16 11:27 | 2022-01-14 20:00 | 2022-01-14 08:23 | 2022-02-16 12:12 | 2022-02-16 15:01 |  | 2022-03-08 09:30 | 2022-03-08 09:15 | 2022-03-02 12:16 | 2022-03-15 12:00 | CR0014291 | Service Management3rd Party BillingTPB ProcessTPB Handling | OPUS-TPB | 2022-W10 | 2022-03 | 199 | 222 | 111.9185 | 6 | 1 | 1 | 0.08 | 153138 | 3.1 | 1 | 2 | 0 | 3 |  | 2 | 8 | 38 | 0.16667 | 0 | 2021-11 | 2 | 1
2032 | CR0014291 | CTASK0030890 | Closed | OPUS-TPB | Manh Nguyen | 72 | 80 | 2021-12-31 20:00 | 2021-12-01 06:00 | Container | Service Management | 3rd Party Billing | TPB Process | TPB Handling |  | [202112] TPB Invoices to Apply Credit Terms | 2021-11-16 11:27 | 2022-01-14 20:00 | 2022-01-14 08:23 | 2022-02-16 12:12 | 2022-02-16 15:01 |  | 2022-03-08 09:30 | 2022-03-08 09:15 | 2022-03-02 12:16 | 2022-03-15 12:00 | CR0014291 | Service Management3rd Party BillingTPB ProcessTPB Handling | OPUS-TPB | 2022-W10 | 2022-03 | 199 | 222 | 111.9185 | 6 | 1 | 1 | 0.08 | 153138 | 3.1 | 1 | 2 | 0 | 3 |  | 2 | 8 | 38 | 0.16667 | 0 | 2021-11 | 2 | 1
2033 | CR0014291 | CTASK0031417 | Closed | OPUS-TPB | Manh Nguyen | 34 | 50 | 2022-01-31 20:00 | 2022-01-03 06:00 | Container | Service Management | 3rd Party Billing | TPB Process | TPB Handling |  | [202201] TPB Invoices to Apply Credit Terms | 2021-11-16 11:27 | 2022-01-14 20:00 | 2022-01-14 08:23 | 2022-02-16 12:12 | 2022-02-16 15:01 |  | 2022-03-08 09:30 | 2022-03-08 09:15 | 2022-03-02 12:16 | 2022-03-15 12:00 | CR0014291 | Service Management3rd Party BillingTPB ProcessTPB Handling | OPUS-TPB | 2022-W10 | 2022-03 | 199 | 222 | 111.9185 | 6 | 1 | 1 | 0.08 | 153138 | 3.1 | 1 | 2 | 0 | 3 |  | 2 | 8 | 38 | 0.16667 | 0 | 2021-11 | 2 | 1
2034 | CR0014291 | CTASK0032067 | Closed | OPUS-TPB | Manh Nguyen | 16 | 15 | 2022-02-28 19:00 | 2022-02-03 06:00 | Container | Service Management | 3rd Party Billing | TPB Process | TPB Handling |  | [202202] TPB Invoices to Apply Credit Terms | 2021-11-16 11:27 | 2022-01-14 20:00 | 2022-01-14 08:23 | 2022-02-16 12:12 | 2022-02-16 15:01 |  | 2022-03-08 09:30 | 2022-03-08 09:15 | 2022-03-02 12:16 | 2022-03-15 12:00 | CR0014291 | Service Management3rd Party BillingTPB ProcessTPB Handling | OPUS-TPB | 2022-W10 | 2022-03 | 199 | 222 | 111.9185 | 6 | 1 | 1 | 0.08 | 153138 | 3.1 | 1 | 2 | 0 | 3 |  | 2 | 8 | 38 | 0.16667 | 0 | 2021-11 | 2 | 1
2035 | CR0014291 | CTASK0032600 | Closed | OPUS-TPB | Manh Nguyen | 16 | 15 | 2022-03-31 13:03 | 2022-03-02 13:03 | Container | Service Management | 3rd Party Billing | TPB Process | TPB Handling |  | [202203] TPB Invoices to Apply Credit Terms | 2021-11-16 11:27 | 2022-01-14 20:00 | 2022-01-14 08:23 | 2022-02-16 12:12 | 2022-02-16 15:01 |  | 2022-03-08 09:30 | 2022-03-08 09:15 | 2022-03-02 12:16 | 2022-03-15 12:00 | CR0014291 | Service Management3rd Party BillingTPB ProcessTPB Handling | OPUS-TPB | 2022-W10 | 2022-03 | 199 | 222 | 111.9185 | 6 | 1 | 1 | 0.08 | 153138 | 3.1 | 1 | 2 | 0 | 3 |  | 2 | 8 | 38 | 0.16667 | 0 | 2021-11 | 2 | 1
2036 | CR0014872 | CTASK0031884 | Closed | OPUS-BKG-MFT-M | Linh Dinh Bo | 10 | 10 | 2022-01-31 15:02 | 2022-01-20 15:01 | Container | Service Management | Booking/Documentation | Manifest | Panama | Panama Canal Authority | [Development] LA - OPUS / Manifest - "Panama Canal Authorities" Screen | 2021-12-13 07:24 | 2022-01-21 07:24 | 2022-01-05 07:57 | 2022-01-31 07:20 | 2022-02-03 07:00 |  | 2022-02-15 09:00 | 2022-02-15 08:30 | 2022-02-04 11:07 | 2022-02-23 12:00 | CR0014872 | Service ManagementBooking/DocumentationManifestPanamaPanama Canal Authority | OPUS-BKG-MFT-M | 2022-W7 | 2022-02 | 10 | 10 | 64.0668 | 1 | 1 | 1 | 0.01 | 193522 | 2.5 | 0 | 0 | 2 | 1 |  | 2 | 10 | 30 | 0 | 0 | 2021-12 | 2 | 1
2037 | CR0014795 | CTASK0031795 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 16 | 16 | 2022-02-28 09:27 | 2022-02-01 09:27 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [Develop] (HM) EUA Auth EUA Customs EDI screen - Change form to allow selection of EDI partner | 2022-02-16 11:00 | 2022-02-25 22:00 | 2022-02-24 14:54 | 2022-03-02 07:50 | 2022-03-07 07:11 |  | 2022-03-22 08:10 | 2022-03-22 08:55 | 2022-03-07 14:56 | 2022-03-29 12:00 | CR0014795 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W12 | 2022-03 | 40 | 40 | 33.8824 | 3 | 1 | 1 | 0.05 | 193606 | 2.3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 4.25 | 0 | 2022-02 | 0 | 0
2038 | CR0014795 | CTASK0031796 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 16 | 16 | 2022-02-28 09:29 | 2022-02-01 09:29 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [Test + Deploy] (HM) EUA Auth EUA Customs EDI screen - Change form to allow selection of EDI partner | 2022-02-16 11:00 | 2022-02-25 22:00 | 2022-02-24 14:54 | 2022-03-02 07:50 | 2022-03-07 07:11 |  | 2022-03-22 08:10 | 2022-03-22 08:55 | 2022-03-07 14:56 | 2022-03-29 12:00 | CR0014795 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W12 | 2022-03 | 40 | 40 | 33.8824 | 3 | 1 | 1 | 0.05 | 193606 | 2.3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 4.25 | 0 | 2022-02 | 0 | 0
2039 | CR0014795 | CTASK0031533 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 8 | 8 | 2022-01-31 13:30 | 2022-01-01 13:30 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [Estimate] (HM) EUA Auth EUA Customs EDI screen - Change form to allow selection of EDI partner | 2022-02-16 11:00 | 2022-02-25 22:00 | 2022-02-24 14:54 | 2022-03-02 07:50 | 2022-03-07 07:11 |  | 2022-03-22 08:10 | 2022-03-22 08:55 | 2022-03-07 14:56 | 2022-03-29 12:00 | CR0014795 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W12 | 2022-03 | 40 | 40 | 33.8824 | 3 | 1 | 1 | 0.05 | 193606 | 2.3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 4.25 | 0 | 2022-02 | 0 | 0
2040 | CR0014212 | CTASK0030102 | Closed | OPUS-TES | Thai Nguyen | 41 | 46 | 2021-11-30 20:00 | 2021-11-01 12:55 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202111][CLT Internal] Adding validation when container quantity is exceeded | 2021-10-25 07:10 | 2021-11-30 20:10 | 2021-11-29 09:07 | 2021-12-14 09:08 | 2021-12-14 09:17 |  | 2021-12-21 09:30 | 2021-12-21 07:42 | 2021-12-15 16:23 | 2021-12-28 12:01 | CR0014212 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W51 | 2021-12 | 46 | 51 | 57.0969 | 2 | 1 | 1 | 0.04 | 173249 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 3 | 26 | 0.89474 | 0 | 2021-10 | 0 | 0
2041 | CR0014212 | CTASK0028498 | Closed | OPUS-TES | Thai Nguyen | 5 | 5 | 2021-08-31 22:00 | 2021-08-01 | Container | Service Management | TML INV | Invoice | Invoice Creation | Marine Terminal Invoice Creation & Correction | [202108][CLT Internal] Adding validation when container quantity is exceeded | 2021-10-25 07:10 | 2021-11-30 20:10 | 2021-11-29 09:07 | 2021-12-14 09:08 | 2021-12-14 09:17 |  | 2021-12-21 09:30 | 2021-12-21 07:42 | 2021-12-15 16:23 | 2021-12-28 12:01 | CR0014212 | Service ManagementTML INVInvoiceInvoice CreationMarine Terminal Invoice Creation & Correction | OPUS-TES | 2021-W51 | 2021-12 | 46 | 51 | 57.0969 | 2 | 1 | 1 | 0.04 | 173249 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 3 | 26 | 0.89474 | 0 | 2021-10 | 0 | 0
2042 | CR0015207 | CTASK0033067 | Closed | OPUS-SCO | Mohamed Hary | 30 | 30 | 2022-03-31 11:41 | 2022-03-21 11:41 | Container | Statement Management | Statement Account Receivable | Collection Manager | Pament Request Letter EUA |  | [Mar 2022] (CLEAR RD)PRL format Issue due to number of digits | 2022-03-15 12:10 | 2022-04-29 19:00 | 2022-04-29 13:06 | 2022-05-17 08:48 | 2022-05-18 12:13 |  | 2022-05-24 10:13 | 2022-05-24 07:48 | 2022-05-20 12:37 | 2022-05-26 09:13 | CR0015207 | Statement ManagementStatement Account ReceivableCollection ManagerPament Request Letter EUA | OPUS-SAR | 2022-W21 | 2022-05 | 82 | 80 | 69.9184 | 5 | 2 | 3 | 0.05 | 193489 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.72727 | 0 | 2022-03 | 0 | 0
2043 | CR0015207 | CTASK0033069 | Closed | OPUS-SAR | Nguyen Hoang Trong Phu | 15 | 15 | 2022-03-31 11:43 | 2022-03-21 11:43 | Container | Statement Management | Statement Account Receivable | Collection Manager | Pament Request Letter EUA |  | [Mar 2022] (CLEAR RD)PRL format Issue due to number of digits | 2022-03-15 12:10 | 2022-04-29 19:00 | 2022-04-29 13:06 | 2022-05-17 08:48 | 2022-05-18 12:13 |  | 2022-05-24 10:13 | 2022-05-24 07:48 | 2022-05-20 12:37 | 2022-05-26 09:13 | CR0015207 | Statement ManagementStatement Account ReceivableCollection ManagerPament Request Letter EUA | OPUS-SAR | 2022-W21 | 2022-05 | 82 | 80 | 69.9184 | 5 | 2 | 3 | 0.05 | 203704 | 1.5 | 2 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0 | 0 | 2022-03 | 0 | 0
2044 | CR0015207 | CTASK0034257 | Closed | OPUS-SCO | Chuong Ta | 11 | 10 | 2022-05-24 15:07 | 2022-05-17 15:07 | Container | Statement Management | Statement Account Receivable | Collection Manager | Pament Request Letter EUA |  | [OTG, Test] (CLEAR RD)PRL format Issue due to number of digits | 2022-03-15 12:10 | 2022-04-29 19:00 | 2022-04-29 13:06 | 2022-05-17 08:48 | 2022-05-18 12:13 |  | 2022-05-24 10:13 | 2022-05-24 07:48 | 2022-05-20 12:37 | 2022-05-26 09:13 | CR0015207 | Statement ManagementStatement Account ReceivableCollection ManagerPament Request Letter EUA | OPUS-SAR | 2022-W21 | 2022-05 | 82 | 80 | 69.9184 | 5 | 2 | 3 | 0.05 | 183379 | 3 | 2 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.32 | 0 | 2022-03 | 0 | 0
2045 | CR0015207 | CTASK0034256 | Closed | OPUS-SCO | Mohamed Hary | 10 | 10 | 2022-05-24 15:06 | 2022-05-17 15:06 | Container | Statement Management | Statement Account Receivable | Collection Manager | Pament Request Letter EUA |  | [Deployment] (CLEAR RD)PRL format Issue due to number of digits | 2022-03-15 12:10 | 2022-04-29 19:00 | 2022-04-29 13:06 | 2022-05-17 08:48 | 2022-05-18 12:13 |  | 2022-05-24 10:13 | 2022-05-24 07:48 | 2022-05-20 12:37 | 2022-05-26 09:13 | CR0015207 | Statement ManagementStatement Account ReceivableCollection ManagerPament Request Letter EUA | OPUS-SAR | 2022-W21 | 2022-05 | 82 | 80 | 69.9184 | 5 | 2 | 3 | 0.05 | 193489 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.72727 | 0 | 2022-03 | 0 | 0
2046 | CR0015207 | CTASK0033068 | Closed | OPUS-SCO | Chuong Ta | 16 | 15 | 2022-03-31 11:42 | 2022-03-21 11:42 | Container | Statement Management | Statement Account Receivable | Collection Manager | Pament Request Letter EUA |  | [Mar 2022] (CLEAR RD)PRL format Issue due to number of digits | 2022-03-15 12:10 | 2022-04-29 19:00 | 2022-04-29 13:06 | 2022-05-17 08:48 | 2022-05-18 12:13 |  | 2022-05-24 10:13 | 2022-05-24 07:48 | 2022-05-20 12:37 | 2022-05-26 09:13 | CR0015207 | Statement ManagementStatement Account ReceivableCollection ManagerPament Request Letter EUA | OPUS-SAR | 2022-W21 | 2022-05 | 82 | 80 | 69.9184 | 5 | 2 | 3 | 0.05 | 183379 | 3 | 2 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.32 | 0 | 2022-03 | 0 | 0
2047 | CR0014994 | CTASK0032574 | Closed | OPUS-INV | Mohamed Hary | 10 | 10 | 2022-03-31 11:23 | 2022-03-01 11:23 | Container | Service Management | A/R Invoice | Invoice Inquiry |  |  | [Mar 2022] Add a new field "Original INV No" in Invoice Inquiry Screens. | 2022-02-14 06:19 | 2022-03-04 22:00 | 2022-03-03 16:38 | 2022-03-31 08:35 | 2022-04-14 09:08 |  | 2022-04-19 08:00 | 2022-04-19 08:14 | 2022-04-14 11:29 | 2022-04-26 12:00 | CR0014994 | Service ManagementA/R InvoiceInvoice Inquiry | OPUS-INV | 2022-W16 | 2022-04 | 50 | 50 | 64.07 | 3 | 1 | 2 | 0.03 | 193489 | 2.7 | 2 | 0 | 0 | 1 |  | 2 | 4 | 18 | 0.72727 | 0 | 2022-02 | 0 | 0
2048 | CR0014994 | CTASK0032151 | Closed | OPUS-INV | Mohamed Hary | 32 | 32 | 2022-02-28 14:23 | 2022-02-07 14:23 | Container | Service Management | A/R Invoice | Invoice Inquiry |  |  | [Feb-2022] Add a new field "Original INV No" in Invoice Inquiry Screens. | 2022-02-14 06:19 | 2022-03-04 22:00 | 2022-03-03 16:38 | 2022-03-31 08:35 | 2022-04-14 09:08 |  | 2022-04-19 08:00 | 2022-04-19 08:14 | 2022-04-14 11:29 | 2022-04-26 12:00 | CR0014994 | Service ManagementA/R InvoiceInvoice Inquiry | OPUS-INV | 2022-W16 | 2022-04 | 50 | 50 | 64.07 | 3 | 1 | 2 | 0.03 | 193489 | 2.7 | 2 | 0 | 0 | 1 |  | 2 | 4 | 18 | 0.72727 | 0 | 2022-02 | 0 | 0
2049 | CR0014994 | CTASK0032152 | Closed | OPUS-INV | Nguyen Ha Vi | 8 | 8 | 2022-02-28 14:24 | 2022-02-07 14:24 | Container | Service Management | A/R Invoice | Invoice Inquiry |  |  | [Feb-2022] Add a new field "Original INV No" in Invoice Inquiry Screens. | 2022-02-14 06:19 | 2022-03-04 22:00 | 2022-03-03 16:38 | 2022-03-31 08:35 | 2022-04-14 09:08 |  | 2022-04-19 08:00 | 2022-04-19 08:14 | 2022-04-14 11:29 | 2022-04-26 12:00 | CR0014994 | Service ManagementA/R InvoiceInvoice Inquiry | OPUS-INV | 2022-W16 | 2022-04 | 50 | 50 | 64.07 | 3 | 1 | 2 | 0.03 | 203664 | 1.7 | 2 | 0 | 0 | 1 |  | 2 | 4 | 18 | 1.8182 | 2.5 | 2022-02 | 0 | 0
2050 | CR0015349 | CTASK0033575 | Closed | OPUS-PSO | Lanh Le | 10 | 10 | 2022-04-15 16:06 | 2022-04-14 16:06 | Container | Vessel Operation | Port Service Order |  |  |  | [Analysis][Design] [Enhancement] PSO - Object for Vessel Dimension Depth | 2022-04-28 08:26 | 2022-05-20 17:30 | 2022-05-18 12:08 | 2022-05-20 08:22 | 2022-05-20 08:25 |  | 2022-05-24 08:25 | 2022-05-24 08:26 | 2022-05-20 12:08 | 2022-05-31 12:00 | CR0015349 | Vessel OperationPort Service Order | OPUS-PSO | 2022-W21 | 2022-05 | 70 | 70 | 25.9992 | 6 | 1 | 1 | 0.11 | 183422 | 3.5 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 0 | 0 | 2022-04 | 0 | 0
2051 | CR0015349 | CTASK0033579 | Closed | OPUS-PSO | Lanh Le | 10 | 10 | 2022-05-20 16:16 | 2022-05-02 16:16 | Container | Vessel Operation | Port Service Order |  |  |  | [TAS] [Enhancement] PSO - Object for Vessel Dimension Depth | 2022-04-28 08:26 | 2022-05-20 17:30 | 2022-05-18 12:08 | 2022-05-20 08:22 | 2022-05-20 08:25 |  | 2022-05-24 08:25 | 2022-05-24 08:26 | 2022-05-20 12:08 | 2022-05-31 12:00 | CR0015349 | Vessel OperationPort Service Order | OPUS-PSO | 2022-W21 | 2022-05 | 70 | 70 | 25.9992 | 6 | 1 | 1 | 0.11 | 183422 | 3.5 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 0 | 0 | 2022-04 | 0 | 0
2052 | CR0015349 | CTASK0033580 | Closed | OPUS-PSO | Lanh Le | 5 | 5 | 2022-05-25 16:18 | 2022-05-20 16:18 | Container | Vessel Operation | Port Service Order |  |  |  | [Deployment] [Enhancement] PSO - Object for Vessel Dimension Depth | 2022-04-28 08:26 | 2022-05-20 17:30 | 2022-05-18 12:08 | 2022-05-20 08:22 | 2022-05-20 08:25 |  | 2022-05-24 08:25 | 2022-05-24 08:26 | 2022-05-20 12:08 | 2022-05-31 12:00 | CR0015349 | Vessel OperationPort Service Order | OPUS-PSO | 2022-W21 | 2022-05 | 70 | 70 | 25.9992 | 6 | 1 | 1 | 0.11 | 183422 | 3.5 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 0 | 0 | 2022-04 | 0 | 0
2053 | CR0015349 | CTASK0033576 | Closed | OPUS-PSO | Lanh Le | 35 | 35 | 2022-05-20 22:00 | 2022-05-02 07:00 | Container | Vessel Operation | Port Service Order |  |  |  | [Development] [Enhancement] PSO - Object for Vessel Dimension Depth | 2022-04-28 08:26 | 2022-05-20 17:30 | 2022-05-18 12:08 | 2022-05-20 08:22 | 2022-05-20 08:25 |  | 2022-05-24 08:25 | 2022-05-24 08:26 | 2022-05-20 12:08 | 2022-05-31 12:00 | CR0015349 | Vessel OperationPort Service Order | OPUS-PSO | 2022-W21 | 2022-05 | 70 | 70 | 25.9992 | 6 | 1 | 1 | 0.11 | 183422 | 3.5 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 0 | 0 | 2022-04 | 0 | 0
2054 | CR0015349 | CTASK0033577 | Closed | OPUS-PSO | Lanh Le | 10 | 10 | 2022-05-20 16:13 | 2022-05-02 16:13 | Container | Vessel Operation | Port Service Order |  |  |  | [TEST] [Enhancement] PSO - Object for Vessel Dimension Depth | 2022-04-28 08:26 | 2022-05-20 17:30 | 2022-05-18 12:08 | 2022-05-20 08:22 | 2022-05-20 08:25 |  | 2022-05-24 08:25 | 2022-05-24 08:26 | 2022-05-20 12:08 | 2022-05-31 12:00 | CR0015349 | Vessel OperationPort Service Order | OPUS-PSO | 2022-W21 | 2022-05 | 70 | 70 | 25.9992 | 6 | 1 | 1 | 0.11 | 183422 | 3.5 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 0 | 0 | 2022-04 | 0 | 0
2055 | CR0015349 | CTASK0033574 | Closed | OPUS-PSO | Lanh Le | 1 | 1 | 2022-05-20 22:00 | 2022-05-01 07:00 | Container | Vessel Operation | Port Service Order |  |  |  | [Documentation] [Enhancement] PSO - Object for Vessel Dimension Depth | 2022-04-28 08:26 | 2022-05-20 17:30 | 2022-05-18 12:08 | 2022-05-20 08:22 | 2022-05-20 08:25 |  | 2022-05-24 08:25 | 2022-05-24 08:26 | 2022-05-20 12:08 | 2022-05-31 12:00 | CR0015349 | Vessel OperationPort Service Order | OPUS-PSO | 2022-W21 | 2022-05 | 70 | 70 | 25.9992 | 6 | 1 | 1 | 0.11 | 183422 | 3.5 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 0 | 0 | 2022-04 | 0 | 0
2056 | CR0014952 | CTASK0031493 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 6 | 8 | 2022-01-07 16:35 | 2022-01-04 16:35 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Fax & E-Mail | [Documentation] Rollback of CR0013928 - EUA - Change of Logic of A/N Email selection | 2022-01-06 15:30 | 2022-01-28 21:30 | 2022-01-19 12:12 | 2022-01-27 07:08 | 2022-01-27 09:01 |  | 2022-01-28 09:01 | 2022-01-28 07:55 | 2022-01-27 11:36 | 2022-02-04 12:00 | CR0014952 | Service ManagementBooking/DocumentationInbound DocArrival NoticeFax & E-Mail | OPUS-BKG-IB | 2022-W4 | 2022-01 | 25 | 27 | 21.7296 | 2 | 1 | 1 | 0.05 | 193512 | 2.5 | 1 | 0 | 0 | 1 |  | 1 | 9 | 33 | 0.2963 | 0 | 2022-01 | 0 | 0
2057 | CR0014952 | CTASK0031744 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 19 | 19 | 2022-01-21 15:20 | 2022-01-06 15:20 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Fax & E-Mail | [Development+ Testing+ Deployment] Rollback of CR0013928 - EUA - Change of Logic of A/N Email selection | 2022-01-06 15:30 | 2022-01-28 21:30 | 2022-01-19 12:12 | 2022-01-27 07:08 | 2022-01-27 09:01 |  | 2022-01-28 09:01 | 2022-01-28 07:55 | 2022-01-27 11:36 | 2022-02-04 12:00 | CR0014952 | Service ManagementBooking/DocumentationInbound DocArrival NoticeFax & E-Mail | OPUS-BKG-IB | 2022-W4 | 2022-01 | 25 | 27 | 21.7296 | 2 | 1 | 1 | 0.05 | 193512 | 2.5 | 1 | 0 | 0 | 1 |  | 1 | 9 | 33 | 0.2963 | 0 | 2022-01 | 0 | 0
2058 | CR0014332 | CTASK0029048 | Closed | OPUS-SCG | Trang Duy Thong | 12 | 21 | 2021-10-01 09:49 | 2021-08-30 09:49 | Container | Vessel Operation | Special Cargo | Reports |  |  | [Documentation] New Screen for DG List for Stowman | 2021-09-06 10:12 | 2021-10-01 10:12 | 2021-09-29 13:05 | 2021-11-04 07:17 | 2021-11-05 14:02 |  | 2021-11-16 08:01 | 2021-11-16 12:10 | 2021-11-12 11:35 | 2021-11-24 12:00 | CR0014332 | Vessel OperationSpecial CargoReports | OPUS-SCG | 2021-W46 | 2021-11 | 72 | 81 | 70.9093 | 2 | 1 | 2 | 0.05 | 193511 | 1.2 | 3 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.81818 | 2.6667 | 2021-09 | 0 | 0
2059 | CR0014332 | CTASK0029049 | Closed | OPUS-SCG | Tran Anh Duy | 60 | 60 | 2021-10-01 09:56 | 2021-08-30 09:56 | Container | Vessel Operation | Special Cargo | Reports |  |  | [CLV] New Screen for DG List for Stowman | 2021-09-06 10:12 | 2021-10-01 10:12 | 2021-09-29 13:05 | 2021-11-04 07:17 | 2021-11-05 14:02 |  | 2021-11-16 08:01 | 2021-11-16 12:10 | 2021-11-12 11:35 | 2021-11-24 12:00 | CR0014332 | Vessel OperationSpecial CargoReports | OPUS-SCG | 2021-W46 | 2021-11 | 72 | 81 | 70.9093 | 2 | 1 | 2 | 0.05 | 193516 | 2.5 | 3 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0 | 0 | 2021-09 | 0 | 0
2060 | CR0014656 | CTASK0030303 | Closed | OPUS-JOO | Linh Nguyen | 53 | 53 | 2021-12-10 20:27 | 2021-11-03 20:26 | Container | Support & Admin | Joint Operation | CSR |  |  | [CLV-JOO][CLT Internal]JOO - Enhance the approval process to fix the approval shown as W in the CSR List | 2021-11-03 08:51 | 2021-12-15 20:00 | 2021-12-10 16:50 | 2021-12-21 14:14 | 2021-12-23 15:00 |  | 2022-01-11 17:00 | 2022-01-11 20:00 | 2021-12-24 08:51 | 2022-01-18 12:01 | CR0014656 | Support & AdminJoint OperationCSR | OPUS-JOO | 2022-W2 | 2022-01 | 53 | 53 | 69.3395 | 2 | 1 | 1 | 0.03 | 193464 | 2.7 | 1 | 0 | 0 | 1 |  | 2 | 7 | 33 | 0.375 | 1.5 | 2021-11 | 0 | 0
2061 | CR0014656 | CTASK0030270 | Closed | OPUS-JOO | Linh Nguyen |  |  |  |  | Container | Support & Admin | Joint Operation | CSR |  |  | [Document][CLT Internal]JOO - Enhance the approval process to fix the approval shown as W in the CSR List | 2021-11-03 08:51 | 2021-12-15 20:00 | 2021-12-10 16:50 | 2021-12-21 14:14 | 2021-12-23 15:00 |  | 2022-01-11 17:00 | 2022-01-11 20:00 | 2021-12-24 08:51 | 2022-01-18 12:01 | CR0014656 | Support & AdminJoint OperationCSR | OPUS-JOO | 2022-W2 | 2022-01 | 53 | 53 | 69.3395 | 2 | 1 | 1 | 0.03 | 193464 | 2.7 | 1 | 0 | 0 | 1 |  | 2 | 7 | 33 | 0.375 | 1.5 | 2021-11 | 0 | 0
2062 | CR0015016 | CTASK0031759 | Closed | OPUS-ACM | Huynh Tuan Khanh | 36 | 30 | 2022-01-28 08:36 | 2022-01-17 08:36 | Container | Biz Common | Master Data | Service | Revenue Lane |  | [CLT Internal] Add validation to Revenue Lane | 2022-01-17 14:12 | 2022-02-11 21:38 | 2022-02-08 11:50 | 2022-02-10 09:25 | 2022-02-10 15:06 |  | 2022-02-15 15:06 | 2022-02-15 12:45 | 2022-02-10 15:44 | 2022-02-23 12:00 | CR0015016 | Biz CommonMaster DataServiceRevenue Lane | OPUS-MDA | 2022-W7 | 2022-02 | 36 | 30 | 29.0375 | 1 | 1 | 1 | 0.04 | 193499 | 2.6 | 2 | 0 | 0 | 1 |  | 1 | 10 | 30 | 0 | 0 | 2022-01 | 0 | 0
2063 | CR0014149 | CTASK0030888 | Closed | OPUS-TPB | Manh Nguyen | 4 | 4 | 2022-01-31 20:00 | 2022-01-03 06:00 | Container | Service Management | A/R Invoice | Code | Office Code | A/R Office Code Management | [202201] EUA // A/R Office Code Management // Update Email Sender Flag | 2021-09-28 12:03 | 2021-11-19 12:02 | 2021-11-18 11:40 | 2022-01-11 09:32 | 2022-01-11 12:29 |  | 2022-01-18 10:00 | 2022-01-18 11:00 | 2022-01-11 13:47 | 2022-01-25 12:00 | CR0014149 | Service ManagementA/R InvoiceCodeOffice CodeA/R Office Code Management | OPUS-INV | 2022-W3 | 2022-01 | 117 | 130 | 111.9148 | 7 | 3 | 5 | 0.05 | 153138 | 3 | 3 | 1 | 0 | 2 |  | 2 | 11 | 33 | 0.16667 | 0.16667 | 2021-09 | 1 | 1
2064 | CR0014149 | CTASK0029490 | Closed | OPUS-INV | Nguyen Hoang Trong Phu | 34 | 30 | 2021-09-30 10:05 | 2021-09-01 10:05 | Container | Service Management | A/R Invoice | Code | Office Code | A/R Office Code Management | [Sep 2021] EUA // A/R Office Code Management // Update Email Sender Flag | 2021-09-28 12:03 | 2021-11-19 12:02 | 2021-11-18 11:40 | 2022-01-11 09:32 | 2022-01-11 12:29 |  | 2022-01-18 10:00 | 2022-01-18 11:00 | 2022-01-11 13:47 | 2022-01-25 12:00 | CR0014149 | Service ManagementA/R InvoiceCodeOffice CodeA/R Office Code Management | OPUS-INV | 2022-W3 | 2022-01 | 117 | 130 | 111.9148 | 7 | 3 | 5 | 0.05 | 203704 | 1.1 | 3 | 1 | 0 | 2 |  | 2 | 11 | 33 | 0 | 0 | 2021-09 | 1 | 1
2065 | CR0014149 | CTASK0029488 | Closed | OPUS-INV | Lien Le | 25 | 22 | 2021-09-30 10:03 | 2021-09-01 10:02 | Container | Service Management | A/R Invoice | Code | Office Code | A/R Office Code Management | [Sep 2021]EUA // A/R Office Code Management // Update Email Sender Flag | 2021-09-28 12:03 | 2021-11-19 12:02 | 2021-11-18 11:40 | 2022-01-11 09:32 | 2022-01-11 12:29 |  | 2022-01-18 10:00 | 2022-01-18 11:00 | 2022-01-11 13:47 | 2022-01-25 12:00 | CR0014149 | Service ManagementA/R InvoiceCodeOffice CodeA/R Office Code Management | OPUS-INV | 2022-W3 | 2022-01 | 117 | 130 | 111.9148 | 7 | 3 | 5 | 0.05 | 193441 | 2.6 | 3 | 1 | 0 | 2 |  | 2 | 11 | 33 | 0.42308 | 0 | 2021-09 | 1 | 1
2066 | CR0014149 | CTASK0029489 | Closed | OPUS-INV | Nguyen Ha Vi | 25 | 25 | 2021-09-30 10:04 | 2021-09-01 10:04 | Container | Service Management | A/R Invoice | Code | Office Code | A/R Office Code Management | [Sep 2021]EUA // A/R Office Code Management // Update Email Sender Flag | 2021-09-28 12:03 | 2021-11-19 12:02 | 2021-11-18 11:40 | 2022-01-11 09:32 | 2022-01-11 12:29 |  | 2022-01-18 10:00 | 2022-01-18 11:00 | 2022-01-11 13:47 | 2022-01-25 12:00 | CR0014149 | Service ManagementA/R InvoiceCodeOffice CodeA/R Office Code Management | OPUS-INV | 2022-W3 | 2022-01 | 117 | 130 | 111.9148 | 7 | 3 | 5 | 0.05 | 203664 | 1.3 | 3 | 1 | 0 | 2 |  | 2 | 11 | 33 | 1.8182 | 2.5 | 2021-09 | 1 | 1
2067 | CR0014149 | CTASK0029252 | Closed | OPUS-TPB | Manh Nguyen | 2 | 2 | 2021-09-30 22:00 | 2021-09-01 | Container | Service Management | A/R Invoice | Code | Office Code | A/R Office Code Management | [202109] EUA // A/R Office Code Management // Update Email Sender Flag | 2021-09-28 12:03 | 2021-11-19 12:02 | 2021-11-18 11:40 | 2022-01-11 09:32 | 2022-01-11 12:29 |  | 2022-01-18 10:00 | 2022-01-18 11:00 | 2022-01-11 13:47 | 2022-01-25 12:00 | CR0014149 | Service ManagementA/R InvoiceCodeOffice CodeA/R Office Code Management | OPUS-INV | 2022-W3 | 2022-01 | 117 | 130 | 111.9148 | 7 | 3 | 5 | 0.05 | 153138 | 3 | 3 | 1 | 0 | 2 |  | 2 | 11 | 33 | 0.16667 | 0.16667 | 2021-09 | 1 | 1
2068 | CR0014149 | CTASK0030234 | Closed | OPUS-TPB | Manh Nguyen | 12 | 15 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Service Management | A/R Invoice | Code | Office Code | A/R Office Code Management | [202111] EUA // A/R Office Code Management // Update Email Sender Flag | 2021-09-28 12:03 | 2021-11-19 12:02 | 2021-11-18 11:40 | 2022-01-11 09:32 | 2022-01-11 12:29 |  | 2022-01-18 10:00 | 2022-01-18 11:00 | 2022-01-11 13:47 | 2022-01-25 12:00 | CR0014149 | Service ManagementA/R InvoiceCodeOffice CodeA/R Office Code Management | OPUS-INV | 2022-W3 | 2022-01 | 117 | 130 | 111.9148 | 7 | 3 | 5 | 0.05 | 153138 | 3 | 3 | 1 | 0 | 2 |  | 2 | 11 | 33 | 0.16667 | 0.16667 | 2021-09 | 1 | 1
2069 | CR0014149 | CTASK0028703 | Closed | OPUS-DMT | Cuong Nguyen | 19 | 32 | 2021-11-16 18:00 | 2021-08-23 06:00 | Container | Service Management | A/R Invoice | Code | Office Code | A/R Office Code Management | [CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2021-09-28 12:03 | 2021-11-19 12:02 | 2021-11-18 11:40 | 2022-01-11 09:32 | 2022-01-11 12:29 |  | 2022-01-18 10:00 | 2022-01-18 11:00 | 2022-01-11 13:47 | 2022-01-25 12:00 | CR0014149 | Service ManagementA/R InvoiceCodeOffice CodeA/R Office Code Management | OPUS-INV | 2022-W3 | 2022-01 | 117 | 130 | 111.9148 | 7 | 3 | 5 | 0.05 | 193529 | 2.3 | 3 | 1 | 0 | 2 |  | 2 | 11 | 33 | 0.11538 | 0.22222 | 2021-09 | 1 | 1
2070 | CR0014082 | CTASK0027831 | Closed | OPUS-BKG-M | Loc Tran | 10 | 10 | 2021-07-31 12:00 | 2021-07-01 12:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development]Change mapping logic of CNT from OPUS to COPARN's FF | 2021-07-21 08:22 | 2021-08-11 22:00 | 2021-08-11 11:05 | 2021-09-08 11:04 | 2021-09-08 11:18 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-09-30 07:17 | 2021-10-19 12:00 | CR0014082 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W41 | 2021-10 | 21 | 30 | 82.9845 | 4 | 1 | 1 | 0.02 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 2 | 9 | 26 | 0.33333 | 0 | 2021-07 | 0 | 0
2071 | CR0014082 | CTASK0027834 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment]Change mapping logic of CNT from OPUS to COPARN's FF | 2021-07-21 08:22 | 2021-08-11 22:00 | 2021-08-11 11:05 | 2021-09-08 11:04 | 2021-09-08 11:18 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-09-30 07:17 | 2021-10-19 12:00 | CR0014082 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W41 | 2021-10 | 21 | 30 | 82.9845 | 4 | 1 | 1 | 0.02 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 2 | 9 | 26 | 0.33333 | 0 | 2021-07 | 0 | 0
2072 | CR0014082 | CTASK0027832 | Closed | OPUS-BKG-M | Loc Tran | 7 | 8 | 2021-07-31 12:00 | 2021-07-01 12:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing]Change mapping logic of CNT from OPUS to COPARN's FF | 2021-07-21 08:22 | 2021-08-11 22:00 | 2021-08-11 11:05 | 2021-09-08 11:04 | 2021-09-08 11:18 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-09-30 07:17 | 2021-10-19 12:00 | CR0014082 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W41 | 2021-10 | 21 | 30 | 82.9845 | 4 | 1 | 1 | 0.02 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 2 | 9 | 26 | 0.33333 | 0 | 2021-07 | 0 | 0
2073 | CR0014082 | CTASK0027773 | Closed | OPUS-BKG-M | Loc Tran | 4 | 8 | 2021-06-30 15:49 | 2021-06-24 15:49 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Change mapping logic of CNT from OPUS to COPARN's FF | 2021-07-21 08:22 | 2021-08-11 22:00 | 2021-08-11 11:05 | 2021-09-08 11:04 | 2021-09-08 11:18 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-09-30 07:17 | 2021-10-19 12:00 | CR0014082 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W41 | 2021-10 | 21 | 30 | 82.9845 | 4 | 1 | 1 | 0.02 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 2 | 9 | 26 | 0.33333 | 0 | 2021-07 | 0 | 0
2074 | CR0012394 | CTASK0024458 | Closed | OPUS-DMT | Cuong Nguyen | 15 | 16 | 2021-02-26 18:00 | 2021-02-01 06:00 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [DMT_CLV_CTASK1] Design_Analysis | 2020-09-25 10:07 | 2021-07-30 18:00 | 2021-07-30 12:36 | 2022-04-21 14:13 | 2022-05-02 07:20 |  | 2022-05-10 08:00 | 2022-05-10 08:19 | 2022-05-06 09:53 | 2022-05-17 12:00 | CR0012394 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2022-W19 | 2022-05 | 161 | 180 | 591.9117 | 8 | 2 | 2 | 0.01 | 193529 | 1.3 | 1 | 0 | 0 | 2 |  | 5 | 4 | 26 | 0 | 0.058824 | 2020-09 | 0 | 0
2075 | CR0012394 | CTASK0031840 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2022-05-06 20:40 | 2022-05-04 00:40 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [Deployment] - NA - SCE/DMT - Adding DMT milestones to COP to aid DMT Redesign | 2020-09-25 10:07 | 2021-07-30 18:00 | 2021-07-30 12:36 | 2022-04-21 14:13 | 2022-05-02 07:20 |  | 2022-05-10 08:00 | 2022-05-10 08:19 | 2022-05-06 09:53 | 2022-05-17 12:00 | CR0012394 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2022-W19 | 2022-05 | 161 | 180 | 591.9117 | 8 | 2 | 2 | 0.01 | 153106 | 2 | 1 | 0 | 0 | 2 |  | 5 | 4 | 26 | 0 | 0.4 | 2020-09 | 0 | 0
2076 | CR0012394 | CTASK0024459 | Closed | OPUS-DMT | Cuong Nguyen | 50 | 56 | 2021-04-30 18:00 | 2021-03-01 06:00 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [DMT_CLV_CTASK2] Development | 2020-09-25 10:07 | 2021-07-30 18:00 | 2021-07-30 12:36 | 2022-04-21 14:13 | 2022-05-02 07:20 |  | 2022-05-10 08:00 | 2022-05-10 08:19 | 2022-05-06 09:53 | 2022-05-17 12:00 | CR0012394 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2022-W19 | 2022-05 | 161 | 180 | 591.9117 | 8 | 2 | 2 | 0.01 | 193529 | 1.3 | 1 | 0 | 0 | 2 |  | 5 | 4 | 26 | 0 | 0.058824 | 2020-09 | 0 | 0
2077 | CR0012394 | CTASK0031838 | Closed | OPUS-BKG-M | Kieu Le | 26 | 26 | 2022-01-21 20:50 | 2022-01-17 09:50 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [Development] - NA - SCE/DMT - Adding DMT milestones to COP to aid DMT Redesign | 2020-09-25 10:07 | 2021-07-30 18:00 | 2021-07-30 12:36 | 2022-04-21 14:13 | 2022-05-02 07:20 |  | 2022-05-10 08:00 | 2022-05-10 08:19 | 2022-05-06 09:53 | 2022-05-17 12:00 | CR0012394 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2022-W19 | 2022-05 | 161 | 180 | 591.9117 | 8 | 2 | 2 | 0.01 | 153106 | 2 | 1 | 0 | 0 | 2 |  | 5 | 4 | 26 | 0 | 0.4 | 2020-09 | 0 | 0
2078 | CR0012394 | CTASK0031839 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2022-05-06 20:51 | 2022-05-04 00:51 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [Testing] - NA - SCE/DMT - Adding DMT milestones to COP to aid DMT Redesign | 2020-09-25 10:07 | 2021-07-30 18:00 | 2021-07-30 12:36 | 2022-04-21 14:13 | 2022-05-02 07:20 |  | 2022-05-10 08:00 | 2022-05-10 08:19 | 2022-05-06 09:53 | 2022-05-17 12:00 | CR0012394 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2022-W19 | 2022-05 | 161 | 180 | 591.9117 | 8 | 2 | 2 | 0.01 | 153106 | 2 | 1 | 0 | 0 | 2 |  | 5 | 4 | 26 | 0 | 0.4 | 2020-09 | 0 | 0
2079 | CR0012394 | CTASK0024460 | Closed | OPUS-DMT | Cuong Nguyen | 30 | 40 | 2021-06-25 18:00 | 2021-06-01 06:00 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [DMT_CLV_CTASK3] Test | 2020-09-25 10:07 | 2021-07-30 18:00 | 2021-07-30 12:36 | 2022-04-21 14:13 | 2022-05-02 07:20 |  | 2022-05-10 08:00 | 2022-05-10 08:19 | 2022-05-06 09:53 | 2022-05-17 12:00 | CR0012394 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2022-W19 | 2022-05 | 161 | 180 | 591.9117 | 8 | 2 | 2 | 0.01 | 193529 | 1.3 | 1 | 0 | 0 | 2 |  | 5 | 4 | 26 | 0 | 0.058824 | 2020-09 | 0 | 0
2080 | CR0012394 | CTASK0033951 | Closed | OPUS-DMT | Cuong Nguyen | 19 | 20 | 2022-05-10 08:18 | 2022-05-01 08:18 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [TASK-DMT] TEST4 Milestones | 2020-09-25 10:07 | 2021-07-30 18:00 | 2021-07-30 12:36 | 2022-04-21 14:13 | 2022-05-02 07:20 |  | 2022-05-10 08:00 | 2022-05-10 08:19 | 2022-05-06 09:53 | 2022-05-17 12:00 | CR0012394 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2022-W19 | 2022-05 | 161 | 180 | 591.9117 | 8 | 2 | 2 | 0.01 | 193529 | 1.3 | 1 | 0 | 0 | 2 |  | 5 | 4 | 26 | 0 | 0.058824 | 2020-09 | 0 | 0
2081 | CR0012394 | CTASK0031786 | Closed | OPUS-BKG-M | Kieu Le | 7 | 8 | 2022-01-21 17:36 | 2022-01-17 00:36 | Container | Service Management | SCEM | Customer Order Plan | COP Detail |  | [Design] NA - SCE/DMT - Adding DMT milestones to COP to aid DMT Redesign | 2020-09-25 10:07 | 2021-07-30 18:00 | 2021-07-30 12:36 | 2022-04-21 14:13 | 2022-05-02 07:20 |  | 2022-05-10 08:00 | 2022-05-10 08:19 | 2022-05-06 09:53 | 2022-05-17 12:00 | CR0012394 | Service ManagementSCEMCustomer Order PlanCOP Detail | OPUS-SCE | 2022-W19 | 2022-05 | 161 | 180 | 591.9117 | 8 | 2 | 2 | 0.01 | 153106 | 2 | 1 | 0 | 0 | 2 |  | 5 | 4 | 26 | 0 | 0.4 | 2020-09 | 0 | 0
2082 | CR0015164 | CTASK0032838 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 44 | 44 | 2022-04-05 13:35 | 2022-03-17 13:35 | Container | Service Management | Booking/Documentation | Code | Customer Code | Customer Master Data | [Development+ Testing+ Deployment] EUA - Regulatory requirement - Customer Master Data ** Very High Priority | 2022-03-16 13:01 | 2022-04-07 22:00 | 2022-04-07 11:46 | 2022-04-13 07:11 | 2022-04-20 08:50 |  | 2022-05-03 08:00 | 2022-05-03 08:00 | 2022-04-21 13:31 | 2022-05-10 12:00 | CR0015164 | Service ManagementBooking/DocumentationCodeCustomer CodeCustomer Master Data | OPUS-BKG-IB | 2022-W18 | 2022-05 | 64 | 65 | 47.7908 | 3 | 1 | 2 | 0.06 | 193512 | 2.7 | 2 | 0 | 0 | 1 |  | 1 | 2 | 26 | 0.2963 | 0 | 2022-03 | 0 | 0
2083 | CR0015164 | CTASK0032814 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 6 | 7 | 2022-03-11 16:49 | 2022-03-07 16:49 | Container | Service Management | Booking/Documentation | Code | Customer Code | Customer Master Data | [Estimation] EUA - Regulatory requirement - Customer Master Data ** Very High Priority | 2022-03-16 13:01 | 2022-04-07 22:00 | 2022-04-07 11:46 | 2022-04-13 07:11 | 2022-04-20 08:50 |  | 2022-05-03 08:00 | 2022-05-03 08:00 | 2022-04-21 13:31 | 2022-05-10 12:00 | CR0015164 | Service ManagementBooking/DocumentationCodeCustomer CodeCustomer Master Data | OPUS-BKG-IB | 2022-W18 | 2022-05 | 64 | 65 | 47.7908 | 3 | 1 | 2 | 0.06 | 193512 | 2.7 | 2 | 0 | 0 | 1 |  | 1 | 2 | 26 | 0.2963 | 0 | 2022-03 | 0 | 0
2084 | CR0015164 | CTASK0033847 | Closed | OPUS-BKG-IB | Linh Dinh Bo | 14 | 14 | 2022-04-30 17:16 | 2022-04-18 17:16 | Container | Service Management | Booking/Documentation | Code | Customer Code | Customer Master Data | [Deployment][Testing] EUA - Regulatory requirement - Customer Master Data ** Very High Priority | 2022-03-16 13:01 | 2022-04-07 22:00 | 2022-04-07 11:46 | 2022-04-13 07:11 | 2022-04-20 08:50 |  | 2022-05-03 08:00 | 2022-05-03 08:00 | 2022-04-21 13:31 | 2022-05-10 12:00 | CR0015164 | Service ManagementBooking/DocumentationCodeCustomer CodeCustomer Master Data | OPUS-BKG-IB | 2022-W18 | 2022-05 | 64 | 65 | 47.7908 | 3 | 1 | 2 | 0.06 | 193522 | 2.8 | 2 | 0 | 0 | 1 |  | 1 | 2 | 26 | 0 | 0 | 2022-03 | 0 | 0
2085 | CR0013988 | CTASK0027364 | Closed | OPUS-VSK | Linh Nguyen | 27 | 28 | 2021-06-30 14:58 | 2021-06-01 14:58 | Container | Vessel Operation | Vessel Schedule | VSL SKD |  |  | [CLV][CLT Internal] - Long Range SKD viewing enhancement | 2021-06-04 09:07 | 2021-07-09 15:09 | 2021-06-18 13:05 | 2021-10-28 08:34 | 2021-11-01 10:13 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-11-02 14:48 | 2021-11-17 12:00 | CR0013988 | Vessel OperationVessel ScheduleVSL SKD | OPUS-VSK | 2021-W45 | 2021-11 | 43 | 44 | 157.9537 | 3 | 1 | 3 | 0.01 | 193464 | 2.3 | 2 | 0 | 0 | 1 |  | 3 | 9 | 38 | 0.375 | 1.5 | 2021-06 | 0 | 0
2086 | CR0013988 | CTASK0027288 | Closed | OPUS-VSK | Huy Vu | 1 | 1 |  |  | Container | Vessel Operation | Vessel Schedule | VSL SKD |  |  | [Documentation][CLT Internal] - Long Range SKD viewing enhancement | 2021-06-04 09:07 | 2021-07-09 15:09 | 2021-06-18 13:05 | 2021-10-28 08:34 | 2021-11-01 10:13 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-11-02 14:48 | 2021-11-17 12:00 | CR0013988 | Vessel OperationVessel ScheduleVSL SKD | OPUS-VSK | 2021-W45 | 2021-11 | 43 | 44 | 157.9537 | 3 | 1 | 3 | 0.01 | 193618 | 1.3 | 2 | 0 | 0 | 1 |  | 3 | 9 | 38 | 0 | 0 | 2021-06 | 0 | 0
2087 | CR0013988 | CTASK0027363 | Closed | OPUS-VSK | Thuan Tran | 16 | 16 | 2021-06-30 14:53 | 2021-06-01 14:53 | Container | Vessel Operation | Vessel Schedule | VSL SKD |  |  | [CLV][CLT Internal] - Long Range SKD viewing enhancement | 2021-06-04 09:07 | 2021-07-09 15:09 | 2021-06-18 13:05 | 2021-10-28 08:34 | 2021-11-01 10:13 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-11-02 14:48 | 2021-11-17 12:00 | CR0013988 | Vessel OperationVessel ScheduleVSL SKD | OPUS-VSK | 2021-W45 | 2021-11 | 43 | 44 | 157.9537 | 3 | 1 | 3 | 0.01 | 183423 | 2.6 | 2 | 0 | 0 | 1 |  | 3 | 9 | 38 | 0 | 0 | 2021-06 | 0 | 0
2088 | CR0014483 | CTASK0030002 | Closed | OPUS-PRI | Man Hoang | 153 | 100 | 2021-11-30 09:11 | 2021-10-18 09:11 | Container | Sales Management | Pricing | RFA | Proposal & Amendment | RFA Proposal & Amendment Creation | Tiger to Opus API for Mass Contracts Update | 2021-10-19 12:02 | 2021-11-26 18:01 | 2021-11-24 13:31 | 2022-03-03 09:39 | 2022-03-03 12:36 |  | 2022-03-08 12:36 | 2022-04-01 13:50 | 2022-03-03 13:10 | 2022-04-21 12:00 | CR0014483 | Sales ManagementPricingRFAProposal & AmendmentRFA Proposal & Amendment Creation | OPUS-PRI | 2022-W10 | 2022-03 | 153 | 100 | 140.0239 | 1 | 1 | 1 | 0.03 | 183431 | 2.9 | 0 | 0 | 0 | 1 |  | 2 | 8 | 38 | 0.58333 | 0.5 | 2021-10 | 0 | 0
2089 | CR0014697 | CTASK0031136 | Closed | OPUS-BKG-M | Trang Le Minh | 18 | 18 | 2022-01-28 21:48 | 2022-01-03 15:48 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA - Add 'Drop Down' to expand TRO Vendor Special Instruction/ Customer Remarks when lines exceed 2 | 2022-01-10 07:15 | 2022-02-09 22:00 | 2022-01-29 06:35 | 2022-02-03 11:31 | 2022-02-03 11:36 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-04 11:06 | 2022-03-01 12:00 | CR0014697 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W8 | 2022-02 | 40 | 40 | 43.0313 | 5 | 1 | 2 | 0.04 | 193594 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 14 | 30 | 0 | 0 | 2022-01 | 0 | 0
2090 | CR0014697 | CTASK0031135 | Closed | OPUS-BKG-M | Trang Le Minh | 2 | 2 | 2022-01-28 21:12 | 2022-01-04 09:12 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] EUA - Add 'Drop Down' to expand TRO Vendor Special Instruction/ Customer Remarks when lines exceed 2 | 2022-01-10 07:15 | 2022-02-09 22:00 | 2022-01-29 06:35 | 2022-02-03 11:31 | 2022-02-03 11:36 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-04 11:06 | 2022-03-01 12:00 | CR0014697 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W8 | 2022-02 | 40 | 40 | 43.0313 | 5 | 1 | 2 | 0.04 | 193594 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 14 | 30 | 0 | 0 | 2022-01 | 0 | 0
2091 | CR0014697 | CTASK0031042 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2022-01-07 13:02 | 2022-01-03 13:02 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] EUA - Add 'Drop Down' to expand TRO Vendor Special Instruction/ Customer Remarks when lines exceed 2 | 2022-01-10 07:15 | 2022-02-09 22:00 | 2022-01-29 06:35 | 2022-02-03 11:31 | 2022-02-03 11:36 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-04 11:06 | 2022-03-01 12:00 | CR0014697 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W8 | 2022-02 | 40 | 40 | 43.0313 | 5 | 1 | 2 | 0.04 | 193488 | 2.6 | 1 | 0 | 0 | 1 |  | 1 | 14 | 30 | 0.53659 | 0 | 2022-01 | 0 | 0
2092 | CR0014697 | CTASK0031137 | Closed | OPUS-BKG-M | Trang Le Minh | 8 | 8 | 2022-01-28 21:50 | 2022-01-03 15:50 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Test] EUA - Add 'Drop Down' to expand TRO Vendor Special Instruction/ Customer Remarks when lines exceed 2 | 2022-01-10 07:15 | 2022-02-09 22:00 | 2022-01-29 06:35 | 2022-02-03 11:31 | 2022-02-03 11:36 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-04 11:06 | 2022-03-01 12:00 | CR0014697 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W8 | 2022-02 | 40 | 40 | 43.0313 | 5 | 1 | 2 | 0.04 | 193594 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 14 | 30 | 0 | 0 | 2022-01 | 0 | 0
2093 | CR0014697 | CTASK0031139 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2022-02-23 21:42 | 2022-02-10 08:42 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] EUA - Add 'Drop Down' to expand TRO Vendor Special Instruction/ Customer Remarks when lines exceed 2 | 2022-01-10 07:15 | 2022-02-09 22:00 | 2022-01-29 06:35 | 2022-02-03 11:31 | 2022-02-03 11:36 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-04 11:06 | 2022-03-01 12:00 | CR0014697 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W8 | 2022-02 | 40 | 40 | 43.0313 | 5 | 1 | 2 | 0.04 | 193594 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 14 | 30 | 0 | 0 | 2022-01 | 0 | 0
2094 | CR0014003 | CTASK0028733 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-11-05 20:22 | 2021-11-01 00:22 | Container | Service Management | Booking/Documentation | Outbound Doc |  |  | [Deployment] Booking Receipt Notice & Draft BL Setup ( ESM_BKG_1075 ) - BRN Remark | 2021-08-17 07:00 | 2021-09-16 | 2021-09-14 12:48 | 2021-10-28 07:13 | 2021-10-28 09:33 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-11-04 07:20 | 2021-11-24 12:00 | CR0014003 | Service ManagementBooking/DocumentationOutbound Doc | OPUS-BKG-OB | 2021-W45 | 2021-11 | 66 | 63 | 84.042 | 4 | 1 | 2 | 0.03 | 153106 | 2.9 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0.22951 | 0.13043 | 2021-08 | 0 | 0
2095 | CR0014003 | CTASK0028714 | Closed | OPUS-BKG-M | Loc Tran | 8 | 8 | 2021-08-31 11:43 | 2021-08-04 11:43 | Container | Service Management | Booking/Documentation | Outbound Doc |  |  | [Design] Booking Receipt Notice & Draft BL Setup ( ESM_BKG_1075 ) - BRN Remark | 2021-08-17 07:00 | 2021-09-16 | 2021-09-14 12:48 | 2021-10-28 07:13 | 2021-10-28 09:33 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-11-04 07:20 | 2021-11-24 12:00 | CR0014003 | Service ManagementBooking/DocumentationOutbound Doc | OPUS-BKG-OB | 2021-W45 | 2021-11 | 66 | 63 | 84.042 | 4 | 1 | 2 | 0.03 | 193503 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0.33333 | 0 | 2021-08 | 0 | 0
2096 | CR0014003 | CTASK0028731 | Closed | OPUS-BKG-M | Loc Tran | 24 | 15 | 2021-08-31 12:22 | 2021-08-09 12:22 | Container | Service Management | Booking/Documentation | Outbound Doc |  |  | [Testing] Booking Receipt Notice & Draft BL Setup ( ESM_BKG_1075 ) - BRN Remark | 2021-08-17 07:00 | 2021-09-16 | 2021-09-14 12:48 | 2021-10-28 07:13 | 2021-10-28 09:33 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-11-04 07:20 | 2021-11-24 12:00 | CR0014003 | Service ManagementBooking/DocumentationOutbound Doc | OPUS-BKG-OB | 2021-W45 | 2021-11 | 66 | 63 | 84.042 | 4 | 1 | 2 | 0.03 | 193503 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0.33333 | 0 | 2021-08 | 0 | 0
2097 | CR0014003 | CTASK0028730 | Closed | OPUS-BKG-M | Loc Tran | 38 | 36 | 2021-08-31 09:42 | 2021-08-09 09:42 | Container | Service Management | Booking/Documentation | Outbound Doc |  |  | [Development] Booking Receipt Notice & Draft BL Setup ( ESM_BKG_1075 ) - BRN Remark | 2021-08-17 07:00 | 2021-09-16 | 2021-09-14 12:48 | 2021-10-28 07:13 | 2021-10-28 09:33 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-11-04 07:20 | 2021-11-24 12:00 | CR0014003 | Service ManagementBooking/DocumentationOutbound Doc | OPUS-BKG-OB | 2021-W45 | 2021-11 | 66 | 63 | 84.042 | 4 | 1 | 2 | 0.03 | 193503 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0.33333 | 0 | 2021-08 | 0 | 0
2098 | CR0014684 | CTASK0031680 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2022-02-28 13:58 | 2022-02-07 13:58 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Deployment] Add SCRFA Customer Code to MCT Customer Tab | 2021-12-28 09:35 | 2022-01-07 22:00 | 2022-01-07 14:01 | 2022-01-26 14:42 | 2022-01-27 08:24 |  | 2022-02-15 08:00 | 2022-02-15 08:23 | 2022-01-27 09:06 | 2022-02-22 12:00 | CR0014684 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W7 | 2022-02 | 20 | 20 | 48.9343 | 4 | 1 | 1 | 0.02 | 153106 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 10 | 30 | 0.22951 | 0 | 2021-12 | 0 | 0
2099 | CR0014684 | CTASK0031674 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2022-01-14 13:48 | 2022-01-12 00:48 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Design] Add SCRFA Customer Code to MCT Customer Tab | 2021-12-28 09:35 | 2022-01-07 22:00 | 2022-01-07 14:01 | 2022-01-26 14:42 | 2022-01-27 08:24 |  | 2022-02-15 08:00 | 2022-02-15 08:23 | 2022-01-27 09:06 | 2022-02-22 12:00 | CR0014684 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W7 | 2022-02 | 20 | 20 | 48.9343 | 4 | 1 | 1 | 0.02 | 153106 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 10 | 30 | 0.22951 | 0 | 2021-12 | 0 | 0
2100 | CR0014684 | CTASK0031676 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2022-01-14 20:54 | 2022-01-12 13:54 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Development] Add SCRFA Customer Code to MCT Customer Tab | 2021-12-28 09:35 | 2022-01-07 22:00 | 2022-01-07 14:01 | 2022-01-26 14:42 | 2022-01-27 08:24 |  | 2022-02-15 08:00 | 2022-02-15 08:23 | 2022-01-27 09:06 | 2022-02-22 12:00 | CR0014684 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W7 | 2022-02 | 20 | 20 | 48.9343 | 4 | 1 | 1 | 0.02 | 153106 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 10 | 30 | 0.22951 | 0 | 2021-12 | 0 | 0
2101 | CR0014684 | CTASK0031678 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2022-01-25 20:55 | 2022-01-24 00:55 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Testing] Add SCRFA Customer Code to MCT Customer Tab | 2021-12-28 09:35 | 2022-01-07 22:00 | 2022-01-07 14:01 | 2022-01-26 14:42 | 2022-01-27 08:24 |  | 2022-02-15 08:00 | 2022-02-15 08:23 | 2022-01-27 09:06 | 2022-02-22 12:00 | CR0014684 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W7 | 2022-02 | 20 | 20 | 48.9343 | 4 | 1 | 1 | 0.02 | 153106 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 10 | 30 | 0.22951 | 0 | 2021-12 | 0 | 0
2102 | CR0014924 | CTASK0032727 | Closed | OPUS-SPC | Toai Phan | 12 | 10 | 2022-03-06 23:02 | 2022-03-02 23:02 | Container | Sales Management | Space Control | Standby Management |  |  | [CLV-SPC] Tuning to improve stand by booking performance with DBA | 2021-12-27 15:59 | 2022-01-21 22:00 | 2022-01-20 15:23 | 2022-01-26 07:57 | 2022-02-15 13:52 |  | 2022-02-18 13:52 | 2022-03-10 08:33 | 2022-02-17 12:26 | 2022-03-17 12:00 | CR0014924 | Sales ManagementSpace ControlStandby Management | OPUS-SPC | 2022-W7 | 2022-02 | 12 | 10 | 52.9117 | 1 | 1 | 1 | 0.01 | 183427 | 3.1 | 0 | 0 | 0 | 1 |  | 2 | 10 | 30 | 0 | 0 | 2021-12 | 0 | 0
2103 | CR0015359 | CTASK0033828 | Closed | OPUS-SAR | Nguyen Hoang Trong Phu | 24 | 22 | 2022-05-31 17:49 | 2022-05-02 17:49 | Container | Statement Management | Statement Account Receivable | Adjust | Offset Entry |  | [TAS] [Internal] Enhancing Offset - Duplicate transaction in SAP | 2022-05-12 14:33 | 2022-05-27 14:32 | 2022-05-16 09:22 | 2022-05-17 15:14 | 2022-05-18 06:56 |  | 2022-05-24 06:56 | 2022-05-24 12:16 | 2022-05-18 12:34 | 2022-07-06 12:00 | CR0015359 | Statement ManagementStatement Account ReceivableAdjustOffset Entry | OPUS-SAR | 2022-W21 | 2022-05 | 24 | 22 | 11.6829 | 1 | 1 | 1 | 0.08 | 203704 | 1.7 | 0 | 0 | 0 | 1 |  | 1 | 5 | 26 | 0 | 0 | 2022-05 | 0 | 0
2104 | CR0013608 | CTASK0031194 | Closed | OPUS-PRD | Tran Le | 3 | 3 | 2021-12-31 12:20 | 2021-12-01 12:19 | Container | Service Management | Product Catalog | Network Node | Pick Up CY for Export Booking |  | EUA - Enhance Excel Upload function in Pick Up CY for Export Booking UI - DEC | 2021-08-31 06:03 | 2021-09-17 18:00 | 2021-09-17 13:33 | 2021-12-14 07:36 | 2021-12-16 12:13 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-16 15:33 | 2022-01-04 12:00 | CR0013608 | Service ManagementProduct CatalogNetwork NodePick Up CY for Export Booking | OPUS-PRD | 2021-W52 | 2021-12 | 55 | 63 | 119.0814 | 6 | 1 | 3 | 0.02 | 193501 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.052632 | 0.076923 | 2021-08 | 0 | 0
2105 | CR0013608 | CTASK0029081 | Closed | OPUS-PRD | Son Nguyen The | 1 | 1 | 2021-09-30 05:39 | 2021-09-01 05:39 | Container | Service Management | Product Catalog | Network Node | Pick Up CY for Export Booking |  | EUA - Enhance Excel Upload function in Pick Up CY for Export Booking UI | 2021-08-31 06:03 | 2021-09-17 18:00 | 2021-09-17 13:33 | 2021-12-14 07:36 | 2021-12-16 12:13 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-16 15:33 | 2022-01-04 12:00 | CR0013608 | Service ManagementProduct CatalogNetwork NodePick Up CY for Export Booking | OPUS-PRD | 2021-W52 | 2021-12 | 55 | 63 | 119.0814 | 6 | 1 | 3 | 0.02 | 193531 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0 | 0 | 2021-08 | 0 | 0
2106 | CR0013608 | CTASK0030668 | Closed | OPUS-PRD | Tran Le | 2 | 2 | 2021-11-30 06:12 | 2021-11-01 06:12 | Container | Service Management | Product Catalog | Network Node | Pick Up CY for Export Booking |  | EUA - Enhance Excel Upload function in Pick Up CY for Export Booking UI - NOV | 2021-08-31 06:03 | 2021-09-17 18:00 | 2021-09-17 13:33 | 2021-12-14 07:36 | 2021-12-16 12:13 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-16 15:33 | 2022-01-04 12:00 | CR0013608 | Service ManagementProduct CatalogNetwork NodePick Up CY for Export Booking | OPUS-PRD | 2021-W52 | 2021-12 | 55 | 63 | 119.0814 | 6 | 1 | 3 | 0.02 | 193501 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.052632 | 0.076923 | 2021-08 | 0 | 0
2107 | CR0013608 | CTASK0029094 | Closed | OPUS-PRD | Tran Le | 44 | 48 | 2021-09-30 06:31 | 2021-09-01 06:31 | Container | Service Management | Product Catalog | Network Node | Pick Up CY for Export Booking |  | EUA - Enhance Excel Upload function in Pick Up CY for Export Booking UI - SEP | 2021-08-31 06:03 | 2021-09-17 18:00 | 2021-09-17 13:33 | 2021-12-14 07:36 | 2021-12-16 12:13 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-16 15:33 | 2022-01-04 12:00 | CR0013608 | Service ManagementProduct CatalogNetwork NodePick Up CY for Export Booking | OPUS-PRD | 2021-W52 | 2021-12 | 55 | 63 | 119.0814 | 6 | 1 | 3 | 0.02 | 193501 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.052632 | 0.076923 | 2021-08 | 0 | 0
2108 | CR0013608 | CTASK0029080 | Closed | OPUS-PRD | VInh Bui | 1 | 1 | 2021-09-30 05:35 | 2021-09-01 05:35 | Container | Service Management | Product Catalog | Network Node | Pick Up CY for Export Booking |  | EUA - Enhance Excel Upload function in Pick Up CY for Export Booking UI | 2021-08-31 06:03 | 2021-09-17 18:00 | 2021-09-17 13:33 | 2021-12-14 07:36 | 2021-12-16 12:13 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-16 15:33 | 2022-01-04 12:00 | CR0013608 | Service ManagementProduct CatalogNetwork NodePick Up CY for Export Booking | OPUS-PRD | 2021-W52 | 2021-12 | 55 | 63 | 119.0814 | 6 | 1 | 3 | 0.02 | 193469 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0 | 0 | 2021-08 | 0 | 0
2109 | CR0013608 | CTASK0029786 | Closed | OPUS-PRD | Tran Le | 6 | 10 | 2021-10-31 15:02 | 2021-10-01 15:02 | Container | Service Management | Product Catalog | Network Node | Pick Up CY for Export Booking |  | EUA - Enhance Excel Upload function in Pick Up CY for Export Booking UI - OCT | 2021-08-31 06:03 | 2021-09-17 18:00 | 2021-09-17 13:33 | 2021-12-14 07:36 | 2021-12-16 12:13 |  | 2021-12-28 08:00 | 2021-12-28 08:00 | 2021-12-16 15:33 | 2022-01-04 12:00 | CR0013608 | Service ManagementProduct CatalogNetwork NodePick Up CY for Export Booking | OPUS-PRD | 2021-W52 | 2021-12 | 55 | 63 | 119.0814 | 6 | 1 | 3 | 0.02 | 193501 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.052632 | 0.076923 | 2021-08 | 0 | 0
2110 | CR0014659 | CTASK0030473 | Closed | OPUS-MNR | Tien Le | 30 | 30 | 2021-12-31 17:00 | 2021-12-01 08:00 | Container | Equipment Management | M&R | Repair | Invoice | Invoice Creation & Correction | [CLT Internal] NA *MNR* Data Patch to map manually created invoice to NA Local Accounting - Invoice: RIC14466529 | 2021-12-03 15:18 | 2021-12-31 22:00 | 2021-12-31 09:47 | 2022-02-07 15:26 | 2022-02-16 17:30 |  | 2022-02-22 09:00 | 2022-02-22 08:00 | 2022-02-18 07:41 | 2022-03-01 12:00 | CR0014659 | Equipment ManagementM&RRepairInvoiceInvoice Creation & Correction | OPUS-MNR | 2022-W8 | 2022-02 | 52 | 62 | 80.7374 | 3 | 1 | 1 | 0.03 | 173286 | 3.2 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
2111 | CR0014659 | CTASK0030472 | Closed | OPUS-MNR | Tien Le | 20 | 22 | 2021-11-30 17:00 | 2021-11-15 08:00 | Container | Equipment Management | M&R | Repair | Invoice | Invoice Creation & Correction | [CLT Internal] NA *MNR* Data Patch to map manually created invoice to NA Local Accounting - Invoice: RIC14466529 | 2021-12-03 15:18 | 2021-12-31 22:00 | 2021-12-31 09:47 | 2022-02-07 15:26 | 2022-02-16 17:30 |  | 2022-02-22 09:00 | 2022-02-22 08:00 | 2022-02-18 07:41 | 2022-03-01 12:00 | CR0014659 | Equipment ManagementM&RRepairInvoiceInvoice Creation & Correction | OPUS-MNR | 2022-W8 | 2022-02 | 52 | 62 | 80.7374 | 3 | 1 | 1 | 0.03 | 173286 | 3.2 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
2112 | CR0014659 | CTASK0030471 | Closed | OPUS-MNR | Tien Le | 2 | 10 | 2021-12-31 17:00 | 2021-11-15 08:00 | Container | Equipment Management | M&R | Repair | Invoice | Invoice Creation & Correction | [Documentation][CLT Internal] NA *MNR* Data Patch to map manually created invoice to NA Local Accounting - Invoice: RIC14466529 | 2021-12-03 15:18 | 2021-12-31 22:00 | 2021-12-31 09:47 | 2022-02-07 15:26 | 2022-02-16 17:30 |  | 2022-02-22 09:00 | 2022-02-22 08:00 | 2022-02-18 07:41 | 2022-03-01 12:00 | CR0014659 | Equipment ManagementM&RRepairInvoiceInvoice Creation & Correction | OPUS-MNR | 2022-W8 | 2022-02 | 52 | 62 | 80.7374 | 3 | 1 | 1 | 0.03 | 173286 | 3.2 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
2113 | CR0014524 | CTASK0029631 | Closed | OPUS-BKG-M | Thien Lai | 24 | 24 | 2021-10-29 20:14 | 2021-10-11 00:13 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193567 | 2.2 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.5625 | 0 | 2021-10 | 0 | 0
2114 | CR0014524 | CTASK0030130 | Closed | OPUS-BKG-M | Quy Truong | 43 | 41 | 2021-10-31 13:35 | 2021-10-20 13:35 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 203791 | 1 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0 | 0 | 2021-10 | 0 | 0
2115 | CR0014524 | CTASK0029510 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-09-30 20:21 | 2021-09-23 00:21 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 153106 | 3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.22951 | 0 | 2021-10 | 0 | 0
2116 | CR0014524 | CTASK0029646 | Closed | OPUS-BKG-OB | Nam Nguyen | 33 | 20 | 2021-11-05 17:26 | 2021-10-31 17:26 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing]Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 123048 | 3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.22222 | 0 | 2021-10 | 0 | 0
2117 | CR0014524 | CTASK0029541 | Closed | OPUS-BKG-OB | Nam Nguyen | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 123048 | 3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.22222 | 0 | 2021-10 | 0 | 0
2118 | CR0014524 | CTASK0029627 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2022-01-31 10:09 | 2022-01-04 10:09 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 153106 | 3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.22951 | 0 | 2021-10 | 0 | 0
2119 | CR0014524 | CTASK0029625 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-11-26 20:08 | 2021-11-08 00:07 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 153106 | 3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.22951 | 0 | 2021-10 | 0 | 0
2120 | CR0014524 | CTASK0029644 | Closed | OPUS-BKG-OB | Nam Nguyen | 94 | 94 | 2021-11-30 12:43 | 2021-09-01 12:43 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development]Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 123048 | 3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.22222 | 0 | 2021-10 | 0 | 0
2121 | CR0014524 | CTASK0029635 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 23 | 23 | 2022-01-11 10:17 | 2022-01-04 10:17 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193488 | 2.3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.53659 | 0 | 2021-10 | 0 | 0
2122 | CR0014524 | CTASK0029636 | Closed | OPUS-BKG-M | Trang Le Minh | 8 | 8 | 2021-12-31 10:18 | 2021-12-01 10:18 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193594 | 2.1 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0 | 0 | 2021-10 | 0 | 0
2123 | CR0014524 | CTASK0029623 | Closed | OPUS-BKG-M | Trang Le Minh | 2 | 2 | 2021-09-30 20:05 | 2021-09-27 10:05 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193594 | 2.1 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0 | 0 | 2021-10 | 0 | 0
2124 | CR0014524 | CTASK0029629 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 16 | 16 | 2021-10-29 20:11 | 2021-10-11 00:11 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193488 | 2.3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.53659 | 0 | 2021-10 | 0 | 0
2125 | CR0014524 | CTASK0029648 | Closed | OPUS-BKG-OB | Nam Nguyen | 6 | 20 | 2022-01-31 17:26 | 2022-01-01 17:26 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment]Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 123048 | 3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.22222 | 0 | 2021-10 | 0 | 0
2126 | CR0014524 | CTASK0029633 | Closed | OPUS-BKG-M | Trang Le Minh | 16 | 16 | 2021-11-26 10:16 | 2021-11-08 10:15 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193594 | 2.1 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0 | 0 | 2021-10 | 0 | 0
2127 | CR0014524 | CTASK0029630 | Closed | OPUS-BKG-M | Trang Le Minh | 38 | 38 | 2021-10-29 20:13 | 2021-10-04 00:12 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193594 | 2.1 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0 | 0 | 2021-10 | 0 | 0
2128 | CR0014524 | CTASK0029632 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 22 | 22 | 2021-11-26 20:15 | 2021-11-08 00:14 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193488 | 2.3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.53659 | 0 | 2021-10 | 0 | 0
2129 | CR0014524 | CTASK0029637 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193567 | 2.2 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.5625 | 0 | 2021-10 | 0 | 0
2130 | CR0014524 | CTASK0029624 | Closed | OPUS-BKG-M | Kieu Le | 26 | 26 | 2021-10-29 20:06 | 2021-10-11 00:06 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 153106 | 3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.22951 | 0 | 2021-10 | 0 | 0
2131 | CR0014524 | CTASK0029634 | Closed | OPUS-BKG-M | Thien Lai | 12 | 12 | 2021-11-24 10:16 | 2021-11-08 10:16 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 193567 | 2.2 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.5625 | 0 | 2021-10 | 0 | 0
2132 | CR0014524 | CTASK0029643 | Closed | OPUS-BKG-OB | Nam Nguyen | 10 | 10 | 2021-09-30 12:32 | 2021-09-29 12:32 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design]Global *API* - Logic enhancement to trigger 29 additional trigger points for 301 F/F (Booking API) | 2021-10-15 08:29 | 2021-11-24 22:00 | 2021-11-24 11:22 | 2021-12-23 08:25 | 2021-12-31 21:22 |  | 2022-01-11 08:00 | 2022-01-11 08:30 | 2022-01-03 09:22 | 2022-01-18 12:01 | CR0014524 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W2 | 2022-01 | 405 | 412 | 87.9799 | 20 | 2 | 6 | 0.2 | 123048 | 3 | 1 | 0 | 0 | 4 |  | 2 | 7 | 33 | 0.22222 | 0 | 2021-10 | 0 | 0
2133 | CR0014940 | CTASK0032189 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 | 2022-03-15 21:00 | 2022-03-09 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Deployment] (TS) EUA Cust - K&N - SWB FTP ISSUE - CHANGE REQUEST | 2022-02-17 07:03 | 2022-02-25 22:00 | 2022-02-21 14:16 | 2022-03-10 07:47 | 2022-03-10 08:19 |  | 2022-03-16 08:00 | 2022-03-16 08:00 | 2022-03-11 15:14 | 2022-03-23 12:00 | CR0014940 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2022-W11 | 2022-03 | 26 | 26 | 27.0396 | 3 | 1 | 1 | 0.04 | 193470 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 10 | 38 | 0.36842 | 0.11111 | 2022-02 | 0 | 0
2134 | CR0014940 | CTASK0032188 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 14 | 14 | 2022-02-18 21:00 | 2022-02-15 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Dev + Test] (TS) EUA Cust - K&N - SWB FTP ISSUE - CHANGE REQUEST | 2022-02-17 07:03 | 2022-02-25 22:00 | 2022-02-21 14:16 | 2022-03-10 07:47 | 2022-03-10 08:19 |  | 2022-03-16 08:00 | 2022-03-16 08:00 | 2022-03-11 15:14 | 2022-03-23 12:00 | CR0014940 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2022-W11 | 2022-03 | 26 | 26 | 27.0396 | 3 | 1 | 1 | 0.04 | 193470 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 10 | 38 | 0.36842 | 0.11111 | 2022-02 | 0 | 0
2135 | CR0014940 | CTASK0032187 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2022-02-11 21:00 | 2022-02-10 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Design] (TS) EUA Cust - K&N - SWB FTP ISSUE - CHANGE REQUEST | 2022-02-17 07:03 | 2022-02-25 22:00 | 2022-02-21 14:16 | 2022-03-10 07:47 | 2022-03-10 08:19 |  | 2022-03-16 08:00 | 2022-03-16 08:00 | 2022-03-11 15:14 | 2022-03-23 12:00 | CR0014940 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2022-W11 | 2022-03 | 26 | 26 | 27.0396 | 3 | 1 | 1 | 0.04 | 193470 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 10 | 38 | 0.36842 | 0.11111 | 2022-02 | 0 | 0
2136 | CR0013938 | CTASK0027597 | Closed | OPUS-DMT | Cuong Nguyen | 2 | 2 | 2021-07-02 18:00 | 2021-07-01 06:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK3] CLV_Analysis_Test | 2021-06-23 07:35 | 2021-07-07 18:00 | 2021-07-06 11:23 | 2021-09-24 06:59 | 2021-09-30 07:18 |  | 2021-10-05 08:10 | 2021-10-05 08:34 | 2021-09-30 18:05 | 2021-10-13 12:00 | CR0013938 | Service ManagementDemurrage/Detention | OPUS-DMT | 2021-W40 | 2021-10 | 2 | 2 | 104.0248 | 1 | 1 | 1 | 0 | 193529 | 2.1 | 0 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0 | 0.22222 | 2021-06 | 0 | 0
2137 | CR0013867 | CTASK0028850 | Closed | OPUS-DMT | Cuong Nguyen | 50 | 61 | 2021-10-20 18:00 | 2021-09-01 06:00 | Container | Service Management | Demurrage/Detention | Charge Generation | Charge Inquiry | Last Free Day Inquiry before Container Movement | [CTASK3] Development_Test_Deployment | 2021-09-09 08:22 | 2021-10-05 18:00 | 2021-09-28 14:26 | 2021-11-05 11:49 | 2021-11-17 14:06 |  | 2021-11-23 08:06 | 2021-11-23 09:55 | 2021-11-18 12:18 | 2021-11-30 12:00 | CR0013867 | Service ManagementDemurrage/DetentionCharge GenerationCharge InquiryLast Free Day Inquiry before Container Movement | OPUS-DMT | 2021-W47 | 2021-11 | 50 | 61 | 74.9888 | 1 | 1 | 1 | 0.03 | 193529 | 2.3 | 0 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0 | 0.22222 | 2021-09 | 0 | 0
2138 | CR0011951 | CTASK0027446 | Closed | OPUS-INV | Nguyen Ha Vi | 32 | 30 | 2021-06-30 13:34 | 2021-06-01 13:33 | Container | Service Management | A/R Invoice | Invoice Inquiry |  |  | [June] New Enhancement in MRI Invoice creation and GSTR1 report for Indian | 2021-05-24 14:37 | 2021-07-09 14:36 | 2021-06-21 15:22 | 2021-10-29 08:15 | 2021-11-02 06:15 |  | 2021-11-09 09:00 | 2021-11-09 09:00 | 2021-11-04 11:25 | 2021-11-17 12:00 | CR0011951 | Service ManagementA/R InvoiceInvoice Inquiry | OPUS-INV | 2021-W45 | 2021-11 | 84 | 80 | 168.7659 | 3 | 1 | 3 | 0.02 | 203664 | 1 | 4 | 1 | 0 | 1 |  | 3 | 9 | 38 | 1.8182 | 1.2857 | 2021-05 | 1 | 1
2139 | CR0011951 | CTASK0029226 | Closed | OPUS-INV | Lien Le | 22 | 20 | 2021-09-30 17:07 | 2021-09-01 17:07 | Container | Service Management | A/R Invoice | Invoice Inquiry |  |  | [Sep 2021][Lien Le][New Enhancement in MRI Invoice creation and GSTR1 report for Indian] | 2021-05-24 14:37 | 2021-07-09 14:36 | 2021-06-21 15:22 | 2021-10-29 08:15 | 2021-11-02 06:15 |  | 2021-11-09 09:00 | 2021-11-09 09:00 | 2021-11-04 11:25 | 2021-11-17 12:00 | CR0011951 | Service ManagementA/R InvoiceInvoice Inquiry | OPUS-INV | 2021-W45 | 2021-11 | 84 | 80 | 168.7659 | 3 | 1 | 3 | 0.02 | 193441 | 2.2 | 4 | 1 | 0 | 1 |  | 3 | 9 | 38 | 0.42308 | 0 | 2021-05 | 1 | 1
2140 | CR0011951 | CTASK0029000 | Closed | OPUS-INV | Mohamed Hary | 30 | 30 | 2021-08-31 16:26 | 2021-08-23 16:26 | Container | Service Management | A/R Invoice | Invoice Inquiry |  |  | [August][Hary][New Enhancement in MRI Invoice creation and GSTR1 report for Indian] | 2021-05-24 14:37 | 2021-07-09 14:36 | 2021-06-21 15:22 | 2021-10-29 08:15 | 2021-11-02 06:15 |  | 2021-11-09 09:00 | 2021-11-09 09:00 | 2021-11-04 11:25 | 2021-11-17 12:00 | CR0011951 | Service ManagementA/R InvoiceInvoice Inquiry | OPUS-INV | 2021-W45 | 2021-11 | 84 | 80 | 168.7659 | 3 | 1 | 3 | 0.02 | 193489 | 2 | 4 | 1 | 0 | 1 |  | 3 | 9 | 38 | 0.72727 | 0.63636 | 2021-05 | 1 | 1
2141 | CR0014471 | CTASK0029953 | Closed | OPUS-INV | Lien Le | 35 | 32 | 2021-10-31 14:00 | 2021-10-13 14:00 | Container | Service Management | A/R Invoice |  |  |  | [Oct 2021] Add authority signature in Invoice automatically - Freight Invoice - Thailand | 2021-10-12 09:32 | 2021-10-31 16:32 | 2021-10-22 14:08 | 2021-12-01 12:57 | 2021-12-01 12:57 |  | 2021-12-07 12:57 | 2021-12-07 08:00 | 2021-12-02 13:07 | 2021-12-28 12:01 | CR0014471 | Service ManagementA/R Invoice | OPUS-INV | 2021-W49 | 2021-12 | 43 | 40 | 56.1424 | 2 | 1 | 2 | 0.03 | 193441 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.42308 | 0 | 2021-10 | 0 | 0
2142 | CR0014471 | CTASK0029954 | Closed | OPUS-INV | Nguyen Ha Vi | 8 | 8 | 2021-10-31 14:01 | 2021-10-13 14:01 | Container | Service Management | A/R Invoice |  |  |  | [Oct 2021] Add authority signature in Invoice automatically - Freight Invoice - Thailand | 2021-10-12 09:32 | 2021-10-31 16:32 | 2021-10-22 14:08 | 2021-12-01 12:57 | 2021-12-01 12:57 |  | 2021-12-07 12:57 | 2021-12-07 08:00 | 2021-12-02 13:07 | 2021-12-28 12:01 | CR0014471 | Service ManagementA/R Invoice | OPUS-INV | 2021-W49 | 2021-12 | 43 | 40 | 56.1424 | 2 | 1 | 2 | 0.03 | 203664 | 1.4 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 1.8182 | 2.5 | 2021-10 | 0 | 0
2143 | CR0013838 | CTASK0028193 | Closed | OPUS-BKG-OB | Nam Nguyen | 34 | 20 | 2021-11-05 21:00 | 2021-10-01 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Status Report | [Development + Testing] Adding more search criteria in the B/L status report | 2021-10-18 07:11 | 2021-11-19 07:11 | 2021-11-11 12:27 | 2022-02-15 07:30 | 2022-02-15 08:06 |  | 2022-02-22 08:06 | 2022-03-02 08:23 | 2022-02-17 12:24 | 2022-03-09 12:00 | CR0013838 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Status Report | OPUS-BKG-OB | 2022-W8 | 2022-02 | 40 | 28 | 127.038 | 3 | 1 | 1 | 0.01 | 123048 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0.22222 | 0 | 2021-10 | 0 | 0
2144 | CR0013838 | CTASK0028192 | Closed | OPUS-BKG-OB | Nam Nguyen | 4 | 4 | 2021-07-16 21:00 | 2021-07-15 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Status Report | [Design] Adding more search criteria in the B/L status report | 2021-10-18 07:11 | 2021-11-19 07:11 | 2021-11-11 12:27 | 2022-02-15 07:30 | 2022-02-15 08:06 |  | 2022-02-22 08:06 | 2022-03-02 08:23 | 2022-02-17 12:24 | 2022-03-09 12:00 | CR0013838 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Status Report | OPUS-BKG-OB | 2022-W8 | 2022-02 | 40 | 28 | 127.038 | 3 | 1 | 1 | 0.01 | 123048 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0.22222 | 0 | 2021-10 | 0 | 0
2145 | CR0013838 | CTASK0028194 | Closed | OPUS-BKG-OB | Nam Nguyen | 6 | 4 | 2021-12-31 09:27 | 2021-12-01 10:11 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Status Report | [Deployment] Adding more search criteria in the B/L status report | 2021-10-18 07:11 | 2021-11-19 07:11 | 2021-11-11 12:27 | 2022-02-15 07:30 | 2022-02-15 08:06 |  | 2022-02-22 08:06 | 2022-03-02 08:23 | 2022-02-17 12:24 | 2022-03-09 12:00 | CR0013838 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Status Report | OPUS-BKG-OB | 2022-W8 | 2022-02 | 40 | 28 | 127.038 | 3 | 1 | 1 | 0.01 | 123048 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0.22222 | 0 | 2021-10 | 0 | 0
2146 | CR0014295 | CTASK0028810 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2021-11-12 22:14 | 2021-11-08 22:13 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment]CHINA SEAL KIND and CODE to be 'auto-updated" for ROUTE Change involving any CHINA Ports | 2021-09-07 13:35 | 2021-10-06 13:34 | 2021-10-05 12:44 | 2021-10-18 08:44 | 2021-10-20 11:20 |  | 2021-11-16 11:19 | 2021-11-16 08:40 | 2021-11-04 07:21 | 2021-11-23 12:01 | CR0014295 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W46 | 2021-11 | 52 | 52 | 69.9061 | 5 | 1 | 1 | 0.03 | 193488 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.53659 | 0 | 2021-09 | 0 | 0
2147 | CR0014295 | CTASK0028808 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 34 | 34 | 2021-09-17 19:19 | 2021-09-13 09:19 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development]CHINA SEAL KIND and CODE to be 'auto-updated" for ROUTE Change involving any CHINA Ports | 2021-09-07 13:35 | 2021-10-06 13:34 | 2021-10-05 12:44 | 2021-10-18 08:44 | 2021-10-20 11:20 |  | 2021-11-16 11:19 | 2021-11-16 08:40 | 2021-11-04 07:21 | 2021-11-23 12:01 | CR0014295 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W46 | 2021-11 | 52 | 52 | 69.9061 | 5 | 1 | 1 | 0.03 | 193488 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.53659 | 0 | 2021-09 | 0 | 0
2148 | CR0014295 | CTASK0028757 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design]CHINA SEAL KIND and CODE to be 'auto-updated" for ROUTE Change involving any CHINA Ports | 2021-09-07 13:35 | 2021-10-06 13:34 | 2021-10-05 12:44 | 2021-10-18 08:44 | 2021-10-20 11:20 |  | 2021-11-16 11:19 | 2021-11-16 08:40 | 2021-11-04 07:21 | 2021-11-23 12:01 | CR0014295 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W46 | 2021-11 | 52 | 52 | 69.9061 | 5 | 1 | 1 | 0.03 | 193488 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.53659 | 0 | 2021-09 | 0 | 0
2149 | CR0014295 | CTASK0028809 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 6 | 6 | 2021-10-01 22:54 | 2021-09-27 09:54 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing]CHINA SEAL KIND and CODE to be 'auto-updated" for ROUTE Change involving any CHINA Ports | 2021-09-07 13:35 | 2021-10-06 13:34 | 2021-10-05 12:44 | 2021-10-18 08:44 | 2021-10-20 11:20 |  | 2021-11-16 11:19 | 2021-11-16 08:40 | 2021-11-04 07:21 | 2021-11-23 12:01 | CR0014295 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W46 | 2021-11 | 52 | 52 | 69.9061 | 5 | 1 | 1 | 0.03 | 193488 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.53659 | 0 | 2021-09 | 0 | 0
2150 | CR0014295 | CTASK0028775 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Document]CHINA SEAL KIND and CODE to be 'auto-updated" for ROUTE Change involving any CHINA Ports | 2021-09-07 13:35 | 2021-10-06 13:34 | 2021-10-05 12:44 | 2021-10-18 08:44 | 2021-10-20 11:20 |  | 2021-11-16 11:19 | 2021-11-16 08:40 | 2021-11-04 07:21 | 2021-11-23 12:01 | CR0014295 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W46 | 2021-11 | 52 | 52 | 69.9061 | 5 | 1 | 1 | 0.03 | 193488 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.53659 | 0 | 2021-09 | 0 | 0
2151 | CR0014623 | CTASK0031503 | Closed | OPUS-INV | Lien Le | 8 | 8 | 2022-01-31 17:25 | 2022-01-01 17:25 | Container | Service Management | A/R Invoice | Invoice Creation / Correction | Miscellaneous Revenue Invoice Creation |  | [Jan 2022] [CLT Internal] Match S/A date when creating MIC ( Case of vessel sked change ) | 2021-12-29 09:04 | 2022-01-07 22:00 | 2022-01-07 07:28 | 2022-03-02 18:28 | 2022-03-10 08:34 |  | 2022-03-15 08:00 | 2022-03-15 08:38 | 2022-03-10 16:04 | 2022-03-22 12:00 | CR0014623 | Service ManagementA/R InvoiceInvoice Creation / CorrectionMiscellaneous Revenue Invoice Creation | OPUS-INV | 2022-W11 | 2022-03 | 45 | 43 | 75.9555 | 2 | 1 | 2 | 0.02 | 193441 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0.42308 | 0 | 2021-12 | 0 | 0
2152 | CR0014623 | CTASK0031502 | Closed | OPUS-INV | Nguyen Ha Vi | 37 | 35 | 2022-01-31 17:24 | 2022-01-01 17:24 | Container | Service Management | A/R Invoice | Invoice Creation / Correction | Miscellaneous Revenue Invoice Creation |  | [Jan 2022] [CLT Internal] Match S/A date when creating MIC ( Case of vessel sked change ) | 2021-12-29 09:04 | 2022-01-07 22:00 | 2022-01-07 07:28 | 2022-03-02 18:28 | 2022-03-10 08:34 |  | 2022-03-15 08:00 | 2022-03-15 08:38 | 2022-03-10 16:04 | 2022-03-22 12:00 | CR0014623 | Service ManagementA/R InvoiceInvoice Creation / CorrectionMiscellaneous Revenue Invoice Creation | OPUS-INV | 2022-W11 | 2022-03 | 45 | 43 | 75.9555 | 2 | 1 | 2 | 0.02 | 203664 | 1.6 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 1.8182 | 2.5 | 2021-12 | 0 | 0
2153 | CR0014663 | CTASK0030330 | Closed | OPUS-SCO | Lien Le | 9 | 8 | 2021-11-30 09:29 | 2021-11-01 09:29 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Management By EMail |  | [Nov 2021][CLT Internal] Improvements related to changing passwords for Gmail accounts in Lookup | 2021-10-28 11:33 | 2021-11-12 22:00 | 2021-11-12 08:08 | 2021-11-12 10:04 | 2021-11-12 10:09 |  | 2021-11-16 09:00 | 2021-11-16 08:26 | 2021-11-12 10:38 | 2021-11-24 12:00 | CR0014663 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Management By EMail | OPUS-SAR | 2021-W46 | 2021-11 | 28 | 26 | 18.8938 | 2 | 1 | 2 | 0.06 | 193441 | 2.6 | 1 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0.42308 | 0 | 2021-10 | 0 | 0
2154 | CR0014663 | CTASK0030329 | Closed | OPUS-SCO | Cuong Tran Hung | 19 | 18 | 2021-11-30 09:27 | 2021-11-01 09:27 | Container | Statement Management | Statement Account Receivable | Collection Manager | Collection Management By EMail |  | [Nov 2021][CLT Internal] Improvements related to changing passwords for Gmail accounts in Lookup | 2021-10-28 11:33 | 2021-11-12 22:00 | 2021-11-12 08:08 | 2021-11-12 10:04 | 2021-11-12 10:09 |  | 2021-11-16 09:00 | 2021-11-16 08:26 | 2021-11-12 10:38 | 2021-11-24 12:00 | CR0014663 | Statement ManagementStatement Account ReceivableCollection ManagerCollection Management By EMail | OPUS-SAR | 2021-W46 | 2021-11 | 28 | 26 | 18.8938 | 2 | 1 | 2 | 0.06 | 193530 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 16 | 38 | 1.2308 | 1.25 | 2021-10 | 0 | 0
2155 | CR0014008 | CTASK0029704 | Closed | OPUS-DMT | Cuong Nguyen | 74 | 70 | 2022-04-30 16:16 | 2022-01-30 16:15 | Container | Service Management | Demurrage/Detention |  |  |  | [TASK1] Development & Test | 2021-11-02 11:55 | 2022-03-19 11:54 | 2022-03-17 16:25 | 2022-04-28 07:48 | 2022-05-06 13:52 |  | 2022-05-24 08:01 | 2022-05-24 08:01 | 2022-05-20 15:11 | 2022-05-31 12:00 | CR0014008 | Service ManagementDemurrage/Detention | OPUS-DMT | 2022-W21 | 2022-05 | 74 | 70 | 202.8375 | 1 | 1 | 1 | 0.01 | 193529 | 2.4 | 1 | 0 | 0 | 1 |  | 3 | 5 | 26 | 0 | 0.22222 | 2021-11 | 0 | 0
2156 | CR0013506 | CTASK0025829 | Closed | OPUS-DMT | Cuong Nguyen | 1 | 3 | 2021-05-31 18:00 | 2021-05-03 06:00 | Container | Service Management | Demurrage/Detention |  |  |  | [CTASK4] CLV_Analysis_Pair Test | 2021-05-04 07:44 | 2021-05-21 18:00 | 2021-05-21 12:29 | 2022-01-07 15:45 | 2022-01-10 08:00 |  | 2022-01-18 08:00 | 2022-01-18 10:39 | 2022-01-12 15:41 | 2022-01-25 12:00 | CR0013506 | Service ManagementDemurrage/Detention | OPUS-DMT | 2022-W3 | 2022-01 | 1 | 3 | 259.0113 | 1 | 1 | 1 | 0 | 193529 | 1.9 | 1 | 0 | 0 | 1 |  | 3 | 11 | 33 | 0.11538 | 0.058824 | 2021-05 | 0 | 0
2157 | CR0014209 | CTASK0028263 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 2 | 2 | 2021-10-08 11:14 | 2021-10-01 11:14 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Test]Enhancement of Hong Kong Manifest | 2021-08-19 07:45 | 2021-09-03 22:00 | 2021-09-03 11:13 | 2021-09-07 15:35 | 2021-09-08 09:29 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-30 07:16 | 2021-10-13 12:00 | CR0014209 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W40 | 2021-10 | 2 | 10 | 47.0101 | 4 | 1 | 1 | 0.01 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 4.25 | 2.25 | 2021-08 | 0 | 0
2158 | CR0014209 | CTASK0028261 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 2 | 2 | 2021-10-08 11:15 | 2021-10-01 11:15 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Design]Enhancement of Hong Kong Manifest | 2021-08-19 07:45 | 2021-09-03 22:00 | 2021-09-03 11:13 | 2021-09-07 15:35 | 2021-09-08 09:29 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-30 07:16 | 2021-10-13 12:00 | CR0014209 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W40 | 2021-10 | 2 | 10 | 47.0101 | 4 | 1 | 1 | 0.01 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 4.25 | 2.25 | 2021-08 | 0 | 0
2159 | CR0014209 | CTASK0028262 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 2 | 4 | 2021-10-08 11:13 | 2021-10-01 11:13 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Dev]Enhancement of Hong Kong Manifest | 2021-08-19 07:45 | 2021-09-03 22:00 | 2021-09-03 11:13 | 2021-09-07 15:35 | 2021-09-08 09:29 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-30 07:16 | 2021-10-13 12:00 | CR0014209 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W40 | 2021-10 | 2 | 10 | 47.0101 | 4 | 1 | 1 | 0.01 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 4.25 | 2.25 | 2021-08 | 0 | 0
2160 | CR0014209 | CTASK0028264 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 2 | 2 | 2021-10-08 11:15 | 2021-10-01 11:15 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Deploy]Enhancement of Hong Kong Manifest | 2021-08-19 07:45 | 2021-09-03 22:00 | 2021-09-03 11:13 | 2021-09-07 15:35 | 2021-09-08 09:29 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-30 07:16 | 2021-10-13 12:00 | CR0014209 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2021-W40 | 2021-10 | 2 | 10 | 47.0101 | 4 | 1 | 1 | 0.01 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 1 | 5 | 26 | 4.25 | 2.25 | 2021-08 | 0 | 0
2161 | CR0014543 | CTASK0029778 | Closed | OPUS-BKG-M | Trang Le Minh | 12 | 12 | 2021-10-29 21:31 | 2021-10-11 08:31 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA - Activate Special Cargo indicators in TRO/I - Auto update after selecting Cntr | 2021-10-12 09:02 | 2021-11-04 | 2021-11-02 15:58 | 2021-11-05 06:48 | 2021-11-08 08:50 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-11-09 07:10 | 2021-11-30 12:00 | CR0014543 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W47 | 2021-11 | 28 | 28 | 41.9571 | 4 | 1 | 1 | 0.03 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0 | 0 | 2021-10 | 0 | 0
2162 | CR0014543 | CTASK0029777 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2021-10-29 21:16 | 2021-10-01 08:16 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] EUA - Activate Special Cargo indicators in TRO/I - Auto update after selecting Cntr | 2021-10-12 09:02 | 2021-11-04 | 2021-11-02 15:58 | 2021-11-05 06:48 | 2021-11-08 08:50 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-11-09 07:10 | 2021-11-30 12:00 | CR0014543 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W47 | 2021-11 | 28 | 28 | 41.9571 | 4 | 1 | 1 | 0.03 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0 | 0 | 2021-10 | 0 | 0
2163 | CR0014543 | CTASK0029781 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2021-11-30 21:35 | 2021-11-01 08:35 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] EUA - Activate Special Cargo indicators in TRO/I - Auto update after selecting Cntr | 2021-10-12 09:02 | 2021-11-04 | 2021-11-02 15:58 | 2021-11-05 06:48 | 2021-11-08 08:50 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-11-09 07:10 | 2021-11-30 12:00 | CR0014543 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W47 | 2021-11 | 28 | 28 | 41.9571 | 4 | 1 | 1 | 0.03 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0 | 0 | 2021-10 | 0 | 0
2164 | CR0014543 | CTASK0029779 | Closed | OPUS-BKG-M | Trang Le Minh | 8 | 8 | 2021-10-29 21:33 | 2021-10-11 08:32 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Test] EUA - Activate Special Cargo indicators in TRO/I - Auto update after selecting Cntr | 2021-10-12 09:02 | 2021-11-04 | 2021-11-02 15:58 | 2021-11-05 06:48 | 2021-11-08 08:50 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-11-09 07:10 | 2021-11-30 12:00 | CR0014543 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W47 | 2021-11 | 28 | 28 | 41.9571 | 4 | 1 | 1 | 0.03 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0 | 0 | 2021-10 | 0 | 0
2165 | CR0014995 | CTASK0031663 | Closed | OPUS-PRI | Ngan Nham | 12 | 12 | 2022-01-31 22:00 | 2022-01-09 23:00 | Container | Sales Management | Pricing | Service Contract | S/C Creation |  | [Develop][Kontainers] OPUS payment term as Blank | 2022-01-13 07:57 | 2022-02-28 22:00 | 2022-02-08 08:49 | 2022-02-09 08:45 | 2022-02-09 11:09 |  | 2022-02-15 10:00 | 2022-02-15 09:15 | 2022-02-15 13:29 | 2022-02-23 12:00 | CR0014995 | Sales ManagementPricingService ContractS/C Creation | OPUS-PRI | 2022-W7 | 2022-02 | 16 | 20 | 33.0852 | 2 | 1 | 1 | 0.03 | 193461 | 3.1 | 1 | 0 | 0 | 1 |  | 1 | 10 | 30 | 0.125 | 0 | 2022-01 | 0 | 0
2166 | CR0014995 | CTASK0032061 | Closed | OPUS-PRI | Ngan Nham | 4 | 8 | 2022-02-28 22:00 | 2022-01-31 23:00 | Container | Sales Management | Pricing | Service Contract | S/C Creation |  | [Develop][Kontainers] OPUS payment term as Blank | 2022-01-13 07:57 | 2022-02-28 22:00 | 2022-02-08 08:49 | 2022-02-09 08:45 | 2022-02-09 11:09 |  | 2022-02-15 10:00 | 2022-02-15 09:15 | 2022-02-15 13:29 | 2022-02-23 12:00 | CR0014995 | Sales ManagementPricingService ContractS/C Creation | OPUS-PRI | 2022-W7 | 2022-02 | 16 | 20 | 33.0852 | 2 | 1 | 1 | 0.03 | 193461 | 3.1 | 1 | 0 | 0 | 1 |  | 1 | 10 | 30 | 0.125 | 0 | 2022-01 | 0 | 0
2167 | CR0014646 | CTASK0030521 | Closed | OPUS-MNR | Tien Le | 11 | 11 |  |  | Container | Service Management | A/R Invoice |  |  |  | [MNR][Internal] AR I/F number digit issue | 2021-11-29 13:24 | 2021-12-31 22:00 | 2021-12-17 12:36 | 2021-12-24 07:39 | 2021-12-24 07:53 |  | 2021-12-27 08:00 | 2021-12-27 08:00 | 2021-12-24 08:19 | 2022-01-04 12:00 | CR0014646 | Service ManagementA/R Invoice | OPUS-INV | 2021-W52 | 2021-12 | 39 | 28 | 27.7751 | 4 | 3 | 4 | 0.04 | 173286 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 7 | 26 | 0 | 0 | 2021-11 | 0 | 0
2168 | CR0014646 | CTASK0030451 | Closed | OPUS-TES | Thai Nguyen | 20 | 20 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Service Management | A/R Invoice |  |  |  | [202111][Internal] AR I/F number digit issue | 2021-11-29 13:24 | 2021-12-31 22:00 | 2021-12-17 12:36 | 2021-12-24 07:39 | 2021-12-24 07:53 |  | 2021-12-27 08:00 | 2021-12-27 08:00 | 2021-12-24 08:19 | 2022-01-04 12:00 | CR0014646 | Service ManagementA/R Invoice | OPUS-INV | 2021-W52 | 2021-12 | 39 | 28 | 27.7751 | 4 | 3 | 4 | 0.04 | 173249 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 7 | 26 | 0.89474 | 0 | 2021-11 | 0 | 0
2169 | CR0014646 | CTASK0031266 | Closed | OPUS-TRS | Giang Nguyen Hoang | 4 | 4 | 2021-12-31 22:00 | 2021-12-01 07:00 | Container | Service Management | A/R Invoice |  |  |  | [202112][Internal] AR I/F number digit issue | 2021-11-29 13:24 | 2021-12-31 22:00 | 2021-12-17 12:36 | 2021-12-24 07:39 | 2021-12-24 07:53 |  | 2021-12-27 08:00 | 2021-12-27 08:00 | 2021-12-24 08:19 | 2022-01-04 12:00 | CR0014646 | Service ManagementA/R Invoice | OPUS-INV | 2021-W52 | 2021-12 | 39 | 28 | 27.7751 | 4 | 3 | 4 | 0.04 | 183440 | 2.7 | 1 | 0 | 0 | 1 |  | 1 | 7 | 26 | 0 | 0 | 2021-11 | 0 | 0
2170 | CR0014646 | CTASK0031265 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 4 | 4 | 2021-12-31 22:00 | 2021-12-01 07:00 | Container | Service Management | A/R Invoice |  |  |  | [202112][Internal] AR I/F number digit issue | 2021-11-29 13:24 | 2021-12-31 22:00 | 2021-12-17 12:36 | 2021-12-24 07:39 | 2021-12-24 07:53 |  | 2021-12-27 08:00 | 2021-12-27 08:00 | 2021-12-24 08:19 | 2022-01-04 12:00 | CR0014646 | Service ManagementA/R Invoice | OPUS-INV | 2021-W52 | 2021-12 | 39 | 28 | 27.7751 | 4 | 3 | 4 | 0.04 | 183432 | 2.7 | 1 | 0 | 0 | 1 |  | 1 | 7 | 26 | 0.043478 | 0.22222 | 2021-11 | 0 | 0
2171 | CR0012925 | CTASK0025669 | Closed | OPUS-SCO | Hang To | 30 | 30 | 2021-03-31 11:32 | 2021-03-01 11:32 | Container | Biz Common | Master Data | Partner | Credit Customer |  | [March][Credit UI Phase 2 Enhancements] | 2021-01-21 12:16 | 2021-02-13 21:00 | 2021-02-10 11:50 | 2022-03-11 10:11 | 2022-03-11 10:14 |  | 2022-03-22 10:14 | 2022-03-22 21:20 | 2022-03-17 09:45 | 2022-04-21 12:00 | CR0012925 | Biz CommonMaster DataPartnerCredit Customer | OPUS-MDA | 2022-W12 | 2022-03 | 163 | 152 | 424.915 | 5 | 2 | 2 | 0.01 | 183344 | 1.8 | 2 | 2 | 0 | 2 |  | 4 | 7 | 38 | 2.1111 | 2.4286 | 2021-01 | 2 | 1
2172 | CR0012925 | CTASK0025439 | Closed | OPUS-INV | Hang To | 67 | 62 | 2021-02-28 13:10 | 2021-02-01 13:10 | Container | Biz Common | Master Data | Partner | Credit Customer |  | Credit UI Phase 2 Enhancements | 2021-01-21 12:16 | 2021-02-13 21:00 | 2021-02-10 11:50 | 2022-03-11 10:11 | 2022-03-11 10:14 |  | 2022-03-22 10:14 | 2022-03-22 21:20 | 2022-03-17 09:45 | 2022-04-21 12:00 | CR0012925 | Biz CommonMaster DataPartnerCredit Customer | OPUS-MDA | 2022-W12 | 2022-03 | 163 | 152 | 424.915 | 5 | 2 | 2 | 0.01 | 183344 | 1.8 | 2 | 2 | 0 | 2 |  | 4 | 7 | 38 | 2.1111 | 2.4286 | 2021-01 | 2 | 1
2173 | CR0012925 | CTASK0026517 | Closed | OPUS-SCO | Hang To | 23 | 20 | 2021-04-30 10:50 | 2021-04-15 10:50 | Container | Biz Common | Master Data | Partner | Credit Customer |  | [APR] Credit UI Phase 2 Enhancements | 2021-01-21 12:16 | 2021-02-13 21:00 | 2021-02-10 11:50 | 2022-03-11 10:11 | 2022-03-11 10:14 |  | 2022-03-22 10:14 | 2022-03-22 21:20 | 2022-03-17 09:45 | 2022-04-21 12:00 | CR0012925 | Biz CommonMaster DataPartnerCredit Customer | OPUS-MDA | 2022-W12 | 2022-03 | 163 | 152 | 424.915 | 5 | 2 | 2 | 0.01 | 183344 | 1.8 | 2 | 2 | 0 | 2 |  | 4 | 7 | 38 | 2.1111 | 2.4286 | 2021-01 | 2 | 1
2174 | CR0012925 | CTASK0027801 | Closed | OPUS-INV | Nguyen Ha Vi | 21 | 20 | 2021-07-31 11:56 | 2021-07-01 11:56 | Container | Biz Common | Master Data | Partner | Credit Customer |  | Credit UI Phase 2 Enhancements | 2021-01-21 12:16 | 2021-02-13 21:00 | 2021-02-10 11:50 | 2022-03-11 10:11 | 2022-03-11 10:14 |  | 2022-03-22 10:14 | 2022-03-22 21:20 | 2022-03-17 09:45 | 2022-04-21 12:00 | CR0012925 | Biz CommonMaster DataPartnerCredit Customer | OPUS-MDA | 2022-W12 | 2022-03 | 163 | 152 | 424.915 | 5 | 2 | 2 | 0.01 | 203664 | 0.6 | 2 | 2 | 0 | 2 |  | 4 | 7 | 38 | 1.8182 | 1.2857 | 2021-01 | 2 | 1
2175 | CR0012925 | CTASK0032832 | Closed | OPUS-INV | Nguyen Ha Vi | 22 | 20 | 2022-03-31 11:51 | 2022-03-11 11:51 | Container | Biz Common | Master Data | Partner | Credit Customer |  | [Mar 2022] Credit UI Phase 2 Enhancements | 2021-01-21 12:16 | 2021-02-13 21:00 | 2021-02-10 11:50 | 2022-03-11 10:11 | 2022-03-11 10:14 |  | 2022-03-22 10:14 | 2022-03-22 21:20 | 2022-03-17 09:45 | 2022-04-21 12:00 | CR0012925 | Biz CommonMaster DataPartnerCredit Customer | OPUS-MDA | 2022-W12 | 2022-03 | 163 | 152 | 424.915 | 5 | 2 | 2 | 0.01 | 203664 | 0.6 | 2 | 2 | 0 | 2 |  | 4 | 7 | 38 | 1.8182 | 1.2857 | 2021-01 | 2 | 1
2176 | CR0014498 | CTASK0029725 | Closed | OPUS-SCO | Mohamed Hary | 13 | 13 | 2021-10-30 16:25 | 2021-10-01 16:25 | Container | Statement Management | Statement Account Receivable | Monitoring EUA | Monitor Batch Job |  | [Oct 2021][Internal] To remove hard-coding in Monitor Batch Job and manage by Lookups | 2021-09-28 11:57 | 2021-10-22 11:57 | 2021-10-19 08:34 | 2021-11-09 14:16 | 2021-11-10 14:52 |  | 2021-11-16 10:00 | 2021-11-16 09:00 | 2021-11-11 09:47 | 2021-11-23 12:01 | CR0014498 | Statement ManagementStatement Account ReceivableMonitoring EUAMonitor Batch Job | OPUS-SAR | 2021-W46 | 2021-11 | 40 | 37 | 48.9187 | 2 | 1 | 2 | 0.03 | 193489 | 2.3 | 2 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0.72727 | 0 | 2021-09 | 0 | 0
2177 | CR0014498 | CTASK0029724 | Closed | OPUS-SCO | Chuong Ta | 27 | 24 | 2021-10-30 16:24 | 2021-10-01 16:24 | Container | Statement Management | Statement Account Receivable | Monitoring EUA | Monitor Batch Job |  | [Oct 2021][Internal] To remove hard-coding in Monitor Batch Job and manage by Lookups | 2021-09-28 11:57 | 2021-10-22 11:57 | 2021-10-19 08:34 | 2021-11-09 14:16 | 2021-11-10 14:52 |  | 2021-11-16 10:00 | 2021-11-16 09:00 | 2021-11-11 09:47 | 2021-11-23 12:01 | CR0014498 | Statement ManagementStatement Account ReceivableMonitoring EUAMonitor Batch Job | OPUS-SAR | 2021-W46 | 2021-11 | 40 | 37 | 48.9187 | 2 | 1 | 2 | 0.03 | 183379 | 2.6 | 2 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0.32 | 0.375 | 2021-09 | 0 | 0
2178 | CR0013658 | CTASK0029763 | Closed | OPUS-BKG-M | Quy Truong | 72 | 61 | 2021-10-31 10:27 | 2021-10-01 09:27 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 203791 | 0.8 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0 | 0 | 2021-08 | 0 | 0
2179 | CR0013658 | CTASK0028894 | Closed | OPUS-BKG-M | Kieu Le | 10 | 10 | 2022-03-18 19:00 | 2022-03-14 19:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 153106 | 2.9 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.22951 | 0.13043 | 2021-08 | 0 | 0
2180 | CR0013658 | CTASK0028892 | Closed | OPUS-BKG-M | Tuan Pham Huu | 14 | 24 | 2022-05-02 | 2022-04-01 06:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Document (Operation Technical Guide)] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193523 | 2.2 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.5 | 0 | 2021-08 | 0 | 0
2181 | CR0013658 | CTASK0028891 | Closed | OPUS-BKG-M | Quy Truong | 24 | 24 | 2021-11-19 15:24 | 2021-11-15 15:24 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Document (Operation Technical Guide)] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 203791 | 0.8 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0 | 0 | 2021-08 | 0 | 0
2182 | CR0013658 | CTASK0026737 | Closed | OPUS-BKG-M | Kieu Le | 14 | 23 | 2021-08-31 20:41 | 2021-08-23 00:41 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 153106 | 2.9 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.22951 | 0.13043 | 2021-08 | 0 | 0
2183 | CR0013658 | CTASK0028079 | Closed | OPUS-BKG-M | Loc Tran | 15 | 15 | 2021-07-31 11:28 | 2021-07-01 11:28 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design]EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193503 | 2.1 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.33333 | 0 | 2021-08 | 0 | 0
2184 | CR0013658 | CTASK0026734 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 92 | 92 | 2021-10-27 09:24 | 2021-09-27 09:24 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193488 | 2.2 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.53659 | 0 | 2021-08 | 0 | 0
2185 | CR0013658 | CTASK0028890 | Closed | OPUS-BKG-M | Trang Le Minh | 24 | 24 | 2022-03-11 21:32 | 2022-03-07 06:32 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Document (Operation Technical Guide)] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193594 | 2 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0 | 0 | 2021-08 | 0 | 0
2186 | CR0013658 | CTASK0026736 | Closed | OPUS-BKG-M | Tuan Pham Huu | 12 | 33 | 2022-03-22 | 2022-03-10 06:00 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193523 | 2.2 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.5 | 0 | 2021-08 | 0 | 0
2187 | CR0013658 | CTASK0028999 | Closed | OPUS-BKG-M | Trang Le Minh | 85 | 85 | 2021-09-30 20:54 | 2021-09-01 15:54 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193594 | 2 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0 | 0 | 2021-08 | 0 | 0
2188 | CR0013658 | CTASK0028888 | Closed | OPUS-BKG-M | Loc Tran | 25 | 25 | 2021-11-19 15:24 | 2021-11-15 15:24 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Test] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193503 | 2.1 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.33333 | 0 | 2021-08 | 0 | 0
2189 | CR0013658 | CTASK0028887 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 2 | 2 | 2021-11-19 19:31 | 2021-11-15 19:30 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Test] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193488 | 2.2 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.53659 | 0 | 2021-08 | 0 | 0
2190 | CR0013658 | CTASK0028886 | Closed | OPUS-BKG-M | Trang Le Minh | 15 | 15 | 2021-11-19 15:43 | 2021-11-15 15:43 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Test] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193594 | 2 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0 | 0 | 2021-08 | 0 | 0
2191 | CR0013658 | CTASK0028893 | Closed | OPUS-BKG-M | Trang Le Minh | 11 | 10 | 2022-03-16 21:31 | 2022-03-14 06:31 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193594 | 2 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0 | 0 | 2021-08 | 0 | 0
2192 | CR0013658 | CTASK0028885 | Closed | OPUS-BKG-M | Loc Tran | 63 | 63 | 2021-09-30 14:33 | 2021-09-13 14:33 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193503 | 2.1 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.33333 | 0 | 2021-08 | 0 | 0
2193 | CR0013658 | CTASK0029328 | Closed | OPUS-BKG-M | Loc Tran | 15 | 15 | 2021-09-30 10:46 | 2021-09-01 10:45 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design- DB change] EUA - CR - Multiple M'ty P/up depot functionality logic in Bkg M/H | 2021-08-23 08:34 | 2021-11-24 22:00 | 2021-11-24 12:53 | 2022-03-03 07:51 | 2022-03-03 08:06 |  | 2022-03-22 08:00 | 2022-03-22 08:00 | 2022-03-10 08:15 | 2022-03-29 12:00 | CR0013658 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W12 | 2022-03 | 444 | 521 | 210.9763 | 16 | 1 | 6 | 0.1 | 193503 | 2.1 | 2 | 0 | 0 | 4 |  | 3 | 7 | 38 | 0.33333 | 0 | 2021-08 | 0 | 0
2194 | CR0014857 | CTASK0031500 | Closed | OPUS-SCO | Mohamed Hary | 30 | 30 | 2022-01-31 17:19 | 2022-01-01 17:18 | Container | Statement Management | Statement Account Receivable |  |  |  | [Jan 2022] OPUS exports .XLS and .DOC with .XLSX and .DOCX | 2021-12-28 09:09 | 2022-02-18 09:09 | 2022-02-09 07:38 | 2022-03-31 07:42 | 2022-04-01 09:00 |  | 2022-04-05 10:00 | 2022-04-05 09:00 | 2022-04-01 09:24 | 2022-04-07 12:02 | CR0014857 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W14 | 2022-04 | 111 | 105 | 98.0351 | 3 | 1 | 3 | 0.04 | 193489 | 2.6 | 1 | 0 | 0 | 2 |  | 2 | 6 | 18 | 0.72727 | 0 | 2021-12 | 0 | 0
2195 | CR0014857 | CTASK0031499 | Closed | OPUS-SCO | Lien Le | 21 | 19 | 2022-01-31 17:18 | 2022-01-01 17:18 | Container | Statement Management | Statement Account Receivable |  |  |  | [Jan 2022]OPUS exports .XLS and .DOC with .XLSX and .DOCX | 2021-12-28 09:09 | 2022-02-18 09:09 | 2022-02-09 07:38 | 2022-03-31 07:42 | 2022-04-01 09:00 |  | 2022-04-05 10:00 | 2022-04-05 09:00 | 2022-04-01 09:24 | 2022-04-07 12:02 | CR0014857 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W14 | 2022-04 | 111 | 105 | 98.0351 | 3 | 1 | 3 | 0.04 | 193441 | 2.8 | 1 | 0 | 0 | 2 |  | 2 | 6 | 18 | 0.42308 | 0 | 2021-12 | 0 | 0
2196 | CR0014857 | CTASK0031501 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 60 | 56 | 2022-01-31 17:19 | 2022-01-01 17:19 | Container | Statement Management | Statement Account Receivable |  |  |  | [Jan 2022] OPUS exports .XLS and .DOC with .XLSX and .DOCX | 2021-12-28 09:09 | 2022-02-18 09:09 | 2022-02-09 07:38 | 2022-03-31 07:42 | 2022-04-01 09:00 |  | 2022-04-05 10:00 | 2022-04-05 09:00 | 2022-04-01 09:24 | 2022-04-07 12:02 | CR0014857 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W14 | 2022-04 | 111 | 105 | 98.0351 | 3 | 1 | 3 | 0.04 | 203704 | 1.3 | 1 | 0 | 0 | 2 |  | 2 | 6 | 18 | 0 | 0 | 2021-12 | 0 | 0
2197 | CR0014653 | CTASK0030553 | Closed | OPUS-DMT | Cuong Nguyen | 45 | 70 | 2022-01-14 11:46 | 2021-12-27 11:46 | Container | Service Management | Demurrage/Detention | Charge Generation |  |  | [TASK- Development] | 2022-01-06 10:10 | 2022-01-21 10:10 | 2022-01-19 11:31 | 2022-02-15 11:39 | 2022-02-15 11:48 |  | 2022-02-22 08:10 | 2022-02-22 08:21 | 2022-02-24 07:48 | 2022-03-03 12:00 | CR0014653 | Service ManagementDemurrage/DetentionCharge Generation | OPUS-DMT | 2022-W8 | 2022-02 | 45 | 70 | 46.9167 | 1 | 1 | 1 | 0.06 | 193529 | 2.6 | 2 | 0 | 0 | 1 |  | 1 | 14 | 30 | 0.11538 | 0.22222 | 2022-01 | 0 | 0
2198 | CR0015107 | CTASK0032477 | Closed | OPUS-SCG | Tu Nguyen | 24 | 34 | 2022-02-25 11:58 | 2022-02-23 11:58 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] DG EDI Dummy CNTR ref. no. change for ONE-MSK | 2022-02-22 14:30 | 2022-03-11 14:29 | 2022-02-24 14:27 | 2022-02-28 15:49 | 2022-03-02 11:33 |  | 2022-03-02 09:00 | 2022-03-02 13:52 | 2022-03-02 13:45 | 2022-03-10 12:00 | CR0015107 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W9 | 2022-03 | 40 | 50 | 7.7711 | 2 | 1 | 2 | 0.27 | 123045 | 3.4 | 2 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0 | 0 | 2022-02 | 0 | 0
2199 | CR0015107 | CTASK0032476 | Closed | OPUS-SCG | Trang Duy Thong | 16 | 16 | 2022-02-25 11:57 | 2022-02-23 11:57 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Documentation] DG EDI Dummy CNTR ref. no. change for ONE-MSK | 2022-02-22 14:30 | 2022-03-11 14:29 | 2022-02-24 14:27 | 2022-02-28 15:49 | 2022-03-02 11:33 |  | 2022-03-02 09:00 | 2022-03-02 13:52 | 2022-03-02 13:45 | 2022-03-10 12:00 | CR0015107 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W9 | 2022-03 | 40 | 50 | 7.7711 | 2 | 1 | 2 | 0.27 | 193511 | 1.7 | 2 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.81818 | 2.6667 | 2022-02 | 0 | 0
2200 | CR0013442 | CTASK0027013 | Closed | OPUS-BKG-RPT | Nam Nguyen | 102 | 99 | 2021-07-16 09:38 | 2021-06-28 09:37 | Container | Service Management | Booking/Documentation | Report | Booking Container Report |  | [Development] NA *BKG* MT container volume added to BKG Container Report for VCO/SPC | 2021-05-18 06:02 | 2021-07-23 21:02 | 2021-07-23 14:15 | 2021-12-23 08:36 | 2021-12-27 06:03 |  | 2022-01-04 08:02 | 2022-01-11 08:16 | 2022-01-03 09:20 | 2022-01-18 12:01 | CR0013442 | Service ManagementBooking/DocumentationReportBooking Container Report | OPUS-BKG-RPT | 2022-W1 | 2022-01 | 134 | 148 | 231.0838 | 3 | 1 | 1 | 0.03 | 123048 | 2.6 | 1 | 0 | 0 | 2 |  | 3 | 3 | 33 | 0.22222 | 0.047619 | 2021-05 | 0 | 0
2201 | CR0013442 | CTASK0026937 | Closed | OPUS-BKG-RPT | Nam Nguyen | 8 | 8 | 2021-05-14 15:21 | 2021-05-10 15:21 | Container | Service Management | Booking/Documentation | Report | Booking Container Report |  | [Design]NA *BKG* MT container volume added to BKG Container Report for VCO/SPC | 2021-05-18 06:02 | 2021-07-23 21:02 | 2021-07-23 14:15 | 2021-12-23 08:36 | 2021-12-27 06:03 |  | 2022-01-04 08:02 | 2022-01-11 08:16 | 2022-01-03 09:20 | 2022-01-18 12:01 | CR0013442 | Service ManagementBooking/DocumentationReportBooking Container Report | OPUS-BKG-RPT | 2022-W1 | 2022-01 | 134 | 148 | 231.0838 | 3 | 1 | 1 | 0.03 | 123048 | 2.6 | 1 | 0 | 0 | 2 |  | 3 | 3 | 33 | 0.22222 | 0.047619 | 2021-05 | 0 | 0
2202 | CR0013442 | CTASK0027014 | Closed | OPUS-BKG-RPT | Nam Nguyen | 24 | 41 | 2021-11-05 21:18 | 2021-09-26 21:18 | Container | Service Management | Booking/Documentation | Report | Booking Container Report |  | [Testing & Deployment] NA *BKG* MT container volume added to BKG Container Report for VCO/SPC | 2021-05-18 06:02 | 2021-07-23 21:02 | 2021-07-23 14:15 | 2021-12-23 08:36 | 2021-12-27 06:03 |  | 2022-01-04 08:02 | 2022-01-11 08:16 | 2022-01-03 09:20 | 2022-01-18 12:01 | CR0013442 | Service ManagementBooking/DocumentationReportBooking Container Report | OPUS-BKG-RPT | 2022-W1 | 2022-01 | 134 | 148 | 231.0838 | 3 | 1 | 1 | 0.03 | 123048 | 2.6 | 1 | 0 | 0 | 2 |  | 3 | 3 | 33 | 0.22222 | 0.047619 | 2021-05 | 0 | 0
2203 | CR0014756 | CTASK0030970 | Closed | OPUS-BKG-IB | Linh Dinh Bo | 42 | 38 | 2021-12-31 14:52 | 2021-12-01 14:52 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development+ Testing+ Deployment] EUR - Secure Release @ BEANR - Add SRI to UI | 2021-12-10 11:29 | 2022-01-24 21:28 | 2022-01-20 11:51 | 2022-01-26 07:06 | 2022-02-08 14:56 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-09 07:24 | 2022-03-01 12:00 | CR0014756 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2022-W8 | 2022-02 | 64 | 62 | 73.8552 | 3 | 1 | 1 | 0.03 | 193522 | 2.5 | 1 | 1 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 1 | 1
2204 | CR0014756 | CTASK0030969 | Closed | OPUS-BKG-IB | Linh Dinh Bo | 14 | 14 | 2021-12-31 14:51 | 2021-12-01 14:51 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Estimation] EUR - Secure Release @ BEANR - Add SRI to UI | 2021-12-10 11:29 | 2022-01-24 21:28 | 2022-01-20 11:51 | 2022-01-26 07:06 | 2022-02-08 14:56 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-09 07:24 | 2022-03-01 12:00 | CR0014756 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2022-W8 | 2022-02 | 64 | 62 | 73.8552 | 3 | 1 | 1 | 0.03 | 193522 | 2.5 | 1 | 1 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 1 | 1
2205 | CR0014756 | CTASK0032232 | Closed | OPUS-BKG-IB | Linh Dinh Bo | 8 | 10 | 2022-02-22 13:48 | 2022-02-09 13:48 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Deployment+Testing] EUR - Secure Release @ BEANR - Add SRI to UI | 2021-12-10 11:29 | 2022-01-24 21:28 | 2022-01-20 11:51 | 2022-01-26 07:06 | 2022-02-08 14:56 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-09 07:24 | 2022-03-01 12:00 | CR0014756 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2022-W8 | 2022-02 | 64 | 62 | 73.8552 | 3 | 1 | 1 | 0.03 | 193522 | 2.5 | 1 | 1 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 1 | 1
2206 | CR0011865 | CTASK0022419 | Closed | OPUS-FLT | Tu Nguyen | 41 | 40 | 2020-09-25 16:00 | 2020-09-01 07:00 | Container | Support & Admin | Fleet Management | Invoice | Time Charter Invoice | Time Charter Invoice | [FLT-CLV] Owners Disbursement Recovery_Issue List Affecting Fleet Module (Total 8 issues) | 2019-11-26 16:55 | 2020-01-09 22:00 | 2020-01-09 07:38 | 2021-09-27 10:22 | 2021-10-19 10:46 |  | 2021-11-16 07:00 | 2021-11-16 07:00 | 2021-10-25 15:22 | 2021-11-24 12:00 | CR0011865 | Support & AdminFleet ManagementInvoiceTime Charter InvoiceTime Charter Invoice | OPUS-FLT | 2021-W46 | 2021-11 | 49 | 48 | 720.5867 | 2 | 1 | 1 | 0 | 123045 | 1.2 | 1 | 0 | 0 | 1 |  | 5 | 16 | 38 | 0 | 0 | 2019-11 | 0 | 0
2207 | CR0011865 | CTASK0022202 | Closed | OPUS-FLT | Tu Nguyen | 8 | 8 | 2020-08-31 08:56 | 2020-08-25 08:55 | Container | Support & Admin | Fleet Management | Invoice | Time Charter Invoice | Time Charter Invoice | Design | 2019-11-26 16:55 | 2020-01-09 22:00 | 2020-01-09 07:38 | 2021-09-27 10:22 | 2021-10-19 10:46 |  | 2021-11-16 07:00 | 2021-11-16 07:00 | 2021-10-25 15:22 | 2021-11-24 12:00 | CR0011865 | Support & AdminFleet ManagementInvoiceTime Charter InvoiceTime Charter Invoice | OPUS-FLT | 2021-W46 | 2021-11 | 49 | 48 | 720.5867 | 2 | 1 | 1 | 0 | 123045 | 1.2 | 1 | 0 | 0 | 1 |  | 5 | 16 | 38 | 0 | 0 | 2019-11 | 0 | 0
2208 | CR0014877 | CTASK0031167 | Closed | OPUS-BKG-M | Quy Truong | 21 | 20 | 2022-01-12 09:23 | 2022-01-04 09:23 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Development][CLT Internal] Manual Time of Doc cut off is updated even when there is no change on UI in Booking Receipt Notice (Fax/Email) | 2022-01-04 12:42 | 2022-01-28 | 2022-01-26 11:18 | 2022-01-26 14:03 | 2022-01-27 08:13 |  | 2022-02-15 08:00 | 2022-02-15 08:00 | 2022-01-29 07:20 | 2022-02-22 12:00 | CR0014877 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W7 | 2022-02 | 54 | 54 | 41.804 | 4 | 1 | 1 | 0.05 | 203791 | 1.2 | 1 | 0 | 1 | 1 |  | 1 | 10 | 30 | 0 | 0 | 2022-01 | 1 | 1
2209 | CR0014877 | CTASK0031071 | Closed | OPUS-BKG-M | Quy Truong | 24 | 24 | 2021-12-15 16:16 | 2021-12-09 16:16 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Design][CLT Internal] Manual Time of Doc cut off is updated even when there is no change on UI in Booking Receipt Notice (Fax/Email) | 2022-01-04 12:42 | 2022-01-28 | 2022-01-26 11:18 | 2022-01-26 14:03 | 2022-01-27 08:13 |  | 2022-02-15 08:00 | 2022-02-15 08:00 | 2022-01-29 07:20 | 2022-02-22 12:00 | CR0014877 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W7 | 2022-02 | 54 | 54 | 41.804 | 4 | 1 | 1 | 0.05 | 203791 | 1.2 | 1 | 0 | 1 | 1 |  | 1 | 10 | 30 | 0 | 0 | 2022-01 | 1 | 1
2210 | CR0014877 | CTASK0031169 | Closed | OPUS-BKG-M | Quy Truong | 2 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Delopyment][CLT Internal] Manual Time of Doc cut off is updated even when there is no change on UI in Booking Receipt Notice (Fax/Email) | 2022-01-04 12:42 | 2022-01-28 | 2022-01-26 11:18 | 2022-01-26 14:03 | 2022-01-27 08:13 |  | 2022-02-15 08:00 | 2022-02-15 08:00 | 2022-01-29 07:20 | 2022-02-22 12:00 | CR0014877 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W7 | 2022-02 | 54 | 54 | 41.804 | 4 | 1 | 1 | 0.05 | 203791 | 1.2 | 1 | 0 | 1 | 1 |  | 1 | 10 | 30 | 0 | 0 | 2022-01 | 1 | 1
2211 | CR0014877 | CTASK0031168 | Closed | OPUS-BKG-M | Quy Truong | 7 | 6 |  |  | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Testing][CLT Internal] Manual Time of Doc cut off is updated even when there is no change on UI in Booking Receipt Notice (Fax/Email) | 2022-01-04 12:42 | 2022-01-28 | 2022-01-26 11:18 | 2022-01-26 14:03 | 2022-01-27 08:13 |  | 2022-02-15 08:00 | 2022-02-15 08:00 | 2022-01-29 07:20 | 2022-02-22 12:00 | CR0014877 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W7 | 2022-02 | 54 | 54 | 41.804 | 4 | 1 | 1 | 0.05 | 203791 | 1.2 | 1 | 0 | 1 | 1 |  | 1 | 10 | 30 | 0 | 0 | 2022-01 | 1 | 1
2212 | CR0014191 | CTASK0029536 | Closed | OPUS-TPB | Manh Nguyen | 6 | 6 | 2021-09-30 20:00 | 2021-09-01 06:00 | Container | Service Management | 3rd Party Billing |  |  |  | [202109] Asia *TPB* Billing Place of Supply - Change existing FTP excel to read POS as 97 instead of customer first 2 digit GST# & SEZ customer | 2021-09-24 11:58 | 2021-10-22 21:00 | 2021-10-21 15:23 | 2021-11-03 07:49 | 2021-11-03 09:38 |  | 2021-11-09 09:30 | 2021-11-09 08:00 | 2021-11-04 07:22 | 2021-11-16 12:00 | CR0014191 | Service Management3rd Party Billing | OPUS-TPB | 2021-W45 | 2021-11 | 25 | 29 | 45.8972 | 4 | 1 | 1 | 0.03 | 153138 | 3 | 1 | 1 | 0 | 1 |  | 1 | 9 | 38 | 0.16667 | 0.16667 | 2021-09 | 1 | 1
2213 | CR0014191 | CTASK0028490 | Closed | OPUS-TPB | Manh Nguyen | 5 | 5 | 2021-08-31 22:00 | 2021-08-01 | Container | Service Management | 3rd Party Billing |  |  |  | [202108] Asia *TPB* Billing Place of Supply - Change existing FTP excel to read POS as 97 instead of customer first 2 digit GST# & SEZ customer | 2021-09-24 11:58 | 2021-10-22 21:00 | 2021-10-21 15:23 | 2021-11-03 07:49 | 2021-11-03 09:38 |  | 2021-11-09 09:30 | 2021-11-09 08:00 | 2021-11-04 07:22 | 2021-11-16 12:00 | CR0014191 | Service Management3rd Party Billing | OPUS-TPB | 2021-W45 | 2021-11 | 25 | 29 | 45.8972 | 4 | 1 | 1 | 0.03 | 153138 | 3 | 1 | 1 | 0 | 1 |  | 1 | 9 | 38 | 0.16667 | 0.16667 | 2021-09 | 1 | 1
2214 | CR0014191 | CTASK0029693 | Closed | OPUS-TPB | Manh Nguyen | 10 | 10 | 2021-10-29 20:00 | 2021-10-01 04:00 | Container | Service Management | 3rd Party Billing |  |  |  | [202110] Asia *TPB* Billing Place of Supply - Change existing FTP excel to read POS as 97 instead of customer first 2 digit GST# & SEZ customer | 2021-09-24 11:58 | 2021-10-22 21:00 | 2021-10-21 15:23 | 2021-11-03 07:49 | 2021-11-03 09:38 |  | 2021-11-09 09:30 | 2021-11-09 08:00 | 2021-11-04 07:22 | 2021-11-16 12:00 | CR0014191 | Service Management3rd Party Billing | OPUS-TPB | 2021-W45 | 2021-11 | 25 | 29 | 45.8972 | 4 | 1 | 1 | 0.03 | 153138 | 3 | 1 | 1 | 0 | 1 |  | 1 | 9 | 38 | 0.16667 | 0.16667 | 2021-09 | 1 | 1
2215 | CR0014191 | CTASK0030275 | Closed | OPUS-TPB | Manh Nguyen | 10 | 8 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Service Management | 3rd Party Billing |  |  |  | [202111] Asia *TPB* Billing Place of Supply - Change existing FTP excel to read POS as 97 instead of customer first 2 digit GST# & SEZ customer | 2021-09-24 11:58 | 2021-10-22 21:00 | 2021-10-21 15:23 | 2021-11-03 07:49 | 2021-11-03 09:38 |  | 2021-11-09 09:30 | 2021-11-09 08:00 | 2021-11-04 07:22 | 2021-11-16 12:00 | CR0014191 | Service Management3rd Party Billing | OPUS-TPB | 2021-W45 | 2021-11 | 25 | 29 | 45.8972 | 4 | 1 | 1 | 0.03 | 153138 | 3 | 1 | 1 | 0 | 1 |  | 1 | 9 | 38 | 0.16667 | 0.16667 | 2021-09 | 1 | 1
2216 | CR0012781 | CTASK0025138 | Closed | OPUS-OPF | Thuan Tran | 15 | 15 |  |  | Container | Vessel Operation | Operation & PFMC | Setup | TDR/RDR |  | [CLV][CLT Internal] EUA - Update TDR Package | 2021-02-25 10:02 | 2021-03-20 09:59 | 2021-03-08 13:49 | 2021-10-05 15:34 | 2021-10-06 10:00 |  | 2021-10-19 08:00 | 2021-10-19 07:00 | 2021-10-12 14:54 | 2021-10-27 12:00 | CR0012781 | Vessel OperationOperation & PFMCSetupTDR/RDR | OPUS-OPF | 2021-W42 | 2021-10 | 15 | 15 | 235.9156 | 2 | 1 | 2 | 0 | 183423 | 2.3 | 2 | 0 | 0 | 1 |  | 3 | 6 | 26 | 0 | 0 | 2021-02 | 0 | 0
2217 | CR0012781 | CTASK0025136 | Closed | OPUS-OPF | Huy Vu | 1 | 1 |  |  | Container | Vessel Operation | Operation & PFMC | Setup | TDR/RDR |  | [Document] [CLT Internal] EUA - Update TDR Package | 2021-02-25 10:02 | 2021-03-20 09:59 | 2021-03-08 13:49 | 2021-10-05 15:34 | 2021-10-06 10:00 |  | 2021-10-19 08:00 | 2021-10-19 07:00 | 2021-10-12 14:54 | 2021-10-27 12:00 | CR0012781 | Vessel OperationOperation & PFMCSetupTDR/RDR | OPUS-OPF | 2021-W42 | 2021-10 | 15 | 15 | 235.9156 | 2 | 1 | 2 | 0 | 193618 | 1 | 2 | 0 | 0 | 1 |  | 3 | 6 | 26 | 0 | 0 | 2021-02 | 0 | 0
2218 | CR0014678 | CTASK0030654 | Closed | OPUS-SCO | Nguyen Ha Vi | 31 | 30 | 2021-11-30 14:12 | 2021-11-15 14:11 | Container | [5 empty] | [Nov 2021]To add ePayment format into PRL attachment | 2021-11-15 09:47 | 2021-12-27 19:00 | 2021-12-27 07:59 | 2022-01-13 07:48 | 2022-01-13 14:46 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-13 15:16 | 2022-01-25 10:41 | CR0014678 |  | OPUS-SCO | 2022-W4 | 2022-01 | 145 | 144 | 71.0089 | 6 | 1 | 6 | 0.08 | 203664 | 1.5 | 3 | 0 | 0 | 2 |  | 2 | 9 | 33 | 1.8182 | 2.5 | 2021-11 | 0 | 0
2219 | CR0014678 | CTASK0030653 | Closed | OPUS-SCO | Lien Le | 22 | 20 | 2021-11-30 14:11 | 2021-11-15 14:11 | Container | [5 empty] | [Nov 2021]To add ePayment format into PRL attachment | 2021-11-15 09:47 | 2021-12-27 19:00 | 2021-12-27 07:59 | 2022-01-13 07:48 | 2022-01-13 14:46 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-13 15:16 | 2022-01-25 10:41 | CR0014678 |  | OPUS-SCO | 2022-W4 | 2022-01 | 145 | 144 | 71.0089 | 6 | 1 | 6 | 0.08 | 193441 | 2.7 | 3 | 0 | 0 | 2 |  | 2 | 9 | 33 | 0.42308 | 0 | 2021-11 | 0 | 0
2220 | CR0014678 | CTASK0030656 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 17 | 24 | 2021-11-30 14:17 | 2021-11-15 14:17 | Container | [5 empty] | [Nov 2021] To add ePayment format into PRL attachment | 2021-11-15 09:47 | 2021-12-27 19:00 | 2021-12-27 07:59 | 2022-01-13 07:48 | 2022-01-13 14:46 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-13 15:16 | 2022-01-25 10:41 | CR0014678 |  | OPUS-SCO | 2022-W4 | 2022-01 | 145 | 144 | 71.0089 | 6 | 1 | 6 | 0.08 | 203704 | 1.2 | 3 | 0 | 0 | 2 |  | 2 | 9 | 33 | 0 | 0 | 2021-11 | 0 | 0
2221 | CR0014678 | CTASK0030652 | Closed | OPUS-SCO | Cuong Tran Hung | 22 | 20 | 2021-11-30 14:10 | 2021-11-15 14:10 | Container | [5 empty] | [Nov 2021]To add ePayment format into PRL attachement | 2021-11-15 09:47 | 2021-12-27 19:00 | 2021-12-27 07:59 | 2022-01-13 07:48 | 2022-01-13 14:46 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-13 15:16 | 2022-01-25 10:41 | CR0014678 |  | OPUS-SCO | 2022-W4 | 2022-01 | 145 | 144 | 71.0089 | 6 | 1 | 6 | 0.08 | 193530 | 2.5 | 3 | 0 | 0 | 2 |  | 2 | 9 | 33 | 1.2308 | 1.25 | 2021-11 | 0 | 0
2222 | CR0014678 | CTASK0030655 | Closed | OPUS-SCO | Mohamed Hary | 25 | 25 | 2021-11-30 14:12 | 2021-11-15 14:12 | Container | [5 empty] | [Nov 2021] To add ePayment format into PRL attachment | 2021-11-15 09:47 | 2021-12-27 19:00 | 2021-12-27 07:59 | 2022-01-13 07:48 | 2022-01-13 14:46 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-13 15:16 | 2022-01-25 10:41 | CR0014678 |  | OPUS-SCO | 2022-W4 | 2022-01 | 145 | 144 | 71.0089 | 6 | 1 | 6 | 0.08 | 193489 | 2.5 | 3 | 0 | 0 | 2 |  | 2 | 9 | 33 | 0.72727 | 0 | 2021-11 | 0 | 0
2223 | CR0014678 | CTASK0030651 | Closed | OPUS-SCO | Chuong Ta | 28 | 25 | 2021-11-30 14:09 | 2021-11-15 14:08 | Container | [5 empty] | [Nov 2021] To add ePayment format into PRL attachment | 2021-11-15 09:47 | 2021-12-27 19:00 | 2021-12-27 07:59 | 2022-01-13 07:48 | 2022-01-13 14:46 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-13 15:16 | 2022-01-25 10:41 | CR0014678 |  | OPUS-SCO | 2022-W4 | 2022-01 | 145 | 144 | 71.0089 | 6 | 1 | 6 | 0.08 | 183379 | 2.7 | 3 | 0 | 0 | 2 |  | 2 | 9 | 33 | 0.32 | 0.375 | 2021-11 | 0 | 0
2224 | CR0013928 | CTASK0030768 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 8 | 12 | 2021-11-30 09:02 | 2021-11-23 09:02 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Fax & E-Mail | [Deployment] EUA - Change of Logic of A/N Email selection | 2021-09-17 09:10 | 2021-10-15 21:07 | 2021-10-15 12:27 | 2021-11-23 17:29 | 2021-11-24 09:38 |  | 2021-11-30 09:35 | 2021-11-30 12:01 | 2021-11-25 12:28 | 2021-12-08 12:00 | CR0013928 | Service ManagementBooking/DocumentationInbound DocArrival NoticeFax & E-Mail | OPUS-BKG-IB | 2021-W48 | 2021-11 | 53 | 65 | 74.0175 | 2 | 1 | 1 | 0.04 | 193512 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.2963 | 0 | 2021-09 | 0 | 0
2225 | CR0013928 | CTASK0029473 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 45 | 53 | 2021-10-12 10:37 | 2021-09-17 07:37 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Fax & E-Mail | [Development+ Testing+ Deployment] EUA - Change of Logic of A/N Email selection | 2021-09-17 09:10 | 2021-10-15 21:07 | 2021-10-15 12:27 | 2021-11-23 17:29 | 2021-11-24 09:38 |  | 2021-11-30 09:35 | 2021-11-30 12:01 | 2021-11-25 12:28 | 2021-12-08 12:00 | CR0013928 | Service ManagementBooking/DocumentationInbound DocArrival NoticeFax & E-Mail | OPUS-BKG-IB | 2021-W48 | 2021-11 | 53 | 65 | 74.0175 | 2 | 1 | 1 | 0.04 | 193512 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.2963 | 0 | 2021-09 | 0 | 0
2226 | CR0014551 | CTASK0030408 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 | 2022-03-14 21:00 | 2022-03-08 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print |  | [Deployment] GHQ *EDI* - Flat File B/L Draft enhancement to support eBL | 2021-11-16 11:54 | 2022-01-14 11:54 | 2022-01-06 07:48 | 2022-03-04 07:56 | 2022-03-04 08:02 |  | 2022-03-15 08:02 | 2022-03-15 08:16 | 2022-03-04 08:47 | 2022-03-22 12:00 | CR0014551 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & Print | OPUS-BKG-OB | 2022-W11 | 2022-03 | 77 | 76 | 118.839 | 3 | 1 | 2 | 0.03 | 193470 | 2.7 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0.36842 | 0.11111 | 2021-11 | 0 | 0
2227 | CR0014551 | CTASK0030407 | Closed | OPUS-BKG-OB | Nam Nguyen | 59 | 56 | 2021-12-09 17:30 | 2021-11-29 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print |  | [Dev + Test] GHQ *EDI* - Flat File B/L Draft enhancement to support eBL | 2021-11-16 11:54 | 2022-01-14 11:54 | 2022-01-06 07:48 | 2022-03-04 07:56 | 2022-03-04 08:02 |  | 2022-03-15 08:02 | 2022-03-15 08:16 | 2022-03-04 08:47 | 2022-03-22 12:00 | CR0014551 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & Print | OPUS-BKG-OB | 2022-W11 | 2022-03 | 77 | 76 | 118.839 | 3 | 1 | 2 | 0.03 | 123048 | 3.1 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0.22222 | 0 | 2021-11 | 0 | 0
2228 | CR0014551 | CTASK0030348 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 10 | 12 | 2021-11-05 17:30 | 2021-11-03 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print |  | [Design] GHQ *EDI* - Flat File B/L Draft enhancement to support eBL | 2021-11-16 11:54 | 2022-01-14 11:54 | 2022-01-06 07:48 | 2022-03-04 07:56 | 2022-03-04 08:02 |  | 2022-03-15 08:02 | 2022-03-15 08:16 | 2022-03-04 08:47 | 2022-03-22 12:00 | CR0014551 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & Print | OPUS-BKG-OB | 2022-W11 | 2022-03 | 77 | 76 | 118.839 | 3 | 1 | 2 | 0.03 | 193470 | 2.7 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0.36842 | 0.11111 | 2021-11 | 0 | 0
2229 | CR0013980 | CTASK0028012 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-08-31 09:49 | 2021-08-02 09:49 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Testing] EUA - Discrepancies between Awkward and Special Stowage Cargo Manifest | 2021-07-20 11:44 | 2021-08-11 22:00 | 2021-08-03 11:22 | 2021-10-12 09:05 | 2021-10-12 12:28 |  | 2021-10-26 08:00 | 2021-10-26 08:00 | 2021-10-12 14:45 | 2021-11-02 12:00 | CR0013980 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2021-W43 | 2021-10 | 60 | 60 | 97.8443 | 4 | 1 | 1 | 0.03 | 193567 | 2 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.5625 | 0.53333 | 2021-07 | 0 | 0
2230 | CR0013980 | CTASK0028011 | Closed | OPUS-BKG-M | Thien Lai | 24 | 24 | 2021-08-31 09:49 | 2021-08-02 09:49 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Development] EUA - Discrepancies between Awkward and Special Stowage Cargo Manifest | 2021-07-20 11:44 | 2021-08-11 22:00 | 2021-08-03 11:22 | 2021-10-12 09:05 | 2021-10-12 12:28 |  | 2021-10-26 08:00 | 2021-10-26 08:00 | 2021-10-12 14:45 | 2021-11-02 12:00 | CR0013980 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2021-W43 | 2021-10 | 60 | 60 | 97.8443 | 4 | 1 | 1 | 0.03 | 193567 | 2 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.5625 | 0.53333 | 2021-07 | 0 | 0
2231 | CR0013980 | CTASK0028014 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2021-10-29 13:42 | 2021-10-18 13:42 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Deployment] EUA - Discrepancies between Awkward and Special Stowage Cargo Manifest | 2021-07-20 11:44 | 2021-08-11 22:00 | 2021-08-03 11:22 | 2021-10-12 09:05 | 2021-10-12 12:28 |  | 2021-10-26 08:00 | 2021-10-26 08:00 | 2021-10-12 14:45 | 2021-11-02 12:00 | CR0013980 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2021-W43 | 2021-10 | 60 | 60 | 97.8443 | 4 | 1 | 1 | 0.03 | 193567 | 2 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.5625 | 0.53333 | 2021-07 | 0 | 0
2232 | CR0013980 | CTASK0027753 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-07-02 17:05 | 2021-06-21 17:05 | Container | Service Management | Booking/Documentation | Operation | Special Container List | Special Cargo Manifest | [Design] EUA - Discrepancies between Awkward and Special Stowage Cargo Manifest | 2021-07-20 11:44 | 2021-08-11 22:00 | 2021-08-03 11:22 | 2021-10-12 09:05 | 2021-10-12 12:28 |  | 2021-10-26 08:00 | 2021-10-26 08:00 | 2021-10-12 14:45 | 2021-11-02 12:00 | CR0013980 | Service ManagementBooking/DocumentationOperationSpecial Container ListSpecial Cargo Manifest | OPUS-BKG-M | 2021-W43 | 2021-10 | 60 | 60 | 97.8443 | 4 | 1 | 1 | 0.03 | 193567 | 2 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.5625 | 0.53333 | 2021-07 | 0 | 0
2233 | CR0014540 | CTASK0029653 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 | 2021-10-29 15:56 | 2021-10-18 00:55 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Split | [Testing] [CLT Internal] Memo split is not working when booking has 10 digit B/L number | 2021-10-05 17:05 | 2021-10-28 | 2021-10-19 06:50 | 2021-11-09 08:44 | 2021-11-09 11:12 |  | 2021-11-30 08:00 | 2021-11-30 08:00 | 2021-11-11 08:21 | 2021-12-08 12:00 | CR0014540 | Service ManagementBooking/DocumentationBookingBookingBooking Split | OPUS-BKG-M | 2021-W48 | 2021-11 | 28 | 28 | 55.6213 | 4 | 1 | 1 | 0.02 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.22951 | 0 | 2021-10 | 0 | 0
2234 | CR0014540 | CTASK0029652 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-10-08 15:55 | 2021-10-04 00:55 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Split | [Development] [CLT Internal] Memo split is not working when booking has 10 digit B/L number | 2021-10-05 17:05 | 2021-10-28 | 2021-10-19 06:50 | 2021-11-09 08:44 | 2021-11-09 11:12 |  | 2021-11-30 08:00 | 2021-11-30 08:00 | 2021-11-11 08:21 | 2021-12-08 12:00 | CR0014540 | Service ManagementBooking/DocumentationBookingBookingBooking Split | OPUS-BKG-M | 2021-W48 | 2021-11 | 28 | 28 | 55.6213 | 4 | 1 | 1 | 0.02 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.22951 | 0 | 2021-10 | 0 | 0
2235 | CR0014540 | CTASK0029650 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-10-08 20:54 | 2021-10-01 15:54 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Split | [Design] [CLT Internal] Memo split is not working when booking has 10 digit B/L number | 2021-10-05 17:05 | 2021-10-28 | 2021-10-19 06:50 | 2021-11-09 08:44 | 2021-11-09 11:12 |  | 2021-11-30 08:00 | 2021-11-30 08:00 | 2021-11-11 08:21 | 2021-12-08 12:00 | CR0014540 | Service ManagementBooking/DocumentationBookingBookingBooking Split | OPUS-BKG-M | 2021-W48 | 2021-11 | 28 | 28 | 55.6213 | 4 | 1 | 1 | 0.02 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.22951 | 0 | 2021-10 | 0 | 0
2236 | CR0014540 | CTASK0029655 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-11-30 15:56 | 2021-11-01 15:56 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Split | [Deployment] [CLT Internal] Memo split is not working when booking has 10 digit B/L number | 2021-10-05 17:05 | 2021-10-28 | 2021-10-19 06:50 | 2021-11-09 08:44 | 2021-11-09 11:12 |  | 2021-11-30 08:00 | 2021-11-30 08:00 | 2021-11-11 08:21 | 2021-12-08 12:00 | CR0014540 | Service ManagementBooking/DocumentationBookingBookingBooking Split | OPUS-BKG-M | 2021-W48 | 2021-11 | 28 | 28 | 55.6213 | 4 | 1 | 1 | 0.02 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.22951 | 0 | 2021-10 | 0 | 0
2237 | CR0014303 | CTASK0028815 | Closed | OPUS-PSO | Huy Vu |  |  | 2021-09-14 14:47 | 2021-08-23 14:47 | Container | Vessel Operation | Port Service Order | Report | Port Charge Invoice Summary |  | [Document]PSO - Interface Port Charge Invoice Summary to IBIS PLUS | 2021-09-06 15:09 | 2021-09-16 15:07 | 2021-09-15 13:16 | 2021-10-06 07:44 | 2021-10-06 08:32 |  | 2021-10-12 08:00 | 2021-10-12 07:00 | 2021-10-07 11:25 | 2021-10-20 12:00 | CR0014303 | Vessel OperationPort Service OrderReportPort Charge Invoice Summary | OPUS-PSO | 2021-W41 | 2021-10 | 75 | 74 | 35.7018 | 3 | 1 | 2 | 0.09 | 193618 | 1.6 | 1 | 0 | 0 | 1 |  | 1 | 9 | 26 | 0 | 0 | 2021-09 | 0 | 0
2238 | CR0014303 | CTASK0029219 | Closed | OPUS-PSO | Huy Vu | 65 | 64 | 2021-09-15 14:51 | 2021-09-01 14:51 | Container | Vessel Operation | Port Service Order | Report | Port Charge Invoice Summary |  | [CLV] PSO - Interface Port Charge Invoice Summary to IBIS PLUS | 2021-09-06 15:09 | 2021-09-16 15:07 | 2021-09-15 13:16 | 2021-10-06 07:44 | 2021-10-06 08:32 |  | 2021-10-12 08:00 | 2021-10-12 07:00 | 2021-10-07 11:25 | 2021-10-20 12:00 | CR0014303 | Vessel OperationPort Service OrderReportPort Charge Invoice Summary | OPUS-PSO | 2021-W41 | 2021-10 | 75 | 74 | 35.7018 | 3 | 1 | 2 | 0.09 | 193618 | 1.6 | 1 | 0 | 0 | 1 |  | 1 | 9 | 26 | 0 | 0 | 2021-09 | 0 | 0
2239 | CR0014303 | CTASK0029222 | Closed | OPUS-PSO | Lanh Le | 10 | 10 | 2021-09-15 16:38 | 2021-09-01 16:38 | Container | Vessel Operation | Port Service Order | Report | Port Charge Invoice Summary |  | [CLV]PSO - Interface Port Charge Invoice Summary to IBIS PLUS | 2021-09-06 15:09 | 2021-09-16 15:07 | 2021-09-15 13:16 | 2021-10-06 07:44 | 2021-10-06 08:32 |  | 2021-10-12 08:00 | 2021-10-12 07:00 | 2021-10-07 11:25 | 2021-10-20 12:00 | CR0014303 | Vessel OperationPort Service OrderReportPort Charge Invoice Summary | OPUS-PSO | 2021-W41 | 2021-10 | 75 | 74 | 35.7018 | 3 | 1 | 2 | 0.09 | 183422 | 2.8 | 1 | 0 | 0 | 1 |  | 1 | 9 | 26 | 0 | 0 | 2021-09 | 0 | 0
2240 | CR0015086 | CTASK0032495 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2022-02-23 09:21 | 2022-02-16 09:21 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Design] Fix LDF file transfer problem for Hong Kong (SR0143189) | 2022-02-28 14:44 | 2022-04-08 22:00 | 2022-04-08 11:16 | 2022-04-28 14:09 | 2022-04-28 14:17 |  | 2022-05-10 08:00 | 2022-05-10 08:00 | 2022-05-06 09:52 | 2022-05-17 12:00 | CR0015086 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2022-W19 | 2022-05 | 42 | 42 | 70.7193 | 4 | 1 | 2 | 0.02 | 193567 | 2.6 | 2 | 0 | 0 | 1 |  | 2 | 4 | 26 | 0.5625 | 0 | 2022-02 | 0 | 0
2241 | CR0015086 | CTASK0032498 | Closed | OPUS-BKG-M | Khoi Bui | 6 | 6 | 2022-03-18 19:30 | 2022-03-14 07:30 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Testing] Fix LDF file transfer problem for Hong Kong (SR0143189) | 2022-02-28 14:44 | 2022-04-08 22:00 | 2022-04-08 11:16 | 2022-04-28 14:09 | 2022-04-28 14:17 |  | 2022-05-10 08:00 | 2022-05-10 08:00 | 2022-05-06 09:52 | 2022-05-17 12:00 | CR0015086 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2022-W19 | 2022-05 | 42 | 42 | 70.7193 | 4 | 1 | 2 | 0.02 | 203713 | 1.2 | 2 | 0 | 0 | 1 |  | 2 | 4 | 26 | 0 | 0 | 2022-02 | 0 | 0
2242 | CR0015086 | CTASK0032496 | Closed | OPUS-BKG-M | Khoi Bui | 16 | 16 | 2022-03-04 19:30 | 2022-02-28 07:30 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Development] Fix LDF file transfer problem for Hong Kong (SR0143189) | 2022-02-28 14:44 | 2022-04-08 22:00 | 2022-04-08 11:16 | 2022-04-28 14:09 | 2022-04-28 14:17 |  | 2022-05-10 08:00 | 2022-05-10 08:00 | 2022-05-06 09:52 | 2022-05-17 12:00 | CR0015086 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2022-W19 | 2022-05 | 42 | 42 | 70.7193 | 4 | 1 | 2 | 0.02 | 203713 | 1.2 | 2 | 0 | 0 | 1 |  | 2 | 4 | 26 | 0 | 0 | 2022-02 | 0 | 0
2243 | CR0015086 | CTASK0032500 | Closed | OPUS-BKG-M | Khoi Bui | 4 | 4 | 2022-04-30 19:30 | 2022-04-01 07:30 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Deployment] Fix LDF file transfer problem for Hong Kong (SR0143189) | 2022-02-28 14:44 | 2022-04-08 22:00 | 2022-04-08 11:16 | 2022-04-28 14:09 | 2022-04-28 14:17 |  | 2022-05-10 08:00 | 2022-05-10 08:00 | 2022-05-06 09:52 | 2022-05-17 12:00 | CR0015086 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2022-W19 | 2022-05 | 42 | 42 | 70.7193 | 4 | 1 | 2 | 0.02 | 203713 | 1.2 | 2 | 0 | 0 | 1 |  | 2 | 4 | 26 | 0 | 0 | 2022-02 | 0 | 0
2244 | CR0014078 | CTASK0028235 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-08-17 20:35 | 2021-08-02 00:34 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] Standby direction logic | 2021-07-26 09:04 | 2021-08-19 | 2021-08-17 15:05 | 2021-11-01 13:44 | 2021-11-02 11:39 |  | 2021-11-16 08:00 | 2021-11-16 08:00 | 2021-11-11 08:20 | 2021-11-23 12:01 | CR0014078 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W46 | 2021-11 | 76 | 76 | 112.9557 | 6 | 1 | 1 | 0.03 | 153106 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
2245 | CR0014078 | CTASK0028318 | Closed | OPUS-BKG-M | Kieu Le | 20 | 20 | 2021-08-06 20:55 | 2021-08-02 00:55 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] Standby direction logic | 2021-07-26 09:04 | 2021-08-19 | 2021-08-17 15:05 | 2021-11-01 13:44 | 2021-11-02 11:39 |  | 2021-11-16 08:00 | 2021-11-16 08:00 | 2021-11-11 08:20 | 2021-11-23 12:01 | CR0014078 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W46 | 2021-11 | 76 | 76 | 112.9557 | 6 | 1 | 1 | 0.03 | 153106 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
2246 | CR0014078 | CTASK0028234 | Closed | OPUS-BKG-M | Kieu Le | 18 | 18 | 2021-07-30 20:33 | 2021-07-26 00:32 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] Standby direction logic | 2021-07-26 09:04 | 2021-08-19 | 2021-08-17 15:05 | 2021-11-01 13:44 | 2021-11-02 11:39 |  | 2021-11-16 08:00 | 2021-11-16 08:00 | 2021-11-11 08:20 | 2021-11-23 12:01 | CR0014078 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W46 | 2021-11 | 76 | 76 | 112.9557 | 6 | 1 | 1 | 0.03 | 153106 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
2247 | CR0014078 | CTASK0029404 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2021-09-17 18:48 | 2021-09-13 18:48 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development][Additional request] Standby direction logic | 2021-07-26 09:04 | 2021-08-19 | 2021-08-17 15:05 | 2021-11-01 13:44 | 2021-11-02 11:39 |  | 2021-11-16 08:00 | 2021-11-16 08:00 | 2021-11-11 08:20 | 2021-11-23 12:01 | CR0014078 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W46 | 2021-11 | 76 | 76 | 112.9557 | 6 | 1 | 1 | 0.03 | 153106 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
2248 | CR0014078 | CTASK0028237 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-11-30 20:36 | 2021-11-01 00:36 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] Standby direction logic | 2021-07-26 09:04 | 2021-08-19 | 2021-08-17 15:05 | 2021-11-01 13:44 | 2021-11-02 11:39 |  | 2021-11-16 08:00 | 2021-11-16 08:00 | 2021-11-11 08:20 | 2021-11-23 12:01 | CR0014078 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W46 | 2021-11 | 76 | 76 | 112.9557 | 6 | 1 | 1 | 0.03 | 153106 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
2249 | CR0014078 | CTASK0028065 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-07-23 18:42 | 2021-07-09 00:42 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] Standby direction logic | 2021-07-26 09:04 | 2021-08-19 | 2021-08-17 15:05 | 2021-11-01 13:44 | 2021-11-02 11:39 |  | 2021-11-16 08:00 | 2021-11-16 08:00 | 2021-11-11 08:20 | 2021-11-23 12:01 | CR0014078 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2021-W46 | 2021-11 | 76 | 76 | 112.9557 | 6 | 1 | 1 | 0.03 | 153106 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.22951 | 0.13043 | 2021-07 | 0 | 0
2250 | CR0014050 | CTASK0028561 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 43 | 40 | 2021-08-31 13:55 | 2021-08-01 13:55 | Container | Statement Management | Statement Common | Setup | Office Information |  | [August 2021][Phu Nguyen]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 203704 | 0.8 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 0 | 0 | 2021-07 | 1 | 1
2251 | CR0014050 | CTASK0028201 | Closed | OPUS-SCO | Chuong Ta | 44 | 40 | 2021-07-31 12:05 | 2021-07-16 12:05 | Container | Statement Management | Statement Common | Setup | Office Information |  | [July 2021][Chuong Ta]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 183379 | 2.3 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 0.32 | 0.375 | 2021-07 | 1 | 1
2252 | CR0014050 | CTASK0028557 | Closed | OPUS-SCO | Chuong Ta | 56 | 50 | 2021-08-31 13:52 | 2021-08-01 13:52 | Container | Statement Management | Statement Common | Setup | Office Information |  | [August 2021][Chuong Ta]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 183379 | 2.3 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 0.32 | 0.375 | 2021-07 | 1 | 1
2253 | CR0014050 | CTASK0028559 | Closed | OPUS-SCO | Mohamed Hary | 20 | 20 | 2021-08-31 13:54 | 2021-08-01 13:54 | Container | Statement Management | Statement Common | Setup | Office Information |  | [August 2021][Hary]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 193489 | 2.1 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 0.72727 | 0 | 2021-07 | 1 | 1
2254 | CR0014050 | CTASK0028308 | Closed | OPUS-SCO | Mohamed Hary | 52 | 50 | 2021-07-31 13:15 | 2021-07-16 13:15 | Container | Statement Management | Statement Common | Setup | Office Information |  | [July 2021][Hary Mohamed]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 193489 | 2.1 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 0.72727 | 0 | 2021-07 | 1 | 1
2255 | CR0014050 | CTASK0028455 | Closed | OPUS-SCO | Lien Le | 21 | 20 | 2021-07-31 09:21 | 2021-07-16 09:21 | Container | Statement Management | Statement Common | Setup | Office Information |  | [July 2021][Lien Le]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 193441 | 2.3 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 0.42308 | 0 | 2021-07 | 1 | 1
2256 | CR0014050 | CTASK0028456 | Closed | OPUS-SCO | Nguyen Ha Vi | 10 | 10 | 2021-07-31 09:22 | 2021-07-16 09:22 | Container | Statement Management | Statement Common | Setup | Office Information |  | [July 2021][Vi Nguyen]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 203664 | 1.1 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 1.8182 | 2.5 | 2021-07 | 1 | 1
2257 | CR0014050 | CTASK0028558 | Closed | OPUS-SCO | Cuong Tran Hung | 42 | 40 | 2021-08-31 13:53 | 2021-08-01 13:53 | Container | Statement Management | Statement Common | Setup | Office Information |  | [August 2021][Cuong Tran]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 193530 | 2.1 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 1.2308 | 1.25 | 2021-07 | 1 | 1
2258 | CR0014050 | CTASK0028560 | Closed | OPUS-SCO | Nguyen Ha Vi | 60 | 60 | 2021-08-31 13:55 | 2021-08-01 13:55 | Container | Statement Management | Statement Common | Setup | Office Information |  | [August 2021][Vi Nguyen]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 203664 | 1.1 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 1.8182 | 2.5 | 2021-07 | 1 | 1
2259 | CR0014050 | CTASK0028556 | Closed | OPUS-SCO | Lien Le | 76 | 70 | 2021-08-31 13:51 | 2021-08-01 13:51 | Container | Statement Management | Statement Common | Setup | Office Information |  | [August 2021][Lien Le]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 193441 | 2.3 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 0.42308 | 0 | 2021-07 | 1 | 1
2260 | CR0014050 | CTASK0028397 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 34 | 30 | 2021-07-31 09:08 | 2021-07-16 09:08 | Container | Statement Management | Statement Common | Setup | Office Information |  | [July 2021][Phu Nguyen]To ensure that CLEAR functionality is available for use by offices that are set as "Balancing Agents". | 2021-07-08 07:52 | 2021-08-27 07:51 | 2021-08-11 15:20 | 2021-09-30 07:50 | 2021-10-06 06:23 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-06 07:45 | 2021-10-20 12:00 | CR0014050 | Statement ManagementStatement CommonSetupOffice Information | OPUS-SCO | 2021-W41 | 2021-10 | 458 | 430 | 96.0473 | 11 | 1 | 6 | 0.19 | 203704 | 0.8 | 4 | 1 | 0 | 4 |  | 2 | 9 | 26 | 0 | 0 | 2021-07 | 1 | 1
2261 | CR0014502 | CTASK0029905 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2022-03-31 14:26 | 2022-03-28 14:26 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Add additional Terminal information in BRN. Now in BRN TS Port is mentioned as Rotterdam, Hamburg etc but we have few Terminals there. | 2021-11-15 08:57 | 2021-12-09 | 2021-12-03 15:12 | 2021-12-14 08:04 | 2021-12-14 08:06 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-25 11:40 | 2022-04-12 12:00 | CR0014502 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W14 | 2022-04 | 39 | 40 | 140.9606 | 5 | 1 | 2 | 0.01 | 153106 | 3.1 | 2 | 0 | 0 | 1 |  | 2 | 6 | 18 | 0.22951 | 0 | 2021-11 | 0 | 0
2262 | CR0014502 | CTASK0029902 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-11-19 20:23 | 2021-11-15 00:23 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Add additional Terminal information in BRN. Now in BRN TS Port is mentioned as Rotterdam, Hamburg etc but we have few Terminals there. | 2021-11-15 08:57 | 2021-12-09 | 2021-12-03 15:12 | 2021-12-14 08:04 | 2021-12-14 08:06 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-25 11:40 | 2022-04-12 12:00 | CR0014502 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W14 | 2022-04 | 39 | 40 | 140.9606 | 5 | 1 | 2 | 0.01 | 153106 | 3.1 | 2 | 0 | 0 | 1 |  | 2 | 6 | 18 | 0.22951 | 0 | 2021-11 | 0 | 0
2263 | CR0014502 | CTASK0029903 | Closed | OPUS-BKG-M | Kieu Le | 7 | 8 | 2021-11-30 20:25 | 2021-11-22 14:24 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Add additional Terminal information in BRN. Now in BRN TS Port is mentioned as Rotterdam, Hamburg etc but we have few Terminals there. | 2021-11-15 08:57 | 2021-12-09 | 2021-12-03 15:12 | 2021-12-14 08:04 | 2021-12-14 08:06 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-25 11:40 | 2022-04-12 12:00 | CR0014502 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W14 | 2022-04 | 39 | 40 | 140.9606 | 5 | 1 | 2 | 0.01 | 153106 | 3.1 | 2 | 0 | 0 | 1 |  | 2 | 6 | 18 | 0.22951 | 0 | 2021-11 | 0 | 0
2264 | CR0014502 | CTASK0030578 | Closed | OPUS-BKG-M | Trang Le Minh | 2 | 2 | 2021-11-19 08:49 | 2021-11-15 08:49 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [DB] Add additional Terminal information in BRN. Now in BRN TS Port is mentioned as Rotterdam, Hamburg etc but we have few Terminals there. | 2021-11-15 08:57 | 2021-12-09 | 2021-12-03 15:12 | 2021-12-14 08:04 | 2021-12-14 08:06 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-25 11:40 | 2022-04-12 12:00 | CR0014502 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W14 | 2022-04 | 39 | 40 | 140.9606 | 5 | 1 | 2 | 0.01 | 193594 | 2.2 | 2 | 0 | 0 | 1 |  | 2 | 6 | 18 | 0 | 0 | 2021-11 | 0 | 0
2265 | CR0014502 | CTASK0029861 | Closed | OPUS-BKG-M | Kieu Le | 10 | 10 | 2021-10-15 16:43 | 2021-10-11 00:43 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Add additional Terminal information in BRN. Now in BRN TS Port is mentioned as Rotterdam, Hamburg etc but we have few Terminals there. | 2021-11-15 08:57 | 2021-12-09 | 2021-12-03 15:12 | 2021-12-14 08:04 | 2021-12-14 08:06 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-25 11:40 | 2022-04-12 12:00 | CR0014502 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W14 | 2022-04 | 39 | 40 | 140.9606 | 5 | 1 | 2 | 0.01 | 153106 | 3.1 | 2 | 0 | 0 | 1 |  | 2 | 6 | 18 | 0.22951 | 0 | 2021-11 | 0 | 0
2266 | CR0014248 | CTASK0028437 | Closed | OPUS-SCG | Lanh Le | 8 | 8 | 2021-08-26 15:06 | 2021-07-29 15:06 | Container | Vessel Operation | Special Cargo |  |  |  | [Documentation] OPUS Enhancement Request>> For - STABILIZED Shipment - Stowage summary report- CD : D | 2021-08-10 15:15 | 2021-08-27 15:15 | 2021-08-25 08:49 | 2021-09-28 14:16 | 2021-10-05 12:16 |  | 2021-10-12 08:00 | 2021-10-12 09:42 | 2021-10-06 07:47 | 2021-10-19 12:00 | CR0014248 | Vessel OperationSpecial Cargo | OPUS-SCG | 2021-W41 | 2021-10 | 28 | 28 | 62.6977 | 2 | 1 | 1 | 0.02 | 183422 | 2.7 | 1 | 0 | 0 | 1 |  | 2 | 9 | 26 | 0 | 0 | 2021-08 | 0 | 0
2267 | CR0014248 | CTASK0028438 | Closed | OPUS-SCG | Lanh Le | 20 | 20 | 2021-08-26 15:08 | 2021-08-04 15:08 | Container | Vessel Operation | Special Cargo |  |  |  | OPUS Enhancement Request>> For - STABILIZED Shipment - Stowage summary report- CD : D | 2021-08-10 15:15 | 2021-08-27 15:15 | 2021-08-25 08:49 | 2021-09-28 14:16 | 2021-10-05 12:16 |  | 2021-10-12 08:00 | 2021-10-12 09:42 | 2021-10-06 07:47 | 2021-10-19 12:00 | CR0014248 | Vessel OperationSpecial Cargo | OPUS-SCG | 2021-W41 | 2021-10 | 28 | 28 | 62.6977 | 2 | 1 | 1 | 0.02 | 183422 | 2.7 | 1 | 0 | 0 | 1 |  | 2 | 9 | 26 | 0 | 0 | 2021-08 | 0 | 0
2268 | CR0014680 | CTASK0030241 | Closed | OPUS-SPC | Toai Phan | 20 | 20 |  |  | Container | Sales Management | Space Control | Allocation Control | Control by HO |  | Control by HO - Apply logic for virtual add calling | 2021-11-03 08:52 | 2021-11-08 08:51 | 2021-11-05 07:50 | 2021-11-08 10:21 | 2021-11-09 06:34 |  | 2021-11-16 06:34 | 2021-11-16 12:07 | 2021-11-09 07:15 | 2021-11-24 12:00 | CR0014680 | Sales ManagementSpace ControlAllocation ControlControl by HO | OPUS-SPC | 2021-W46 | 2021-11 | 20 | 20 | 12.9043 | 1 | 1 | 1 | 0.06 | 183427 | 2.9 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0 | 2021-11 | 0 | 0
2269 | CR0014427 | CTASK0029951 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 71 | 96 | 2021-11-30 13:12 | 2021-11-01 13:12 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [EST + DEV] ROOT Project Squad 16 - Booking Reconciliation Process - Israel Customs | 2021-10-21 14:22 | 2021-12-17 22:00 | 2021-12-17 13:22 | 2022-02-10 08:40 | 2022-02-22 14:39 |  | 2022-03-08 08:38 | 2022-03-08 08:05 | 2022-02-22 15:27 | 2022-03-17 12:00 | CR0014427 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 93 | 128 | 137.7616 | 2 | 1 | 1 | 0.04 | 193606 | 2 | 1 | 1 | 0 | 2 |  | 2 | 8 | 38 | 4.25 | 0 | 2021-10 | 1 | 1
2270 | CR0014427 | CTASK0029952 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 22 | 32 | 2021-11-30 13:13 | 2021-11-01 13:13 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [TEST+ DEPLOY] ROOT Project Squad 16 - Booking Reconciliation Process - Israel Customs | 2021-10-21 14:22 | 2021-12-17 22:00 | 2021-12-17 13:22 | 2022-02-10 08:40 | 2022-02-22 14:39 |  | 2022-03-08 08:38 | 2022-03-08 08:05 | 2022-02-22 15:27 | 2022-03-17 12:00 | CR0014427 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W10 | 2022-03 | 93 | 128 | 137.7616 | 2 | 1 | 1 | 0.04 | 193606 | 2 | 1 | 1 | 0 | 2 |  | 2 | 8 | 38 | 4.25 | 0 | 2021-10 | 1 | 1
2271 | CR0014336 | CTASK0033337 | Closed | OPUS-SCG | Trang Duy Thong | 50 | 50 | 2022-06-30 17:30 | 2022-06-01 08:30 | Container | Vessel Operation | Special Cargo | DG Restriction | Port Limit | DG Port/Terminal Limits – Check – Total Weight/TEU/Unit | [Test][CLT internal] SCG bug fix | 2022-02-10 17:26 | 2022-03-11 17:23 | 2022-03-11 08:10 | 2022-04-27 15:57 | 2022-05-04 12:39 |  | 2022-05-17 12:39 | 2022-05-17 09:50 | 2022-05-06 09:56 | 2022-05-24 12:00 | CR0014336 | Vessel OperationSpecial CargoDG RestrictionPort LimitDG Port/Terminal Limits – Check – Total Weight/TEU/Unit | OPUS-SCG | 2022-W20 | 2022-05 | 65 | 145 | 95.8006 | 4 | 1 | 3 | 0.06 | 193511 | 1.7 | 1 | 4 | 0 | 2 |  | 2 | 8 | 26 | 0.81818 | 2.6667 | 2022-02 | 4 | 1
2272 | CR0014336 | CTASK0031903 | Closed | OPUS-SCG | Huy Vu | 55 | 55 | 2022-03-04 11:28 | 2022-01-24 11:28 | Container | Vessel Operation | Special Cargo | DG Restriction | Port Limit | DG Port/Terminal Limits – Check – Total Weight/TEU/Unit | [CLV][CLT internal] SCG bug fix | 2022-02-10 17:26 | 2022-03-11 17:23 | 2022-03-11 08:10 | 2022-04-27 15:57 | 2022-05-04 12:39 |  | 2022-05-17 12:39 | 2022-05-17 09:50 | 2022-05-06 09:56 | 2022-05-24 12:00 | CR0014336 | Vessel OperationSpecial CargoDG RestrictionPort LimitDG Port/Terminal Limits – Check – Total Weight/TEU/Unit | OPUS-SCG | 2022-W20 | 2022-05 | 65 | 145 | 95.8006 | 4 | 1 | 3 | 0.06 | 193618 | 2 | 1 | 4 | 0 | 2 |  | 2 | 8 | 26 | 0 | 0 | 2022-02 | 4 | 1
2273 | CR0014336 | CTASK0033336 | Closed | OPUS-SCG | Tu Nguyen | 30 | 30 | 2022-06-30 17:30 | 2022-06-01 08:30 | Container | Vessel Operation | Special Cargo | DG Restriction | Port Limit | DG Port/Terminal Limits – Check – Total Weight/TEU/Unit | [Deployment][CLT internal] SCG bug fix | 2022-02-10 17:26 | 2022-03-11 17:23 | 2022-03-11 08:10 | 2022-04-27 15:57 | 2022-05-04 12:39 |  | 2022-05-17 12:39 | 2022-05-17 09:50 | 2022-05-06 09:56 | 2022-05-24 12:00 | CR0014336 | Vessel OperationSpecial CargoDG RestrictionPort LimitDG Port/Terminal Limits – Check – Total Weight/TEU/Unit | OPUS-SCG | 2022-W20 | 2022-05 | 65 | 145 | 95.8006 | 4 | 1 | 3 | 0.06 | 123045 | 3.4 | 1 | 4 | 0 | 2 |  | 2 | 8 | 26 | 0 | 0 | 2022-02 | 4 | 1
2274 | CR0014336 | CTASK0031902 | Closed | OPUS-SCG | Trang Duy Thong | 10 | 10 | 2022-03-04 11:27 | 2022-01-24 11:27 | Container | Vessel Operation | Special Cargo | DG Restriction | Port Limit | DG Port/Terminal Limits – Check – Total Weight/TEU/Unit | [CLV][CLT internal] SCG bug fix | 2022-02-10 17:26 | 2022-03-11 17:23 | 2022-03-11 08:10 | 2022-04-27 15:57 | 2022-05-04 12:39 |  | 2022-05-17 12:39 | 2022-05-17 09:50 | 2022-05-06 09:56 | 2022-05-24 12:00 | CR0014336 | Vessel OperationSpecial CargoDG RestrictionPort LimitDG Port/Terminal Limits – Check – Total Weight/TEU/Unit | OPUS-SCG | 2022-W20 | 2022-05 | 65 | 145 | 95.8006 | 4 | 1 | 3 | 0.06 | 193511 | 1.7 | 1 | 4 | 0 | 2 |  | 2 | 8 | 26 | 0.81818 | 2.6667 | 2022-02 | 4 | 1
2275 | CR0015374 | CTASK0033573 | Closed | OPUS-SCG | Lanh Le | 2 | 2 | 2022-04-27 15:37 | 2022-04-25 15:37 | Container | Vessel Operation | Special Cargo | Reports | DG List for Vessel |  | [Testing]//Revision// DG List for Vessel // | 2022-04-18 11:04 | 2022-04-29 11:03 | 2022-04-29 06:58 | 2022-05-12 12:52 | 2022-05-12 13:17 |  | 2022-05-17 17:30 | 2022-05-17 09:57 | 2022-05-13 09:26 | 2022-05-24 12:00 | CR0015374 | Vessel OperationSpecial CargoReportsDG List for Vessel | OPUS-SCG | 2022-W20 | 2022-05 | 52 | 52 | 29.2684 | 2 | 1 | 2 | 0.07 | 183422 | 3.4 | 2 | 0 | 0 | 1 |  | 1 | 8 | 26 | 0 | 0 | 2022-04 | 0 | 0
2276 | CR0015374 | CTASK0033571 | Closed | OPUS-SCG | Tu Nguyen | 50 | 50 | 2022-05-01 15:25 | 2022-04-14 15:25 | Container | Vessel Operation | Special Cargo | Reports | DG List for Vessel |  | [All] //Revision// DG List for Vessel // | 2022-04-18 11:04 | 2022-04-29 11:03 | 2022-04-29 06:58 | 2022-05-12 12:52 | 2022-05-12 13:17 |  | 2022-05-17 17:30 | 2022-05-17 09:57 | 2022-05-13 09:26 | 2022-05-24 12:00 | CR0015374 | Vessel OperationSpecial CargoReportsDG List for Vessel | OPUS-SCG | 2022-W20 | 2022-05 | 52 | 52 | 29.2684 | 2 | 1 | 2 | 0.07 | 123045 | 3.5 | 2 | 0 | 0 | 1 |  | 1 | 8 | 26 | 0 | 0 | 2022-04 | 0 | 0
2277 | CR0013200 | CTASK0024137 | Closed | OPUS-SCE | VInh Bui | 6 | 6 | 2020-12-31 17:52 | 2020-12-01 17:52 | Container | Service Management | SCEM | Visibility | Vessel Schedule EDI Management |  | Vessel Schedule EDI with Customer Rio Tinto with New FF Items | 2020-11-18 15:40 | 2020-12-10 15:37 | 2020-12-09 14:40 | 2021-09-01 12:41 | 2021-09-10 14:20 |  | 2021-09-28 10:00 | 2021-09-28 12:19 | 2021-09-23 07:56 | 2021-10-06 12:00 | CR0013200 | Service ManagementSCEMVisibilityVessel Schedule EDI Management | OPUS-SCE | 2021-W39 | 2021-09 | 93 | 0 | 313.7639 | 6 | 1 | 2 | 0 | 193469 | 1.1 | 0 | 0 | 0 | 1 |  | 4 | 6 | 6 | 0 | 0 | 2020-11 | 0 | 0
2278 | CR0013200 | CTASK0025154 | Closed | OPUS-SCE | Son Nguyen The | 9 | 9 | 2021-02-28 16:24 | 2021-02-01 16:24 | Container | Service Management | SCEM | Visibility | Vessel Schedule EDI Management |  | Vessel Schedule EDI with Customer Rio Tinto with New FF Items | 2020-11-18 15:40 | 2020-12-10 15:37 | 2020-12-09 14:40 | 2021-09-01 12:41 | 2021-09-10 14:20 |  | 2021-09-28 10:00 | 2021-09-28 12:19 | 2021-09-23 07:56 | 2021-10-06 12:00 | CR0013200 | Service ManagementSCEMVisibilityVessel Schedule EDI Management | OPUS-SCE | 2021-W39 | 2021-09 | 93 | 0 | 313.7639 | 6 | 1 | 2 | 0 | 193531 | 1.1 | 0 | 0 | 0 | 1 |  | 4 | 6 | 6 | 0 | 0 | 2020-11 | 0 | 0
2279 | CR0013200 | CTASK0024294 | Closed | OPUS-SCE | Son Nguyen The | 7 | 7 | 2020-12-31 11:36 | 2020-12-01 11:36 | Container | Service Management | SCEM | Visibility | Vessel Schedule EDI Management |  | Vessel Schedule EDI with Customer Rio Tinto with New FF Items | 2020-11-18 15:40 | 2020-12-10 15:37 | 2020-12-09 14:40 | 2021-09-01 12:41 | 2021-09-10 14:20 |  | 2021-09-28 10:00 | 2021-09-28 12:19 | 2021-09-23 07:56 | 2021-10-06 12:00 | CR0013200 | Service ManagementSCEMVisibilityVessel Schedule EDI Management | OPUS-SCE | 2021-W39 | 2021-09 | 93 | 0 | 313.7639 | 6 | 1 | 2 | 0 | 193531 | 1.1 | 0 | 0 | 0 | 1 |  | 4 | 6 | 6 | 0 | 0 | 2020-11 | 0 | 0
2280 | CR0013200 | CTASK0023654 | Closed | OPUS-SCE | Son Nguyen The | 54 | 54 | 2020-11-30 14:15 | 2020-11-16 14:15 | Container | Service Management | SCEM | Visibility | Vessel Schedule EDI Management |  | Vessel Schedule EDI with Customer Rio Tinto with New FF Items | 2020-11-18 15:40 | 2020-12-10 15:37 | 2020-12-09 14:40 | 2021-09-01 12:41 | 2021-09-10 14:20 |  | 2021-09-28 10:00 | 2021-09-28 12:19 | 2021-09-23 07:56 | 2021-10-06 12:00 | CR0013200 | Service ManagementSCEMVisibilityVessel Schedule EDI Management | OPUS-SCE | 2021-W39 | 2021-09 | 93 | 0 | 313.7639 | 6 | 1 | 2 | 0 | 193531 | 1.1 | 0 | 0 | 0 | 1 |  | 4 | 6 | 6 | 0 | 0 | 2020-11 | 0 | 0
2281 | CR0013200 | CTASK0029350 | Closed | OPUS-SCE | Son Nguyen The | 16 | 16 | 2021-09-30 14:33 | 2021-09-01 14:33 | Container | Service Management | SCEM | Visibility | Vessel Schedule EDI Management |  | Vessel Schedule EDI with Customer Rio Tinto with New FF Items(SEP.21) | 2020-11-18 15:40 | 2020-12-10 15:37 | 2020-12-09 14:40 | 2021-09-01 12:41 | 2021-09-10 14:20 |  | 2021-09-28 10:00 | 2021-09-28 12:19 | 2021-09-23 07:56 | 2021-10-06 12:00 | CR0013200 | Service ManagementSCEMVisibilityVessel Schedule EDI Management | OPUS-SCE | 2021-W39 | 2021-09 | 93 | 0 | 313.7639 | 6 | 1 | 2 | 0 | 193531 | 1.1 | 0 | 0 | 0 | 1 |  | 4 | 6 | 6 | 0 | 0 | 2020-11 | 0 | 0
2282 | CR0013200 | CTASK0024622 | Closed | OPUS-SCE | Son Nguyen The | 1 | 1 | 2021-01-31 13:55 | 2021-01-01 13:55 | Container | Service Management | SCEM | Visibility | Vessel Schedule EDI Management |  | Vessel Schedule EDI with Customer Rio Tinto with New FF Items | 2020-11-18 15:40 | 2020-12-10 15:37 | 2020-12-09 14:40 | 2021-09-01 12:41 | 2021-09-10 14:20 |  | 2021-09-28 10:00 | 2021-09-28 12:19 | 2021-09-23 07:56 | 2021-10-06 12:00 | CR0013200 | Service ManagementSCEMVisibilityVessel Schedule EDI Management | OPUS-SCE | 2021-W39 | 2021-09 | 93 | 0 | 313.7639 | 6 | 1 | 2 | 0 | 193531 | 1.1 | 0 | 0 | 0 | 1 |  | 4 | 6 | 6 | 0 | 0 | 2020-11 | 0 | 0
2283 | CR0014802 | CTASK0030672 | Closed | OPUS-VSK | Linh Nguyen | 1 | 1 |  |  | Container | Vessel Operation | Vessel Schedule | VSL SKD |  |  | [Documentation][COP Detail not showing correct eta (to fix SR0154611, SR0148526, INC0135718)] | 2021-11-25 11:50 | 2021-12-24 20:00 | 2021-12-22 20:00 | 2022-03-08 11:45 | 2022-03-10 08:04 |  | 2022-03-22 20:00 | 2022-03-22 10:26 | 2022-03-10 08:10 | 2022-03-29 12:00 | CR0014802 | Vessel OperationVessel ScheduleVSL SKD | OPUS-VSK | 2022-W12 | 2022-03 | 53 | 53 | 117.3403 | 2 | 1 | 1 | 0.02 | 193464 | 2.7 | 2 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.375 | 1.5 | 2021-11 | 0 | 0
2284 | CR0014802 | CTASK0030697 | Closed | OPUS-VSK | Linh Nguyen | 53 | 53 | 2021-12-31 20:24 | 2021-11-25 20:24 | Container | Vessel Operation | Vessel Schedule | VSL SKD |  |  | [CLV-VSK][COP Detail not showing correct eta (to fix SR0154611, SR0148526, INC0135718) ] | 2021-11-25 11:50 | 2021-12-24 20:00 | 2021-12-22 20:00 | 2022-03-08 11:45 | 2022-03-10 08:04 |  | 2022-03-22 20:00 | 2022-03-22 10:26 | 2022-03-10 08:10 | 2022-03-29 12:00 | CR0014802 | Vessel OperationVessel ScheduleVSL SKD | OPUS-VSK | 2022-W12 | 2022-03 | 53 | 53 | 117.3403 | 2 | 1 | 1 | 0.02 | 193464 | 2.7 | 2 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0.375 | 1.5 | 2021-11 | 0 | 0
2285 | CR0014467 | CTASK0029213 | Closed | OPUS-FLT | Tran Anh Duy | 1 | 1 |  |  | Container | Support & Admin | Fleet Management | Invoice | Time Charter Invoice | Time Charter Invoice | [Documentation][CLT Internal] Remove the hardcoding logic from row copy function. | 2021-10-06 16:37 | 2021-10-29 17:00 | 2021-10-28 09:16 | 2021-11-23 09:16 | 2021-11-23 15:12 |  | 2021-12-14 08:00 | 2021-12-14 08:00 | 2021-11-23 15:27 | 2021-12-21 12:01 | CR0014467 | Support & AdminFleet ManagementInvoiceTime Charter InvoiceTime Charter Invoice | OPUS-FLT | 2021-W50 | 2021-12 | 34 | 34 | 68.641 | 2 | 1 | 1 | 0.02 | 193516 | 2.5 | 2 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0 | 0 | 2021-10 | 0 | 0
2286 | CR0014467 | CTASK0029334 | Closed | OPUS-FLT | Tran Anh Duy | 34 | 34 |  |  | Container | Support & Admin | Fleet Management | Invoice | Time Charter Invoice | Time Charter Invoice | [CLV][CLT Internal] Remove the hardcoding logic from row copy function. | 2021-10-06 16:37 | 2021-10-29 17:00 | 2021-10-28 09:16 | 2021-11-23 09:16 | 2021-11-23 15:12 |  | 2021-12-14 08:00 | 2021-12-14 08:00 | 2021-11-23 15:27 | 2021-12-21 12:01 | CR0014467 | Support & AdminFleet ManagementInvoiceTime Charter InvoiceTime Charter Invoice | OPUS-FLT | 2021-W50 | 2021-12 | 34 | 34 | 68.641 | 2 | 1 | 1 | 0.02 | 193516 | 2.5 | 2 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0 | 0 | 2021-10 | 0 | 0
2287 | CR0014694 | CTASK0030420 | Closed | OPUS-SAP | Chuong Ta | 38 | 32 | 2021-11-30 09:50 | 2021-11-08 09:50 | Container | Statement Management | Statement Account Payable | Payments | CSR Receipt Entry |  | [Nov 2021][Internal] To prevent CSR reject duplication | 2021-11-08 06:33 | 2021-12-10 06:33 | 2021-12-08 16:49 | 2021-12-20 08:58 | 2021-12-22 09:36 |  | 2021-12-28 10:00 | 2021-12-28 09:00 | 2021-12-23 13:07 | 2022-01-05 12:00 | CR0014694 | Statement ManagementStatement Account PayablePaymentsCSR Receipt Entry | OPUS-SAP | 2021-W52 | 2021-12 | 38 | 32 | 50.1437 | 1 | 1 | 1 | 0.03 | 183379 | 2.7 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.32 | 0.375 | 2021-11 | 0 | 0
2288 | CR0014865 | CTASK0031748 | Closed | OPUS-SCO | Cuong Tran Hung | 22 | 20 | 2022-01-31 15:38 | 2022-01-01 15:38 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [Jan 2022] [Internal] Enhance DSO batch job & TML performance | 2021-12-16 15:15 | 2022-02-11 15:15 | 2022-01-26 07:18 | 2022-02-04 11:38 | 2022-02-04 12:53 |  | 2022-02-15 10:00 | 2022-02-17 09:45 | 2022-02-07 09:29 | 2022-02-24 12:00 | CR0014865 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2022-W7 | 2022-02 | 101 | 95 | 60.7809 | 4 | 1 | 3 | 0.07 | 193530 | 2.5 | 2 | 0 | 0 | 1 |  | 2 | 10 | 30 | 1.2308 | 1.25 | 2021-12 | 0 | 0
2289 | CR0014865 | CTASK0031235 | Closed | OPUS-SCO | Cuong Tran Hung | 42 | 40 | 2021-12-31 14:52 | 2021-12-16 14:51 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [DEC] Enhance TML performance | 2021-12-16 15:15 | 2022-02-11 15:15 | 2022-01-26 07:18 | 2022-02-04 11:38 | 2022-02-04 12:53 |  | 2022-02-15 10:00 | 2022-02-17 09:45 | 2022-02-07 09:29 | 2022-02-24 12:00 | CR0014865 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2022-W7 | 2022-02 | 101 | 95 | 60.7809 | 4 | 1 | 3 | 0.07 | 193530 | 2.5 | 2 | 0 | 0 | 1 |  | 2 | 10 | 30 | 1.2308 | 1.25 | 2021-12 | 0 | 0
2290 | CR0014865 | CTASK0031749 | Closed | OPUS-SCO | Lien Le | 22 | 20 | 2022-01-31 15:39 | 2022-01-01 15:39 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [Jan 2022] [Internal] Enhance DSO batch job & TML performance | 2021-12-16 15:15 | 2022-02-11 15:15 | 2022-01-26 07:18 | 2022-02-04 11:38 | 2022-02-04 12:53 |  | 2022-02-15 10:00 | 2022-02-17 09:45 | 2022-02-07 09:29 | 2022-02-24 12:00 | CR0014865 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2022-W7 | 2022-02 | 101 | 95 | 60.7809 | 4 | 1 | 3 | 0.07 | 193441 | 2.8 | 2 | 0 | 0 | 1 |  | 2 | 10 | 30 | 0.42308 | 0 | 2021-12 | 0 | 0
2291 | CR0014865 | CTASK0031236 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 15 | 15 | 2021-12-31 14:53 | 2021-12-16 14:53 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [DEC] Enhance TML performance | 2021-12-16 15:15 | 2022-02-11 15:15 | 2022-01-26 07:18 | 2022-02-04 11:38 | 2022-02-04 12:53 |  | 2022-02-15 10:00 | 2022-02-17 09:45 | 2022-02-07 09:29 | 2022-02-24 12:00 | CR0014865 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2022-W7 | 2022-02 | 101 | 95 | 60.7809 | 4 | 1 | 3 | 0.07 | 203704 | 1.3 | 2 | 0 | 0 | 1 |  | 2 | 10 | 30 | 0 | 0 | 2021-12 | 0 | 0
2292 | CR0014210 | CTASK0028982 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 90 | 104 | 2021-10-31 16:21 | 2021-10-01 16:21 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Develop] ROOT Project Squad 16 - Booking Reconciliation Process - GB Advanced Filling | 2021-09-03 12:04 | 2021-10-15 22:00 | 2021-10-15 08:45 | 2022-01-14 07:49 | 2022-01-17 13:49 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-21 07:12 | 2022-02-01 12:00 | CR0014210 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 100 | 148 | 143.8305 | 4 | 1 | 1 | 0.04 | 193606 | 1.9 | 1 | 0 | 0 | 2 |  | 2 | 9 | 33 | 4.25 | 2.25 | 2021-09 | 0 | 0
2293 | CR0014210 | CTASK0028980 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 32 | 32 |  |  | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Test + Deploy] ROOT Project Squad 16 - Booking Reconciliation Process - GB Advanced Filling | 2021-09-03 12:04 | 2021-10-15 22:00 | 2021-10-15 08:45 | 2022-01-14 07:49 | 2022-01-17 13:49 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-21 07:12 | 2022-02-01 12:00 | CR0014210 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 100 | 148 | 143.8305 | 4 | 1 | 1 | 0.04 | 193606 | 1.9 | 1 | 0 | 0 | 2 |  | 2 | 9 | 33 | 4.25 | 2.25 | 2021-09 | 0 | 0
2294 | CR0014210 | CTASK0028981 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 6 | 8 | 2021-10-31 16:20 | 2021-08-24 16:20 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Estimate] ROOT Project Squad 16 - Booking Reconciliation Process - GB Advanced Filling | 2021-09-03 12:04 | 2021-10-15 22:00 | 2021-10-15 08:45 | 2022-01-14 07:49 | 2022-01-17 13:49 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-21 07:12 | 2022-02-01 12:00 | CR0014210 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 100 | 148 | 143.8305 | 4 | 1 | 1 | 0.04 | 193606 | 1.9 | 1 | 0 | 0 | 2 |  | 2 | 9 | 33 | 4.25 | 2.25 | 2021-09 | 0 | 0
2295 | CR0014210 | CTASK0031859 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 4 | 4 | 2022-01-31 21:57 | 2022-01-01 21:56 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [PROD] ROOT Project Squad 16 - Booking Reconciliation Process - GB Advanced Filling | 2021-09-03 12:04 | 2021-10-15 22:00 | 2021-10-15 08:45 | 2022-01-14 07:49 | 2022-01-17 13:49 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-21 07:12 | 2022-02-01 12:00 | CR0014210 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 100 | 148 | 143.8305 | 4 | 1 | 1 | 0.04 | 193606 | 1.9 | 1 | 0 | 0 | 2 |  | 2 | 9 | 33 | 4.25 | 2.25 | 2021-09 | 0 | 0
2296 | CR0015125 | CTASK0032520 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 24 | 24 | 2022-04-08 16:01 | 2022-03-14 16:01 | Container | Service Management | Booking/Documentation | Code | Customer Code | Customer Code Inquiry | [Development+ Testing+ Deployment] [CLT internal] Customer is blacklisted in MDA but still shows as Blacklisted = N under Customer code inquiry | 2022-03-07 07:15 | 2022-04-13 22:00 | 2022-04-12 13:08 | 2022-05-04 15:26 | 2022-05-09 09:46 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-09 13:45 | 2022-05-24 12:00 | CR0015125 | Service ManagementBooking/DocumentationCodeCustomer CodeCustomer Code Inquiry | OPUS-BKG-IB | 2022-W20 | 2022-05 | 24 | 24 | 71.0312 | 1 | 1 | 1 | 0.01 | 193512 | 2.7 | 1 | 0 | 0 | 1 |  | 2 | 8 | 26 | 0.2963 | 0 | 2022-03 | 0 | 0
2297 | CR0014206 | CTASK0028605 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 12 | 8 | 2021-08-31 19:18 | 2021-08-02 19:18 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Estimate] ROOT Project Squad 16 - Booking Reconciliation Process - Japan AFR | 2021-09-03 12:05 | 2021-10-15 22:00 | 2021-10-15 09:52 | 2022-01-14 07:26 | 2022-01-17 13:48 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-21 07:20 | 2022-02-01 12:00 | CR0014206 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 125 | 200 | 143.8302 | 4 | 1 | 1 | 0.06 | 193606 | 1.9 | 1 | 0 | 0 | 2 |  | 2 | 9 | 33 | 4.25 | 2.25 | 2021-09 | 0 | 0
2298 | CR0014206 | CTASK0028665 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 107 | 140 | 2021-09-30 22:50 | 2021-08-02 22:50 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Develop] ROOT Project Squad 16 - Booking Reconciliation Process - Japan AFR | 2021-09-03 12:05 | 2021-10-15 22:00 | 2021-10-15 09:52 | 2022-01-14 07:26 | 2022-01-17 13:48 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-21 07:20 | 2022-02-01 12:00 | CR0014206 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 125 | 200 | 143.8302 | 4 | 1 | 1 | 0.06 | 193606 | 1.9 | 1 | 0 | 0 | 2 |  | 2 | 9 | 33 | 4.25 | 2.25 | 2021-09 | 0 | 0
2299 | CR0014206 | CTASK0031858 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 4 | 4 | 2022-01-31 21:55 | 2022-01-01 21:55 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [PROD] ROOT Project Squad 16 - Booking Reconciliation Process - Japan AFR | 2021-09-03 12:05 | 2021-10-15 22:00 | 2021-10-15 09:52 | 2022-01-14 07:26 | 2022-01-17 13:48 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-21 07:20 | 2022-02-01 12:00 | CR0014206 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 125 | 200 | 143.8302 | 4 | 1 | 1 | 0.06 | 193606 | 1.9 | 1 | 0 | 0 | 2 |  | 2 | 9 | 33 | 4.25 | 2.25 | 2021-09 | 0 | 0
2300 | CR0014206 | CTASK0028666 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 2 | 48 | 2021-09-30 22:51 | 2021-08-02 22:51 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Test + Deploy] ROOT Project Squad 16 - Booking Reconciliation Process - Japan AFR | 2021-09-03 12:05 | 2021-10-15 22:00 | 2021-10-15 09:52 | 2022-01-14 07:26 | 2022-01-17 13:48 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-21 07:20 | 2022-02-01 12:00 | CR0014206 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 125 | 200 | 143.8302 | 4 | 1 | 1 | 0.06 | 193606 | 1.9 | 1 | 0 | 0 | 2 |  | 2 | 9 | 33 | 4.25 | 2.25 | 2021-09 | 0 | 0
2301 | CR0010598 | CTASK0017148 | Closed | OPUS-BKG-M | Nam Nguyen | 167 | 132 | 2019-12-27 15:01 | 2019-11-25 15:01 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | NA *DOC* Prompt user to review/update payer information after customer code change | 2019-11-19 14:44 | 2020-01-20 22:00 | 2020-01-20 13:08 | 2022-02-24 01:56 | 2022-03-02 09:23 |  | 2022-03-29 08:00 | 2022-03-29 08:15 | 2022-03-11 15:14 | 2022-04-05 12:00 | CR0010598 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W13 | 2022-03 | 381 | 303 | 860.7194 | 7 | 2 | 2 | 0.01 | 123048 | 1.1 | 1 | 0 | 1 | 4 |  | 5 | 6 | 38 | 0.22222 | 0.46154 | 2019-11 | 1 | 1
2302 | CR0010598 | CTASK0029020 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 78 | 60 | 2021-09-30 14:42 | 2021-08-24 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Development]NA *DOC* Prompt user to review/update payer information after customer code change - 3rd | 2019-11-19 14:44 | 2020-01-20 22:00 | 2020-01-20 13:08 | 2022-02-24 01:56 | 2022-03-02 09:23 |  | 2022-03-29 08:00 | 2022-03-29 08:15 | 2022-03-11 15:14 | 2022-04-05 12:00 | CR0010598 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W13 | 2022-03 | 381 | 303 | 860.7194 | 7 | 2 | 2 | 0.01 | 193470 | 0.7 | 1 | 0 | 1 | 4 |  | 5 | 6 | 38 | 0.36842 | 1.3333 | 2019-11 | 1 | 1
2303 | CR0010598 | CTASK0017152 | Closed | OPUS-BKG-M | Nam Nguyen | 11 | 10 | 2020-01-17 15:27 | 2019-12-30 15:27 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | NA *DOC* Prompt user to review/update payer information after customer code change | 2019-11-19 14:44 | 2020-01-20 22:00 | 2020-01-20 13:08 | 2022-02-24 01:56 | 2022-03-02 09:23 |  | 2022-03-29 08:00 | 2022-03-29 08:15 | 2022-03-11 15:14 | 2022-04-05 12:00 | CR0010598 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W13 | 2022-03 | 381 | 303 | 860.7194 | 7 | 2 | 2 | 0.01 | 123048 | 1.1 | 1 | 0 | 1 | 4 |  | 5 | 6 | 38 | 0.22222 | 0.46154 | 2019-11 | 1 | 1
2304 | CR0010598 | CTASK0032953 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 29 | 21 | 2022-03-21 21:00 | 2022-03-15 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Deployment]NA *DOC* Prompt user to review/update payer information after customer code change - 3rd | 2019-11-19 14:44 | 2020-01-20 22:00 | 2020-01-20 13:08 | 2022-02-24 01:56 | 2022-03-02 09:23 |  | 2022-03-29 08:00 | 2022-03-29 08:15 | 2022-03-11 15:14 | 2022-04-05 12:00 | CR0010598 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W13 | 2022-03 | 381 | 303 | 860.7194 | 7 | 2 | 2 | 0.01 | 193470 | 0.7 | 1 | 0 | 1 | 4 |  | 5 | 6 | 38 | 0.36842 | 1.3333 | 2019-11 | 1 | 1
2305 | CR0010598 | CTASK0028933 | Closed | OPUS-BKG-OB | Nam Nguyen | 40 | 40 | 2021-09-10 21:20 | 2021-09-01 21:20 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Development]NA *DOC* Prompt user to review/update payer information after customer code change - 3rd | 2019-11-19 14:44 | 2020-01-20 22:00 | 2020-01-20 13:08 | 2022-02-24 01:56 | 2022-03-02 09:23 |  | 2022-03-29 08:00 | 2022-03-29 08:15 | 2022-03-11 15:14 | 2022-04-05 12:00 | CR0010598 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W13 | 2022-03 | 381 | 303 | 860.7194 | 7 | 2 | 2 | 0.01 | 123048 | 1.1 | 1 | 0 | 1 | 4 |  | 5 | 6 | 38 | 0.22222 | 0.46154 | 2019-11 | 1 | 1
2306 | CR0010598 | CTASK0019831 | Closed | OPUS-BKG-OB | Nam Nguyen | 44 | 40 | 2020-05-07 16:17 | 2020-04-24 16:17 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Development] NA *DOC* Prompt user to review/update payer information after customer code change | 2019-11-19 14:44 | 2020-01-20 22:00 | 2020-01-20 13:08 | 2022-02-24 01:56 | 2022-03-02 09:23 |  | 2022-03-29 08:00 | 2022-03-29 08:15 | 2022-03-11 15:14 | 2022-04-05 12:00 | CR0010598 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W13 | 2022-03 | 381 | 303 | 860.7194 | 7 | 2 | 2 | 0.01 | 123048 | 1.1 | 1 | 0 | 1 | 4 |  | 5 | 6 | 38 | 0.22222 | 0.46154 | 2019-11 | 1 | 1
2307 | CR0010598 | CTASK0028495 | Closed | OPUS-BKG-OB | Nam Nguyen | 12 | 12 | 2021-08-31 10:58 | 2021-07-29 10:58 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Development] NA *DOC* Prompt user to review/update payer information after customer code change | 2019-11-19 14:44 | 2020-01-20 22:00 | 2020-01-20 13:08 | 2022-02-24 01:56 | 2022-03-02 09:23 |  | 2022-03-29 08:00 | 2022-03-29 08:15 | 2022-03-11 15:14 | 2022-04-05 12:00 | CR0010598 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2022-W13 | 2022-03 | 381 | 303 | 860.7194 | 7 | 2 | 2 | 0.01 | 123048 | 1.1 | 1 | 0 | 1 | 4 |  | 5 | 6 | 38 | 0.22222 | 0.46154 | 2019-11 | 1 | 1
2308 | CR0014341 | CTASK0029983 | Closed | OPUS-SCO | Lien Le | 22 | 20 | 2021-10-31 18:12 | 2021-10-15 18:12 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [Oct 2021][NA *F&A*- AR- Clear Payment Letter] | 2021-10-08 06:20 | 2021-11-19 06:20 | 2021-11-17 15:05 | 2022-01-14 16:24 | 2022-01-17 14:49 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-20 15:02 | 2022-02-01 12:00 | CR0014341 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2022-W4 | 2022-01 | 125 | 116 | 109.1529 | 5 | 1 | 5 | 0.04 | 193441 | 2.6 | 3 | 1 | 0 | 2 |  | 2 | 9 | 33 | 0.42308 | 0 | 2021-10 | 1 | 1
2309 | CR0014341 | CTASK0029985 | Closed | OPUS-SCO | Chuong Ta | 10 | 10 | 2021-10-31 18:14 | 2021-10-15 18:14 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [Oct 2021][NA *F&A*- AR- Clear Payment Letter] | 2021-10-08 06:20 | 2021-11-19 06:20 | 2021-11-17 15:05 | 2022-01-14 16:24 | 2022-01-17 14:49 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-20 15:02 | 2022-02-01 12:00 | CR0014341 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2022-W4 | 2022-01 | 125 | 116 | 109.1529 | 5 | 1 | 5 | 0.04 | 183379 | 2.6 | 3 | 1 | 0 | 2 |  | 2 | 9 | 33 | 0.32 | 0.375 | 2021-10 | 1 | 1
2310 | CR0014341 | CTASK0029982 | Closed | OPUS-SCO | Mohamed Hary | 30 | 30 | 2021-10-31 18:10 | 2021-10-15 18:10 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [Oct 2021][NA *F&A*- AR- Clear Payment Letter] | 2021-10-08 06:20 | 2021-11-19 06:20 | 2021-11-17 15:05 | 2022-01-14 16:24 | 2022-01-17 14:49 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-20 15:02 | 2022-02-01 12:00 | CR0014341 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2022-W4 | 2022-01 | 125 | 116 | 109.1529 | 5 | 1 | 5 | 0.04 | 193489 | 2.4 | 3 | 1 | 0 | 2 |  | 2 | 9 | 33 | 0.72727 | 0 | 2021-10 | 1 | 1
2311 | CR0014341 | CTASK0029984 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 18 | 16 | 2021-10-31 18:13 | 2021-10-15 18:13 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [Oct 2021][NA *F&A*- AR- Clear Payment Letter] | 2021-10-08 06:20 | 2021-11-19 06:20 | 2021-11-17 15:05 | 2022-01-14 16:24 | 2022-01-17 14:49 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-20 15:02 | 2022-02-01 12:00 | CR0014341 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2022-W4 | 2022-01 | 125 | 116 | 109.1529 | 5 | 1 | 5 | 0.04 | 203704 | 1.1 | 3 | 1 | 0 | 2 |  | 2 | 9 | 33 | 0 | 0 | 2021-10 | 1 | 1
2312 | CR0014341 | CTASK0029981 | Closed | OPUS-SCO | Cuong Tran Hung | 45 | 40 | 2021-10-31 18:09 | 2021-10-15 18:09 | Container | Statement Management | Statement Account Receivable | Collection Manager | Debtors Cockpit |  | [Oct 2021][NA *F&A*- AR- Clear Payment Letter] | 2021-10-08 06:20 | 2021-11-19 06:20 | 2021-11-17 15:05 | 2022-01-14 16:24 | 2022-01-17 14:49 |  | 2022-01-25 10:00 | 2022-01-25 10:00 | 2022-01-20 15:02 | 2022-02-01 12:00 | CR0014341 | Statement ManagementStatement Account ReceivableCollection ManagerDebtors Cockpit | OPUS-SAR | 2022-W4 | 2022-01 | 125 | 116 | 109.1529 | 5 | 1 | 5 | 0.04 | 193530 | 2.4 | 3 | 1 | 0 | 2 |  | 2 | 9 | 33 | 1.2308 | 1.25 | 2021-10 | 1 | 1
2313 | CR0015177 | CTASK0033268 | Closed | OPUS-PRD | Tran Le | 14 | 20 | 2022-04-30 10:02 | 2022-04-01 10:02 | Container | Service Management | Product Catalog | Network Link (Ocean) | Ocean Route Management |  | GHQ - Update Ocean Route Management UI-APR | 2022-03-16 15:03 | 2022-04-20 18:00 | 2022-04-19 09:16 | 2022-04-29 09:08 | 2022-04-29 12:57 |  | 2022-05-10 08:00 | 2022-05-10 07:00 | 2022-05-06 09:56 | 2022-05-17 12:00 | CR0015177 | Service ManagementProduct CatalogNetwork Link (Ocean)Ocean Route Management | OPUS-PRD | 2022-W19 | 2022-05 | 82 | 83 | 54.7063 | 4 | 1 | 2 | 0.06 | 193501 | 2.4 | 1 | 0 | 1 | 1 |  | 2 | 4 | 26 | 0.052632 | 0 | 2022-03 | 1 | 1
2314 | CR0015177 | CTASK0032994 | Closed | OPUS-PRD | Phu Nguyen Hoang | 23 | 28 | 2022-04-30 06:27 | 2022-04-01 06:27 | Container | Service Management | Product Catalog | Network Link (Ocean) | Ocean Route Management |  | GHQ - Update Ocean Route Management UI-APR | 2022-03-16 15:03 | 2022-04-20 18:00 | 2022-04-19 09:16 | 2022-04-29 09:08 | 2022-04-29 12:57 |  | 2022-05-10 08:00 | 2022-05-10 07:00 | 2022-05-06 09:56 | 2022-05-17 12:00 | CR0015177 | Service ManagementProduct CatalogNetwork Link (Ocean)Ocean Route Management | OPUS-PRD | 2022-W19 | 2022-05 | 82 | 83 | 54.7063 | 4 | 1 | 2 | 0.06 | 193463 | 3 | 1 | 0 | 1 | 1 |  | 2 | 4 | 26 | 0.16667 | 0 | 2022-03 | 1 | 1
2315 | CR0015177 | CTASK0032940 | Closed | OPUS-PRD | Phu Nguyen Hoang | 40 | 30 | 2022-03-31 12:06 | 2022-03-16 12:06 | Container | Service Management | Product Catalog | Network Link (Ocean) | Ocean Route Management |  | GHQ - Update Ocean Route Management UI-MAR | 2022-03-16 15:03 | 2022-04-20 18:00 | 2022-04-19 09:16 | 2022-04-29 09:08 | 2022-04-29 12:57 |  | 2022-05-10 08:00 | 2022-05-10 07:00 | 2022-05-06 09:56 | 2022-05-17 12:00 | CR0015177 | Service ManagementProduct CatalogNetwork Link (Ocean)Ocean Route Management | OPUS-PRD | 2022-W19 | 2022-05 | 82 | 83 | 54.7063 | 4 | 1 | 2 | 0.06 | 193463 | 3 | 1 | 0 | 1 | 1 |  | 2 | 4 | 26 | 0.16667 | 0 | 2022-03 | 1 | 1
2316 | CR0015177 | CTASK0033117 | Closed | OPUS-PRD | Tran Le | 5 | 5 | 2022-03-31 17:54 | 2022-03-24 17:54 | Container | Service Management | Product Catalog | Network Link (Ocean) | Ocean Route Management |  | GHQ - Update Ocean Route Management UI-MAR | 2022-03-16 15:03 | 2022-04-20 18:00 | 2022-04-19 09:16 | 2022-04-29 09:08 | 2022-04-29 12:57 |  | 2022-05-10 08:00 | 2022-05-10 07:00 | 2022-05-06 09:56 | 2022-05-17 12:00 | CR0015177 | Service ManagementProduct CatalogNetwork Link (Ocean)Ocean Route Management | OPUS-PRD | 2022-W19 | 2022-05 | 82 | 83 | 54.7063 | 4 | 1 | 2 | 0.06 | 193501 | 2.4 | 1 | 0 | 1 | 1 |  | 2 | 4 | 26 | 0.052632 | 0 | 2022-03 | 1 | 1
2317 | CR0014405 | CTASK0029037 | Closed | OPUS-JOO | Linh Nguyen | 1 | 1 |  |  | Container | Support & Admin | Joint Operation | CSR |  |  | [Document][CLT Internal] JOO - Enhance the issue of duplicate when reversing CSR multi times | 2021-09-06 09:13 | 2021-09-24 09:13 | 2021-09-23 15:36 | 2021-12-21 14:11 | 2021-12-23 14:58 |  | 2022-01-11 17:00 | 2022-01-11 20:00 | 2021-12-24 08:50 | 2022-01-18 12:01 | CR0014405 | Support & AdminJoint OperationCSR | OPUS-JOO | 2022-W2 | 2022-01 | 24 | 24 | 127.3243 | 2 | 1 | 1 | 0.01 | 193464 | 2.5 | 2 | 0 | 0 | 1 |  | 2 | 7 | 33 | 0.375 | 1.5 | 2021-09 | 0 | 0
2318 | CR0014405 | CTASK0029202 | Closed | OPUS-JOO | Linh Nguyen | 24 | 24 | 2021-09-30 09:07 | 2021-09-10 09:07 | Container | Support & Admin | Joint Operation | CSR |  |  | [CLV][CLT Internal] JOO - Enhance the issue of duplicate when reversing CSR multi times | 2021-09-06 09:13 | 2021-09-24 09:13 | 2021-09-23 15:36 | 2021-12-21 14:11 | 2021-12-23 14:58 |  | 2022-01-11 17:00 | 2022-01-11 20:00 | 2021-12-24 08:50 | 2022-01-18 12:01 | CR0014405 | Support & AdminJoint OperationCSR | OPUS-JOO | 2022-W2 | 2022-01 | 24 | 24 | 127.3243 | 2 | 1 | 1 | 0.01 | 193464 | 2.5 | 2 | 0 | 0 | 1 |  | 2 | 7 | 33 | 0.375 | 1.5 | 2021-09 | 0 | 0
2319 | CR0013489 | CTASK0032733 | Closed | OPUS-DMT | Cuong Nguyen | 27 | 27 | 2022-07-01 08:22 | 2022-03-07 08:22 | Container | Statement Management | Statement Account Receivable |  |  |  | [TASK9] TEST | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 193529 | 2.2 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.11538 | 0.22222 | 2021-07 | 3 | 1
2320 | CR0013489 | CTASK0030229 | Closed | OPUS-TPB | Manh Nguyen | 1 | 1 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Statement Management | Statement Account Receivable |  |  |  | [202111] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2321 | CR0013489 | CTASK0029685 | Closed | OPUS-TPB | Manh Nguyen | 59 | 65 | 2021-10-29 20:00 | 2021-10-01 04:00 | Container | Statement Management | Statement Account Receivable |  |  |  | [202110] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2322 | CR0013489 | CTASK0032490 | Closed | OPUS-TPB | Manh Nguyen | 11 | 11 | 2022-02-28 19:00 | 2022-02-07 08:12 | Container | Statement Management | Statement Account Receivable |  |  |  | [202202] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2323 | CR0013489 | CTASK0028992 | Closed | OPUS-PRI | Ngan Nham | 22 | 22 | 2021-08-31 23:00 | 2021-08-24 23:00 | Container | Statement Management | Statement Account Receivable |  |  |  | [Development][MDA] Customer integration | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 193461 | 2.7 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.125 | 0 | 2021-07 | 3 | 1
2324 | CR0013489 | CTASK0033308 | Closed | OPUS-TPB | Manh Nguyen | 40 | 42 | 2022-05-31 15:13 | 2022-04-01 15:13 | Container | Statement Management | Statement Account Receivable |  |  |  | [Test] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2325 | CR0013489 | CTASK0027245 | Closed | OPUS-DMT | Cuong Nguyen | 41 | 42 | 2021-11-15 18:00 | 2021-07-01 06:00 | Container | Statement Management | Statement Account Receivable |  |  |  | [CTASK5] CLV_Analysis_Development | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 193529 | 2.2 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.11538 | 0.22222 | 2021-07 | 3 | 1
2326 | CR0013489 | CTASK0025785 | Closed | OPUS-TPB | Manh Nguyen | 1 | 1 | 2021-03-31 19:00 | 2021-03-01 07:00 | Container | Statement Management | Statement Account Receivable |  |  |  | [202103] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2327 | CR0013489 | CTASK0027317 | Closed | OPUS-TPB | Manh Nguyen | 10 | 10 | 2021-06-30 20:00 | 2021-06-01 | Container | Statement Management | Statement Account Receivable |  |  |  | [202106] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2328 | CR0013489 | CTASK0028504 | Closed | OPUS-TPB | Manh Nguyen | 57 | 60 | 2021-08-31 22:00 | 2021-08-01 | Container | Statement Management | Statement Account Receivable |  |  |  | [202108] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2329 | CR0013489 | CTASK0028030 | Closed | OPUS-INV | Nguyen Hoang Trong Phu | 23 | 20 | 2021-07-31 10:33 | 2021-07-01 10:33 | Container | Statement Management | Statement Account Receivable |  |  |  | [July 2021][Phu Nguyen]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality] | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 203704 | 0.9 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0 | 0 | 2021-07 | 3 | 1
2330 | CR0013489 | CTASK0029122 | Closed | OPUS-TPB | Manh Nguyen | 39 | 40 | 2021-09-30 22:00 | 2021-09-01 | Container | Statement Management | Statement Account Receivable |  |  |  | [202109] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2331 | CR0013489 | CTASK0027090 | Closed | OPUS-TPB | Manh Nguyen | 5 | 5 | 2021-05-31 20:00 | 2021-05-01 | Container | Statement Management | Statement Account Receivable |  |  |  | [202105] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2332 | CR0013489 | CTASK0032489 | Closed | OPUS-MDA | Ngan Nham | 8 | 8 | 2022-02-28 22:00 | 2022-02-20 23:00 | Container | Statement Management | Statement Account Receivable |  |  |  | [Deployment][MDA] Customer integration | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 193461 | 2.7 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.125 | 0 | 2021-07 | 3 | 1
2333 | CR0013489 | CTASK0029232 | Closed | OPUS-INV | Nguyen Ha Vi | 32 | 30 | 2021-09-30 17:16 | 2021-09-01 17:16 | Container | Statement Management | Statement Account Receivable |  |  |  | [Sep 2021][Vi Nguyen] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 203664 | 1.1 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 1.8182 | 2.5 | 2021-07 | 3 | 1
2334 | CR0013489 | CTASK0027894 | Closed | OPUS-TPB | Manh Nguyen | 14 | 20 | 2021-07-31 23:00 | 2021-07-01 | Container | Statement Management | Statement Account Receivable |  |  |  | [202107] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2335 | CR0013489 | CTASK0033783 | Closed | OPUS-INV | Lien Le | 26 | 25 | 2022-04-30 15:57 | 2022-04-18 15:56 | Container | Statement Management | Statement Account Receivable |  |  |  | [Test] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 193441 | 2.4 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.42308 | 0 | 2021-07 | 3 | 1
2336 | CR0013489 | CTASK0029233 | Closed | OPUS-INV | Chuong Ta | 10 | 9 | 2021-09-30 17:18 | 2021-09-01 17:18 | Container | Statement Management | Statement Account Receivable |  |  |  | [Sep 2021][Chuong Ta] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 183379 | 2.4 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.32 | 0.375 | 2021-07 | 3 | 1
2337 | CR0013489 | CTASK0032598 | Closed | OPUS-TPB | Manh Nguyen | 12 | 15 | 2022-03-31 13:01 | 2022-03-02 13:01 | Container | Statement Management | Statement Account Receivable |  |  |  | [202203] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 153138 | 2.8 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.16667 | 0.16667 | 2021-07 | 3 | 1
2338 | CR0013489 | CTASK0029133 | Closed | OPUS-PRI | Ngan Nham | 8 | 8 | 2021-09-30 23:00 | 2021-08-31 23:00 | Container | Statement Management | Statement Account Receivable |  |  |  | [Development][MDA] Customer integration | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 193461 | 2.7 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.125 | 0 | 2021-07 | 3 | 1
2339 | CR0013489 | CTASK0033780 | Closed | OPUS-INV | Nguyen Ha Vi | 34 | 30 | 2022-04-30 15:53 | 2022-04-18 15:53 | Container | Statement Management | Statement Account Receivable |  |  |  | [Deployment] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS AR | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 203664 | 1.1 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 1.8182 | 2.5 | 2021-07 | 3 | 1
2340 | CR0013489 | CTASK0027246 | Closed | OPUS-DMT | Cuong Nguyen | 40 | 40 | 2021-08-31 18:00 | 2021-08-02 06:00 | Container | Statement Management | Statement Account Receivable |  |  |  | [CTASK6] CLV_Test_Deployment | 2021-07-26 09:24 | 2021-10-22 21:59 | 2021-10-18 12:51 | 2022-03-16 12:41 | 2022-04-22 14:27 |  | 2022-04-26 08:30 | 2022-04-26 13:37 | 2022-04-22 14:46 | 2022-07-01 13:38 | CR0013489 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 513 | 530 | 273.9628 | 22 | 5 | 7 | 0.08 | 193529 | 2.2 | 4 | 2 | 1 | 4 |  | 3 | 6 | 18 | 0.11538 | 0.22222 | 2021-07 | 3 | 1
2341 | CR0014123 | CTASK0028909 | Closed | OPUS-BKG-EBKG | Vinh Tran | 8 | 8 | 2022-01-29 | 2022-01-24 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] Auto Upload Feasibility check- Expired Contract/Invalid Contract | 2021-08-25 07:59 | 2021-10-06 22:00 | 2021-10-05 06:20 | 2022-01-18 12:19 | 2022-01-26 07:40 |  | 2022-02-08 09:00 | 2022-02-08 08:01 | 2022-02-07 09:24 | 2022-02-15 12:00 | CR0014123 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W6 | 2022-02 | 78 | 77 | 167.0427 | 3 | 1 | 1 | 0.02 | 193525 | 2.2 | 1 | 0 | 0 | 1 |  | 3 | 6 | 30 | 0.41667 | 0.16667 | 2021-08 | 0 | 0
2342 | CR0014123 | CTASK0028907 | Closed | OPUS-BKG-EBKG | Vinh Tran | 14 | 14 | 2021-08-20 | 2021-08-18 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] Auto Upload Feasibility check- Expired Contract/Invalid Contract | 2021-08-25 07:59 | 2021-10-06 22:00 | 2021-10-05 06:20 | 2022-01-18 12:19 | 2022-01-26 07:40 |  | 2022-02-08 09:00 | 2022-02-08 08:01 | 2022-02-07 09:24 | 2022-02-15 12:00 | CR0014123 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W6 | 2022-02 | 78 | 77 | 167.0427 | 3 | 1 | 1 | 0.02 | 193525 | 2.2 | 1 | 0 | 0 | 1 |  | 3 | 6 | 30 | 0.41667 | 0.16667 | 2021-08 | 0 | 0
2343 | CR0014123 | CTASK0028908 | Closed | OPUS-BKG-EBKG | Vinh Tran | 56 | 55 | 2021-10-01 | 2021-09-13 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development+Test] Auto Upload Feasibility check- Expired Contract/Invalid Contract | 2021-08-25 07:59 | 2021-10-06 22:00 | 2021-10-05 06:20 | 2022-01-18 12:19 | 2022-01-26 07:40 |  | 2022-02-08 09:00 | 2022-02-08 08:01 | 2022-02-07 09:24 | 2022-02-15 12:00 | CR0014123 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W6 | 2022-02 | 78 | 77 | 167.0427 | 3 | 1 | 1 | 0.02 | 193525 | 2.2 | 1 | 0 | 0 | 1 |  | 3 | 6 | 30 | 0.41667 | 0.16667 | 2021-08 | 0 | 0
2344 | CR0014563 | CTASK0029765 | Closed | OPUS-SCO | Lien Le | 11 | 15 | 2021-10-30 11:07 | 2021-10-06 11:07 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [Oct 2021][Internal] Enhance program to prevent DSO batch exception | 2021-10-06 08:38 | 2021-11-12 08:38 | 2021-11-10 14:30 | 2021-11-12 09:58 | 2021-11-16 09:04 |  | 2021-11-23 10:00 | 2021-11-23 10:00 | 2021-11-16 14:03 | 2021-12-01 12:00 | CR0014563 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2021-W47 | 2021-11 | 46 | 49 | 48.0569 | 2 | 1 | 2 | 0.04 | 193441 | 2.6 | 3 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.42308 | 0 | 2021-10 | 0 | 0
2345 | CR0014563 | CTASK0029764 | Closed | OPUS-SCO | Cuong Tran Hung | 35 | 34 | 2021-10-30 11:06 | 2021-10-06 11:05 | Container | Statement Management | Statement Account Receivable | Collection Manager | DSO Inquiry |  | [Oct 2021][Internal] Enhance program to prevent DSO batch exception | 2021-10-06 08:38 | 2021-11-12 08:38 | 2021-11-10 14:30 | 2021-11-12 09:58 | 2021-11-16 09:04 |  | 2021-11-23 10:00 | 2021-11-23 10:00 | 2021-11-16 14:03 | 2021-12-01 12:00 | CR0014563 | Statement ManagementStatement Account ReceivableCollection ManagerDSO Inquiry | OPUS-SAR | 2021-W47 | 2021-11 | 46 | 49 | 48.0569 | 2 | 1 | 2 | 0.04 | 193530 | 2.4 | 3 | 0 | 0 | 1 |  | 1 | 7 | 38 | 1.2308 | 1.25 | 2021-10 | 0 | 0
2346 | CR0014414 | CTASK0029775 | Closed | OPUS-BKG-MFT-M | Tung Nguyen Thanh | 8 | 8 | 2021-12-31 10:31 | 2021-12-01 10:31 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Deploy]Mexico [enhancement]// Customs submission // X12 // 2 | 2021-10-29 11:56 | 2021-11-10 22:00 | 2021-11-10 13:10 | 2022-01-28 20:11 | 2022-01-28 20:18 |  | 2022-01-31 07:00 | 2022-01-31 08:00 | 2022-01-29 07:19 | 2022-02-07 12:00 | CR0014414 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 10 | 36 | 93.7942 | 3 | 1 | 2 | 0.02 | 193606 | 2 | 2 | 0 | 0 | 1 |  | 2 | 3 | 33 | 4.25 | 0 | 2021-10 | 0 | 0
2347 | CR0014414 | CTASK0029774 | Closed | OPUS-BKG-MFT-M | Linh Dinh Bo | 24 | 24 | 2021-11-05 15:47 | 2021-10-25 15:47 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Test]Mexico [enhancement]// Customs submission // X12 // 2 | 2021-10-29 11:56 | 2021-11-10 22:00 | 2021-11-10 13:10 | 2022-01-28 20:11 | 2022-01-28 20:18 |  | 2022-01-31 07:00 | 2022-01-31 08:00 | 2022-01-29 07:19 | 2022-02-07 12:00 | CR0014414 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 10 | 36 | 93.7942 | 3 | 1 | 2 | 0.02 | 193522 | 2.4 | 2 | 0 | 0 | 1 |  | 2 | 3 | 33 | 0 | 0 | 2021-10 | 0 | 0
2348 | CR0014414 | CTASK0029771 | Closed | OPUS-BKG-MFT-M | Tung Nguyen Thanh | 2 | 4 |  |  | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [EST]Mexico [enhancement]// Customs submission // X12 // 2 | 2021-10-29 11:56 | 2021-11-10 22:00 | 2021-11-10 13:10 | 2022-01-28 20:11 | 2022-01-28 20:18 |  | 2022-01-31 07:00 | 2022-01-31 08:00 | 2022-01-29 07:19 | 2022-02-07 12:00 | CR0014414 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 10 | 36 | 93.7942 | 3 | 1 | 2 | 0.02 | 193606 | 2 | 2 | 0 | 0 | 1 |  | 2 | 3 | 33 | 4.25 | 0 | 2021-10 | 0 | 0
2349 | CR0015287 | CTASK0033164 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 14 | 14 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [Development + Testing] Updating/ Replacing the URL link for those notification sent to customers by 9th May 2022 | 2022-03-31 06:11 | 2022-04-13 22:00 | 2022-04-13 12:16 | 2022-04-29 12:20 | 2022-05-03 14:32 |  | 2022-05-09 08:00 | 2022-05-09 07:57 | 2022-05-06 09:51 | 2022-05-16 12:00 | CR0015287 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2022-W19 | 2022-05 | 50 | 48 | 39.0755 | 5 | 2 | 2 | 0.05 | 193470 | 3 | 1 | 0 | 0 | 1 |  | 1 | 4 | 26 | 0.36842 | 0 | 2022-03 | 0 | 0
2350 | CR0015287 | CTASK0033163 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2022-03-30 16:56 | 2022-03-28 16:56 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [Design] Updating/ Replacing the URL link for those notification sent to customers by 9th May 2022 | 2022-03-31 06:11 | 2022-04-13 22:00 | 2022-04-13 12:16 | 2022-04-29 12:20 | 2022-05-03 14:32 |  | 2022-05-09 08:00 | 2022-05-09 07:57 | 2022-05-06 09:51 | 2022-05-16 12:00 | CR0015287 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2022-W19 | 2022-05 | 50 | 48 | 39.0755 | 5 | 2 | 2 | 0.05 | 193470 | 3 | 1 | 0 | 0 | 1 |  | 1 | 4 | 26 | 0.36842 | 0 | 2022-03 | 0 | 0
2351 | CR0015287 | CTASK0033214 | Closed | OPUS-BKG-IB | Linh Dinh Bo | 6 | 6 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [Deployment] Updating/ Replacing the URL link for those notification sent to customers by 9th May 2022 | 2022-03-31 06:11 | 2022-04-13 22:00 | 2022-04-13 12:16 | 2022-04-29 12:20 | 2022-05-03 14:32 |  | 2022-05-09 08:00 | 2022-05-09 07:57 | 2022-05-06 09:51 | 2022-05-16 12:00 | CR0015287 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2022-W19 | 2022-05 | 50 | 48 | 39.0755 | 5 | 2 | 2 | 0.05 | 193522 | 2.8 | 1 | 0 | 0 | 1 |  | 1 | 4 | 26 | 0 | 0 | 2022-03 | 0 | 0
2352 | CR0015287 | CTASK0033165 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 | 2022-05-06 17:22 | 2022-05-04 17:22 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [Deployment] Updating/ Replacing the URL link for those notification sent to customers by 9th May 2022 | 2022-03-31 06:11 | 2022-04-13 22:00 | 2022-04-13 12:16 | 2022-04-29 12:20 | 2022-05-03 14:32 |  | 2022-05-09 08:00 | 2022-05-09 07:57 | 2022-05-06 09:51 | 2022-05-16 12:00 | CR0015287 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2022-W19 | 2022-05 | 50 | 48 | 39.0755 | 5 | 2 | 2 | 0.05 | 193470 | 3 | 1 | 0 | 0 | 1 |  | 1 | 4 | 26 | 0.36842 | 0 | 2022-03 | 0 | 0
2353 | CR0015287 | CTASK0033213 | Closed | OPUS-BKG-IB | Linh Dinh Bo | 18 | 16 | 2022-04-08 11:27 | 2022-03-31 11:27 | Container | Service Management | Booking/Documentation | Outbound Doc | Fax/E-Mail/EDI | Draft B/L & Waybill (Fax/E-Mail) | [Analysis+Development+Testing] Updating/ Replacing the URL link for those notification sent to customers by 9th May 2022 | 2022-03-31 06:11 | 2022-04-13 22:00 | 2022-04-13 12:16 | 2022-04-29 12:20 | 2022-05-03 14:32 |  | 2022-05-09 08:00 | 2022-05-09 07:57 | 2022-05-06 09:51 | 2022-05-16 12:00 | CR0015287 | Service ManagementBooking/DocumentationOutbound DocFax/E-Mail/EDIDraft B/L & Waybill (Fax/E-Mail) | OPUS-BKG-OB | 2022-W19 | 2022-05 | 50 | 48 | 39.0755 | 5 | 2 | 2 | 0.05 | 193522 | 2.8 | 1 | 0 | 0 | 1 |  | 1 | 4 | 26 | 0 | 0 | 2022-03 | 0 | 0
2354 | CR0014572 | CTASK0030171 | Closed | OPUS-BKG-MFT-M | Linh Dinh Bo | 52 | 46 | 2021-11-30 15:01 | 2021-11-01 07:00 | Container | Service Management | Booking/Documentation | Advance Manifest | Canada ACI (Canada Office) | Location of Goods Setup | [Development+Testing+Development] NA *Customs* - Request to Create Inquiry Only Location Of Goods Table | 2021-10-29 07:30 | 2021-11-30 22:00 | 2021-11-25 08:43 | 2021-12-31 08:36 | 2022-01-04 07:43 |  | 2022-01-25 09:00 | 2022-01-25 09:00 | 2022-01-04 16:04 | 2022-02-01 12:00 | CR0014572 | Service ManagementBooking/DocumentationAdvance ManifestCanada ACI (Canada Office)Location of Goods Setup | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 64 | 62 | 88.0623 | 2 | 2 | 1 | 0.03 | 193522 | 2.4 | 1 | 0 | 0 | 1 |  | 2 | 9 | 33 | 0 | 0 | 2021-10 | 0 | 0
2355 | CR0014572 | CTASK0031846 | Closed | OPUS-BKG-MFT-A | Linh Dinh Bo | 12 | 16 | 2022-01-31 14:19 | 2022-01-18 14:19 | Container | Service Management | Booking/Documentation | Advance Manifest | Canada ACI (Canada Office) | Location of Goods Setup | [Testing+Deploy] NA *Customs* - Request to Create Inquiry Only Location Of Goods Table | 2021-10-29 07:30 | 2021-11-30 22:00 | 2021-11-25 08:43 | 2021-12-31 08:36 | 2022-01-04 07:43 |  | 2022-01-25 09:00 | 2022-01-25 09:00 | 2022-01-04 16:04 | 2022-02-01 12:00 | CR0014572 | Service ManagementBooking/DocumentationAdvance ManifestCanada ACI (Canada Office)Location of Goods Setup | OPUS-BKG-MFT-M | 2022-W4 | 2022-01 | 64 | 62 | 88.0623 | 2 | 2 | 1 | 0.03 | 193522 | 2.4 | 1 | 0 | 0 | 1 |  | 2 | 9 | 33 | 0 | 0 | 2021-10 | 0 | 0
2356 | CR0014818 | CTASK0032837 | Closed | OPUS-BKG-MFT-A | Linh Dinh Bo | 8 | 8 | 2022-03-14 13:27 | 2022-03-07 13:27 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Deployment+Testing] Enhancement of Hong Kong Manifest UI - V2 | 2021-12-21 06:30 | 2022-01-31 22:00 | 2022-01-21 13:48 | 2022-02-23 13:08 | 2022-03-07 07:05 |  | 2022-03-15 08:05 | 2022-03-15 08:01 | 2022-03-07 07:56 | 2022-03-22 12:00 | CR0014818 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2022-W11 | 2022-03 | 48 | 48 | 84.0659 | 2 | 1 | 1 | 0.02 | 193522 | 2.6 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2021-12 | 0 | 0
2357 | CR0014818 | CTASK0030968 | Closed | OPUS-BKG-MFT-A | Linh Dinh Bo | 40 | 40 | 2021-12-31 14:52 | 2021-12-01 14:52 | Container | Service Management | Booking/Documentation | Manifest |  |  | [Development+ Testing+ Deployment] Enhancement of Hong Kong Manifest UI - V2 | 2021-12-21 06:30 | 2022-01-31 22:00 | 2022-01-21 13:48 | 2022-02-23 13:08 | 2022-03-07 07:05 |  | 2022-03-15 08:05 | 2022-03-15 08:01 | 2022-03-07 07:56 | 2022-03-22 12:00 | CR0014818 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2022-W11 | 2022-03 | 48 | 48 | 84.0659 | 2 | 1 | 1 | 0.02 | 193522 | 2.6 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2021-12 | 0 | 0
2358 | CR0014234 | CTASK0028270 | Closed | OPUS-ACM | Huynh Tuan Khanh | 94 | 65 | 2021-10-29 11:56 | 2021-08-02 11:56 | Container | Support & Admin | Agent Commission Management | Request |  |  | [CLT Internal] Modification to apply the 'Pay Term' for detailed management of ACM contract | 2021-07-23 13:16 | 2021-08-27 16:16 | 2021-08-27 14:07 | 2022-02-03 11:07 | 2022-02-03 11:55 |  | 2022-02-08 11:40 | 2022-02-08 06:55 | 2022-02-04 11:04 | 2022-02-16 12:00 | CR0014234 | Support & AdminAgent Commission ManagementRequest | OPUS-ACM | 2022-W6 | 2022-02 | 94 | 65 | 199.9332 | 1 | 1 | 1 | 0.01 | 193499 | 2.1 | 1 | 0 | 0 | 1 |  | 3 | 6 | 30 | 0 | 0 | 2021-07 | 0 | 0
2359 | CR0015027 | CTASK0032358 | Closed | OPUS-BKG-M | Quy Truong | 20 | 20 | 2022-02-18 21:47 | 2022-02-14 21:47 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Design] EUA - Add Down Excel buttons to Group VVD Port Assign | 2022-02-28 06:40 | 2022-03-23 22:00 | 2022-03-23 07:25 | 2022-04-08 14:10 | 2022-04-08 14:15 |  | 2022-04-19 08:00 | 2022-04-19 08:00 | 2022-04-12 11:40 | 2022-04-26 12:00 | CR0015027 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2022-W16 | 2022-04 | 66 | 56 | 50.0555 | 5 | 1 | 1 | 0.05 | 203791 | 1.4 | 1 | 2 | 0 | 1 |  | 2 | 4 | 18 | 0 | 0 | 2022-02 | 2 | 1
2360 | CR0015027 | CTASK0032362 | Closed | OPUS-BKG-M | Quy Truong | 30 | 20 | 2022-03-04 13:05 | 2022-03-01 13:05 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Development] EUA - Add Down Excel buttons to Group VVD Port Assign | 2022-02-28 06:40 | 2022-03-23 22:00 | 2022-03-23 07:25 | 2022-04-08 14:10 | 2022-04-08 14:15 |  | 2022-04-19 08:00 | 2022-04-19 08:00 | 2022-04-12 11:40 | 2022-04-26 12:00 | CR0015027 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2022-W16 | 2022-04 | 66 | 56 | 50.0555 | 5 | 1 | 1 | 0.05 | 203791 | 1.4 | 1 | 2 | 0 | 1 |  | 2 | 4 | 18 | 0 | 0 | 2022-02 | 2 | 1
2361 | CR0015027 | CTASK0032365 | Closed | OPUS-BKG-M | Quy Truong | 8 | 8 | 2022-03-05 | 2022-02-28 08:00 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Deployment]EUA - Add Down Excel buttons to Group VVD Port Assign | 2022-02-28 06:40 | 2022-03-23 22:00 | 2022-03-23 07:25 | 2022-04-08 14:10 | 2022-04-08 14:15 |  | 2022-04-19 08:00 | 2022-04-19 08:00 | 2022-04-12 11:40 | 2022-04-26 12:00 | CR0015027 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2022-W16 | 2022-04 | 66 | 56 | 50.0555 | 5 | 1 | 1 | 0.05 | 203791 | 1.4 | 1 | 2 | 0 | 1 |  | 2 | 4 | 18 | 0 | 0 | 2022-02 | 2 | 1
2362 | CR0015027 | CTASK0032392 | Closed | OPUS-BKG-M | Quy Truong | 1 | 1 |  | 2022-02-24 13:06 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [TAS] EUA - Add Down Excel buttons to Group VVD Port Assign | 2022-02-28 06:40 | 2022-03-23 22:00 | 2022-03-23 07:25 | 2022-04-08 14:10 | 2022-04-08 14:15 |  | 2022-04-19 08:00 | 2022-04-19 08:00 | 2022-04-12 11:40 | 2022-04-26 12:00 | CR0015027 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2022-W16 | 2022-04 | 66 | 56 | 50.0555 | 5 | 1 | 1 | 0.05 | 203791 | 1.4 | 1 | 2 | 0 | 1 |  | 2 | 4 | 18 | 0 | 0 | 2022-02 | 2 | 1
2363 | CR0015027 | CTASK0032363 | Closed | OPUS-BKG-M | Quy Truong | 8 | 8 | 2022-03-18 13:06 | 2022-03-14 13:05 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Group VVD/Port Assign | [Testing]EUA - Add Down Excel buttons to Group VVD Port Assign | 2022-02-28 06:40 | 2022-03-23 22:00 | 2022-03-23 07:25 | 2022-04-08 14:10 | 2022-04-08 14:15 |  | 2022-04-19 08:00 | 2022-04-19 08:00 | 2022-04-12 11:40 | 2022-04-26 12:00 | CR0015027 | Service ManagementBooking/DocumentationOperationTransshipmentGroup VVD/Port Assign | OPUS-BKG-M | 2022-W16 | 2022-04 | 66 | 56 | 50.0555 | 5 | 1 | 1 | 0.05 | 203791 | 1.4 | 1 | 2 | 0 | 1 |  | 2 | 4 | 18 | 0 | 0 | 2022-02 | 2 | 1
2364 | CR0014233 | CTASK0030078 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 6 | 6 | 2021-10-19 08:42 | 2021-10-18 08:42 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Deployment] Change logic for VVD extraction in flat file (SR0138776) | 2021-09-03 07:27 | 2021-09-24 07:27 | 2021-09-23 12:29 | 2021-09-30 14:31 | 2021-10-12 14:04 |  | 2021-10-26 09:57 | 2021-10-26 10:00 | 2021-10-18 11:23 | 2021-11-02 12:00 | CR0014233 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2021-W43 | 2021-10 | 44 | 46 | 53.1043 | 2 | 1 | 1 | 0.04 | 193512 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.2963 | 0 | 2021-09 | 0 | 0
2365 | CR0014233 | CTASK0028781 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 38 | 40 | 2021-08-27 08:35 | 2021-08-11 08:35 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Notice Send | [Development+ Testing+ Deployment] Change logic for VVD extraction in flat file (SR0138776) | 2021-09-03 07:27 | 2021-09-24 07:27 | 2021-09-23 12:29 | 2021-09-30 14:31 | 2021-10-12 14:04 |  | 2021-10-26 09:57 | 2021-10-26 10:00 | 2021-10-18 11:23 | 2021-11-02 12:00 | CR0014233 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Notice Send | OPUS-BKG-IB | 2021-W43 | 2021-10 | 44 | 46 | 53.1043 | 2 | 1 | 1 | 0.04 | 193512 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.2963 | 0 | 2021-09 | 0 | 0
2366 | CR0013973 | CTASK0028429 | Closed | OPUS-BKG-M | Loc Tran | 30 | 30 | 2021-08-31 15:17 | 2021-08-02 15:17 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Development]LA - Logistics Vendor Setup changes to split EDI 301M for MTY Release Order submissions | 2021-08-03 09:25 | 2021-09-01 22:00 | 2021-09-01 14:20 | 2022-03-22 14:56 | 2022-03-22 15:22 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-23 16:36 | 2022-04-12 12:00 | CR0013973 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2022-W14 | 2022-04 | 62 | 59 | 244.9413 | 4 | 1 | 2 | 0.01 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 3 | 6 | 18 | 0.33333 | 0 | 2021-08 | 0 | 0
2367 | CR0013973 | CTASK0028430 | Closed | OPUS-BKG-M | Loc Tran | 18 | 15 | 2021-08-31 15:17 | 2021-08-02 15:17 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Testing] LA - Logistics Vendor Setup changes to split EDI 301M for MTY Release Order submissions | 2021-08-03 09:25 | 2021-09-01 22:00 | 2021-09-01 14:20 | 2022-03-22 14:56 | 2022-03-22 15:22 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-23 16:36 | 2022-04-12 12:00 | CR0013973 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2022-W14 | 2022-04 | 62 | 59 | 244.9413 | 4 | 1 | 2 | 0.01 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 3 | 6 | 18 | 0.33333 | 0 | 2021-08 | 0 | 0
2368 | CR0013973 | CTASK0028432 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2022-03-30 21:37 | 2022-03-29 06:37 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Deployment] LA - Logistics Vendor Setup changes to split EDI 301M for MTY Release Order submissions | 2021-08-03 09:25 | 2021-09-01 22:00 | 2021-09-01 14:20 | 2022-03-22 14:56 | 2022-03-22 15:22 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-23 16:36 | 2022-04-12 12:00 | CR0013973 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2022-W14 | 2022-04 | 62 | 59 | 244.9413 | 4 | 1 | 2 | 0.01 | 193594 | 1.9 | 1 | 0 | 0 | 1 |  | 3 | 6 | 18 | 0 | 0 | 2021-08 | 0 | 0
2369 | CR0013973 | CTASK0028428 | Closed | OPUS-BKG-M | Loc Tran | 10 | 10 | 2021-07-31 14:46 | 2021-07-01 14:46 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Empty Container Release Order | [Design]LA - Logistics Vendor Setup changes to split EDI 301M for MTY Release Order submissions | 2021-08-03 09:25 | 2021-09-01 22:00 | 2021-09-01 14:20 | 2022-03-22 14:56 | 2022-03-22 15:22 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-23 16:36 | 2022-04-12 12:00 | CR0013973 | Service ManagementBooking/DocumentationBookingFax/Email/EDIEmpty Container Release Order | OPUS-BKG-M | 2022-W14 | 2022-04 | 62 | 59 | 244.9413 | 4 | 1 | 2 | 0.01 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 3 | 6 | 18 | 0.33333 | 0 | 2021-08 | 0 | 0
2370 | CR0013474 | CTASK0026069 | Closed | OPUS-SPC | Toai Phan | 20 | 20 |  |  | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | Master Constraint Table (MCT) to feature 'utilisation' pop-up in EQ Availability Tab | 2021-03-23 06:56 | 2021-04-09 22:00 | 2021-04-08 15:07 | 2021-12-20 08:06 | 2021-12-27 07:30 |  | 2022-01-04 08:00 | 2022-01-04 08:07 | 2021-12-29 16:21 | 2022-01-11 12:00 | CR0013474 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W1 | 2022-01 | 20 | 20 | 287.0446 | 1 | 1 | 1 | 0 | 183427 | 2.3 | 0 | 0 | 0 | 1 |  | 3 | 3 | 33 | 0 | 0 | 2021-03 | 0 | 0
2371 | CR0014195 | CTASK0028147 | Closed | OPUS-BKG-EBKG | Vinh Tran | 18 | 18 | 2021-07-15 | 2021-07-12 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] [CLT Internal] e-Booking Upload modification to enable Dry + Special cargo (Mixed) upload | 2021-07-23 06:06 | 2021-09-10 22:00 | 2021-09-10 08:28 | 2021-09-28 13:46 | 2021-09-28 13:46 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-28 14:23 | 2021-10-12 12:00 | CR0014195 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W40 | 2021-10 | 57 | 50 | 74.0789 | 3 | 1 | 1 | 0.03 | 193525 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.41667 | 0.16667 | 2021-07 | 0 | 0
2372 | CR0014195 | CTASK0028155 | Closed | OPUS-BKG-EBKG | Vinh Tran | 35 | 28 | 2021-08-24 | 2021-07-23 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development+Test] [CLT Internal] e-Booking Upload modification to enable Dry + Special cargo (Mixed) upload | 2021-07-23 06:06 | 2021-09-10 22:00 | 2021-09-10 08:28 | 2021-09-28 13:46 | 2021-09-28 13:46 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-28 14:23 | 2021-10-12 12:00 | CR0014195 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W40 | 2021-10 | 57 | 50 | 74.0789 | 3 | 1 | 1 | 0.03 | 193525 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.41667 | 0.16667 | 2021-07 | 0 | 0
2373 | CR0014195 | CTASK0028156 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-10-02 | 2021-10-01 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] [CLT Internal] e-Booking Upload modification to enable Dry + Special cargo (Mixed) upload | 2021-07-23 06:06 | 2021-09-10 22:00 | 2021-09-10 08:28 | 2021-09-28 13:46 | 2021-09-28 13:46 |  | 2021-10-05 08:00 | 2021-10-05 08:00 | 2021-09-28 14:23 | 2021-10-12 12:00 | CR0014195 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W40 | 2021-10 | 57 | 50 | 74.0789 | 3 | 1 | 1 | 0.03 | 193525 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.41667 | 0.16667 | 2021-07 | 0 | 0
2374 | CR0014464 | CTASK0030083 | Closed | OPUS-SPC | Toai Phan | 18 | 15 |  |  | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [ENHANCEMENT] LA - Comm - Standby - TTL Weight logic | 2021-11-25 13:54 | 2021-12-17 22:00 | 2021-12-17 09:06 | 2022-02-03 06:47 | 2022-02-03 07:08 |  | 2022-02-15 08:00 | 2022-02-15 08:23 | 2022-02-09 07:27 | 2022-02-22 12:00 | CR0014464 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2022-W7 | 2022-02 | 18 | 15 | 81.754 | 1 | 1 | 1 | 0.01 | 183427 | 3 | 0 | 0 | 0 | 1 |  | 2 | 10 | 30 | 0 | 0 | 2021-11 | 0 | 0
2375 | CR0014377 | CTASK0029896 | Closed | OPUS-BKG-M | Kieu Le | 32 | 32 | 2021-10-25 20:56 | 2021-10-13 00:56 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Development][LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 153106 | 3 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.22951 | 0.13043 | 2021-09 | 1 | 1
2376 | CR0014377 | CTASK0032401 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 4 | 4 | 2022-02-22 14:37 | 2022-02-15 14:37 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Deployment] [LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 193512 | 2.3 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.2963 | 0 | 2021-09 | 1 | 1
2377 | CR0014377 | CTASK0029899 | Closed | OPUS-BKG-M | Kieu Le | 2 | 2 | 2022-02-18 12:02 | 2022-02-14 12:02 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Deployment] [LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 153106 | 3 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.22951 | 0.13043 | 2021-09 | 1 | 1
2378 | CR0014377 | CTASK0029374 | Closed | OPUS-MDA | Ngan Nham | 34 | 34 | 2021-10-31 23:00 | 2021-09-30 23:00 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Development] [LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 193461 | 2.8 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.125 | 0 | 2021-09 | 1 | 1
2379 | CR0014377 | CTASK0029929 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 4 | 4 | 2021-10-29 13:16 | 2021-10-14 13:16 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Deployment] [LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 193512 | 2.3 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.2963 | 0 | 2021-09 | 1 | 1
2380 | CR0014377 | CTASK0029928 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 7 | 8 | 2021-10-19 13:15 | 2021-10-15 13:15 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Testing] [LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 193512 | 2.3 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.2963 | 0 | 2021-09 | 1 | 1
2381 | CR0014377 | CTASK0031203 | Closed | OPUS-BKG-EBKG | Vinh Tran | 6 | 6 | 2021-12-16 | 2021-12-13 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Testing] [LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 193525 | 2.3 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.41667 | 0.16667 | 2021-09 | 1 | 1
2382 | CR0014377 | CTASK0029927 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 27 | 27 | 2021-10-14 13:13 | 2021-10-11 07:13 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Development][LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 193512 | 2.3 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.2963 | 0 | 2021-09 | 1 | 1
2383 | CR0014377 | CTASK0030191 | Closed | OPUS-PRI | Ngan Nham | 8 | 8 | 2022-02-28 22:00 | 2022-02-13 23:00 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Deployment] [LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 193461 | 2.8 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.125 | 0 | 2021-09 | 1 | 1
2384 | CR0014377 | CTASK0029897 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-11-05 20:58 | 2021-11-01 00:58 | Container | Biz Common | Master Data | Partner | Customer Integration |  | [Testing] [LA ENHANCEMENT] - Inclusion of Tax payer ID information | 2021-09-29 06:28 | 2021-11-05 23:00 | 2021-10-29 09:27 | 2022-02-04 07:46 | 2022-02-09 15:29 |  | 2022-02-22 10:00 | 2022-02-22 09:30 | 2022-02-11 07:39 | 2022-03-01 12:00 | CR0014377 | Biz CommonMaster DataPartnerCustomer Integration | OPUS-MDA | 2022-W8 | 2022-02 | 124 | 127 | 146.1474 | 10 | 5 | 4 | 0.04 | 153106 | 3 | 2 | 0 | 1 | 2 |  | 2 | 14 | 30 | 0.22951 | 0.13043 | 2021-09 | 1 | 1
2385 | CR0013994 | CTASK0027451 | Closed | OPUS-TPB | Manh Nguyen | 13 | 20 | 2021-06-30 20:00 | 2021-06-01 | Container | Service Management | 3rd Party Billing |  |  |  | [202106] JO TPB Auto Interface - An extension for CR0013207 | 2021-07-05 12:27 | 2021-09-10 22:26 | 2021-09-08 12:27 | 2021-10-18 09:57 | 2021-10-18 13:43 |  | 2021-10-26 09:30 | 2021-10-26 07:51 | 2021-10-21 12:38 | 2021-11-02 12:00 | CR0013994 | Service Management3rd Party Billing | OPUS-TPB | 2021-W43 | 2021-10 | 70 | 92 | 112.8772 | 6 | 1 | 1 | 0.03 | 153138 | 2.8 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.16667 | 0.16667 | 2021-07 | 0 | 0
2386 | CR0013994 | CTASK0029687 | Closed | OPUS-TPB | Manh Nguyen | 6 | 6 | 2021-10-29 20:00 | 2021-10-01 04:00 | Container | Service Management | 3rd Party Billing |  |  |  | [202110] JO TPB Auto Interface - An extension for CR0013207 | 2021-07-05 12:27 | 2021-09-10 22:26 | 2021-09-08 12:27 | 2021-10-18 09:57 | 2021-10-18 13:43 |  | 2021-10-26 09:30 | 2021-10-26 07:51 | 2021-10-21 12:38 | 2021-11-02 12:00 | CR0013994 | Service Management3rd Party Billing | OPUS-TPB | 2021-W43 | 2021-10 | 70 | 92 | 112.8772 | 6 | 1 | 1 | 0.03 | 153138 | 2.8 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.16667 | 0.16667 | 2021-07 | 0 | 0
2387 | CR0013994 | CTASK0027163 | Closed | OPUS-TPB | Manh Nguyen | 8 | 8 | 2021-05-31 20:00 | 2021-05-01 | Container | Service Management | 3rd Party Billing |  |  |  | [202105] JO TPB Auto Interface - An extension for CR0013207 | 2021-07-05 12:27 | 2021-09-10 22:26 | 2021-09-08 12:27 | 2021-10-18 09:57 | 2021-10-18 13:43 |  | 2021-10-26 09:30 | 2021-10-26 07:51 | 2021-10-21 12:38 | 2021-11-02 12:00 | CR0013994 | Service Management3rd Party Billing | OPUS-TPB | 2021-W43 | 2021-10 | 70 | 92 | 112.8772 | 6 | 1 | 1 | 0.03 | 153138 | 2.8 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.16667 | 0.16667 | 2021-07 | 0 | 0
2388 | CR0013994 | CTASK0028506 | Closed | OPUS-TPB | Manh Nguyen | 29 | 30 | 2021-08-31 22:00 | 2021-07-31 23:00 | Container | Service Management | 3rd Party Billing |  |  |  | [202108] JO TPB Auto Interface - An extension for CR0013207 | 2021-07-05 12:27 | 2021-09-10 22:26 | 2021-09-08 12:27 | 2021-10-18 09:57 | 2021-10-18 13:43 |  | 2021-10-26 09:30 | 2021-10-26 07:51 | 2021-10-21 12:38 | 2021-11-02 12:00 | CR0013994 | Service Management3rd Party Billing | OPUS-TPB | 2021-W43 | 2021-10 | 70 | 92 | 112.8772 | 6 | 1 | 1 | 0.03 | 153138 | 2.8 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.16667 | 0.16667 | 2021-07 | 0 | 0
2389 | CR0013994 | CTASK0029124 | Closed | OPUS-TPB | Manh Nguyen | 6 | 8 | 2021-09-30 22:00 | 2021-09-01 | Container | Service Management | 3rd Party Billing |  |  |  | [202109] JO TPB Auto Interface - An extension for CR0013207 | 2021-07-05 12:27 | 2021-09-10 22:26 | 2021-09-08 12:27 | 2021-10-18 09:57 | 2021-10-18 13:43 |  | 2021-10-26 09:30 | 2021-10-26 07:51 | 2021-10-21 12:38 | 2021-11-02 12:00 | CR0013994 | Service Management3rd Party Billing | OPUS-TPB | 2021-W43 | 2021-10 | 70 | 92 | 112.8772 | 6 | 1 | 1 | 0.03 | 153138 | 2.8 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.16667 | 0.16667 | 2021-07 | 0 | 0
2390 | CR0013994 | CTASK0027902 | Closed | OPUS-TPB | Manh Nguyen | 22 | 20 | 2021-07-30 22:00 | 2021-07-01 | Container | Service Management | 3rd Party Billing |  |  |  | [202107] JO TPB Auto Interface - An extension for CR0013207 | 2021-07-05 12:27 | 2021-09-10 22:26 | 2021-09-08 12:27 | 2021-10-18 09:57 | 2021-10-18 13:43 |  | 2021-10-26 09:30 | 2021-10-26 07:51 | 2021-10-21 12:38 | 2021-11-02 12:00 | CR0013994 | Service Management3rd Party Billing | OPUS-TPB | 2021-W43 | 2021-10 | 70 | 92 | 112.8772 | 6 | 1 | 1 | 0.03 | 153138 | 2.8 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.16667 | 0.16667 | 2021-07 | 0 | 0
2391 | CR0013701 | CTASK0025958 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 4 | 4 | 2021-03-18 | 2021-03-18 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Estimate]MEXICO [enhancement]// Customs submission // X12 XML // Customs result 355 and 997 on OPUS screen | 2021-03-30 14:21 | 2021-04-02 22:00 | 2021-03-31 12:28 | 2021-09-30 08:08 | 2022-01-28 20:19 |  | 2022-01-31 08:00 | 2022-01-31 08:00 | 2022-01-29 07:20 | 2022-02-07 12:00 | CR0013701 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 73 | 52 | 306.7355 | 4 | 1 | 1 | 0.01 | 193506 | 1.8 | 1 | 0 | 0 | 1 |  | 4 | 3 | 33 | 1.1212 | 1.25 | 2021-03 | 0 | 0
2392 | CR0013701 | CTASK0025743 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 36 | 16 | 2021-03-19 | 2021-03-15 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Test]MEXICO [enhancement]// Customs submission // X12 XML // Customs result 355 and 997 on OPUS screen | 2021-03-30 14:21 | 2021-04-02 22:00 | 2021-03-31 12:28 | 2021-09-30 08:08 | 2022-01-28 20:19 |  | 2022-01-31 08:00 | 2022-01-31 08:00 | 2022-01-29 07:20 | 2022-02-07 12:00 | CR0013701 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 73 | 52 | 306.7355 | 4 | 1 | 1 | 0.01 | 193506 | 1.8 | 1 | 0 | 0 | 1 |  | 4 | 3 | 33 | 1.1212 | 1.25 | 2021-03 | 0 | 0
2393 | CR0013701 | CTASK0026454 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 2 | 2 | 2021-04-13 | 2021-04-13 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Dev-Test-Feedback]MEXICO [enhancement]// Customs submission // X12 XML // Customs result 355 and 997 on OPUS screen | 2021-03-30 14:21 | 2021-04-02 22:00 | 2021-03-31 12:28 | 2021-09-30 08:08 | 2022-01-28 20:19 |  | 2022-01-31 08:00 | 2022-01-31 08:00 | 2022-01-29 07:20 | 2022-02-07 12:00 | CR0013701 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 73 | 52 | 306.7355 | 4 | 1 | 1 | 0.01 | 193506 | 1.8 | 1 | 0 | 0 | 1 |  | 4 | 3 | 33 | 1.1212 | 1.25 | 2021-03 | 0 | 0
2394 | CR0013701 | CTASK0025742 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 31 | 30 | 2021-03-31 | 2021-03-09 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Dev]MEXICO [enhancement]// Customs submission // X12 XML // Customs result 355 and 997 on OPUS screen | 2021-03-30 14:21 | 2021-04-02 22:00 | 2021-03-31 12:28 | 2021-09-30 08:08 | 2022-01-28 20:19 |  | 2022-01-31 08:00 | 2022-01-31 08:00 | 2022-01-29 07:20 | 2022-02-07 12:00 | CR0013701 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 73 | 52 | 306.7355 | 4 | 1 | 1 | 0.01 | 193506 | 1.8 | 1 | 0 | 0 | 1 |  | 4 | 3 | 33 | 1.1212 | 1.25 | 2021-03 | 0 | 0
2395 | CR0014472 | CTASK0029555 | Closed | OPUS-DMT | Cuong Nguyen | 35 | 47 | 2021-10-31 12:10 | 2021-10-18 12:09 | Container | Service Management | Demurrage/Detention | Billing | Invoice Creation & Issue |  | [CTASK2] CLV_Design_Analysis_Development_Test_Deployment | 2021-10-12 09:49 | 2021-10-30 09:49 | 2021-10-29 06:40 | 2021-12-01 11:09 | 2021-12-01 11:26 |  | 2021-12-07 11:26 | 2021-12-07 11:21 | 2021-12-02 15:15 | 2021-12-14 12:01 | CR0014472 | Service ManagementDemurrage/DetentionBillingInvoice Creation & Issue | OPUS-DMT | 2021-W49 | 2021-12 | 35 | 47 | 56.0669 | 1 | 1 | 1 | 0.03 | 193529 | 2.4 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.11538 | 0.22222 | 2021-10 | 0 | 0
2396 | CR0013912 | CTASK0027395 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 15 | 48 | 2021-07-31 11:20 | 2021-07-01 11:19 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Test, Deploy] ROOT Project Squad 16 - Booking Reconciliation Process - CCAM Filing (check points validation) | 2021-06-07 07:25 | 2021-07-28 22:00 | 2021-07-28 15:34 | 2021-11-03 17:14 | 2021-11-29 14:15 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-12-02 13:00 | 2021-12-14 12:01 | CR0013912 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 100 | 158 | 183.0243 | 4 | 1 | 1 | 0.04 | 193606 | 1.6 | 1 | 0 | 0 | 2 |  | 3 | 10 | 26 | 4.25 | 2.25 | 2021-06 | 0 | 0
2397 | CR0013912 | CTASK0027394 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 74 | 100 |  |  | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Devevlop] ROOT Project Squad 16 - Booking Reconciliation Process - CCAM Filing (check points validation) | 2021-06-07 07:25 | 2021-07-28 22:00 | 2021-07-28 15:34 | 2021-11-03 17:14 | 2021-11-29 14:15 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-12-02 13:00 | 2021-12-14 12:01 | CR0013912 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 100 | 158 | 183.0243 | 4 | 1 | 1 | 0.04 | 193606 | 1.6 | 1 | 0 | 0 | 2 |  | 3 | 10 | 26 | 4.25 | 2.25 | 2021-06 | 0 | 0
2398 | CR0013912 | CTASK0027392 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 8 | 10 | 2021-07-31 11:18 | 2021-07-01 11:18 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Design] ROOT Project Squad 16 - Booking Reconciliation Process - CCAM Filing (check points validation) | 2021-06-07 07:25 | 2021-07-28 22:00 | 2021-07-28 15:34 | 2021-11-03 17:14 | 2021-11-29 14:15 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-12-02 13:00 | 2021-12-14 12:01 | CR0013912 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 100 | 158 | 183.0243 | 4 | 1 | 1 | 0.04 | 193606 | 1.6 | 1 | 0 | 0 | 2 |  | 3 | 10 | 26 | 4.25 | 2.25 | 2021-06 | 0 | 0
2399 | CR0013912 | CTASK0030964 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 3 | 3 | 2021-12-31 09:38 | 2021-12-01 09:38 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [PROD] ROOT Project Squad 16 - Booking Reconciliation Process - CCAM Filing (check points validation) | 2021-06-07 07:25 | 2021-07-28 22:00 | 2021-07-28 15:34 | 2021-11-03 17:14 | 2021-11-29 14:15 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-12-02 13:00 | 2021-12-14 12:01 | CR0013912 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 100 | 158 | 183.0243 | 4 | 1 | 1 | 0.04 | 193606 | 1.6 | 1 | 0 | 0 | 2 |  | 3 | 10 | 26 | 4.25 | 2.25 | 2021-06 | 0 | 0
2400 | CR0013420 | CTASK0028404 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 42 | 37 | 2021-08-13 13:09 | 2021-07-26 13:09 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | B/L Copy Send | [Development+ Testing+ Deployment] LA - CSVC - Request for logic change in NNL BL Copy send (Email contacts) | 2021-07-22 11:31 | 2021-08-30 21:30 | 2021-08-25 15:16 | 2021-11-25 16:41 | 2021-11-26 08:44 |  | 2021-12-07 08:43 | 2021-12-14 14:14 | 2021-12-01 09:35 | 2021-12-22 12:00 | CR0013420 | Service ManagementBooking/DocumentationInbound DocArrival NoticeB/L Copy Send | OPUS-BKG-IB | 2021-W49 | 2021-12 | 74 | 71 | 137.8838 | 3 | 1 | 1 | 0.02 | 193512 | 2.1 | 2 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.2963 | 0 | 2021-07 | 0 | 0
2401 | CR0013420 | CTASK0028139 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 19 | 19 | 2021-07-19 13:24 | 2021-07-12 13:24 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | B/L Copy Send | [Estimation] LA - CSVC - Request for logic change in NNL BL Copy send (Email contacts) | 2021-07-22 11:31 | 2021-08-30 21:30 | 2021-08-25 15:16 | 2021-11-25 16:41 | 2021-11-26 08:44 |  | 2021-12-07 08:43 | 2021-12-14 14:14 | 2021-12-01 09:35 | 2021-12-22 12:00 | CR0013420 | Service ManagementBooking/DocumentationInbound DocArrival NoticeB/L Copy Send | OPUS-BKG-IB | 2021-W49 | 2021-12 | 74 | 71 | 137.8838 | 3 | 1 | 1 | 0.02 | 193512 | 2.1 | 2 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.2963 | 0 | 2021-07 | 0 | 0
2402 | CR0013420 | CTASK0031062 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 13 | 15 | 2021-12-31 17:47 | 2021-12-01 17:47 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | B/L Copy Send | [PROD] LA - CSVC - Request for logic change in NNL BL Copy send (Email contacts) | 2021-07-22 11:31 | 2021-08-30 21:30 | 2021-08-25 15:16 | 2021-11-25 16:41 | 2021-11-26 08:44 |  | 2021-12-07 08:43 | 2021-12-14 14:14 | 2021-12-01 09:35 | 2021-12-22 12:00 | CR0013420 | Service ManagementBooking/DocumentationInbound DocArrival NoticeB/L Copy Send | OPUS-BKG-IB | 2021-W49 | 2021-12 | 74 | 71 | 137.8838 | 3 | 1 | 1 | 0.02 | 193512 | 2.1 | 2 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.2963 | 0 | 2021-07 | 0 | 0
2403 | CR0014989 | CTASK0032438 | Closed | OPUS-JOO | Huy Vu | 34 | 31 | 2022-02-18 22:00 | 2022-02-15 07:00 | Container | Support & Admin | Joint Operation | Settlement |  |  | [CLT-Internal]-Clipboard function on amount column in JOO | 2022-02-16 10:35 | 2022-03-11 20:00 | 2022-03-11 14:16 | 2022-03-21 07:35 | 2022-03-23 14:49 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-28 15:26 | 2022-04-13 12:00 | CR0014989 | Support & AdminJoint OperationSettlement | OPUS-JOO | 2022-W14 | 2022-04 | 39 | 36 | 47.8921 | 3 | 1 | 2 | 0.03 | 193618 | 2 | 1 | 2 | 0 | 1 |  | 1 | 6 | 18 | 0 | 0 | 2022-02 | 2 | 1
2404 | CR0014989 | CTASK0032222 | Closed | OPUS-JOO | Huy Vu | 1 | 1 |  |  | Container | Support & Admin | Joint Operation | Settlement |  |  | [Document][CLT-Internal]-Clipboard function on amount column in JOO | 2022-02-16 10:35 | 2022-03-11 20:00 | 2022-03-11 14:16 | 2022-03-21 07:35 | 2022-03-23 14:49 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-28 15:26 | 2022-04-13 12:00 | CR0014989 | Support & AdminJoint OperationSettlement | OPUS-JOO | 2022-W14 | 2022-04 | 39 | 36 | 47.8921 | 3 | 1 | 2 | 0.03 | 193618 | 2 | 1 | 2 | 0 | 1 |  | 1 | 6 | 18 | 0 | 0 | 2022-02 | 2 | 1
2405 | CR0014989 | CTASK0032763 | Closed | OPUS-JOO | Linh Nguyen | 5 | 5 | 2022-03-31 13:01 | 2022-03-01 13:01 | Container | Support & Admin | Joint Operation | Settlement |  |  | [CLV-JOO][[CLT-Internal]-Clipboard function on amount column in JOO] | 2022-02-16 10:35 | 2022-03-11 20:00 | 2022-03-11 14:16 | 2022-03-21 07:35 | 2022-03-23 14:49 |  | 2022-04-05 08:00 | 2022-04-05 08:00 | 2022-03-28 15:26 | 2022-04-13 12:00 | CR0014989 | Support & AdminJoint OperationSettlement | OPUS-JOO | 2022-W14 | 2022-04 | 39 | 36 | 47.8921 | 3 | 1 | 2 | 0.03 | 193464 | 3 | 1 | 2 | 0 | 1 |  | 1 | 6 | 18 | 0.375 | 1.5 | 2022-02 | 2 | 1
2406 | CR0013809 | CTASK0028660 | Closed | OPUS-BKG-MFT-E | Thuc Tran | 31 | 32 | 2021-08-09 17:30 | 2021-08-02 09:30 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [Development+Testing+Deployment] (HBA) EUA EDI AUTH ¦ Adding Load indication and selection criteria in the EUA Customs EDI form | 2021-08-03 14:01 | 2021-09-30 22:00 | 2021-09-14 14:23 | 2021-10-07 11:45 | 2021-12-02 08:55 |  | 2021-12-28 08:00 | 2021-12-28 08:22 | 2021-12-02 13:17 | 2022-01-04 12:00 | CR0013809 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2021-W52 | 2021-12 | 31 | 32 | 146.7495 | 1 | 1 | 1 | 0.01 | 173280 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.375 | 1 | 2021-08 | 0 | 0
2407 | CR0015111 | CTASK0032330 | Closed | OPUS-SCG | Lanh Le | 20 | 20 | 2022-03-18 17:30 | 2022-02-21 08:00 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [Documentation][CLT internal] Logic change request for SAME EDI REF NO //FOR DIFFERENT LOADING | 2022-02-17 08:21 | 2022-04-08 17:30 | 2022-04-07 15:13 | 2022-05-06 10:01 | 2022-05-06 10:09 |  | 2022-05-17 17:30 | 2022-05-17 09:54 | 2022-05-09 13:46 | 2022-05-24 12:00 | CR0015111 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W20 | 2022-05 | 65 | 65 | 89.3814 | 2 | 1 | 1 | 0.03 | 183422 | 3.3 | 3 | 0 | 0 | 1 |  | 2 | 8 | 26 | 0 | 0 | 2022-02 | 0 | 0
2408 | CR0015111 | CTASK0032332 | Closed | OPUS-SCG | Lanh Le | 45 | 45 | 2022-03-18 12:54 | 2022-02-21 12:54 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | [CLV] [CLT Internal] Logic change request for SAME EDI REF NO //FOR DIFFERENT LOADING | 2022-02-17 08:21 | 2022-04-08 17:30 | 2022-04-07 15:13 | 2022-05-06 10:01 | 2022-05-06 10:09 |  | 2022-05-17 17:30 | 2022-05-17 09:54 | 2022-05-09 13:46 | 2022-05-24 12:00 | CR0015111 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W20 | 2022-05 | 65 | 65 | 89.3814 | 2 | 1 | 1 | 0.03 | 183422 | 3.3 | 3 | 0 | 0 | 1 |  | 2 | 8 | 26 | 0 | 0 | 2022-02 | 0 | 0
2409 | CR0014996 | CTASK0031807 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 1 | 1 |  |  | Container | Service Management | Booking/Documentation | Report | VGM Dashboard |  | [Design] Adding via Channel as "APP" in VGM Dashboard and eCommerce VGM Info search | 2022-01-24 14:37 | 2022-01-27 22:00 | 2022-01-26 08:52 | 2022-02-08 06:53 | 2022-02-08 08:14 |  | 2022-02-09 08:00 | 2022-02-09 08:27 | 2022-02-09 06:49 | 2022-02-16 12:00 | CR0014996 | Service ManagementBooking/DocumentationReportVGM Dashboard | OPUS-BKG-RPT | 2022-W6 | 2022-02 | 17 | 22 | 15.7245 | 2 | 2 | 2 | 0.06 | 193488 | 2.6 | 2 | 0 | 0 | 1 |  | 1 | 6 | 30 | 0.53659 | 0 | 2022-01 | 0 | 0
2410 | CR0014996 | CTASK0031782 | Closed | OPUS-BKG-RPT | Nam Nguyen | 17 | 22 | 2022-02-18 15:17 | 2022-01-21 15:16 | Container | Service Management | Booking/Documentation | Report | VGM Dashboard |  | [RPT] Adding via Channel as "APP" in VGM Dashboard and eCommerce VGM Info search | 2022-01-24 14:37 | 2022-01-27 22:00 | 2022-01-26 08:52 | 2022-02-08 06:53 | 2022-02-08 08:14 |  | 2022-02-09 08:00 | 2022-02-09 08:27 | 2022-02-09 06:49 | 2022-02-16 12:00 | CR0014996 | Service ManagementBooking/DocumentationReportVGM Dashboard | OPUS-BKG-RPT | 2022-W6 | 2022-02 | 17 | 22 | 15.7245 | 2 | 2 | 2 | 0.06 | 123048 | 3.3 | 2 | 0 | 0 | 1 |  | 1 | 6 | 30 | 0.22222 | 0 | 2022-01 | 0 | 0
2411 | CR0014390 | CTASK0029288 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [TG] EUA - Add Soft Stop warning in TRO/I if shipment is not Release Ready | 2021-09-28 06:21 | 2021-10-28 | 2021-10-20 09:14 | 2021-11-22 11:59 | 2021-11-22 12:13 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-23 15:30 | 2021-12-15 12:00 | CR0014390 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W49 | 2021-12 | 80 | 84 | 70.0684 | 5 | 1 | 1 | 0.05 | 193567 | 2.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.5625 | 0 | 2021-09 | 0 | 0
2412 | CR0014390 | CTASK0029290 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-12-07 08:12 | 2021-11-29 08:12 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] EUA - Add Soft Stop warning in TRO/I if shipment is not Release Ready | 2021-09-28 06:21 | 2021-10-28 | 2021-10-20 09:14 | 2021-11-22 11:59 | 2021-11-22 12:13 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-23 15:30 | 2021-12-15 12:00 | CR0014390 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W49 | 2021-12 | 80 | 84 | 70.0684 | 5 | 1 | 1 | 0.05 | 193567 | 2.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.5625 | 0 | 2021-09 | 0 | 0
2413 | CR0014390 | CTASK0029287 | Closed | OPUS-BKG-M | Thien Lai | 8 | 8 | 2021-10-08 09:11 | 2021-09-13 09:11 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] EUA - Add Soft Stop warning in TRO/I if shipment is not Release Ready | 2021-09-28 06:21 | 2021-10-28 | 2021-10-20 09:14 | 2021-11-22 11:59 | 2021-11-22 12:13 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-23 15:30 | 2021-12-15 12:00 | CR0014390 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W49 | 2021-12 | 80 | 84 | 70.0684 | 5 | 1 | 1 | 0.05 | 193567 | 2.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.5625 | 0 | 2021-09 | 0 | 0
2414 | CR0014390 | CTASK0029039 | Closed | OPUS-BKG-M | Thien Lai | 24 | 24 | 2021-09-07 17:47 | 2021-08-24 17:47 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] EUA - Add Soft Stop warning in TRO/I if shipment is not Release Ready | 2021-09-28 06:21 | 2021-10-28 | 2021-10-20 09:14 | 2021-11-22 11:59 | 2021-11-22 12:13 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-23 15:30 | 2021-12-15 12:00 | CR0014390 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W49 | 2021-12 | 80 | 84 | 70.0684 | 5 | 1 | 1 | 0.05 | 193567 | 2.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.5625 | 0 | 2021-09 | 0 | 0
2415 | CR0014390 | CTASK0029285 | Closed | OPUS-BKG-M | Thien Lai | 40 | 40 | 2021-10-08 09:11 | 2021-09-13 09:11 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA - Add Soft Stop warning in TRO/I if shipment is not Release Ready | 2021-09-28 06:21 | 2021-10-28 | 2021-10-20 09:14 | 2021-11-22 11:59 | 2021-11-22 12:13 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-23 15:30 | 2021-12-15 12:00 | CR0014390 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W49 | 2021-12 | 80 | 84 | 70.0684 | 5 | 1 | 1 | 0.05 | 193567 | 2.2 | 2 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.5625 | 0 | 2021-09 | 0 | 0
2416 | CR0014350 | CTASK0029343 | Closed | OPUS-SCE | VInh Bui | 2 | 15 | 2021-09-30 08:34 | 2021-09-01 08:34 | Container | [5 empty] | NA *OPUS * Request for label change of Master /Slave (SEP) | 2021-08-31 09:08 | 2021-09-30 09:08 | 2021-09-13 12:23 | 2021-10-05 08:17 | 2021-10-22 09:57 |  | 2021-11-09 09:00 | 2021-11-09 07:00 | 2021-10-25 15:20 | 2021-11-16 12:00 | CR0014350 |  | OPUS-SCE | 2021-W45 | 2021-11 | 15 | 50 | 69.9942 | 3 | 1 | 1 | 0.03 | 193469 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0 | 0 | 2021-08 | 0 | 0
2417 | CR0014350 | CTASK0029855 | Closed | OPUS-SCE | VInh Bui | 7 | 10 | 2021-10-31 18:46 | 2021-10-01 18:46 | Container | [5 empty] | NA *OPUS * Request for label change of Master /Slave (OCT) | 2021-08-31 09:08 | 2021-09-30 09:08 | 2021-09-13 12:23 | 2021-10-05 08:17 | 2021-10-22 09:57 |  | 2021-11-09 09:00 | 2021-11-09 07:00 | 2021-10-25 15:20 | 2021-11-16 12:00 | CR0014350 |  | OPUS-SCE | 2021-W45 | 2021-11 | 15 | 50 | 69.9942 | 3 | 1 | 1 | 0.03 | 193469 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0 | 0 | 2021-08 | 0 | 0
2418 | CR0014350 | CTASK0028996 | Closed | OPUS-SCE | VInh Bui | 6 | 25 | 2021-08-31 13:35 | 2021-08-01 13:35 | Container | [5 empty] | NA *OPUS * Request for label change of Master /Slave (AUG) | 2021-08-31 09:08 | 2021-09-30 09:08 | 2021-09-13 12:23 | 2021-10-05 08:17 | 2021-10-22 09:57 |  | 2021-11-09 09:00 | 2021-11-09 07:00 | 2021-10-25 15:20 | 2021-11-16 12:00 | CR0014350 |  | OPUS-SCE | 2021-W45 | 2021-11 | 15 | 50 | 69.9942 | 3 | 1 | 1 | 0.03 | 193469 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0 | 0 | 2021-08 | 0 | 0
2419 | CR0014581 | CTASK0029806 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 30 | 24 | 2021-10-29 21:00 | 2021-10-07 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | [Dev + Test] EUA Regulatory Egypt ACI BL printing hard stop logic update | 2021-10-08 06:23 | 2021-11-19 22:00 | 2021-10-29 06:07 | 2021-12-01 11:05 | 2021-12-09 11:23 |  | 2021-12-14 08:00 | 2021-12-14 08:10 | 2021-12-09 12:05 | 2021-12-21 12:01 | CR0014581 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2021-W50 | 2021-12 | 48 | 42 | 67.0675 | 4 | 2 | 2 | 0.03 | 193470 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.36842 | 0.11111 | 2021-10 | 0 | 0
2420 | CR0014581 | CTASK0029805 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2021-10-08 21:00 | 2021-10-07 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | [Design] EUA Regulatory Egypt ACI BL printing hard stop logic update | 2021-10-08 06:23 | 2021-11-19 22:00 | 2021-10-29 06:07 | 2021-12-01 11:05 | 2021-12-09 11:23 |  | 2021-12-14 08:00 | 2021-12-14 08:10 | 2021-12-09 12:05 | 2021-12-21 12:01 | CR0014581 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2021-W50 | 2021-12 | 48 | 42 | 67.0675 | 4 | 2 | 2 | 0.03 | 193470 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.36842 | 0.11111 | 2021-10 | 0 | 0
2421 | CR0014581 | CTASK0030047 | Closed | OPUS-BKG-MFT-A | Linh Dinh Bo | 10 | 10 | 2021-10-31 21:38 | 2021-10-17 21:38 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | [Develop] EUA Regulatory Egypt ACI BL printing hard stop logic update | 2021-10-08 06:23 | 2021-11-19 22:00 | 2021-10-29 06:07 | 2021-12-01 11:05 | 2021-12-09 11:23 |  | 2021-12-14 08:00 | 2021-12-14 08:10 | 2021-12-09 12:05 | 2021-12-21 12:01 | CR0014581 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2021-W50 | 2021-12 | 48 | 42 | 67.0675 | 4 | 2 | 2 | 0.03 | 193522 | 2.4 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0 | 0 | 2021-10 | 0 | 0
2422 | CR0014581 | CTASK0029807 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2021-12-13 17:30 | 2021-12-07 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Mark & Description [Alt+6] | [Deployment] EUA Regulatory Egypt ACI BL printing hard stop logic update | 2021-10-08 06:23 | 2021-11-19 22:00 | 2021-10-29 06:07 | 2021-12-01 11:05 | 2021-12-09 11:23 |  | 2021-12-14 08:00 | 2021-12-14 08:10 | 2021-12-09 12:05 | 2021-12-21 12:01 | CR0014581 | Service ManagementBooking/DocumentationOutbound DocB/L CreationMark & Description [Alt+6] | OPUS-BKG-OB | 2021-W50 | 2021-12 | 48 | 42 | 67.0675 | 4 | 2 | 2 | 0.03 | 193470 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0.36842 | 0.11111 | 2021-10 | 0 | 0
2423 | CR0014148 | CTASK0028851 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 14 | 14 | 2021-08-18 17:30 | 2021-08-16 08:30 | Container | Service Management | Booking/Documentation | Report | Booking Status Report |  | [Design] Add new columns of 'No. of TEUs Picked' against a VVD under BOOKING STATUS REPORT | 2021-09-06 16:05 | 2021-09-24 22:00 | 2021-09-23 11:06 | 2021-11-03 17:18 | 2021-11-08 09:40 |  | 2021-11-16 08:00 | 2021-11-16 08:00 | 2021-11-09 07:11 | 2021-11-23 12:01 | CR0014148 | Service ManagementBooking/DocumentationReportBooking Status Report | OPUS-BKG-RPT | 2021-W46 | 2021-11 | 41 | 62 | 70.6629 | 3 | 1 | 1 | 0.04 | 193470 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.36842 | 0.11111 | 2021-09 | 0 | 0
2424 | CR0014148 | CTASK0028853 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 |  | 2021-09-27 14:16 | Container | Service Management | Booking/Documentation | Report | Booking Status Report |  | [Deployment] Add new columns of 'No. of TEUs Picked' against a VVD under BOOKING STATUS REPORT | 2021-09-06 16:05 | 2021-09-24 22:00 | 2021-09-23 11:06 | 2021-11-03 17:18 | 2021-11-08 09:40 |  | 2021-11-16 08:00 | 2021-11-16 08:00 | 2021-11-09 07:11 | 2021-11-23 12:01 | CR0014148 | Service ManagementBooking/DocumentationReportBooking Status Report | OPUS-BKG-RPT | 2021-W46 | 2021-11 | 41 | 62 | 70.6629 | 3 | 1 | 1 | 0.04 | 193470 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.36842 | 0.11111 | 2021-09 | 0 | 0
2425 | CR0014148 | CTASK0028852 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 27 | 40 | 2021-09-17 13:33 | 2021-09-01 08:30 | Container | Service Management | Booking/Documentation | Report | Booking Status Report |  | [Development + Testing] Add new columns of 'No. of TEUs Picked' against a VVD under BOOKING STATUS REPORT | 2021-09-06 16:05 | 2021-09-24 22:00 | 2021-09-23 11:06 | 2021-11-03 17:18 | 2021-11-08 09:40 |  | 2021-11-16 08:00 | 2021-11-16 08:00 | 2021-11-09 07:11 | 2021-11-23 12:01 | CR0014148 | Service ManagementBooking/DocumentationReportBooking Status Report | OPUS-BKG-RPT | 2021-W46 | 2021-11 | 41 | 62 | 70.6629 | 3 | 1 | 1 | 0.04 | 193470 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.36842 | 0.11111 | 2021-09 | 0 | 0
2426 | CR0014615 | CTASK0029892 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 22 | 24 | 2021-11-03 13:01 | 2021-10-20 13:01 | Container | Service Management | Booking/Documentation | Outbound Doc | C/M (Container Manifest) | C/M by Booking | [Dev + Test][CLT-Internal] Modify PK Update Query on Booking Creation C/M tab | 2021-10-21 14:46 | 2021-11-17 21:46 | 2021-11-11 12:26 | 2021-12-16 07:08 | 2021-12-16 07:39 |  | 2022-01-11 08:38 | 2022-01-11 08:15 | 2022-01-04 16:04 | 2022-01-18 12:01 | CR0014615 | Service ManagementBooking/DocumentationOutbound DocC/M (Container Manifest)C/M by Booking | OPUS-BKG-OB | 2022-W2 | 2022-01 | 30 | 32 | 81.7441 | 3 | 1 | 1 | 0.02 | 193470 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 7 | 33 | 0.36842 | 0.11111 | 2021-10 | 0 | 0
2427 | CR0014615 | CTASK0029891 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2022-01-10 17:30 | 2022-01-05 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | C/M (Container Manifest) | C/M by Booking | [CLT-Internal] Modify PK Update Query on Booking Creation C/M tab | 2021-10-21 14:46 | 2021-11-17 21:46 | 2021-11-11 12:26 | 2021-12-16 07:08 | 2021-12-16 07:39 |  | 2022-01-11 08:38 | 2022-01-11 08:15 | 2022-01-04 16:04 | 2022-01-18 12:01 | CR0014615 | Service ManagementBooking/DocumentationOutbound DocC/M (Container Manifest)C/M by Booking | OPUS-BKG-OB | 2022-W2 | 2022-01 | 30 | 32 | 81.7441 | 3 | 1 | 1 | 0.02 | 193470 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 7 | 33 | 0.36842 | 0.11111 | 2021-10 | 0 | 0
2428 | CR0014615 | CTASK0029893 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2022-01-10 17:30 | 2022-01-05 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | C/M (Container Manifest) | C/M by Booking | [Deployment][CLT-Internal] Modify PK Update Query on Booking Creation C/M tab | 2021-10-21 14:46 | 2021-11-17 21:46 | 2021-11-11 12:26 | 2021-12-16 07:08 | 2021-12-16 07:39 |  | 2022-01-11 08:38 | 2022-01-11 08:15 | 2022-01-04 16:04 | 2022-01-18 12:01 | CR0014615 | Service ManagementBooking/DocumentationOutbound DocC/M (Container Manifest)C/M by Booking | OPUS-BKG-OB | 2022-W2 | 2022-01 | 30 | 32 | 81.7441 | 3 | 1 | 1 | 0.02 | 193470 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 7 | 33 | 0.36842 | 0.11111 | 2021-10 | 0 | 0
2429 | CR0014388 | CTASK0029313 | Closed | OPUS-MNR | Tien Le | 10 | 10 | 2021-10-29 17:00 | 2021-09-09 08:00 | Container | Equipment Management | M&R | Total Loss |  |  | [Documentation] [CLT Internal] Adjust validation logic for OW cntr Total Loss | 2021-10-15 17:27 | 2021-11-12 22:00 | 2021-11-12 15:03 | 2021-11-15 15:18 | 2021-11-29 13:54 |  | 2021-12-07 09:00 | 2021-12-07 08:00 | 2021-12-01 09:37 | 2021-12-14 12:01 | CR0014388 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2021-W49 | 2021-12 | 70 | 54 | 52.6476 | 3 | 1 | 1 | 0.04 | 173286 | 3 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0 | 0 | 2021-10 | 0 | 0
2430 | CR0014388 | CTASK0029306 | Closed | OPUS-MNR | Tien Le | 30 | 22 | 2021-09-30 17:00 | 2021-09-09 08:00 | Container | Equipment Management | M&R | Total Loss |  |  | [CLT Internal] Adjust validation logic for OW cntr Total Loss | 2021-10-15 17:27 | 2021-11-12 22:00 | 2021-11-12 15:03 | 2021-11-15 15:18 | 2021-11-29 13:54 |  | 2021-12-07 09:00 | 2021-12-07 08:00 | 2021-12-01 09:37 | 2021-12-14 12:01 | CR0014388 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2021-W49 | 2021-12 | 70 | 54 | 52.6476 | 3 | 1 | 1 | 0.04 | 173286 | 3 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0 | 0 | 2021-10 | 0 | 0
2431 | CR0014388 | CTASK0029312 | Closed | OPUS-MNR | Tien Le | 30 | 22 | 2021-10-29 17:00 | 2021-10-01 08:00 | Container | Equipment Management | M&R | Total Loss |  |  | [CLT Internal] Adjust validation logic for OW cntr Total Loss | 2021-10-15 17:27 | 2021-11-12 22:00 | 2021-11-12 15:03 | 2021-11-15 15:18 | 2021-11-29 13:54 |  | 2021-12-07 09:00 | 2021-12-07 08:00 | 2021-12-01 09:37 | 2021-12-14 12:01 | CR0014388 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2021-W49 | 2021-12 | 70 | 54 | 52.6476 | 3 | 1 | 1 | 0.04 | 173286 | 3 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0 | 0 | 2021-10 | 0 | 0
2432 | CR0013985 | CTASK0027606 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-08-20 13:39 | 2021-08-12 13:39 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] OPUS - Enhancement Request - Technical Name Field | 2021-08-12 13:37 | 2021-09-08 22:00 | 2021-09-08 11:46 | 2021-10-25 08:07 | 2021-10-25 09:05 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-10-25 15:21 | 2021-11-16 12:00 | CR0013985 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W45 | 2021-11 | 52 | 52 | 88.766 | 4 | 1 | 1 | 0.02 | 193567 | 2 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0.5625 | 0 | 2021-08 | 0 | 0
2433 | CR0013985 | CTASK0027608 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-08-24 13:39 | 2021-08-12 13:39 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] OPUS - Enhancement Request - Technical Name Field | 2021-08-12 13:37 | 2021-09-08 22:00 | 2021-09-08 11:46 | 2021-10-25 08:07 | 2021-10-25 09:05 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-10-25 15:21 | 2021-11-16 12:00 | CR0013985 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W45 | 2021-11 | 52 | 52 | 88.766 | 4 | 1 | 1 | 0.02 | 193567 | 2 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0.5625 | 0 | 2021-08 | 0 | 0
2434 | CR0013985 | CTASK0027609 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2021-11-12 17:35 | 2021-11-01 17:35 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] OPUS - Enhancement Request - Technical Name Field | 2021-08-12 13:37 | 2021-09-08 22:00 | 2021-09-08 11:46 | 2021-10-25 08:07 | 2021-10-25 09:05 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-10-25 15:21 | 2021-11-16 12:00 | CR0013985 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W45 | 2021-11 | 52 | 52 | 88.766 | 4 | 1 | 1 | 0.02 | 193567 | 2 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0.5625 | 0 | 2021-08 | 0 | 0
2435 | CR0013985 | CTASK0027541 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-06-18 13:43 | 2021-06-14 13:43 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] OPUS - Enhancement Request - Technical Name Field | 2021-08-12 13:37 | 2021-09-08 22:00 | 2021-09-08 11:46 | 2021-10-25 08:07 | 2021-10-25 09:05 |  | 2021-11-09 08:00 | 2021-11-09 08:00 | 2021-10-25 15:21 | 2021-11-16 12:00 | CR0013985 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W45 | 2021-11 | 52 | 52 | 88.766 | 4 | 1 | 1 | 0.02 | 193567 | 2 | 1 | 0 | 0 | 1 |  | 2 | 9 | 38 | 0.5625 | 0 | 2021-08 | 0 | 0
2436 | CR0014314 | CTASK0029294 | Closed | OPUS-TRS | Giang Nguyen Hoang | 8 | 8 |  |  | Container | Service Management | SCEM |  |  |  | [CLT Internal] ONE DDE Project - PK logic Update for SCE | 2021-08-17 06:59 | 2021-09-17 18:00 | 2021-09-13 13:42 | 2021-09-15 15:23 | 2021-09-17 08:36 |  | 2021-09-28 08:34 | 2021-09-28 10:16 | 2021-09-23 07:55 | 2021-10-05 12:01 | CR0014314 | Service ManagementSCEM | OPUS-SCE | 2021-W39 | 2021-09 | 16 | 16 | 42.066 | 2 | 1 | 2 | 0.02 | 183440 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 0 | 0 | 2021-08 | 0 | 0
2437 | CR0014314 | CTASK0029293 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 8 | 8 |  |  | Container | Service Management | SCEM |  |  |  | [CLT Internal] ONE DDE Project - PK logic Update for SCE | 2021-08-17 06:59 | 2021-09-17 18:00 | 2021-09-13 13:42 | 2021-09-15 15:23 | 2021-09-17 08:36 |  | 2021-09-28 08:34 | 2021-09-28 10:16 | 2021-09-23 07:55 | 2021-10-05 12:01 | CR0014314 | Service ManagementSCEM | OPUS-SCE | 2021-W39 | 2021-09 | 16 | 16 | 42.066 | 2 | 1 | 2 | 0.02 | 183432 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 0.043478 | 0.22222 | 2021-08 | 0 | 0
2438 | CR0014371 | CTASK0029980 | Closed | OPUS-INV | Nguyen Ha Vi | 16 | 15 | 2021-10-31 18:05 | 2021-10-15 18:05 | Container | Service Management | A/R Invoice | Invoice Issue | Customer Invoice EDI |  | [Oct 2021][CLT internal] period default setup for Customer invoice EDI (FNS_INV_0112) | 2021-11-08 06:03 | 2021-11-30 22:00 | 2021-11-29 15:19 | 2022-01-06 08:39 | 2022-01-11 15:23 |  | 2022-01-18 08:00 | 2022-02-08 20:09 | 2022-01-14 07:23 | 2022-02-21 12:00 | CR0014371 | Service ManagementA/R InvoiceInvoice IssueCustomer Invoice EDI | OPUS-INV | 2022-W3 | 2022-01 | 16 | 15 | 71.0811 | 1 | 1 | 1 | 0.01 | 203664 | 1.4 | 2 | 0 | 0 | 1 |  | 2 | 11 | 33 | 1.8182 | 2.5 | 2021-11 | 0 | 0
2439 | CR0014804 | CTASK0030928 | Closed | OPUS-BKG-MFT-E | Linh Dinh Bo | 4 | 8 |  |  | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [DEPLOY] (HBA) EUA AUTH ¦ Adding CUSTOMS COMMON CODE to allow address error ignore in EUA CUSTOMS EDI | 2021-12-07 16:38 | 2022-01-11 22:00 | 2022-01-11 09:33 | 2022-01-14 07:54 | 2022-01-20 09:35 |  | 2022-02-08 08:00 | 2022-02-08 08:00 | 2022-01-20 15:41 | 2022-02-15 12:00 | CR0014804 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W6 | 2022-02 | 20 | 32 | 62.6405 | 4 | 1 | 2 | 0.02 | 193522 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 6 | 30 | 0 | 0 | 2021-12 | 0 | 0
2440 | CR0014804 | CTASK0030925 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 4 | 4 | 2021-12-31 14:49 | 2021-12-01 14:49 | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [EST] (HBA) EUA AUTH ¦ Adding CUSTOMS COMMON CODE to allow address error ignore in EUA CUSTOMS EDI | 2021-12-07 16:38 | 2022-01-11 22:00 | 2022-01-11 09:33 | 2022-01-14 07:54 | 2022-01-20 09:35 |  | 2022-02-08 08:00 | 2022-02-08 08:00 | 2022-01-20 15:41 | 2022-02-15 12:00 | CR0014804 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W6 | 2022-02 | 20 | 32 | 62.6405 | 4 | 1 | 2 | 0.02 | 193606 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 30 | 4.25 | 0 | 2021-12 | 0 | 0
2441 | CR0014804 | CTASK0030926 | Closed | OPUS-BKG-MFT-E | Linh Dinh Bo | 12 | 12 |  |  | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [DEV] (HBA) EUA AUTH ¦ Adding CUSTOMS COMMON CODE to allow address error ignore in EUA CUSTOMS EDI | 2021-12-07 16:38 | 2022-01-11 22:00 | 2022-01-11 09:33 | 2022-01-14 07:54 | 2022-01-20 09:35 |  | 2022-02-08 08:00 | 2022-02-08 08:00 | 2022-01-20 15:41 | 2022-02-15 12:00 | CR0014804 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W6 | 2022-02 | 20 | 32 | 62.6405 | 4 | 1 | 2 | 0.02 | 193522 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 6 | 30 | 0 | 0 | 2021-12 | 0 | 0
2442 | CR0014804 | CTASK0030927 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 8 | 8 |  |  | Container | Service Management | Booking/Documentation | Manifest | EUA | Europe Customs EDI | [TEST] (HBA) EUA AUTH ¦ Adding CUSTOMS COMMON CODE to allow address error ignore in EUA CUSTOMS EDI | 2021-12-07 16:38 | 2022-01-11 22:00 | 2022-01-11 09:33 | 2022-01-14 07:54 | 2022-01-20 09:35 |  | 2022-02-08 08:00 | 2022-02-08 08:00 | 2022-01-20 15:41 | 2022-02-15 12:00 | CR0014804 | Service ManagementBooking/DocumentationManifestEUAEurope Customs EDI | OPUS-BKG-MFT | 2022-W6 | 2022-02 | 20 | 32 | 62.6405 | 4 | 1 | 2 | 0.02 | 193606 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 30 | 4.25 | 0 | 2021-12 | 0 | 0
2443 | CR0014851 | CTASK0031255 | Closed | OPUS-DMT | Cuong Nguyen | 44 | 50 | 2022-02-25 08:41 | 2022-02-01 08:41 | Container | Service Management | Demurrage/Detention | Billing | Invoice Creation & Issue |  | [TASK1] [CLT Internal] Add the validation logic when user changes the payer customer on the screen. | 2022-01-21 09:38 | 2022-02-26 09:37 | 2022-02-24 09:19 | 2022-04-13 11:00 | 2022-04-13 12:10 |  | 2022-04-26 08:09 | 2022-04-26 09:48 | 2022-04-21 13:27 | 2022-05-03 12:00 | CR0014851 | Service ManagementDemurrage/DetentionBillingInvoice Creation & Issue | OPUS-DMT | 2022-W17 | 2022-04 | 44 | 50 | 94.9386 | 1 | 1 | 1 | 0.02 | 193529 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 6 | 18 | 0.11538 | 0.22222 | 2022-01 | 0 | 0
2444 | CR0013531 | CTASK0025141 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 2 | 2 | 2021-02-05 17:30 | 2021-02-03 09:00 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (Origin Office) | Transmission Status Cross-Check | [Analysis][CLT Internal]NA * AMS * B/L Data for NMAT0604W not retrieving in Transmission Status Cross-Check UI | 2021-08-11 09:27 | 2021-10-15 09:26 | 2021-08-24 05:14 | 2021-11-09 17:03 | 2021-11-12 14:28 |  | 2021-12-07 09:00 | 2021-12-07 08:00 | 2021-12-01 09:37 | 2021-12-14 12:01 | CR0013531 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (Origin Office)Transmission Status Cross-Check | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 31 | 31 | 117.9814 | 2 | 1 | 1 | 0.01 | 173280 | 2.7 | 0 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.375 | 1 | 2021-08 | 0 | 0
2445 | CR0013531 | CTASK0025147 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 29 | 29 | 2021-03-12 17:30 | 2021-02-17 09:00 | Container | Service Management | Booking/Documentation | Advance Manifest | US AMS (Origin Office) | Transmission Status Cross-Check | [Development+Testing+Development][CLT Internal]NA * AMS * B/L Data for NMAT0604W not retrieving in Transmission Status Cross-Check UI | 2021-08-11 09:27 | 2021-10-15 09:26 | 2021-08-24 05:14 | 2021-11-09 17:03 | 2021-11-12 14:28 |  | 2021-12-07 09:00 | 2021-12-07 08:00 | 2021-12-01 09:37 | 2021-12-14 12:01 | CR0013531 | Service ManagementBooking/DocumentationAdvance ManifestUS AMS (Origin Office)Transmission Status Cross-Check | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 31 | 31 | 117.9814 | 2 | 1 | 1 | 0.01 | 173280 | 2.7 | 0 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.375 | 1 | 2021-08 | 0 | 0
2446 | CR0014521 | CTASK0031352 | Closed | OPUS-INV | Nguyen Ha Vi | 22 | 22 | 2021-12-31 14:04 | 2021-12-22 14:04 | Container | Biz Common | Master Data | Partner | Credit Customer |  | [DEC] child CR of CR0012925 credit ui enhancement - changes to renewal of credit agreement number formula | 2021-12-13 05:50 | 2021-12-31 05:49 | 2021-12-30 09:41 | 2022-02-07 11:35 | 2022-03-08 11:52 |  | 2022-03-15 11:52 | 2022-03-22 21:27 | 2022-03-17 09:47 | 2022-04-21 12:00 | CR0014521 | Biz CommonMaster DataPartnerCredit Customer | OPUS-MDA | 2022-W11 | 2022-03 | 22 | 22 | 92.2514 | 1 | 1 | 1 | 0.01 | 203664 | 1.5 | 2 | 0 | 0 | 1 |  | 2 | 10 | 38 | 1.8182 | 2.5 | 2021-12 | 0 | 0
2447 | CR0014497 | CTASK0029557 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-10-15 13:23 | 2021-10-11 13:23 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Development] [CLT Internal] [DDE] PK Update Case should be enhanced (Update -> Delete/Insert) | 2021-10-15 09:02 | 2021-11-11 | 2021-11-08 08:29 | 2021-11-09 08:53 | 2021-11-09 09:45 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-11-11 08:19 | 2021-11-30 12:00 | CR0014497 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W47 | 2021-11 | 40 | 40 | 38.9572 | 4 | 1 | 1 | 0.04 | 193567 | 2.2 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.5625 | 0 | 2021-10 | 0 | 0
2448 | CR0014497 | CTASK0029461 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-09-30 09:37 | 2021-09-15 09:37 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Design] [CLT Internal] [DDE] PK Update Case should be enhanced (Update -> Delete/Insert) | 2021-10-15 09:02 | 2021-11-11 | 2021-11-08 08:29 | 2021-11-09 08:53 | 2021-11-09 09:45 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-11-11 08:19 | 2021-11-30 12:00 | CR0014497 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W47 | 2021-11 | 40 | 40 | 38.9572 | 4 | 1 | 1 | 0.04 | 193567 | 2.2 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.5625 | 0 | 2021-10 | 0 | 0
2449 | CR0014497 | CTASK0029559 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2021-10-15 13:23 | 2021-10-11 13:23 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Testing] [CLT Internal] [DDE] PK Update Case should be enhanced (Update -> Delete/Insert) | 2021-10-15 09:02 | 2021-11-11 | 2021-11-08 08:29 | 2021-11-09 08:53 | 2021-11-09 09:45 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-11-11 08:19 | 2021-11-30 12:00 | CR0014497 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W47 | 2021-11 | 40 | 40 | 38.9572 | 4 | 1 | 1 | 0.04 | 193567 | 2.2 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.5625 | 0 | 2021-10 | 0 | 0
2450 | CR0014497 | CTASK0029561 | Closed | OPUS-BKG-M | Thien Lai | 4 | 4 | 2021-11-23 08:11 | 2021-11-15 08:11 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Deployment] [CLT Internal] [DDE] PK Update Case should be enhanced (Update -> Delete/Insert) | 2021-10-15 09:02 | 2021-11-11 | 2021-11-08 08:29 | 2021-11-09 08:53 | 2021-11-09 09:45 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-11-11 08:19 | 2021-11-30 12:00 | CR0014497 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2021-W47 | 2021-11 | 40 | 40 | 38.9572 | 4 | 1 | 1 | 0.04 | 193567 | 2.2 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.5625 | 0 | 2021-10 | 0 | 0
2451 | CR0013828 | CTASK0026708 | Closed | OPUS-ACM | Huynh Tuan Khanh | 103 | 130 | 2021-10-31 16:00 | 2021-05-03 07:50 | Container | Support & Admin | Agent Commission Management | Agreement | Special Compensation Agreement Creation |  | [LA ENHANCEMENT] CSA ACM OPUS Production Special Compensation Validation Requests (Change Request) | 2021-07-09 03:57 | 2021-08-31 03:57 | 2021-08-27 15:15 | 2021-12-08 12:23 | 2021-12-18 02:22 |  | 2021-12-21 10:49 | 2021-12-21 08:23 | 2021-12-20 07:59 | 2021-12-28 12:01 | CR0013828 | Support & AdminAgent Commission ManagementAgreementSpecial Compensation Agreement Creation | OPUS-ACM | 2021-W51 | 2021-12 | 103 | 130 | 165.2864 | 1 | 1 | 1 | 0.03 | 193499 | 2.1 | 2 | 0 | 0 | 2 |  | 3 | 3 | 26 | 0 | 0 | 2021-07 | 0 | 0
2452 | CR0013478 | CTASK0024696 | Closed | OPUS-BKG-M | Quy Truong | 32 | 28 | 2022-01-25 | 2022-01-17 08:00 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Development] [CLT Internal] DG Cargo UI Enhancement about multi user issue related to discrepancy between DG Cargo and DG Declaration | 2022-01-17 07:10 | 2022-02-23 22:00 | 2022-02-21 08:07 | 2022-02-21 16:03 | 2022-02-22 06:46 |  | 2022-03-15 08:00 | 2022-03-15 08:00 | 2022-02-22 14:47 | 2022-03-22 12:00 | CR0013478 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2022-W11 | 2022-03 | 64 | 64 | 57.0349 | 5 | 1 | 1 | 0.05 | 203791 | 1.2 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2022-01 | 0 | 0
2453 | CR0013478 | CTASK0024698 | Closed | OPUS-BKG-M | Quy Truong | 8 | 8 | 2022-03-12 | 2022-02-25 08:00 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Testing] [CLT Internal] DG Cargo UI Enhancement about multi user issue related to discrepancy between DG Cargo and DG Declaration | 2022-01-17 07:10 | 2022-02-23 22:00 | 2022-02-21 08:07 | 2022-02-21 16:03 | 2022-02-22 06:46 |  | 2022-03-15 08:00 | 2022-03-15 08:00 | 2022-02-22 14:47 | 2022-03-22 12:00 | CR0013478 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2022-W11 | 2022-03 | 64 | 64 | 57.0349 | 5 | 1 | 1 | 0.05 | 203791 | 1.2 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2022-01 | 0 | 0
2454 | CR0013478 | CTASK0024668 | Closed | OPUS-BKG-M | Quy Truong | 20 | 20 | 2022-01-15 11:10 | 2022-01-01 11:09 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Design] [CLT Internal] DG Cargo UI Enhancement about multi user issue related to discrepancy between DG Cargo and DG Declaration | 2022-01-17 07:10 | 2022-02-23 22:00 | 2022-02-21 08:07 | 2022-02-21 16:03 | 2022-02-22 06:46 |  | 2022-03-15 08:00 | 2022-03-15 08:00 | 2022-02-22 14:47 | 2022-03-22 12:00 | CR0013478 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2022-W11 | 2022-03 | 64 | 64 | 57.0349 | 5 | 1 | 1 | 0.05 | 203791 | 1.2 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2022-01 | 0 | 0
2455 | CR0013478 | CTASK0031520 | Closed | OPUS-BKG-M | Quy Truong | 1 | 1 | 2022-01-28 12:59 | 2022-01-17 12:59 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Development] [CLT Internal] DG Cargo UI Enhancement about multi user issue related to discrepancy between DG Cargo and DG Declaration | 2022-01-17 07:10 | 2022-02-23 22:00 | 2022-02-21 08:07 | 2022-02-21 16:03 | 2022-02-22 06:46 |  | 2022-03-15 08:00 | 2022-03-15 08:00 | 2022-02-22 14:47 | 2022-03-22 12:00 | CR0013478 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2022-W11 | 2022-03 | 64 | 64 | 57.0349 | 5 | 1 | 1 | 0.05 | 203791 | 1.2 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2022-01 | 0 | 0
2456 | CR0013478 | CTASK0024700 | Closed | OPUS-BKG-M | Quy Truong | 4 | 8 | 2022-03-15 13:00 | 2022-03-07 13:00 | Container | Service Management | Booking/Documentation | Booking | Special Cargo | Dangerous Cargo Application | [Deployment] [CLT Internal] DG Cargo UI Enhancement about multi user issue related to discrepancy between DG Cargo and DG Declaration | 2022-01-17 07:10 | 2022-02-23 22:00 | 2022-02-21 08:07 | 2022-02-21 16:03 | 2022-02-22 06:46 |  | 2022-03-15 08:00 | 2022-03-15 08:00 | 2022-02-22 14:47 | 2022-03-22 12:00 | CR0013478 | Service ManagementBooking/DocumentationBookingSpecial CargoDangerous Cargo Application | OPUS-BKG-M | 2022-W11 | 2022-03 | 64 | 64 | 57.0349 | 5 | 1 | 1 | 0.05 | 203791 | 1.2 | 1 | 0 | 0 | 1 |  | 2 | 10 | 38 | 0 | 0 | 2022-01 | 0 | 0
2457 | CR0013576 | CTASK0027742 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-06-24 | 2021-06-23 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design] Remove the pop up "Booking data does not exist. Do you have data copied ? " | 2021-08-20 06:58 | 2021-09-30 22:00 | 2021-09-29 15:03 | 2021-11-22 11:55 | 2021-11-22 11:59 |  | 2021-11-30 09:00 | 2021-11-30 08:00 | 2021-11-23 15:29 | 2021-12-08 12:00 | CR0013576 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W48 | 2021-11 | 60 | 60 | 102.0844 | 3 | 1 | 1 | 0.02 | 193525 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.41667 | 0.16667 | 2021-08 | 0 | 0
2458 | CR0013576 | CTASK0027744 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-11-25 | 2021-11-24 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment] Remove the pop up "Booking data does not exist. Do you have data copied ? " | 2021-08-20 06:58 | 2021-09-30 22:00 | 2021-09-29 15:03 | 2021-11-22 11:55 | 2021-11-22 11:59 |  | 2021-11-30 09:00 | 2021-11-30 08:00 | 2021-11-23 15:29 | 2021-12-08 12:00 | CR0013576 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W48 | 2021-11 | 60 | 60 | 102.0844 | 3 | 1 | 1 | 0.02 | 193525 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.41667 | 0.16667 | 2021-08 | 0 | 0
2459 | CR0013576 | CTASK0027743 | Closed | OPUS-BKG-EBKG | Vinh Tran | 52 | 52 | 2021-10-01 | 2021-08-25 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development+Test] Remove the pop up "Booking data does not exist. Do you have data copied ? " | 2021-08-20 06:58 | 2021-09-30 22:00 | 2021-09-29 15:03 | 2021-11-22 11:55 | 2021-11-22 11:59 |  | 2021-11-30 09:00 | 2021-11-30 08:00 | 2021-11-23 15:29 | 2021-12-08 12:00 | CR0013576 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2021-W48 | 2021-11 | 60 | 60 | 102.0844 | 3 | 1 | 1 | 0.02 | 193525 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 3 | 38 | 0.41667 | 0.16667 | 2021-08 | 0 | 0
2460 | CR0014854 | CTASK0031546 | Closed | OPUS-PRD | VInh Bui | 60 | 45 | 2022-01-31 11:37 | 2022-01-01 11:37 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | NA * PRD * Constraint Management -Exposing Constraint Sequence Number in System - JAN | 2022-01-11 07:23 | 2022-02-25 18:00 | 2022-02-24 09:44 | 2022-04-29 15:59 | 2022-05-04 11:49 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:01 | 2022-05-24 12:00 | CR0014854 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 104 | 89 | 126.0256 | 3 | 1 | 2 | 0.03 | 193469 | 2.3 | 2 | 0 | 0 | 1 |  | 2 | 8 | 26 | 0 | 0 | 2022-01 | 0 | 0
2461 | CR0014854 | CTASK0031929 | Closed | OPUS-PRD | Tran Le | 16 | 16 | 2022-01-31 09:09 | 2022-01-01 09:09 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | NA * PRD * Constraint Management -Exposing Constraint Sequence Number in System - JAN | 2022-01-11 07:23 | 2022-02-25 18:00 | 2022-02-24 09:44 | 2022-04-29 15:59 | 2022-05-04 11:49 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:01 | 2022-05-24 12:00 | CR0014854 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 104 | 89 | 126.0256 | 3 | 1 | 2 | 0.03 | 193501 | 2.3 | 2 | 0 | 0 | 1 |  | 2 | 8 | 26 | 0.052632 | 0 | 2022-01 | 0 | 0
2462 | CR0014854 | CTASK0031550 | Closed | OPUS-PRD | VInh Bui | 28 | 28 | 2022-02-28 13:20 | 2022-02-01 13:20 | Container | Service Management | Product Catalog | Network Constraint | Constraint Management |  | NA * PRD * Constraint Management -Exposing Constraint Sequence Number in System - FEB | 2022-01-11 07:23 | 2022-02-25 18:00 | 2022-02-24 09:44 | 2022-04-29 15:59 | 2022-05-04 11:49 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-13 07:01 | 2022-05-24 12:00 | CR0014854 | Service ManagementProduct CatalogNetwork ConstraintConstraint Management | OPUS-PRD | 2022-W20 | 2022-05 | 104 | 89 | 126.0256 | 3 | 1 | 2 | 0.03 | 193469 | 2.3 | 2 | 0 | 0 | 1 |  | 2 | 8 | 26 | 0 | 0 | 2022-01 | 0 | 0
2463 | CR0014099 | CTASK0027960 | Closed | OPUS-SCG | Trang Duy Thong | 18 | 20 | 2021-07-30 14:15 | 2021-07-07 14:15 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [Documentation] Checkbox Enhancement on the SPCL CGO APVL/Inquiry for Partner Lines (VOP_SCG_5001) >> Update screen | 2021-07-07 09:53 | 2021-07-30 09:52 | 2021-07-30 07:47 | 2021-09-28 11:08 | 2021-10-06 11:17 |  | 2021-10-12 08:00 | 2021-10-12 09:36 | 2021-10-07 11:26 | 2021-10-19 12:00 | CR0014099 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W41 | 2021-10 | 66 | 70 | 96.9218 | 2 | 1 | 1 | 0.03 | 193511 | 1.1 | 2 | 0 | 0 | 1 |  | 2 | 9 | 26 | 0.81818 | 2.6667 | 2021-07 | 0 | 0
2464 | CR0014099 | CTASK0027961 | Closed | OPUS-SCG | Trang Duy Thong | 48 | 50 | 2021-07-23 14:17 | 2021-07-07 14:17 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [CLV] Checkbox Enhancement on the SPCL CGO APVL/Inquiry for Partner Lines (VOP_SCG_5001) >> Update screen | 2021-07-07 09:53 | 2021-07-30 09:52 | 2021-07-30 07:47 | 2021-09-28 11:08 | 2021-10-06 11:17 |  | 2021-10-12 08:00 | 2021-10-12 09:36 | 2021-10-07 11:26 | 2021-10-19 12:00 | CR0014099 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2021-W41 | 2021-10 | 66 | 70 | 96.9218 | 2 | 1 | 1 | 0.03 | 193511 | 1.1 | 2 | 0 | 0 | 1 |  | 2 | 9 | 26 | 0.81818 | 2.6667 | 2021-07 | 0 | 0
2465 | CR0013676 | CTASK0025886 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-03-19 15:07 | 2021-03-15 15:06 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] LA - EDI COPARN - Addition of TAA at F/F | 2021-07-19 07:22 | 2021-07-28 22:00 | 2021-07-26 13:55 | 2022-01-11 07:04 | 2022-01-11 07:27 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-12 15:40 | 2022-02-02 12:00 | CR0013676 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W4 | 2022-01 | 58 | 56 | 190.0264 | 4 | 1 | 2 | 0.01 | 193567 | 2 | 1 | 0 | 0 | 1 |  | 3 | 9 | 33 | 0.5625 | 0.53333 | 2021-07 | 0 | 0
2466 | CR0013676 | CTASK0025994 | Closed | OPUS-BKG-M | Loc Tran | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] LA - EDI COPARN - Addition of TAA at F/F | 2021-07-19 07:22 | 2021-07-28 22:00 | 2021-07-26 13:55 | 2022-01-11 07:04 | 2022-01-11 07:27 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-12 15:40 | 2022-02-02 12:00 | CR0013676 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W4 | 2022-01 | 58 | 56 | 190.0264 | 4 | 1 | 2 | 0.01 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 3 | 9 | 33 | 0.33333 | 0.28571 | 2021-07 | 0 | 0
2467 | CR0013676 | CTASK0025990 | Closed | OPUS-BKG-M | Loc Tran | 26 | 20 | 2021-05-31 09:57 | 2021-05-06 09:57 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] LA - EDI COPARN - Addition of TAA at F/F | 2021-07-19 07:22 | 2021-07-28 22:00 | 2021-07-26 13:55 | 2022-01-11 07:04 | 2022-01-11 07:27 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-12 15:40 | 2022-02-02 12:00 | CR0013676 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W4 | 2022-01 | 58 | 56 | 190.0264 | 4 | 1 | 2 | 0.01 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 3 | 9 | 33 | 0.33333 | 0.28571 | 2021-07 | 0 | 0
2468 | CR0013676 | CTASK0025992 | Closed | OPUS-BKG-M | Loc Tran | 16 | 16 | 2021-07-31 09:07 | 2021-07-13 09:07 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] LA - EDI COPARN - Addition of TAA at F/F | 2021-07-19 07:22 | 2021-07-28 22:00 | 2021-07-26 13:55 | 2022-01-11 07:04 | 2022-01-11 07:27 |  | 2022-01-25 08:00 | 2022-01-25 08:00 | 2022-01-12 15:40 | 2022-02-02 12:00 | CR0013676 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W4 | 2022-01 | 58 | 56 | 190.0264 | 4 | 1 | 2 | 0.01 | 193503 | 2 | 1 | 0 | 0 | 1 |  | 3 | 9 | 33 | 0.33333 | 0.28571 | 2021-07 | 0 | 0
2469 | CR0014359 | CTASK0028786 | Closed | OPUS-VSK | Huy Vu | 29 | 30 | 2021-08-31 18:00 | 2021-08-18 07:00 | Container | Vessel Operation |  |  |  |  | [CLV][CLT Internal] OPUS SQL Tuning - OPER V | 2021-09-03 14:29 | 2021-09-17 12:25 | 2021-09-10 14:54 | 2021-11-11 09:42 | 2021-11-11 16:07 |  | 2021-11-23 08:00 | 2021-11-23 07:00 | 2021-11-19 14:21 | 2021-12-01 12:00 | CR0014359 | Vessel Operation | OPUS-VSK | 2021-W47 | 2021-11 | 29 | 30 | 80.73 | 1 | 1 | 1 | 0.02 | 193618 | 1.6 | 2 | 0 | 0 | 1 |  | 2 | 7 | 38 | 0 | 0 | 2021-09 | 0 | 0
2470 | CR0015245 | CTASK0033049 | Closed | OPUS-PRI | Ngan Nham | 14 | 11 | 2022-03-31 22:00 | 2022-03-20 23:00 | Container | Sales Management | Pricing | Service Contract | S/C Creation | S/C Proposal & Amendment Creation | [Development][Kontainers] Premium only _OPUS PRI | 2022-03-23 13:27 | 2022-04-15 22:00 | 2022-03-31 08:15 | 2022-05-12 11:04 | 2022-05-12 11:06 |  | 2022-05-17 10:00 | 2022-05-17 09:15 | 2022-05-16 09:35 | 2022-05-24 12:00 | CR0015245 | Sales ManagementPricingService ContractS/C CreationS/C Proposal & Amendment Creation | OPUS-PRI | 2022-W20 | 2022-05 | 14 | 11 | 54.8564 | 1 | 1 | 1 | 0.01 | 193461 | 3.3 | 0 | 0 | 0 | 1 |  | 2 | 8 | 26 | 0 | 0 | 2022-03 | 0 | 0
2471 | CR0013879 | CTASK0029229 | Closed | OPUS-INV | Nguyen Ha Vi | 22 | 20 | 2021-09-30 17:11 | 2021-09-01 17:10 | Container | Service Management | A/R Invoice | Invoice Creation / Correction | Miscellaneous Revenue Invoice Creation |  | [Sep 2021][Vi Nguyen]To improve MIV creation when using 'Auto generate B/L number' | 2021-07-14 07:17 | 2021-08-13 07:16 | 2021-08-10 08:57 | 2021-11-09 09:41 | 2021-11-10 14:53 |  | 2021-11-16 10:00 | 2021-11-16 10:00 | 2021-11-11 09:46 | 2021-11-23 12:01 | CR0013879 | Service ManagementA/R InvoiceInvoice Creation / CorrectionMiscellaneous Revenue Invoice Creation | OPUS-INV | 2021-W46 | 2021-11 | 27 | 25 | 125.1134 | 2 | 1 | 2 | 0.01 | 203664 | 1.1 | 4 | 0 | 0 | 1 |  | 2 | 16 | 38 | 1.8182 | 2.5 | 2021-07 | 0 | 0
2472 | CR0013879 | CTASK0029228 | Closed | OPUS-INV | Lien Le | 5 | 5 | 2021-09-30 17:09 | 2021-09-01 17:09 | Container | Service Management | A/R Invoice | Invoice Creation / Correction | Miscellaneous Revenue Invoice Creation |  | [Sep 2021][Lien Le] To improve MIV creation when using 'Auto generate B/L number' | 2021-07-14 07:17 | 2021-08-13 07:16 | 2021-08-10 08:57 | 2021-11-09 09:41 | 2021-11-10 14:53 |  | 2021-11-16 10:00 | 2021-11-16 10:00 | 2021-11-11 09:46 | 2021-11-23 12:01 | CR0013879 | Service ManagementA/R InvoiceInvoice Creation / CorrectionMiscellaneous Revenue Invoice Creation | OPUS-INV | 2021-W46 | 2021-11 | 27 | 25 | 125.1134 | 2 | 1 | 2 | 0.01 | 193441 | 2.3 | 4 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.42308 | 0 | 2021-07 | 0 | 0
2473 | CR0014063 | CTASK0029790 | Closed | OPUS-SPC | Toai Phan | 12 | 15 | 2021-10-22 22:00 | 2021-10-01 07:00 | Container | Sales Management | Space Control |  |  |  | Standby Hardcoding Table transhipment/feeder addition SR0126712 | 2021-09-02 07:57 | 2021-10-08 22:00 | 2021-10-07 15:17 | 2021-12-10 14:29 | 2021-12-16 16:02 |  | 2021-12-29 16:01 | 2021-12-28 08:32 | 2021-12-24 08:45 | 2022-01-04 12:00 | CR0014063 | Sales ManagementSpace Control | OPUS-SPC | 2021-W52 | 2021-12 | 12 | 15 | 118.3364 | 1 | 1 | 1 | 0.01 | 183427 | 2.8 | 0 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0 | 0 | 2021-09 | 0 | 0
2474 | CR0014334 | CTASK0029111 | Closed | OPUS-BKG-M | Kieu Le | 26 | 26 | 2021-10-15 16:37 | 2021-10-06 16:37 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Development][ LA ENHANCEMENT] LA - Comm - Standby - Weight in Feeder tab | 2021-10-06 12:21 | 2021-11-03 12:21 | 2021-11-03 09:06 | 2021-12-13 13:11 | 2021-12-15 15:50 |  | 2021-12-28 08:00 | 2021-12-28 08:31 | 2021-12-24 08:47 | 2022-01-04 12:00 | CR0014334 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W52 | 2021-12 | 50 | 54 | 82.8188 | 6 | 1 | 2 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2475 | CR0014334 | CTASK0029115 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-12-31 09:29 | 2021-12-01 09:29 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Deployment][ LA ENHANCEMENT] LA - Comm - Standby - Weight in Feeder tab | 2021-10-06 12:21 | 2021-11-03 12:21 | 2021-11-03 09:06 | 2021-12-13 13:11 | 2021-12-15 15:50 |  | 2021-12-28 08:00 | 2021-12-28 08:31 | 2021-12-24 08:47 | 2022-01-04 12:00 | CR0014334 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W52 | 2021-12 | 50 | 54 | 82.8188 | 6 | 1 | 2 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2476 | CR0014334 | CTASK0029114 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-11-30 16:39 | 2021-11-01 16:39 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [TG][ LA ENHANCEMENT] LA - Comm - Standby - Weight in Feeder tab | 2021-10-06 12:21 | 2021-11-03 12:21 | 2021-11-03 09:06 | 2021-12-13 13:11 | 2021-12-15 15:50 |  | 2021-12-28 08:00 | 2021-12-28 08:31 | 2021-12-24 08:47 | 2022-01-04 12:00 | CR0014334 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W52 | 2021-12 | 50 | 54 | 82.8188 | 6 | 1 | 2 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2477 | CR0014334 | CTASK0029755 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2021-10-15 08:42 | 2021-10-06 08:41 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [DB][ LA ENHANCEMENT] LA - Comm - Standby - Weight in Feeder tab | 2021-10-06 12:21 | 2021-11-03 12:21 | 2021-11-03 09:06 | 2021-12-13 13:11 | 2021-12-15 15:50 |  | 2021-12-28 08:00 | 2021-12-28 08:31 | 2021-12-24 08:47 | 2022-01-04 12:00 | CR0014334 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W52 | 2021-12 | 50 | 54 | 82.8188 | 6 | 1 | 2 | 0.03 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0 | 0 | 2021-10 | 0 | 0
2478 | CR0014334 | CTASK0029112 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-10-29 16:38 | 2021-10-18 16:38 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Testing][ LA ENHANCEMENT] LA - Comm - Standby - Weight in Feeder tab | 2021-10-06 12:21 | 2021-11-03 12:21 | 2021-11-03 09:06 | 2021-12-13 13:11 | 2021-12-15 15:50 |  | 2021-12-28 08:00 | 2021-12-28 08:31 | 2021-12-24 08:47 | 2022-01-04 12:00 | CR0014334 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W52 | 2021-12 | 50 | 54 | 82.8188 | 6 | 1 | 2 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2479 | CR0014334 | CTASK0029110 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-09-17 09:25 | 2021-09-01 09:25 | Container | Sales Management | Space Control | Standby Management | Master Constraint Table Creation |  | [Design][ LA ENHANCEMENT] LA - Comm - Standby - Weight in Feeder tab | 2021-10-06 12:21 | 2021-11-03 12:21 | 2021-11-03 09:06 | 2021-12-13 13:11 | 2021-12-15 15:50 |  | 2021-12-28 08:00 | 2021-12-28 08:31 | 2021-12-24 08:47 | 2022-01-04 12:00 | CR0014334 | Sales ManagementSpace ControlStandby ManagementMaster Constraint Table Creation | OPUS-SPC | 2021-W52 | 2021-12 | 50 | 54 | 82.8188 | 6 | 1 | 2 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2480 | CR0014844 | CTASK0031079 | Closed | OPUS-CTM | Hoa Nguyen | 32 | 32 |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | Duplicate logic of chassis and attached genset no assignment in CR0013120 for cases of EDI CTM movement reprocessing - Manage effort | 2021-12-13 12:31 | 2022-01-07 18:10 | 2022-01-07 07:15 | 2022-01-27 13:59 | 2022-02-07 09:25 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-11 16:03 | 2022-03-01 12:00 | CR0014844 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2022-W8 | 2022-02 | 44 | 34 | 70.8119 | 3 | 1 | 2 | 0.02 | 213814 | 0.7 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
2481 | CR0014844 | CTASK0030840 | Closed | OPUS-CTM | Tran Le | 34 | 34 | 2022-01-15 09:52 | 2021-12-20 09:52 | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | [Documentation] Duplicate logic of chassis and attached genset no assignment in CR0013120 for cases of EDI CTM movement reprocessing | 2021-12-13 12:31 | 2022-01-07 18:10 | 2022-01-07 07:15 | 2022-01-27 13:59 | 2022-02-07 09:25 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-11 16:03 | 2022-03-01 12:00 | CR0014844 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2022-W8 | 2022-02 | 44 | 34 | 70.8119 | 3 | 1 | 2 | 0.02 | 193501 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0.052632 | 0 | 2021-12 | 0 | 0
2482 | CR0014844 | CTASK0030843 | Closed | OPUS-CTM | Tran Le | 12 |  |  |  | Container | Service Management | CNTR Movement | MVMT Update | Update of EDI Message - All MSG |  | Duplicate logic of chassis and attached genset no assignment in CR0013120 for cases of EDI CTM movement reprocessing - Manage effort | 2021-12-13 12:31 | 2022-01-07 18:10 | 2022-01-07 07:15 | 2022-01-27 13:59 | 2022-02-07 09:25 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-11 16:03 | 2022-03-01 12:00 | CR0014844 | Service ManagementCNTR MovementMVMT UpdateUpdate of EDI Message - All MSG | OPUS-CTM | 2022-W8 | 2022-02 | 44 | 34 | 70.8119 | 3 | 1 | 2 | 0.02 | 193501 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0.052632 | 0 | 2021-12 | 0 | 0
2483 | CR0013027 | CTASK0023326 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 16 | 16 | 2020-11-06 | 2020-11-02 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Analysis] Mexico [enhancement]// Customs submission // X12 | 2020-12-03 16:40 | 2020-12-15 22:00 | 2020-12-15 12:32 | 2021-10-15 12:21 | 2022-01-28 20:20 |  | 2022-01-31 08:00 | 2022-01-31 08:00 | 2022-01-29 07:21 | 2022-02-07 12:00 | CR0013027 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 215 | 215 | 423.6388 | 4 | 1 | 1 | 0.02 | 193506 | 1.5 | 0 | 4 | 0 | 3 |  | 4 | 3 | 33 | 0 | 1.25 | 2020-12 | 4 | 1
2484 | CR0013027 | CTASK0023492 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 60 | 60 | 2020-12-18 | 2020-12-01 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Test][License Service] Mexico [enhancement]// Customs submission // X12 | 2020-12-03 16:40 | 2020-12-15 22:00 | 2020-12-15 12:32 | 2021-10-15 12:21 | 2022-01-28 20:20 |  | 2022-01-31 08:00 | 2022-01-31 08:00 | 2022-01-29 07:21 | 2022-02-07 12:00 | CR0013027 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 215 | 215 | 423.6388 | 4 | 1 | 1 | 0.02 | 193506 | 1.5 | 0 | 4 | 0 | 3 |  | 4 | 3 | 33 | 0 | 1.25 | 2020-12 | 4 | 1
2485 | CR0013027 | CTASK0023656 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 47 | 47 | 2020-12-31 | 2020-12-01 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Dev-Test]Mexico [enhancement]// Customs submission // X12 | 2020-12-03 16:40 | 2020-12-15 22:00 | 2020-12-15 12:32 | 2021-10-15 12:21 | 2022-01-28 20:20 |  | 2022-01-31 08:00 | 2022-01-31 08:00 | 2022-01-29 07:21 | 2022-02-07 12:00 | CR0013027 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 215 | 215 | 423.6388 | 4 | 1 | 1 | 0.02 | 193506 | 1.5 | 0 | 4 | 0 | 3 |  | 4 | 3 | 33 | 0 | 1.25 | 2020-12 | 4 | 1
2486 | CR0013027 | CTASK0023491 | Closed | OPUS-BKG-MFT-M | Tan Nguyen | 92 | 92 | 2020-11-30 | 2020-11-11 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Develop][License Service] Mexico [enhancement]// Customs submission // X12 | 2020-12-03 16:40 | 2020-12-15 22:00 | 2020-12-15 12:32 | 2021-10-15 12:21 | 2022-01-28 20:20 |  | 2022-01-31 08:00 | 2022-01-31 08:00 | 2022-01-29 07:21 | 2022-02-07 12:00 | CR0013027 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2022-W5 | 2022-01 | 215 | 215 | 423.6388 | 4 | 1 | 1 | 0.02 | 193506 | 1.5 | 0 | 4 | 0 | 3 |  | 4 | 3 | 33 | 0 | 1.25 | 2020-12 | 4 | 1
2487 | CR0014707 | CTASK0030311 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 13 | 20 | 2021-11-09 17:30 | 2021-11-05 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Dev + Test] BL Ready for Release Batch Report: Change report to include countries and offices under Expdoc RPA Phase 1C | 2021-11-09 11:56 | 2021-11-17 22:00 | 2021-11-15 12:37 | 2021-12-31 07:27 | 2021-12-31 08:47 |  | 2022-01-18 08:00 | 2022-01-18 09:45 | 2022-01-12 15:39 | 2022-01-25 12:00 | CR0014707 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2022-W3 | 2022-01 | 22 | 30 | 69.8362 | 3 | 1 | 1 | 0.02 | 193470 | 2.7 | 0 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0 | 0.11111 | 2021-11 | 0 | 0
2488 | CR0014707 | CTASK0030294 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 2 | 2 | 2021-11-04 17:30 | 2021-11-03 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Design] BL Ready for Release Batch Report: Change report to include countries and offices under Expdoc RPA Phase 1C | 2021-11-09 11:56 | 2021-11-17 22:00 | 2021-11-15 12:37 | 2021-12-31 07:27 | 2021-12-31 08:47 |  | 2022-01-18 08:00 | 2022-01-18 09:45 | 2022-01-12 15:39 | 2022-01-25 12:00 | CR0014707 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2022-W3 | 2022-01 | 22 | 30 | 69.8362 | 3 | 1 | 1 | 0.02 | 193470 | 2.7 | 0 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0 | 0.11111 | 2021-11 | 0 | 0
2489 | CR0014707 | CTASK0030312 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 7 | 8 | 2022-01-17 17:30 | 2022-01-13 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Deployment] BL Ready for Release Batch Report: Change report to include countries and offices under Expdoc RPA Phase 1C | 2021-11-09 11:56 | 2021-11-17 22:00 | 2021-11-15 12:37 | 2021-12-31 07:27 | 2021-12-31 08:47 |  | 2022-01-18 08:00 | 2022-01-18 09:45 | 2022-01-12 15:39 | 2022-01-25 12:00 | CR0014707 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2022-W3 | 2022-01 | 22 | 30 | 69.8362 | 3 | 1 | 1 | 0.02 | 193470 | 2.7 | 0 | 0 | 0 | 1 |  | 2 | 11 | 33 | 0 | 0.11111 | 2021-11 | 0 | 0
2490 | CR0013490 | CTASK0027642 | Closed | OPUS-SCO | Mohamed Hary | 50 | 50 | 2021-07-31 11:22 | 2021-07-01 11:22 | Container | Statement Management | Statement Account Receivable |  |  |  | [July 2021][Hary Mohamed]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 193489 | 2.1 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0.72727 | 0 | 2021-07 | 2 | 1
2491 | CR0013490 | CTASK0027638 | Closed | OPUS-SCO | Chuong Ta | 47 | 45 | 2021-07-31 11:17 | 2021-07-01 11:17 | Container | Statement Management | Statement Account Receivable |  |  |  | [July 2021][Chuong Ta]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 183379 | 2.4 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0.32 | 0.375 | 2021-07 | 2 | 1
2492 | CR0013490 | CTASK0027646 | Closed | OPUS-SCO | Lien Le | 36 | 35 | 2021-07-31 11:25 | 2021-07-01 11:25 | Container | Statement Management | Statement Account Receivable |  |  |  | [July 2021][Lien Le]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 193441 | 2.4 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0.42308 | 0 | 2021-07 | 2 | 1
2493 | CR0013490 | CTASK0027655 | Closed | OPUS-SCO | Nguyen Ha Vi | 31 | 30 | 2021-07-31 11:31 | 2021-07-01 11:31 | Container | Statement Management | Statement Account Receivable |  |  |  | [July 2021][Vi Nguyen]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 203664 | 1.1 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 1.8182 | 2.5 | 2021-07 | 2 | 1
2494 | CR0013490 | CTASK0027650 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 46 | 40 | 2021-07-31 11:26 | 2021-07-01 11:26 | Container | Statement Management | Statement Account Receivable |  |  |  | [July 2021][Phu Nguyen]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 203704 | 0.9 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0 | 0 | 2021-07 | 2 | 1
2495 | CR0013490 | CTASK0029230 | Closed | OPUS-SCO | Lien Le | 11 | 10 | 2021-09-30 17:13 | 2021-09-01 17:12 | Container | Statement Management | Statement Account Receivable |  |  |  | [Sep 2021][Lien Le] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 193441 | 2.4 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0.42308 | 0 | 2021-07 | 2 | 1
2496 | CR0013490 | CTASK0027640 | Closed | OPUS-SCO | Cuong Tran Hung | 46 | 45 | 2021-07-31 11:19 | 2021-07-01 11:19 | Container | Statement Management | Statement Account Receivable |  |  |  | [July 2021][Cuong Tran]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 193530 | 2.1 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 1.2308 | 1.25 | 2021-07 | 2 | 1
2497 | CR0013490 | CTASK0027637 | Closed | OPUS-SCO | Chuong Ta | 10 | 10 | 2021-06-30 11:16 | 2021-06-17 11:16 | Container | Statement Management | Statement Account Receivable |  |  |  | [June 2021][Chuong Ta]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 183379 | 2.4 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0.32 | 0.375 | 2021-07 | 2 | 1
2498 | CR0013490 | CTASK0027644 | Closed | OPUS-SCO | Lien Le | 11 | 10 | 2021-06-30 11:24 | 2021-06-17 11:24 | Container | Statement Management | Statement Account Receivable |  |  |  | [June 2021][Lien Le]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 193441 | 2.4 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0.42308 | 0 | 2021-07 | 2 | 1
2499 | CR0013490 | CTASK0027654 | Closed | OPUS-SCO | Nguyen Ha Vi | 10 | 10 | 2021-06-30 11:30 | 2021-06-17 11:30 | Container | Statement Management | Statement Account Receivable |  |  |  | [June 2021][Vi Nguyen]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 203664 | 1.1 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 1.8182 | 2.5 | 2021-07 | 2 | 1
2500 | CR0013490 | CTASK0027639 | Closed | OPUS-SCO | Cuong Tran Hung | 10 | 10 | 2021-06-30 11:18 | 2021-06-17 11:18 | Container | Statement Management | Statement Account Receivable |  |  |  | [June 2021][Cuong Tran]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 193530 | 2.1 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 1.2308 | 1.25 | 2021-07 | 2 | 1
2501 | CR0013490 | CTASK0029231 | Closed | OPUS-SCO | Mohamed Hary | 10 | 10 | 2021-09-30 17:14 | 2021-09-01 17:14 | Container | Statement Management | Statement Account Receivable |  |  |  | [Sep 2021][Hary] Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 193489 | 2.1 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0.72727 | 0 | 2021-07 | 2 | 1
2502 | CR0013490 | CTASK0027648 | Closed | OPUS-SCO | Nguyen Hoang Trong Phu | 10 | 10 | 2021-06-30 11:26 | 2021-06-17 11:26 | Container | Statement Management | Statement Account Receivable |  |  |  | [June 2021][Phu Nguyen]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 203704 | 0.9 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0 | 0 | 2021-07 | 2 | 1
2503 | CR0013490 | CTASK0027641 | Closed | OPUS-SCO | Mohamed Hary | 10 | 10 | 2021-06-30 11:20 | 2021-06-17 11:20 | Container | Statement Management | Statement Account Receivable |  |  |  | [June 2021][Hary Mohamed]Changes needed in OPUS to enable ONE Turkey PTE to USE OPUS CLEAR Functionality | 2021-07-21 07:08 | 2021-10-15 16:00 | 2021-10-01 09:42 | 2022-03-16 12:34 | 2022-04-21 18:20 |  | 2022-04-26 10:00 | 2022-04-26 13:20 | 2022-04-22 14:44 | 2022-07-09 12:00 | CR0013490 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2022-W17 | 2022-04 | 328 | 325 | 279.1194 | 14 | 1 | 6 | 0.05 | 193489 | 2.1 | 3 | 2 | 0 | 4 |  | 3 | 6 | 18 | 0.72727 | 0 | 2021-07 | 2 | 1
2504 | CR0014822 | CTASK0030755 | Closed | OPUS-CHS | Tuyen Truong | 35 | 30 | 2022-01-31 17:05 | 2021-12-01 17:05 | [6 empty] | [CGM] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-CHS | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 173255 | 3.2 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2505 | CR0014822 | CTASK0030965 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 10 | 10 | 2021-12-31 09:43 | 2021-12-01 09:43 | [6 empty] | [BKG-MFT] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-BKG-MFT-A | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193606 | 2.1 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 4.25 | 0 | 2021-11 | 0 | 0
2506 | CR0014822 | CTASK0030765 | Closed | OPUS-JOO | Huy Vu | 40 | 40 | [8 empty] | [JOO] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-JOO | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193618 | 1.8 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2507 | CR0014822 | CTASK0031018 | Closed | OPUS-BSA | Tuan Pham Huu | 40 | 40 | 2022-01-31 13:36 | 2021-12-01 13:36 | [6 empty] | [BSA] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-BSA | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193523 | 2.5 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.5 | 0 | 2021-11 | 0 | 0
2508 | CR0014822 | CTASK0030834 | Closed | OPUS-SAP | Chuong Ta | 14 | 14 | 2021-11-30 09:26 | 2021-11-29 09:26 | [6 empty] | [NOV][SAP] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-SAP | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 183379 | 2.7 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.32 | 0.375 | 2021-11 | 0 | 0
2509 | CR0014822 | CTASK0030805 | Closed | OPUS-MDA | Thuan Tran | 40 | 40 | 2021-12-31 07:48 | 2021-12-01 07:48 | [6 empty] | [MDA OPERV] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-MDA | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 183423 | 3 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2510 | CR0014822 | CTASK0030967 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 20 | 20 | 2021-12-31 09:57 | 2021-12-01 09:57 | [6 empty] | [BKG-IB] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-BKG-IB | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193512 | 2.4 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.2963 | 0 | 2021-11 | 0 | 0
2511 | CR0014822 | CTASK0030803 | Closed | OPUS-TPB | Manh Nguyen | 15 | 20 | 2022-01-18 20:00 | 2021-12-01 06:00 | [6 empty] | [TPB] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-TPB | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 153138 | 3.2 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.16667 | 0 | 2021-11 | 0 | 0
2512 | CR0014822 | CTASK0031746 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 14 | 20 | 2022-01-19 15:25 | 2022-01-11 15:25 | [6 empty] | [BKG-IB] [CLT Internal] OPUS Source Code Clean Up (PROD site) | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-BKG-IB | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193512 | 2.4 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.2963 | 0 | 2021-11 | 0 | 0
2513 | CR0014822 | CTASK0030764 | Closed | OPUS-PSO | Lanh Le | 40 | 40 | 2022-01-18 22:00 | 2021-12-01 07:00 | [6 empty] | [PSO] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-PSO | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 183422 | 3 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2514 | CR0014822 | CTASK0031657 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 8 | 8 | 2022-01-31 23:04 | 2022-01-01 23:04 | [6 empty] | [BKG-MFT] [CLT Internal] OPUS Source Code Clean Up (PROD site) | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-BKG-MFT-E | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193606 | 2.1 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 4.25 | 0 | 2021-11 | 0 | 0
2515 | CR0014822 | CTASK0030763 | Closed | OPUS-OPF | Huy Vu | 40 | 40 | 2022-01-18 22:00 | 2021-12-01 07:00 | [6 empty] | [OPF] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-OPF | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193618 | 1.8 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2516 | CR0014822 | CTASK0031050 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 19 | 30 | [8 empty] | [TRS] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-TRS | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 183432 | 2.7 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.043478 | 0.22222 | 2021-11 | 0 | 0
2517 | CR0014822 | CTASK0031017 | Closed | OPUS-ACM | Huynh Tuan Khanh | 62 | 50 | 2022-01-31 13:33 | 2021-12-01 13:33 | [6 empty] | [ACM&AGT] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-ACM | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193499 | 2.5 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2518 | CR0014822 | CTASK0031220 | Closed | OPUS-TRS | Giang Nguyen Hoang | 36 | 30 | [8 empty] | [TRS] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-TRS | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 183440 | 2.7 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2519 | CR0014822 | CTASK0030754 | Closed | OPUS-MNR | Tuyen Truong | 40 | 40 | 2022-01-31 17:01 | 2021-12-01 17:01 | [6 empty] | [MNR] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-MNR | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 173255 | 3.2 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2520 | CR0014822 | CTASK0030940 | Closed | OPUS-SAP | Chuong Ta | 27 | 26 | 2021-12-31 11:43 | 2021-12-01 11:43 | [6 empty] | [DEC][SAP] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-SAP | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 183379 | 2.7 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.32 | 0.375 | 2021-11 | 0 | 0
2521 | CR0014822 | CTASK0031978 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 7 | 16 | 2022-02-09 14:27 | 2022-01-24 14:27 | [6 empty] | [BKG-IB] [CLT Internal][Additional] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-BKG-IB | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193512 | 2.4 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.2963 | 0 | 2021-11 | 0 | 0
2522 | CR0014822 | CTASK0030762 | Closed | OPUS-VSK | Huy Vu | 40 | 40 | 2022-01-18 22:00 | 2021-12-01 07:00 | [6 empty] | [VSK] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-VSK | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193618 | 1.8 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2523 | CR0014822 | CTASK0031711 | Closed | OPUS-BKG-MFT-A | Linh Dinh Bo | 21 | 18 | 2022-01-13 13:13 | 2022-01-10 13:13 | [6 empty] | [BKG-MFT] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-BKG-MFT-A | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193522 | 2.5 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2524 | CR0014822 | CTASK0030804 | Closed | OPUS-SCG | Trang Duy Thong | 40 | 40 | 2021-12-31 07:47 | 2021-12-01 07:47 | [6 empty] | [SCG] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-SCG | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193511 | 1.5 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.81818 | 2.6667 | 2021-11 | 0 | 0
2525 | CR0014822 | CTASK0030941 | Closed | OPUS-SCO | Chuong Ta | 44 | 40 | 2021-12-31 11:44 | 2021-12-01 11:44 | [6 empty] | [SCO] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-SCO | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 183379 | 2.7 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.32 | 0.375 | 2021-11 | 0 | 0
2526 | CR0014822 | CTASK0030777 | Closed | OPUS-DMT | Cuong Nguyen | 34 | 40 | 2022-01-21 11:56 | 2021-12-27 11:56 | [6 empty] | [DMT] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-DMT | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193529 | 2.5 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.11538 | 0.22222 | 2021-11 | 0 | 0
2527 | CR0014822 | CTASK0030821 | Closed | OPUS-FLT | Tran Anh Duy | 39 | 40 | 2022-01-18 14:31 | 2021-12-01 14:31 | [6 empty] | [FLT] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-FLT | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 193516 | 2.7 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2528 | CR0014822 | CTASK0030802 | Closed | OPUS-TES | Thai Nguyen | 27 | 30 | 2022-01-18 20:00 | 2021-12-01 06:00 | [6 empty] | [TES] [CLT Internal] OPUS Source Code Clean Up | 2021-11-29 11:24 | 2022-02-28 11:24 | 2022-01-13 09:39 |  | 2022-01-13 09:39 |  | 2022-01-18 09:39 | 2022-01-18 11:29 | 2022-01-13 15:02 | 2022-01-27 12:00 | CR0014822 |  | OPUS-TES | 2022-W3 | 2022-01 | 672 | 762 | 49.9267 | 25 | 20 | 17 | 0.64 | 173249 | 3.2 | 5 | 0 | 0 | 4 |  | 1 | 11 | 33 | 0.89474 | 0 | 2021-11 | 0 | 0
2529 | CR0014132 | CTASK0030339 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 39 | 35 | 2021-11-16 10:35 | 2021-11-01 10:34 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Deployment+ Testing] (HBA) EUA AUTH ¦ Using last received ATB# for Full Cargo Release in DE ports | 2021-09-06 14:11 | 2021-10-01 21:09 | 2021-10-01 15:02 | 2021-10-07 11:56 | 2021-11-03 12:19 |  | 2021-11-16 12:19 | 2021-12-21 14:01 | 2021-11-04 07:19 | 2021-12-29 12:00 | CR0014132 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W46 | 2021-11 | 82 | 83 | 70.922 | 3 | 2 | 3 | 0.05 | 193512 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.2963 | 0 | 2021-09 | 0 | 0
2530 | CR0014132 | CTASK0027988 | Closed | OPUS-BKG-IB | Thuc Tran | 40 | 40 | 2021-08-31 17:30 | 2021-08-02 09:00 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Development + Testing + Deployment] (HBA) EUA AUTH ¦ Using last received ATB# for Full Cargo Release in DE ports | 2021-09-06 14:11 | 2021-10-01 21:09 | 2021-10-01 15:02 | 2021-10-07 11:56 | 2021-11-03 12:19 |  | 2021-11-16 12:19 | 2021-12-21 14:01 | 2021-11-04 07:19 | 2021-12-29 12:00 | CR0014132 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W46 | 2021-11 | 82 | 83 | 70.922 | 3 | 2 | 3 | 0.05 | 173280 | 2.7 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 0.375 | 1 | 2021-09 | 0 | 0
2531 | CR0014132 | CTASK0031288 | Closed | OPUS-BKG-MFT-E | Tung Nguyen Thanh | 3 | 8 | 2021-12-31 17:44 | 2021-12-13 17:44 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [PROD] (HBA) EUA AUTH ¦ Using last received ATB# for Full Cargo Release in DE ports | 2021-09-06 14:11 | 2021-10-01 21:09 | 2021-10-01 15:02 | 2021-10-07 11:56 | 2021-11-03 12:19 |  | 2021-11-16 12:19 | 2021-12-21 14:01 | 2021-11-04 07:19 | 2021-12-29 12:00 | CR0014132 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2021-W46 | 2021-11 | 82 | 83 | 70.922 | 3 | 2 | 3 | 0.05 | 193606 | 1.9 | 1 | 0 | 0 | 1 |  | 2 | 16 | 38 | 4.25 | 2.25 | 2021-09 | 0 | 0
2532 | CR0015046 | CTASK0031937 | Closed | OPUS-TPB | Manh Nguyen | 4 | 4 | 2022-01-31 15:29 | 2022-01-03 15:29 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202201][CLT Internal] NA * TPB * Customer Code updated but Bill To did not | 2022-02-08 13:40 | 2022-03-04 19:37 | 2022-03-02 11:00 | 2022-03-18 12:07 | 2022-03-18 12:57 |  | 2022-03-29 09:30 | 2022-03-29 09:56 | 2022-03-23 16:36 | 2022-04-05 12:00 | CR0015046 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2022-W13 | 2022-03 | 68 | 69 | 48.8267 | 3 | 1 | 1 | 0.06 | 153138 | 3.4 | 1 | 0 | 0 | 1 |  | 1 | 6 | 38 | 0.16667 | 0 | 2022-02 | 0 | 0
2533 | CR0015046 | CTASK0032608 | Closed | OPUS-TPB | Manh Nguyen | 9 | 10 | 2022-03-31 13:18 | 2022-03-02 13:18 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202203][CLT Internal] NA * TPB * Customer Code updated but Bill To did not | 2022-02-08 13:40 | 2022-03-04 19:37 | 2022-03-02 11:00 | 2022-03-18 12:07 | 2022-03-18 12:57 |  | 2022-03-29 09:30 | 2022-03-29 09:56 | 2022-03-23 16:36 | 2022-04-05 12:00 | CR0015046 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2022-W13 | 2022-03 | 68 | 69 | 48.8267 | 3 | 1 | 1 | 0.06 | 153138 | 3.4 | 1 | 0 | 0 | 1 |  | 1 | 6 | 38 | 0.16667 | 0 | 2022-02 | 0 | 0
2534 | CR0015046 | CTASK0032075 | Closed | OPUS-TPB | Manh Nguyen | 55 | 55 | 2022-02-28 19:00 | 2022-02-03 06:00 | Container | Service Management | 3rd Party Billing | TPB Process | Invoice Revise/Cancel |  | [202202][CLT Internal] NA * TPB * Customer Code updated but Bill To did not | 2022-02-08 13:40 | 2022-03-04 19:37 | 2022-03-02 11:00 | 2022-03-18 12:07 | 2022-03-18 12:57 |  | 2022-03-29 09:30 | 2022-03-29 09:56 | 2022-03-23 16:36 | 2022-04-05 12:00 | CR0015046 | Service Management3rd Party BillingTPB ProcessInvoice Revise/Cancel | OPUS-TPB | 2022-W13 | 2022-03 | 68 | 69 | 48.8267 | 3 | 1 | 1 | 0.06 | 153138 | 3.4 | 1 | 0 | 0 | 1 |  | 1 | 6 | 38 | 0.16667 | 0 | 2022-02 | 0 | 0
2535 | CR0014527 | CTASK0029901 | Closed | OPUS-SCG | Lanh Le | 170 | 170 | 2021-12-31 13:12 | 2021-10-11 13:12 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL for Own BKG |  | New DG EDI exchange with WAN HAI LINES & ONE | 2021-11-19 12:45 | 2021-12-31 12:44 | 2021-12-31 07:21 | 2022-01-13 15:46 | 2022-01-14 08:01 |  | 2022-01-18 08:01 | 2022-01-18 08:00 | 2022-01-14 12:25 | 2022-01-28 12:00 | CR0014527 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL for Own BKG | OPUS-SCG | 2022-W3 | 2022-01 | 170 | 170 | 59.803 | 1 | 1 | 1 | 0.12 | 183422 | 3 | 2 | 0 | 0 | 2 |  | 2 | 11 | 33 | 0 | 0 | 2021-11 | 0 | 0
2536 | CR0014526 | CTASK0029534 | Closed | OPUS-BKG-M | Kieu Le | 6 | 6 | 2021-11-30 08:55 | 2021-11-01 08:55 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Next VVD Assign | [Deployment] [CLT Internal] Next VVD Assign Screen Enhancement | 2021-10-05 16:28 | 2021-10-21 | 2021-10-15 14:43 | 2021-11-09 09:39 | 2021-11-09 11:18 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-11 08:21 | 2021-12-15 12:00 | CR0014526 | Service ManagementBooking/DocumentationOperationTransshipmentNext VVD Assign | OPUS-BKG-M | 2021-W49 | 2021-12 | 45 | 47 | 62.6472 | 5 | 1 | 1 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2537 | CR0014526 | CTASK0029677 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-10-08 20:03 | 2021-10-01 00:03 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Next VVD Assign | [Development] [CLT Internal] Next VVD Assign Screen Enhancement | 2021-10-05 16:28 | 2021-10-21 | 2021-10-15 14:43 | 2021-11-09 09:39 | 2021-11-09 11:18 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-11 08:21 | 2021-12-15 12:00 | CR0014526 | Service ManagementBooking/DocumentationOperationTransshipmentNext VVD Assign | OPUS-BKG-M | 2021-W49 | 2021-12 | 45 | 47 | 62.6472 | 5 | 1 | 1 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2538 | CR0014526 | CTASK0029531 | Closed | OPUS-BKG-M | Kieu Le | 10 | 12 | 2021-09-30 12:52 | 2021-09-27 00:52 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Next VVD Assign | [Development] [CLT Internal] Next VVD Assign Screen Enhancement | 2021-10-05 16:28 | 2021-10-21 | 2021-10-15 14:43 | 2021-11-09 09:39 | 2021-11-09 11:18 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-11 08:21 | 2021-12-15 12:00 | CR0014526 | Service ManagementBooking/DocumentationOperationTransshipmentNext VVD Assign | OPUS-BKG-M | 2021-W49 | 2021-12 | 45 | 47 | 62.6472 | 5 | 1 | 1 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2539 | CR0014526 | CTASK0029530 | Closed | OPUS-BKG-M | Kieu Le | 5 | 5 | 2021-09-30 20:51 | 2021-09-24 00:50 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Next VVD Assign | [Design] [CLT Internal] Next VVD Assign Screen Enhancement | 2021-10-05 16:28 | 2021-10-21 | 2021-10-15 14:43 | 2021-11-09 09:39 | 2021-11-09 11:18 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-11 08:21 | 2021-12-15 12:00 | CR0014526 | Service ManagementBooking/DocumentationOperationTransshipmentNext VVD Assign | OPUS-BKG-M | 2021-W49 | 2021-12 | 45 | 47 | 62.6472 | 5 | 1 | 1 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2540 | CR0014526 | CTASK0029532 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-10-15 20:54 | 2021-10-11 08:54 | Container | Service Management | Booking/Documentation | Operation | Transshipment | Next VVD Assign | [Testing] [CLT Internal] Next VVD Assign Screen Enhancement | 2021-10-05 16:28 | 2021-10-21 | 2021-10-15 14:43 | 2021-11-09 09:39 | 2021-11-09 11:18 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-11-11 08:21 | 2021-12-15 12:00 | CR0014526 | Service ManagementBooking/DocumentationOperationTransshipmentNext VVD Assign | OPUS-BKG-M | 2021-W49 | 2021-12 | 45 | 47 | 62.6472 | 5 | 1 | 1 | 0.03 | 153106 | 3 | 1 | 0 | 0 | 1 |  | 2 | 10 | 26 | 0.22951 | 0 | 2021-10 | 0 | 0
2541 | CR0014955 | CTASK0031836 | Closed | OPUS-DMT | Cuong Nguyen | 26 | 45 | 2022-02-18 12:34 | 2022-01-03 12:34 | Container | Service Management | Demurrage/Detention |  |  |  | [Documentation] [TASK1] | 2022-01-19 12:27 | 2022-02-26 12:26 | 2022-01-28 08:41 | 2022-03-24 07:31 | 2022-03-24 07:53 |  | 2022-03-29 07:53 | 2022-03-29 12:47 | 2022-03-24 14:55 | 2023-01-12 12:00 | CR0014955 | Service ManagementDemurrage/Detention | OPUS-DMT | 2022-W13 | 2022-03 | 26 | 45 | 68.8096 | 1 | 1 | 1 | 0.03 | 193529 | 2.6 | 0 | 0 | 0 | 1 |  | 2 | 6 | 38 | 0 | 0.22222 | 2022-01 | 0 | 0
2542 | CR0013873 | CTASK0026586 | Closed | OPUS-FLT | Tran Anh Duy | 18 | 18 |  |  | Container | Support & Admin | Fleet Management | Contract | Schedule Management | Off Hire Entry | [CLV][CLT Internal] Calculation change for average C/H rate in Off-Hire entry | 2021-04-23 08:55 | 2021-05-31 16:30 | 2021-05-25 15:13 | 2021-11-29 08:12 | 2021-11-29 09:03 |  | 2021-12-14 08:00 | 2021-12-14 08:00 | 2021-12-10 14:46 | 2021-12-21 12:01 | CR0013873 | Support & AdminFleet ManagementContractSchedule ManagementOff Hire Entry | OPUS-FLT | 2021-W50 | 2021-12 | 34 | 34 | 234.9621 | 2 | 1 | 1 | 0.01 | 193516 | 2.1 | 3 | 0 | 0 | 1 |  | 3 | 6 | 26 | 0 | 0 | 2021-04 | 0 | 0
2543 | CR0013873 | CTASK0026585 | Closed | OPUS-FLT | Tran Anh Duy | 16 | 16 |  |  | Container | Support & Admin | Fleet Management | Contract | Schedule Management | Off Hire Entry | [Documentation][CLT Internal] Calculation change for average C/H rate in Off-Hire entry | 2021-04-23 08:55 | 2021-05-31 16:30 | 2021-05-25 15:13 | 2021-11-29 08:12 | 2021-11-29 09:03 |  | 2021-12-14 08:00 | 2021-12-14 08:00 | 2021-12-10 14:46 | 2021-12-21 12:01 | CR0013873 | Support & AdminFleet ManagementContractSchedule ManagementOff Hire Entry | OPUS-FLT | 2021-W50 | 2021-12 | 34 | 34 | 234.9621 | 2 | 1 | 1 | 0.01 | 193516 | 2.1 | 3 | 0 | 0 | 1 |  | 3 | 6 | 26 | 0 | 0 | 2021-04 | 0 | 0
2544 | CR0015224 | CTASK0032991 | Closed | OPUS-BKG-M | Tuan Pham Huu | 4 | 4 | 2022-03-22 09:47 | 2022-03-14 09:47 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Design] Global *EDI* - Addition of A/Customer customer code (Actual Customer - Named Account) in 301 F/F (TRADELENS : ONES-184) | 2022-04-04 07:36 | 2022-04-27 22:00 | 2022-04-26 13:43 | 2022-05-03 07:32 | 2022-05-03 11:06 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-12 11:41 | 2022-05-24 12:00 | CR0015224 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2022-W20 | 2022-05 | 43 | 38 | 43.0165 | 4 | 1 | 1 | 0.04 | 193523 | 2.8 | 1 | 0 | 0 | 1 |  | 1 | 8 | 26 | 0.5 | 0 | 2022-04 | 0 | 0
2545 | CR0015224 | CTASK0033028 | Closed | OPUS-BKG-M | Tuan Pham Huu | 9 | 8 | 2022-04-22 | 2022-04-18 06:00 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Testing] Global *EDI* - Addition of A/Customer customer code (Actual Customer - Named Account) in 301 F/F (TRADELENS : ONES-184) | 2022-04-04 07:36 | 2022-04-27 22:00 | 2022-04-26 13:43 | 2022-05-03 07:32 | 2022-05-03 11:06 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-12 11:41 | 2022-05-24 12:00 | CR0015224 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2022-W20 | 2022-05 | 43 | 38 | 43.0165 | 4 | 1 | 1 | 0.04 | 193523 | 2.8 | 1 | 0 | 0 | 1 |  | 1 | 8 | 26 | 0.5 | 0 | 2022-04 | 0 | 0
2546 | CR0015224 | CTASK0033026 | Closed | OPUS-BKG-M | Tuan Pham Huu | 24 | 20 | 2022-04-08 | 2022-04-04 06:00 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Development] Global *EDI* - Addition of A/Customer customer code (Actual Customer - Named Account) in 301 F/F (TRADELENS : ONES-184) | 2022-04-04 07:36 | 2022-04-27 22:00 | 2022-04-26 13:43 | 2022-05-03 07:32 | 2022-05-03 11:06 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-12 11:41 | 2022-05-24 12:00 | CR0015224 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2022-W20 | 2022-05 | 43 | 38 | 43.0165 | 4 | 1 | 1 | 0.04 | 193523 | 2.8 | 1 | 0 | 0 | 1 |  | 1 | 8 | 26 | 0.5 | 0 | 2022-04 | 0 | 0
2547 | CR0015224 | CTASK0033029 | Closed | OPUS-BKG-M | Tuan Pham Huu | 6 | 6 |  |  | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (EDI) | [Deployment] Global *EDI* - Addition of A/Customer customer code (Actual Customer - Named Account) in 301 F/F (TRADELENS : ONES-184) | 2022-04-04 07:36 | 2022-04-27 22:00 | 2022-04-26 13:43 | 2022-05-03 07:32 | 2022-05-03 11:06 |  | 2022-05-17 08:00 | 2022-05-17 08:00 | 2022-05-12 11:41 | 2022-05-24 12:00 | CR0015224 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (EDI) | OPUS-BKG-M | 2022-W20 | 2022-05 | 43 | 38 | 43.0165 | 4 | 1 | 1 | 0.04 | 193523 | 2.8 | 1 | 0 | 0 | 1 |  | 1 | 8 | 26 | 0.5 | 0 | 2022-04 | 0 | 0
2548 | CR0014902 | CTASK0031504 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 20 | 20 | 2022-01-18 17:48 | 2022-01-12 08:48 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Development][CLT Internal] Enhance manual sending BRN logic | 2022-01-17 07:11 | 2022-02-16 | 2022-02-09 14:31 | 2022-02-15 07:17 | 2022-02-15 08:21 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-15 13:20 | 2022-03-10 12:00 | CR0014902 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W9 | 2022-03 | 28 | 40 | 44.034 | 4 | 1 | 1 | 0.04 | 193488 | 2.6 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.53659 | 0 | 2022-01 | 0 | 0
2549 | CR0014902 | CTASK0031505 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2022-01-28 13:01 | 2022-01-17 13:01 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Testing][CLT Internal] Enhance manual sending BRN logic | 2022-01-17 07:11 | 2022-02-16 | 2022-02-09 14:31 | 2022-02-15 07:17 | 2022-02-15 08:21 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-15 13:20 | 2022-03-10 12:00 | CR0014902 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W9 | 2022-03 | 28 | 40 | 44.034 | 4 | 1 | 1 | 0.04 | 193488 | 2.6 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.53659 | 0 | 2022-01 | 0 | 0
2550 | CR0014902 | CTASK0031506 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 4 | 4 | 2022-02-25 13:01 | 2022-02-21 13:01 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Deployment][CLT Internal] Enhance manual sending BRN logic | 2022-01-17 07:11 | 2022-02-16 | 2022-02-09 14:31 | 2022-02-15 07:17 | 2022-02-15 08:21 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-15 13:20 | 2022-03-10 12:00 | CR0014902 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W9 | 2022-03 | 28 | 40 | 44.034 | 4 | 1 | 1 | 0.04 | 193488 | 2.6 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.53659 | 0 | 2022-01 | 0 | 0
2551 | CR0014902 | CTASK0031385 | Closed | OPUS-BKG-M | Dat Nguyen Hoang | 8 | 8 | 2022-01-05 17:46 | 2021-12-29 08:46 | Container | Service Management | Booking/Documentation | Booking | Fax/Email/EDI | Booking Receipt Notice (Fax/Email) | [Design] [CLT Internal] Enhance manual sending BRN logic | 2022-01-17 07:11 | 2022-02-16 | 2022-02-09 14:31 | 2022-02-15 07:17 | 2022-02-15 08:21 |  | 2022-03-02 08:00 | 2022-03-02 08:00 | 2022-02-15 13:20 | 2022-03-10 12:00 | CR0014902 | Service ManagementBooking/DocumentationBookingFax/Email/EDIBooking Receipt Notice (Fax/Email) | OPUS-BKG-M | 2022-W9 | 2022-03 | 28 | 40 | 44.034 | 4 | 1 | 1 | 0.04 | 193488 | 2.6 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.53659 | 0 | 2022-01 | 0 | 0
2552 | CR0014224 | CTASK0029401 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 16 | 16 | 2021-11-23 17:30 | 2021-11-19 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Design] Asia * BKG/DOC BL clause remarks to print directly on BL and collect surcharge on OBL | 2021-12-29 09:27 | 2022-01-21 09:26 | 2022-01-17 07:14 | 2022-04-20 07:51 | 2022-04-20 07:57 |  | 2022-05-03 07:57 | 2022-05-03 08:17 | 2022-04-27 16:04 | 2022-05-10 12:00 | CR0014224 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2022-W18 | 2022-05 | 116 | 116 | 124.9375 | 3 | 1 | 1 | 0.04 | 193470 | 2.8 | 1 | 0 | 0 | 2 |  | 2 | 2 | 26 | 0.36842 | 0.11111 | 2021-12 | 0 | 0
2553 | CR0014224 | CTASK0030637 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 12 | 12 | 2022-04-29 17:21 | 2022-04-25 17:21 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Deployment] Asia * BKG/DOC BL clause remarks to print directly on BL and collect surcharge on OBL | 2021-12-29 09:27 | 2022-01-21 09:26 | 2022-01-17 07:14 | 2022-04-20 07:51 | 2022-04-20 07:57 |  | 2022-05-03 07:57 | 2022-05-03 08:17 | 2022-04-27 16:04 | 2022-05-10 12:00 | CR0014224 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2022-W18 | 2022-05 | 116 | 116 | 124.9375 | 3 | 1 | 1 | 0.04 | 193470 | 2.8 | 1 | 0 | 0 | 2 |  | 2 | 2 | 26 | 0.36842 | 0.11111 | 2021-12 | 0 | 0
2554 | CR0014224 | CTASK0030636 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 88 | 88 | 2021-12-31 21:59 | 2021-11-23 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | B/L Issue [Alt+8] | [Dev + Test] Asia * BKG/DOC BL clause remarks to print directly on BL and collect surcharge on OBL | 2021-12-29 09:27 | 2022-01-21 09:26 | 2022-01-17 07:14 | 2022-04-20 07:51 | 2022-04-20 07:57 |  | 2022-05-03 07:57 | 2022-05-03 08:17 | 2022-04-27 16:04 | 2022-05-10 12:00 | CR0014224 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintB/L Issue [Alt+8] | OPUS-BKG-OB | 2022-W18 | 2022-05 | 116 | 116 | 124.9375 | 3 | 1 | 1 | 0.04 | 193470 | 2.8 | 1 | 0 | 0 | 2 |  | 2 | 2 | 26 | 0.36842 | 0.11111 | 2021-12 | 0 | 0
2555 | CR0014260 | CTASK0028511 | Closed | OPUS-PRI | Ngan Nham | 26 | 26 | 2021-08-31 23:00 | 2021-08-01 23:00 | Data Integration | Customer |  |  |  |  | [Develop] Change the Customer Hierarchy | 2021-07-28 15:49 | 2021-08-20 23:00 | 2021-08-20 06:22 | 2021-09-14 14:51 | 2021-09-28 09:52 |  | 2021-09-28 10:00 | 2021-09-28 09:00 | 2022-01-27 13:41 | 2022-02-04 12:00 | CR0014260 | Customer | OPUS-PRI | 2021-W39 | 2021-09 | 60 | 60 | 61.7579 | 3 | 1 | 1 | 0.04 | 193461 | 2.7 | 0 | 0 | 0 | 1 |  | 2 | 6 | 6 | 0 | 0 | 2021-07 | 0 | 0
2556 | CR0014260 | CTASK0028406 | Closed | OPUS-PRI | Ngan Nham | 20 | 20 | 2021-07-30 23:00 | 2021-07-25 23:00 | Data Integration | Customer |  |  |  |  | [Develop] Change the Customer Hierarchy | 2021-07-28 15:49 | 2021-08-20 23:00 | 2021-08-20 06:22 | 2021-09-14 14:51 | 2021-09-28 09:52 |  | 2021-09-28 10:00 | 2021-09-28 09:00 | 2022-01-27 13:41 | 2022-02-04 12:00 | CR0014260 | Customer | OPUS-PRI | 2021-W39 | 2021-09 | 60 | 60 | 61.7579 | 3 | 1 | 1 | 0.04 | 193461 | 2.7 | 0 | 0 | 0 | 1 |  | 2 | 6 | 6 | 0 | 0 | 2021-07 | 0 | 0
2557 | CR0014260 | CTASK0029208 | Closed | OPUS-PRI | Ngan Nham | 14 | 14 | 2021-09-30 23:00 | 2021-09-05 23:00 | Data Integration | Customer |  |  |  |  | [Develop] Change the Customer Hierarchy | 2021-07-28 15:49 | 2021-08-20 23:00 | 2021-08-20 06:22 | 2021-09-14 14:51 | 2021-09-28 09:52 |  | 2021-09-28 10:00 | 2021-09-28 09:00 | 2022-01-27 13:41 | 2022-02-04 12:00 | CR0014260 | Customer | OPUS-PRI | 2021-W39 | 2021-09 | 60 | 60 | 61.7579 | 3 | 1 | 1 | 0.04 | 193461 | 2.7 | 0 | 0 | 0 | 1 |  | 2 | 6 | 6 | 0 | 0 | 2021-07 | 0 | 0
2558 | CR0012061 | CTASK0022427 | Closed | OPUS-BKG-M | Vinh Tran | 52 | 50 | 2021-04-24 | 2021-04-05 | Container | Service Management | Trans S/O |  |  |  | PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 193525 | 1.7 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0.41667 | 0.47368 | 2021-02 | 1 | 1
2559 | CR0012061 | CTASK0030354 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 21 | 30 |  |  | Container | Service Management | Trans S/O |  |  |  | [202111] PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 183432 | 2 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0.043478 | 0 | 2021-02 | 1 | 1
2560 | CR0012061 | CTASK0028531 | Closed | OPUS-TRS | Giang Nguyen Hoang | 14 | 15 |  |  | Container | Service Management | Trans S/O |  |  |  | [202108] PARIS Phase 1 - Additional requirements to add to CR0012061 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 183440 | 2 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0 | 0 | 2021-02 | 1 | 1
2561 | CR0012061 | CTASK0026185 | Closed | OPUS-TRS | Giang Nguyen Hoang | 40 | 40 | 2021-04-30 14:32 | 2021-04-01 14:32 | Container | Service Management | Trans S/O |  |  |  | [202104] PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 183440 | 2 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0 | 0 | 2021-02 | 1 | 1
2562 | CR0012061 | CTASK0029732 | Closed | OPUS-TRS | Giang Nguyen Hoang | 21 | 30 |  |  | Container | Service Management | Trans S/O |  |  |  | [202110] PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 183440 | 2 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0 | 0 | 2021-02 | 1 | 1
2563 | CR0012061 | CTASK0028520 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 16 | 15 |  |  | Container | Service Management | Trans S/O |  |  |  | [202108] PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 183432 | 2 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0.043478 | 0 | 2021-02 | 1 | 1
2564 | CR0012061 | CTASK0025781 | Closed | OPUS-TRS | Giang Nguyen Hoang | 59 | 60 | 2021-03-31 14:39 | 2021-03-10 14:39 | Container | Service Management | Trans S/O |  |  |  | [202103] PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 183440 | 2 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0 | 0 | 2021-02 | 1 | 1
2565 | CR0012061 | CTASK0029729 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 57 | 60 |  |  | Container | Service Management | Trans S/O |  |  |  | [202110] PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 183432 | 2 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0.043478 | 0 | 2021-02 | 1 | 1
2566 | CR0012061 | CTASK0030143 | Closed | OPUS-BKG-M | Vinh Tran | 11 | 11 | 2021-10-30 | 2021-10-25 | Container | Service Management | Trans S/O |  |  |  | [Deployment] PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 193525 | 1.7 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0.41667 | 0.47368 | 2021-02 | 1 | 1
2567 | CR0012061 | CTASK0025780 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 60 | 60 | 2021-03-31 14:39 | 2021-03-10 14:39 | Container | Service Management | Trans S/O |  |  |  | [202103] PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 183432 | 2 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0.043478 | 0 | 2021-02 | 1 | 1
2568 | CR0012061 | CTASK0026184 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 45 | 40 | 2021-04-30 14:31 | 2021-04-01 14:31 | Container | Service Management | Trans S/O |  |  |  | [202104] PARIS Phase 1 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:23 | 2021-10-07 19:34 | 2021-10-28 09:07 |  | 2021-11-03 22:00 | 2021-11-03 09:15 | 2021-10-29 08:40 | 2021-11-10 12:00 | CR0012061 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 396 | 400 | 254.5552 | 11 | 2 | 3 | 0.07 | 183432 | 2 | 2 | 0 | 1 | 4 |  | 3 | 3 | 38 | 0.043478 | 0 | 2021-02 | 1 | 1
2569 | CR0013940 | CTASK0027349 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 125 | 140 |  |  | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Develop] ROOT Project Squad 16 - Booking Reconciliation Process - ENS Filling (Validation) | 2021-06-07 07:25 | 2021-07-28 22:00 | 2021-07-28 17:47 | 2021-11-23 17:25 | 2021-11-29 14:13 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-12-02 13:04 | 2021-12-14 12:01 | CR0013940 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 169 | 198 | 183.0246 | 4 | 1 | 1 | 0.05 | 193606 | 1.6 | 1 | 0 | 0 | 2 |  | 3 | 10 | 26 | 4.25 | 2.25 | 2021-06 | 0 | 0
2570 | CR0013940 | CTASK0027350 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 31 | 40 | 2021-07-31 11:22 | 2021-07-01 11:22 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Test] ROOT Project Squad 16 - Booking Reconciliation Process - ENS Filling (Validation) | 2021-06-07 07:25 | 2021-07-28 22:00 | 2021-07-28 17:47 | 2021-11-23 17:25 | 2021-11-29 14:13 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-12-02 13:04 | 2021-12-14 12:01 | CR0013940 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 169 | 198 | 183.0246 | 4 | 1 | 1 | 0.05 | 193606 | 1.6 | 1 | 0 | 0 | 2 |  | 3 | 10 | 26 | 4.25 | 2.25 | 2021-06 | 0 | 0
2571 | CR0013940 | CTASK0027340 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 10 | 10 | 2021-07-31 11:20 | 2021-07-31 11:20 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Design] ROOT Project Squad 16 - Booking Reconciliation Process - ENS Filling (Validation) | 2021-06-07 07:25 | 2021-07-28 22:00 | 2021-07-28 17:47 | 2021-11-23 17:25 | 2021-11-29 14:13 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-12-02 13:04 | 2021-12-14 12:01 | CR0013940 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 169 | 198 | 183.0246 | 4 | 1 | 1 | 0.05 | 193606 | 1.6 | 1 | 0 | 0 | 2 |  | 3 | 10 | 26 | 4.25 | 2.25 | 2021-06 | 0 | 0
2572 | CR0013940 | CTASK0027351 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 3 | 8 | 2021-12-31 09:31 | 2021-12-01 09:31 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Deploy] ROOT Project Squad 16 - Booking Reconciliation Process - ENS Filling (Validation) | 2021-06-07 07:25 | 2021-07-28 22:00 | 2021-07-28 17:47 | 2021-11-23 17:25 | 2021-11-29 14:13 |  | 2021-12-07 08:00 | 2021-12-07 08:00 | 2021-12-02 13:04 | 2021-12-14 12:01 | CR0013940 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W49 | 2021-12 | 169 | 198 | 183.0246 | 4 | 1 | 1 | 0.05 | 193606 | 1.6 | 1 | 0 | 0 | 2 |  | 3 | 10 | 26 | 4.25 | 2.25 | 2021-06 | 0 | 0
2573 | CR0014113 | CTASK0030010 | Closed | OPUS-SCG | Trang Duy Thong | 40 | 40 | 2021-12-31 13:41 | 2021-10-20 13:41 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [Documentation] Request to add Weight Exceeding Pop -Up on DG application window. | 2021-11-03 11:01 | 2021-12-03 11:01 | 2021-12-01 13:59 | 2021-12-21 14:13 | 2021-12-23 15:41 |  | 2022-01-04 15:41 | 2022-01-04 08:10 | 2021-12-24 08:53 | 2022-01-11 12:00 | CR0014113 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2022-W1 | 2022-01 | 148 | 148 | 62.1939 | 2 | 1 | 1 | 0.1 | 193511 | 1.4 | 2 | 0 | 0 | 2 |  | 2 | 3 | 33 | 0.81818 | 2.6667 | 2021-11 | 0 | 0
2574 | CR0014113 | CTASK0030011 | Closed | OPUS-SCG | Trang Duy Thong | 108 | 108 | 2021-12-31 13:42 | 2021-10-20 13:42 | Container | Vessel Operation | Special Cargo | SPCL CGO Approval | SPCL CGO APVL/Inquiry for Partner Lines |  | [CLV] Request to add Weight Exceeding Pop -Up on DG application window. | 2021-11-03 11:01 | 2021-12-03 11:01 | 2021-12-01 13:59 | 2021-12-21 14:13 | 2021-12-23 15:41 |  | 2022-01-04 15:41 | 2022-01-04 08:10 | 2021-12-24 08:53 | 2022-01-11 12:00 | CR0014113 | Vessel OperationSpecial CargoSPCL CGO ApprovalSPCL CGO APVL/Inquiry for Partner Lines | OPUS-SCG | 2022-W1 | 2022-01 | 148 | 148 | 62.1939 | 2 | 1 | 1 | 0.1 | 193511 | 1.4 | 2 | 0 | 0 | 2 |  | 2 | 3 | 33 | 0.81818 | 2.6667 | 2021-11 | 0 | 0
2575 | CR0013819 | CTASK0026979 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 90 | 88 | 2021-06-25 21:00 | 2021-06-02 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | Electronic B/L Print | [Development + Testing] OPUS eBL Enhancement - enhancement requirements to enable eBL document generation (PDF), issuance, release and surrender in OPUS. | 2021-05-26 15:07 | 2021-07-14 22:00 | 2021-07-14 13:42 | 2021-09-24 13:22 | 2021-09-28 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:10 | 2021-10-01 09:34 | 2021-10-19 12:00 | CR0013819 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintElectronic B/L Print | OPUS-BKG-OB | 2021-W41 | 2021-10 | 207 | 204 | 138.7032 | 6 | 2 | 2 | 0.06 | 193470 | 2.2 | 2 | 0 | 0 | 3 |  | 2 | 9 | 26 | 0.36842 | 0.11111 | 2021-05 | 0 | 0
2576 | CR0013819 | CTASK0026980 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 13 | 12 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | Electronic B/L Print | [Deployment] OPUS eBL Enhancement - enhancement requirements to enable eBL document generation (PDF), issuance, release and surrender in OPUS. | 2021-05-26 15:07 | 2021-07-14 22:00 | 2021-07-14 13:42 | 2021-09-24 13:22 | 2021-09-28 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:10 | 2021-10-01 09:34 | 2021-10-19 12:00 | CR0013819 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintElectronic B/L Print | OPUS-BKG-OB | 2021-W41 | 2021-10 | 207 | 204 | 138.7032 | 6 | 2 | 2 | 0.06 | 193470 | 2.2 | 2 | 0 | 0 | 3 |  | 2 | 9 | 26 | 0.36842 | 0.11111 | 2021-05 | 0 | 0
2577 | CR0013819 | CTASK0027037 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-10-02 | 2021-10-01 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | Electronic B/L Print | [Deployment] OPUS eBL Enhancement - enhancement requirements to enable eBL document generation (PDF), issuance, release and surrender in OPUS. | 2021-05-26 15:07 | 2021-07-14 22:00 | 2021-07-14 13:42 | 2021-09-24 13:22 | 2021-09-28 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:10 | 2021-10-01 09:34 | 2021-10-19 12:00 | CR0013819 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintElectronic B/L Print | OPUS-BKG-EBKG | 2021-W41 | 2021-10 | 207 | 204 | 138.7032 | 6 | 2 | 2 | 0.06 | 193525 | 2 | 2 | 0 | 0 | 3 |  | 2 | 9 | 26 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
2578 | CR0013819 | CTASK0026831 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 20 | 20 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | Electronic B/L Print | [Design] OPUS eBL Enhancement - enhancement requirements to enable eBL document generation (PDF), issuance, release and surrender in OPUS. | 2021-05-26 15:07 | 2021-07-14 22:00 | 2021-07-14 13:42 | 2021-09-24 13:22 | 2021-09-28 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:10 | 2021-10-01 09:34 | 2021-10-19 12:00 | CR0013819 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintElectronic B/L Print | OPUS-BKG-OB | 2021-W41 | 2021-10 | 207 | 204 | 138.7032 | 6 | 2 | 2 | 0.06 | 193470 | 2.2 | 2 | 0 | 0 | 3 |  | 2 | 9 | 26 | 0.36842 | 0.11111 | 2021-05 | 0 | 0
2579 | CR0013819 | CTASK0027034 | Closed | OPUS-BKG-EBKG | Vinh Tran | 8 | 8 | 2021-05-15 | 2021-05-13 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | Electronic B/L Print | [Design] OPUS eBL Enhancement - enhancement requirements to enable eBL document generation (PDF), issuance, release and surrender in OPUS. | 2021-05-26 15:07 | 2021-07-14 22:00 | 2021-07-14 13:42 | 2021-09-24 13:22 | 2021-09-28 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:10 | 2021-10-01 09:34 | 2021-10-19 12:00 | CR0013819 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintElectronic B/L Print | OPUS-BKG-EBKG | 2021-W41 | 2021-10 | 207 | 204 | 138.7032 | 6 | 2 | 2 | 0.06 | 193525 | 2 | 2 | 0 | 0 | 3 |  | 2 | 9 | 26 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
2580 | CR0013819 | CTASK0027036 | Closed | OPUS-BKG-EBKG | Vinh Tran | 72 | 72 | 2021-07-10 | 2021-06-16 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Issue & Print | Electronic B/L Print | [Development+Testing] OPUS eBL Enhancement - enhancement requirements to enable eBL document generation (PDF), issuance, release and surrender in OPUS. | 2021-05-26 15:07 | 2021-07-14 22:00 | 2021-07-14 13:42 | 2021-09-24 13:22 | 2021-09-28 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:10 | 2021-10-01 09:34 | 2021-10-19 12:00 | CR0013819 | Service ManagementBooking/DocumentationOutbound DocB/L Issue & PrintElectronic B/L Print | OPUS-BKG-EBKG | 2021-W41 | 2021-10 | 207 | 204 | 138.7032 | 6 | 2 | 2 | 0.06 | 193525 | 2 | 2 | 0 | 0 | 3 |  | 2 | 9 | 26 | 0.41667 | 0.47368 | 2021-05 | 0 | 0
2581 | CR0014959 | CTASK0032676 | Closed | OPUS-TRS | Giang Nguyen Hoang | 20 | 20 | 2022-03-31 17:08 | 2022-03-03 17:08 | Container | Service Management | Trans S/O | Service Order |  |  | [202203][(SVEG) EUA VEND - Time gap between PARISSTART and PARISSO] | 2022-03-10 07:25 | 2022-03-21 22:00 | 2022-03-15 07:50 | 2022-03-16 13:51 | 2022-03-16 16:15 |  | 2022-03-23 16:14 | 2022-03-22 07:57 | 2022-03-17 14:33 | 2022-03-29 15:53 | CR0014959 | Service ManagementTrans S/OService Order | OPUS-TRS | 2022-W12 | 2022-03 | 39 | 40 | 13.3676 | 2 | 1 | 2 | 0.12 | 183440 | 3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0 | 0 | 2022-03 | 0 | 0
2582 | CR0014959 | CTASK0032675 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 19 | 20 | 2022-03-31 17:05 | 2022-03-03 17:05 | Container | Service Management | Trans S/O | Service Order |  |  | [202203][(SVEG) EUA VEND - Time gap between PARISSTART and PARISSO] | 2022-03-10 07:25 | 2022-03-21 22:00 | 2022-03-15 07:50 | 2022-03-16 13:51 | 2022-03-16 16:15 |  | 2022-03-23 16:14 | 2022-03-22 07:57 | 2022-03-17 14:33 | 2022-03-29 15:53 | CR0014959 | Service ManagementTrans S/OService Order | OPUS-TRS | 2022-W12 | 2022-03 | 39 | 40 | 13.3676 | 2 | 1 | 2 | 0.12 | 183432 | 3 | 1 | 0 | 0 | 1 |  | 1 | 7 | 38 | 0.043478 | 0 | 2022-03 | 0 | 0
2583 | CR0014333 | CTASK0028962 | Closed | OPUS-BKG-RPT | Nam Nguyen | 4 | 4 | 2021-08-25 21:17 | 2021-08-25 21:17 | Container | Service Management | Booking/Documentation | Report | B/L Container Information Report |  | [Design]EUA - Add ATB# to 'Report Item Option' in Template creation for B/L Cntr Info Report | 2021-09-03 12:04 | 2021-09-30 22:00 | 2021-09-29 12:44 | 2021-10-05 10:01 | 2021-10-11 15:59 |  | 2021-10-19 08:00 | 2021-10-19 08:00 | 2021-10-12 14:49 | 2021-10-26 12:00 | CR0014333 | Service ManagementBooking/DocumentationReportB/L Container Information Report | OPUS-BKG-RPT | 2021-W42 | 2021-10 | 38 | 38 | 45.8308 | 4 | 2 | 1 | 0.03 | 123048 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0.22222 | 0.047619 | 2021-09 | 0 | 0
2584 | CR0014333 | CTASK0028964 | Closed | OPUS-BKG-OB | Nam Nguyen | 17 | 14 | 2021-09-10 21:14 | 2021-09-01 21:14 | Container | Service Management | Booking/Documentation | Report | B/L Container Information Report |  | [Development] EUA - Add ATB# to 'Report Item Option' in Template creation for B/L Cntr Info Report | 2021-09-03 12:04 | 2021-09-30 22:00 | 2021-09-29 12:44 | 2021-10-05 10:01 | 2021-10-11 15:59 |  | 2021-10-19 08:00 | 2021-10-19 08:00 | 2021-10-12 14:49 | 2021-10-26 12:00 | CR0014333 | Service ManagementBooking/DocumentationReportB/L Container Information Report | OPUS-BKG-RPT | 2021-W42 | 2021-10 | 38 | 38 | 45.8308 | 4 | 2 | 1 | 0.03 | 123048 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0.22222 | 0.047619 | 2021-09 | 0 | 0
2585 | CR0014333 | CTASK0028966 | Closed | OPUS-BKG-OB | Nam Nguyen | 8 | 8 | 2021-10-19 16:51 | 2021-10-11 16:50 | Container | Service Management | Booking/Documentation | Report | B/L Container Information Report |  | [Deployment] EUA - Add ATB# to 'Report Item Option' in Template creation for B/L Cntr Info Report | 2021-09-03 12:04 | 2021-09-30 22:00 | 2021-09-29 12:44 | 2021-10-05 10:01 | 2021-10-11 15:59 |  | 2021-10-19 08:00 | 2021-10-19 08:00 | 2021-10-12 14:49 | 2021-10-26 12:00 | CR0014333 | Service ManagementBooking/DocumentationReportB/L Container Information Report | OPUS-BKG-RPT | 2021-W42 | 2021-10 | 38 | 38 | 45.8308 | 4 | 2 | 1 | 0.03 | 123048 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0.22222 | 0.047619 | 2021-09 | 0 | 0
2586 | CR0014333 | CTASK0028965 | Closed | OPUS-BKG-OB | Nam Nguyen | 9 | 12 | 2021-10-08 21:56 | 2021-09-30 21:56 | Container | Service Management | Booking/Documentation | Report | B/L Container Information Report |  | [Testing] EUA - Add ATB# to 'Report Item Option' in Template creation for B/L Cntr Info Report | 2021-09-03 12:04 | 2021-09-30 22:00 | 2021-09-29 12:44 | 2021-10-05 10:01 | 2021-10-11 15:59 |  | 2021-10-19 08:00 | 2021-10-19 08:00 | 2021-10-12 14:49 | 2021-10-26 12:00 | CR0014333 | Service ManagementBooking/DocumentationReportB/L Container Information Report | OPUS-BKG-RPT | 2021-W42 | 2021-10 | 38 | 38 | 45.8308 | 4 | 2 | 1 | 0.03 | 123048 | 2.9 | 1 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0.22222 | 0.047619 | 2021-09 | 0 | 0
2587 | CR0013336 | CTASK0026187 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 32 | 30 | 2021-04-30 14:34 | 2021-04-01 14:34 | Container | Service Management | Trans S/O |  |  |  | [202104] EUA - PARIS Phase 1 - Additional requirements to add to CR0012061 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:25 | 2021-10-07 19:36 | 2021-10-28 08:58 |  | 2021-11-03 21:57 | 2021-11-03 09:17 | 2021-10-29 08:38 | 2021-11-10 12:00 | CR0013336 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 60 | 60 | 254.5534 | 2 | 1 | 2 | 0.01 | 183432 | 2 | 0 | 0 | 0 | 1 |  | 3 | 3 | 38 | 0 | 0 | 2021-02 | 0 | 0
2588 | CR0013336 | CTASK0026188 | Closed | OPUS-TRS | Giang Nguyen Hoang | 28 | 30 | 2021-04-30 14:35 | 2021-04-01 14:35 | Container | Service Management | Trans S/O |  |  |  | [202104] EUA - PARIS Phase 1 - Additional requirements to add to CR0012061 | 2021-02-22 08:40 | 2021-04-28 19:00 | 2021-04-27 14:25 | 2021-10-07 19:36 | 2021-10-28 08:58 |  | 2021-11-03 21:57 | 2021-11-03 09:17 | 2021-10-29 08:38 | 2021-11-10 12:00 | CR0013336 | Service ManagementTrans S/O | OPUS-TRS | 2021-W44 | 2021-11 | 60 | 60 | 254.5534 | 2 | 1 | 2 | 0.01 | 183440 | 2 | 0 | 0 | 0 | 1 |  | 3 | 3 | 38 | 0 | 0 | 2021-02 | 0 | 0
2589 | CR0013402 | CTASK0025873 | Closed | OPUS-ACM | Huynh Tuan Khanh | 40 | 40 | 2021-04-30 12:27 | 2021-03-15 12:26 | Container | Support & Admin | Agent Commission Management |  |  |  | LA - Comm - CSA SCLBB OPUS ACM Special Compensation Missing calculation for additional fee | 2021-03-15 12:25 | 2021-04-30 12:25 | 2021-04-29 13:17 | 2021-11-16 14:15 | 2021-11-18 09:19 |  | 2021-11-23 09:19 | 2021-11-23 14:49 | 2021-11-19 14:07 | 2021-12-01 12:00 | CR0013402 | Support & AdminAgent Commission Management | OPUS-ACM | 2021-W47 | 2021-11 | 50 | 50 | 252.8704 | 2 | 1 | 1 | 0.01 | 193499 | 1.8 | 1 | 0 | 0 | 1 |  | 3 | 7 | 38 | 0 | 0 | 2021-03 | 0 | 0
2590 | CR0013402 | CTASK0024159 | Closed | OPUS-ACM | Huynh Tuan Khanh | 10 | 10 | 2021-01-29 15:05 | 2020-12-14 15:05 | Container | Support & Admin | Agent Commission Management |  |  |  | LA - Comm - CSA SCLBB OPUS ACM Special Compensation Missing calculation for additional fee | 2021-03-15 12:25 | 2021-04-30 12:25 | 2021-04-29 13:17 | 2021-11-16 14:15 | 2021-11-18 09:19 |  | 2021-11-23 09:19 | 2021-11-23 14:49 | 2021-11-19 14:07 | 2021-12-01 12:00 | CR0013402 | Support & AdminAgent Commission Management | OPUS-ACM | 2021-W47 | 2021-11 | 50 | 50 | 252.8704 | 2 | 1 | 1 | 0.01 | 193499 | 1.8 | 1 | 0 | 0 | 1 |  | 3 | 7 | 38 | 0 | 0 | 2021-03 | 0 | 0
2591 | CR0014487 | CTASK0029505 | Closed | OPUS-BKG-M | Trang Le Minh | 12 | 12 | 2021-10-31 21:57 | 2021-10-01 08:57 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] Issue with CR0013303 - Broken Routes Refresh | 2021-09-24 08:47 | 2021-10-21 | 2021-10-18 15:34 | 2021-11-26 07:51 | 2021-11-26 09:29 |  | 2021-12-14 08:00 | 2021-12-14 08:00 | 2021-11-29 08:15 | 2021-12-21 12:01 | CR0014487 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W50 | 2021-12 | 28 | 28 | 80.9674 | 4 | 1 | 1 | 0.01 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0 | 0 | 2021-09 | 0 | 0
2592 | CR0014487 | CTASK0029507 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2021-12-31 21:01 | 2021-12-01 08:01 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] Issue with CR0013303 - Broken Routes Refresh | 2021-09-24 08:47 | 2021-10-21 | 2021-10-18 15:34 | 2021-11-26 07:51 | 2021-11-26 09:29 |  | 2021-12-14 08:00 | 2021-12-14 08:00 | 2021-11-29 08:15 | 2021-12-21 12:01 | CR0014487 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W50 | 2021-12 | 28 | 28 | 80.9674 | 4 | 1 | 1 | 0.01 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0 | 0 | 2021-09 | 0 | 0
2593 | CR0014487 | CTASK0029501 | Closed | OPUS-BKG-M | Trang Le Minh | 4 | 4 | 2021-09-30 21:20 | 2021-09-23 14:29 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] Issue with CR0013303 - Broken Routes Refresh | 2021-09-24 08:47 | 2021-10-21 | 2021-10-18 15:34 | 2021-11-26 07:51 | 2021-11-26 09:29 |  | 2021-12-14 08:00 | 2021-12-14 08:00 | 2021-11-29 08:15 | 2021-12-21 12:01 | CR0014487 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W50 | 2021-12 | 28 | 28 | 80.9674 | 4 | 1 | 1 | 0.01 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0 | 0 | 2021-09 | 0 | 0
2594 | CR0014487 | CTASK0029504 | Closed | OPUS-BKG-M | Trang Le Minh | 8 | 8 | 2021-09-30 21:55 | 2021-09-23 14:55 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] Issue with CR0013303 - Broken Routes Refresh | 2021-09-24 08:47 | 2021-10-21 | 2021-10-18 15:34 | 2021-11-26 07:51 | 2021-11-26 09:29 |  | 2021-12-14 08:00 | 2021-12-14 08:00 | 2021-11-29 08:15 | 2021-12-21 12:01 | CR0014487 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2021-W50 | 2021-12 | 28 | 28 | 80.9674 | 4 | 1 | 1 | 0.01 | 193594 | 2.1 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 0 | 0 | 2021-09 | 0 | 0
2595 | CR0013504 | CTASK0026116 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 189 | 190 | 2021-05-31 17:30 | 2021-04-15 09:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Development] ROOT Project Squad 16 - Booking Reconciliation Process (check points validation prior to AMS submission and vessel BDR) | 2021-03-30 14:44 | 2021-06-23 22:00 | 2021-06-23 16:04 | 2021-09-29 13:52 | 2021-09-30 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-10-08 08:57 | 2021-10-19 12:00 | CR0013504 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W41 | 2021-10 | 268 | 271 | 195.7194 | 4 | 2 | 2 | 0.06 | 173280 | 2.3 | 1 | 11 | 0 | 3 |  | 3 | 9 | 26 | 0.375 | 1 | 2021-03 | 11 | 1
2596 | CR0013504 | CTASK0026119 | Closed | OPUS-BKG-MFT-A | Thuc Tran | 55 | 55 | 2021-06-30 17:30 | 2021-06-01 09:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Test+Deployment]ROOT Project Squad 16 - Booking Reconciliation Process (check points validation prior to AMS submission and vessel BDR) | 2021-03-30 14:44 | 2021-06-23 22:00 | 2021-06-23 16:04 | 2021-09-29 13:52 | 2021-09-30 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-10-08 08:57 | 2021-10-19 12:00 | CR0013504 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W41 | 2021-10 | 268 | 271 | 195.7194 | 4 | 2 | 2 | 0.06 | 173280 | 2.3 | 1 | 11 | 0 | 3 |  | 3 | 9 | 26 | 0.375 | 1 | 2021-03 | 11 | 1
2597 | CR0013504 | CTASK0026115 | Closed | OPUS-BKG-MFT-M | Thuc Tran | 10 | 10 | 2021-03-31 17:30 | 2021-03-24 09:00 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [Estimation] ROOT Project Squad 16 - Booking Reconciliation Process (check points validation prior to AMS submission and vessel BDR) | 2021-03-30 14:44 | 2021-06-23 22:00 | 2021-06-23 16:04 | 2021-09-29 13:52 | 2021-09-30 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-10-08 08:57 | 2021-10-19 12:00 | CR0013504 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W41 | 2021-10 | 268 | 271 | 195.7194 | 4 | 2 | 2 | 0.06 | 173280 | 2.3 | 1 | 11 | 0 | 3 |  | 3 | 9 | 26 | 0.375 | 1 | 2021-03 | 11 | 1
2598 | CR0013504 | CTASK0029736 | Closed | OPUS-BKG-MFT-M | Tung Nguyen Thanh | 14 | 16 | 2021-10-15 20:11 | 2021-10-01 20:11 | Container | Service Management | Booking/Documentation | Advance Manifest |  |  | [PROD]ROOT Project Squad 16 - Booking Reconciliation Process (check points validation prior to AMS submission and vessel BDR) | 2021-03-30 14:44 | 2021-06-23 22:00 | 2021-06-23 16:04 | 2021-09-29 13:52 | 2021-09-30 13:06 |  | 2021-10-12 08:00 | 2021-10-12 08:00 | 2021-10-08 08:57 | 2021-10-19 12:00 | CR0013504 | Service ManagementBooking/DocumentationAdvance Manifest | OPUS-BKG-MFT-M | 2021-W41 | 2021-10 | 268 | 271 | 195.7194 | 4 | 2 | 2 | 0.06 | 193606 | 1.4 | 1 | 11 | 0 | 3 |  | 3 | 9 | 26 | 4.25 | 2.25 | 2021-03 | 11 | 1
2599 | CR0014660 | CTASK0030476 | Closed | OPUS-MNR | Tien Le | 19 | 14 | 2021-11-30 17:00 | 2021-11-15 08:00 | Container | Equipment Management | M&R | Total Loss |  |  | [CLT Internal] [OCT21] SINHO - Error Message "Flag Date must be the same or later than event date" | 2021-12-03 15:20 | 2021-12-31 22:00 | 2021-12-31 09:55 | 2022-01-13 07:55 | 2022-02-16 17:33 |  | 2022-02-22 09:00 | 2022-02-22 08:00 | 2022-02-18 07:39 | 2022-03-01 12:00 | CR0014660 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2022-W8 | 2022-02 | 54 | 54 | 80.7364 | 3 | 1 | 1 | 0.03 | 173286 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
2600 | CR0014660 | CTASK0030477 | Closed | OPUS-MNR | Tien Le | 30 | 30 | 2021-12-31 17:00 | 2021-12-01 08:00 | Container | Equipment Management | M&R | Total Loss |  |  | [CLT Internal] [OCT21] SINHO - Error Message "Flag Date must be the same or later than event date" | 2021-12-03 15:20 | 2021-12-31 22:00 | 2021-12-31 09:55 | 2022-01-13 07:55 | 2022-02-16 17:33 |  | 2022-02-22 09:00 | 2022-02-22 08:00 | 2022-02-18 07:39 | 2022-03-01 12:00 | CR0014660 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2022-W8 | 2022-02 | 54 | 54 | 80.7364 | 3 | 1 | 1 | 0.03 | 173286 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
2601 | CR0014660 | CTASK0030475 | Closed | OPUS-MNR | Tien Le | 5 | 10 | 2021-12-31 17:00 | 2021-11-15 08:00 | Container | Equipment Management | M&R | Total Loss |  |  | [Documentation][CLT Internal][OCT21] SINHO - Error Message "Flag Date must be the same or later than event date" | 2021-12-03 15:20 | 2021-12-31 22:00 | 2021-12-31 09:55 | 2022-01-13 07:55 | 2022-02-16 17:33 |  | 2022-02-22 09:00 | 2022-02-22 08:00 | 2022-02-18 07:39 | 2022-03-01 12:00 | CR0014660 | Equipment ManagementM&RTotal Loss | OPUS-MNR | 2022-W8 | 2022-02 | 54 | 54 | 80.7364 | 3 | 1 | 1 | 0.03 | 173286 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
2602 | CR0014477 | CTASK0029470 | Closed | OPUS-SCG | Trang Duy Thong | 40 | 40 | 2021-11-30 10:37 | 2021-09-21 10:37 | Container | Vessel Operation | Special Cargo |  |  |  | [CLV] OPUS Enhancement Request - DG Port/Terminal Limits – Creation / Inquiry >>Adding Port/Terminal Information & UNNO , IMDG Class | 2021-09-21 13:25 | 2021-11-05 13:25 | 2021-11-05 12:09 | 2022-02-15 15:49 | 2022-03-03 10:04 |  | 2022-03-15 10:04 | 2022-03-15 12:19 | 2022-03-04 08:48 | 2022-03-23 12:00 | CR0014477 | Vessel OperationSpecial Cargo | OPUS-SCG | 2022-W11 | 2022-03 | 109 | 109 | 174.8602 | 2 | 1 | 1 | 0.03 | 193511 | 1.3 | 2 | 6 | 0 | 2 |  | 3 | 10 | 38 | 0.81818 | 2.6667 | 2021-09 | 6 | 1
2603 | CR0014477 | CTASK0029469 | Closed | OPUS-SCG | Trang Duy Thong | 69 | 69 | 2021-11-05 10:37 | 2021-09-21 10:37 | Container | Vessel Operation | Special Cargo |  |  |  | [Documentation] OPUS Enhancement Request - DG Port/Terminal Limits – Creation / Inquiry >>Adding Port/Terminal Information & UNNO , IMDG Class | 2021-09-21 13:25 | 2021-11-05 13:25 | 2021-11-05 12:09 | 2022-02-15 15:49 | 2022-03-03 10:04 |  | 2022-03-15 10:04 | 2022-03-15 12:19 | 2022-03-04 08:48 | 2022-03-23 12:00 | CR0014477 | Vessel OperationSpecial Cargo | OPUS-SCG | 2022-W11 | 2022-03 | 109 | 109 | 174.8602 | 2 | 1 | 1 | 0.03 | 193511 | 1.3 | 2 | 6 | 0 | 2 |  | 3 | 10 | 38 | 0.81818 | 2.6667 | 2021-09 | 6 | 1
2604 | CR0015186 | CTASK0032647 | Closed | OPUS-VSK | Linh Nguyen | 25 | 26 | 2022-03-31 09:03 | 2022-03-03 09:03 | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Input Ratio Report |  | [CLV-VSK][[CLT Internal] Enhance update of AIS's data via EDI (Voyage mismatch case)] | 2022-03-02 16:49 | 2022-03-21 20:00 | 2022-03-18 17:48 | 2022-04-08 13:41 | 2022-04-08 14:43 |  | 2022-04-19 20:00 | 2022-04-20 07:32 | 2022-04-12 11:40 | 2022-04-27 12:00 | CR0015186 | Vessel OperationVessel ScheduleActual SKDActual SKD Input Ratio Report | OPUS-VSK | 2022-W16 | 2022-04 | 25 | 26 | 48.1327 | 2 | 1 | 1 | 0.02 | 193464 | 3 | 2 | 0 | 0 | 1 |  | 1 | 4 | 18 | 0.375 | 1.5 | 2022-03 | 0 | 0
2605 | CR0015186 | CTASK0032572 | Closed | OPUS-VSK | Linh Nguyen | 1 | 1 |  |  | Container | Vessel Operation | Vessel Schedule | Actual SKD | Actual SKD Input Ratio Report |  | [Document][CLT Internal] Enhance update of AIS's data via EDI | 2022-03-02 16:49 | 2022-03-21 20:00 | 2022-03-18 17:48 | 2022-04-08 13:41 | 2022-04-08 14:43 |  | 2022-04-19 20:00 | 2022-04-20 07:32 | 2022-04-12 11:40 | 2022-04-27 12:00 | CR0015186 | Vessel OperationVessel ScheduleActual SKDActual SKD Input Ratio Report | OPUS-VSK | 2022-W16 | 2022-04 | 25 | 26 | 48.1327 | 2 | 1 | 1 | 0.02 | 193464 | 3 | 2 | 0 | 0 | 1 |  | 1 | 4 | 18 | 0.375 | 1.5 | 2022-03 | 0 | 0
2606 | CR0013414 | CTASK0025557 | Closed | OPUS-BKG-M | Thien Lai | 104 | 100 | 2021-03-31 16:52 | 2021-03-01 16:52 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] EUA - BKG Automatic EDI driven from BKG updates (AUTO EDI HOLD) | 2021-03-02 11:19 | 2021-04-29 | 2021-04-28 12:02 | 2022-05-11 08:30 | 2022-05-11 09:02 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:58 | 2022-06-07 12:00 | CR0013414 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 178 | 174 | 454.8621 | 6 | 2 | 4 | 0.02 | 193567 | 1.6 | 3 | 0 | 1 | 2 |  | 5 | 7 | 26 | 0.5625 | 0.53333 | 2021-03 | 1 | 1
2607 | CR0013414 | CTASK0025560 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-04-30 16:53 | 2021-04-01 16:53 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] EUA - BKG Automatic EDI driven from BKG updates (AUTO EDI HOLD) | 2021-03-02 11:19 | 2021-04-29 | 2021-04-28 12:02 | 2022-05-11 08:30 | 2022-05-11 09:02 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:58 | 2022-06-07 12:00 | CR0013414 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 178 | 174 | 454.8621 | 6 | 2 | 4 | 0.02 | 193567 | 1.6 | 3 | 0 | 1 | 2 |  | 5 | 7 | 26 | 0.5625 | 0.53333 | 2021-03 | 1 | 1
2608 | CR0013414 | CTASK0025365 | Closed | OPUS-BKG-M | Thien Lai | 16 | 16 | 2021-02-26 09:28 | 2021-02-17 09:27 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] EUA - BKG Automatic EDI driven from BKG updates (AUTO EDI HOLD) | 2021-03-02 11:19 | 2021-04-29 | 2021-04-28 12:02 | 2022-05-11 08:30 | 2022-05-11 09:02 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:58 | 2022-06-07 12:00 | CR0013414 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 178 | 174 | 454.8621 | 6 | 2 | 4 | 0.02 | 193567 | 1.6 | 3 | 0 | 1 | 2 |  | 5 | 7 | 26 | 0.5625 | 0.53333 | 2021-03 | 1 | 1
2609 | CR0013414 | CTASK0030868 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 14 | 14 |  |  | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [202112] EUA - BKG Automatic EDI driven from BKG updates (AUTO EDI HOLD) | 2021-03-02 11:19 | 2021-04-29 | 2021-04-28 12:02 | 2022-05-11 08:30 | 2022-05-11 09:02 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:58 | 2022-06-07 12:00 | CR0013414 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 178 | 174 | 454.8621 | 6 | 2 | 4 | 0.02 | 183432 | 2 | 3 | 0 | 1 | 2 |  | 5 | 7 | 26 | 0.043478 | 0 | 2021-03 | 1 | 1
2610 | CR0013414 | CTASK0025562 | Closed | OPUS-BKG-M | Trang Le Minh | 13 | 8 | 2022-05-30 21:54 | 2022-05-16 06:53 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] EUA - BKG Automatic EDI driven from BKG updates (AUTO EDI HOLD) | 2021-03-02 11:19 | 2021-04-29 | 2021-04-28 12:02 | 2022-05-11 08:30 | 2022-05-11 09:02 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:58 | 2022-06-07 12:00 | CR0013414 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 178 | 174 | 454.8621 | 6 | 2 | 4 | 0.02 | 193594 | 1.5 | 3 | 0 | 1 | 2 |  | 5 | 7 | 26 | 0 | 0 | 2021-03 | 1 | 1
2611 | CR0013414 | CTASK0034463 | Closed | OPUS-TRS | Giang Nguyen Hoang | 15 | 20 | 2022-05-31 08:49 | 2022-05-15 08:49 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] EUA - BKG Automatic EDI driven from BKG updates (AUTO EDI HOLD) | 2021-03-02 11:19 | 2021-04-29 | 2021-04-28 12:02 | 2022-05-11 08:30 | 2022-05-11 09:02 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:58 | 2022-06-07 12:00 | CR0013414 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W22 | 2022-05 | 178 | 174 | 454.8621 | 6 | 2 | 4 | 0.02 | 183440 | 2 | 3 | 0 | 1 | 2 |  | 5 | 7 | 26 | 0 | 0 | 2021-03 | 1 | 1
2612 | CR0014549 | CTASK0030405 | Closed | OPUS-SCE | Son Nguyen The | 6 | 7 | 2021-11-24 15:50 | 2021-11-01 15:50 | Container | Service Management | SCEM |  |  |  | Global "API" - Please do not show Rail Unloading and Rail Loading events in TL UI for Rail T/S move involved in inland location [SNT] - NOV | 2021-10-27 14:29 | 2021-11-10 17:00 | 2021-11-03 09:54 | 2021-11-04 08:25 | 2021-11-05 09:29 |  | 2021-11-16 10:00 | 2021-11-16 11:24 | 2021-11-12 09:02 | 2021-11-23 12:01 | CR0014549 | Service ManagementSCEM | OPUS-SCE | 2021-W46 | 2021-11 | 25 | 27 | 19.8134 | 2 | 1 | 1 | 0.06 | 193531 | 2 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0 | 2021-10 | 0 | 0
2613 | CR0014549 | CTASK0030196 | Closed | OPUS-SCE | Son Nguyen The | 19 | 20 | 2021-10-31 09:51 | 2021-10-26 09:51 | Container | Service Management | SCEM |  |  |  | Global "API" - Please do not show Rail Unloading and Rail Loading events in TL UI for Rail T/S move involved in inland location [SNT] - OCT | 2021-10-27 14:29 | 2021-11-10 17:00 | 2021-11-03 09:54 | 2021-11-04 08:25 | 2021-11-05 09:29 |  | 2021-11-16 10:00 | 2021-11-16 11:24 | 2021-11-12 09:02 | 2021-11-23 12:01 | CR0014549 | Service ManagementSCEM | OPUS-SCE | 2021-W46 | 2021-11 | 25 | 27 | 19.8134 | 2 | 1 | 1 | 0.06 | 193531 | 2 | 0 | 0 | 0 | 1 |  | 1 | 16 | 38 | 0 | 0 | 2021-10 | 0 | 0
2614 | CR0014345 | CTASK0028755 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Deployment] [CLT Internal] add the validation message on charge remark popup | 2021-08-12 14:46 | 2021-08-23 22:00 | 2021-08-23 07:54 | 2021-09-07 09:30 | 2021-09-09 11:13 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-09 13:31 | 2021-10-05 12:01 | CR0014345 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W39 | 2021-09 | 11 | 20 | 46.7179 | 3 | 1 | 1 | 0.02 | 193470 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 0.36842 | 0.11111 | 2021-08 | 0 | 0
2615 | CR0014345 | CTASK0028754 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 7 | 12 | 2021-08-23 17:30 | 2021-08-16 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Development + Testing][CLT Internal] add the validation message on charge remark popup | 2021-08-12 14:46 | 2021-08-23 22:00 | 2021-08-23 07:54 | 2021-09-07 09:30 | 2021-09-09 11:13 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-09 13:31 | 2021-10-05 12:01 | CR0014345 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W39 | 2021-09 | 11 | 20 | 46.7179 | 3 | 1 | 1 | 0.02 | 193470 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 0.36842 | 0.11111 | 2021-08 | 0 | 0
2616 | CR0014345 | CTASK0028753 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2021-08-12 17:30 | 2021-08-12 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Analysis & Design] [CLT Internal] add the validation message on charge remark popup | 2021-08-12 14:46 | 2021-08-23 22:00 | 2021-08-23 07:54 | 2021-09-07 09:30 | 2021-09-09 11:13 |  | 2021-09-28 08:00 | 2021-09-28 08:00 | 2021-09-09 13:31 | 2021-10-05 12:01 | CR0014345 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W39 | 2021-09 | 11 | 20 | 46.7179 | 3 | 1 | 1 | 0.02 | 193470 | 2.4 | 1 | 0 | 0 | 1 |  | 1 | 6 | 6 | 0.36842 | 0.11111 | 2021-08 | 0 | 0
2617 | CR0013908 | CTASK0026915 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2021-10-04 21:00 | 2021-10-01 08:30 | Container | Service Management | Booking/Documentation | Setup | Internet BL Control Party Setup | Controlling Party Setup | [Deployment] Global "FTP" - Louis Dreyfus Co (LDC) - Set up of new file naming rule | 2021-05-13 08:33 | 2021-05-31 21:00 | 2021-05-25 10:31 | 2021-07-22 09:01 | 2021-07-29 13:34 |  | 2021-08-10 13:34 | 2021-10-05 08:00 | 2021-09-23 07:58 | 2021-10-12 12:00 | CR0013908 | Service ManagementBooking/DocumentationSetupInternet BL Control Party SetupControlling Party Setup | OPUS-BKG-OB | 2021-W32 | 2021-08 | 39 | 44 | 89.2087 | 3 | 1 | 1 | 0.02 | 193470 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 1 | 1 | 0.36842 | 0.11111 | 2021-05 | 0 | 0
2618 | CR0013908 | CTASK0026865 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 8 | 8 | 2021-05-07 22:00 | 2021-05-06 08:30 | Container | Service Management | Booking/Documentation | Setup | Internet BL Control Party Setup | Controlling Party Setup | [Design] Global "FTP" - Louis Dreyfus Co (LDC) - Set up of new file naming rule | 2021-05-13 08:33 | 2021-05-31 21:00 | 2021-05-25 10:31 | 2021-07-22 09:01 | 2021-07-29 13:34 |  | 2021-08-10 13:34 | 2021-10-05 08:00 | 2021-09-23 07:58 | 2021-10-12 12:00 | CR0013908 | Service ManagementBooking/DocumentationSetupInternet BL Control Party SetupControlling Party Setup | OPUS-BKG-OB | 2021-W32 | 2021-08 | 39 | 44 | 89.2087 | 3 | 1 | 1 | 0.02 | 193470 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 1 | 1 | 0.36842 | 0.11111 | 2021-05 | 0 | 0
2619 | CR0013908 | CTASK0026914 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 27 | 32 | 2021-05-31 21:00 | 2021-05-17 08:30 | Container | Service Management | Booking/Documentation | Setup | Internet BL Control Party Setup | Controlling Party Setup | [Development + Testing] Global "FTP" - Louis Dreyfus Co (LDC) - Set up of new file naming rule | 2021-05-13 08:33 | 2021-05-31 21:00 | 2021-05-25 10:31 | 2021-07-22 09:01 | 2021-07-29 13:34 |  | 2021-08-10 13:34 | 2021-10-05 08:00 | 2021-09-23 07:58 | 2021-10-12 12:00 | CR0013908 | Service ManagementBooking/DocumentationSetupInternet BL Control Party SetupControlling Party Setup | OPUS-BKG-OB | 2021-W32 | 2021-08 | 39 | 44 | 89.2087 | 3 | 1 | 1 | 0.02 | 193470 | 2.2 | 1 | 0 | 0 | 1 |  | 2 | 1 | 1 | 0.36842 | 0.11111 | 2021-05 | 0 | 0
2620 | CR0012343 | CTASK0018923 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 7 | 4 | 2022-01-14 17:30 | 2022-01-11 08:30 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193470 | 1 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.36842 | 0.17391 | 2020-03 | 0 | 0
2621 | CR0012343 | CTASK0018782 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 2 | 2 | 2020-03-05 17:23 | 2020-03-05 17:23 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193512 | 0.7 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.2963 | 0.5 | 2020-03 | 0 | 0
2622 | CR0012343 | CTASK0018917 | Closed | OPUS-BKG-M | Vinh Tran | 2 | 2 | 2020-03-21 | 2020-03-18 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193525 | 0.8 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.41667 | 0.45455 | 2020-03 | 0 | 0
2623 | CR0012343 | CTASK0018925 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 3 | 3 | 2022-01-12 17:30 | 2022-01-06 09:01 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193488 | 0.8 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.53659 | 2.1667 | 2020-03 | 0 | 0
2624 | CR0012343 | CTASK0018921 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 14 | 14 | 2020-03-24 13:49 | 2020-03-18 13:49 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193512 | 0.7 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.2963 | 0.5 | 2020-03 | 0 | 0
2625 | CR0012343 | CTASK0018919 | Closed | OPUS-BKG-M | Vinh Tran | 1 | 1 | 2020-03-24 | 2020-03-20 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Deployment][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193525 | 0.8 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.41667 | 0.45455 | 2020-03 | 0 | 0
2626 | CR0012343 | CTASK0018924 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 3 | 3 | 2020-03-19 13:51 | 2020-03-13 13:51 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193488 | 0.8 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.53659 | 2.1667 | 2020-03 | 0 | 0
2627 | CR0012343 | CTASK0018918 | Closed | OPUS-BKG-M | Vinh Tran | 3 | 3 | 2020-03-21 | 2020-03-18 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193525 | 0.8 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.41667 | 0.45455 | 2020-03 | 0 | 0
2628 | CR0012343 | CTASK0018792 | Closed | OPUS-BKG-M | Vinh Tran | 1 | 1 | 2020-03-06 | 2020-03-05 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193525 | 0.8 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.41667 | 0.45455 | 2020-03 | 0 | 0
2629 | CR0012343 | CTASK0018922 | Closed | OPUS-BKG-OB | Nhut Nguyen Minh | 6 | 6 | 2020-03-24 13:51 | 2020-03-18 13:51 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Testing][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193512 | 0.7 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.2963 | 0.5 | 2020-03 | 0 | 0
2630 | CR0012343 | CTASK0018794 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 1 | 1 | 2020-03-05 14:06 | 2020-03-05 14:05 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Design][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193488 | 0.8 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.53659 | 2.1667 | 2020-03 | 0 | 0
2631 | CR0012343 | CTASK0018914 | Closed | OPUS-BKG-EBKG | Dat Nguyen Hoang | 10 | 10 | 2020-03-19 11:41 | 2020-03-13 11:41 | Container | Service Management | Booking/Documentation | Booking | e-Booking & S/I Process |  | [Development][CLT Internal] Query Tuning for better intuitive visibility to maintain system efficiently related to CR0011360 | 2020-03-27 14:17 | 2021-12-31 22:00 | 2021-12-02 15:07 | 2021-12-24 07:13 | 2021-12-24 07:27 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:01 | 2022-01-25 12:00 | CR0012343 | Service ManagementBooking/DocumentationBookinge-Booking & S/I Process | OPUS-BKG-EBKG | 2022-W3 | 2022-01 | 53 | 50 | 661.7381 | 12 | 3 | 4 | 0 | 193488 | 0.8 | 1 | 0 | 0 | 1 |  | 5 | 11 | 33 | 0.53659 | 2.1667 | 2020-03 | 0 | 0
2632 | CR0015039 | CTASK0032172 | Closed | OPUS-PRD | Tran Le | 45 | 45 |  |  | Container | Service Management | Product Catalog |  |  |  | [CLT Internal] Ocean Route excel upload-FEB | 2022-01-25 06:05 | 2022-02-25 18:00 | 2022-02-25 09:38 | 2022-03-23 16:58 | 2022-03-25 07:23 |  | 2022-03-29 08:00 | 2022-03-29 08:00 | 2022-03-25 11:43 | 2022-04-05 12:00 | CR0015039 | Service ManagementProduct Catalog | OPUS-PRD | 2022-W13 | 2022-03 | 161 | 123 | 63.08 | 6 | 1 | 2 | 0.08 | 193501 | 2.3 | 0 | 0 | 0 | 2 |  | 2 | 6 | 38 | 0 | 0 | 2022-01 | 0 | 0
2633 | CR0015039 | CTASK0031928 | Closed | OPUS-PRD | Tran Le | 10 | 10 | 2022-01-31 09:06 | 2022-01-01 09:06 | Container | Service Management | Product Catalog |  |  |  | [CLT Internal] Ocean Route excel upload-JAN | 2022-01-25 06:05 | 2022-02-25 18:00 | 2022-02-25 09:38 | 2022-03-23 16:58 | 2022-03-25 07:23 |  | 2022-03-29 08:00 | 2022-03-29 08:00 | 2022-03-25 11:43 | 2022-04-05 12:00 | CR0015039 | Service ManagementProduct Catalog | OPUS-PRD | 2022-W13 | 2022-03 | 161 | 123 | 63.08 | 6 | 1 | 2 | 0.08 | 193501 | 2.3 | 0 | 0 | 0 | 2 |  | 2 | 6 | 38 | 0 | 0 | 2022-01 | 0 | 0
2634 | CR0015039 | CTASK0032943 | Closed | OPUS-PRD | Tran Le | 2 | 2 | 2022-03-31 12:17 | 2022-03-01 12:17 | Container | Service Management | Product Catalog |  |  |  | [CLT Internal] Ocean Route excel upload-MAR | 2022-01-25 06:05 | 2022-02-25 18:00 | 2022-02-25 09:38 | 2022-03-23 16:58 | 2022-03-25 07:23 |  | 2022-03-29 08:00 | 2022-03-29 08:00 | 2022-03-25 11:43 | 2022-04-05 12:00 | CR0015039 | Service ManagementProduct Catalog | OPUS-PRD | 2022-W13 | 2022-03 | 161 | 123 | 63.08 | 6 | 1 | 2 | 0.08 | 193501 | 2.3 | 0 | 0 | 0 | 2 |  | 2 | 6 | 38 | 0 | 0 | 2022-01 | 0 | 0
2635 | CR0015039 | CTASK0032942 | Closed | OPUS-PRD | Phu Nguyen Hoang | 10 | 10 | 2022-03-31 12:16 | 2022-03-01 12:16 | Container | Service Management | Product Catalog |  |  |  | [CLT Internal] Ocean Route excel upload-MAR | 2022-01-25 06:05 | 2022-02-25 18:00 | 2022-02-25 09:38 | 2022-03-23 16:58 | 2022-03-25 07:23 |  | 2022-03-29 08:00 | 2022-03-29 08:00 | 2022-03-25 11:43 | 2022-04-05 12:00 | CR0015039 | Service ManagementProduct Catalog | OPUS-PRD | 2022-W13 | 2022-03 | 161 | 123 | 63.08 | 6 | 1 | 2 | 0.08 | 193463 | 2.9 | 0 | 0 | 0 | 2 |  | 2 | 6 | 38 | 0 | 0 | 2022-01 | 0 | 0
2636 | CR0015039 | CTASK0031925 | Closed | OPUS-PRD | Phu Nguyen Hoang | 26 | 26 |  |  | Container | Service Management | Product Catalog |  |  |  | [CLT Internal] Ocean Route excel upload-JAN | 2022-01-25 06:05 | 2022-02-25 18:00 | 2022-02-25 09:38 | 2022-03-23 16:58 | 2022-03-25 07:23 |  | 2022-03-29 08:00 | 2022-03-29 08:00 | 2022-03-25 11:43 | 2022-04-05 12:00 | CR0015039 | Service ManagementProduct Catalog | OPUS-PRD | 2022-W13 | 2022-03 | 161 | 123 | 63.08 | 6 | 1 | 2 | 0.08 | 193463 | 2.9 | 0 | 0 | 0 | 2 |  | 2 | 6 | 38 | 0 | 0 | 2022-01 | 0 | 0
2637 | CR0015039 | CTASK0032309 | Closed | OPUS-PRD | Phu Nguyen Hoang | 68 | 30 |  |  | Container | Service Management | Product Catalog |  |  |  | [CLT Internal] Ocean Route excel upload-FEB | 2022-01-25 06:05 | 2022-02-25 18:00 | 2022-02-25 09:38 | 2022-03-23 16:58 | 2022-03-25 07:23 |  | 2022-03-29 08:00 | 2022-03-29 08:00 | 2022-03-25 11:43 | 2022-04-05 12:00 | CR0015039 | Service ManagementProduct Catalog | OPUS-PRD | 2022-W13 | 2022-03 | 161 | 123 | 63.08 | 6 | 1 | 2 | 0.08 | 193463 | 2.9 | 0 | 0 | 0 | 2 |  | 2 | 6 | 38 | 0 | 0 | 2022-01 | 0 | 0
2638 | CR0014537 | CTASK0031287 | Closed | OPUS-BKG-M | Kieu Le | 16 | 16 | 2021-12-24 20:38 | 2021-12-20 17:38 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Design] [LA ENHANCEMENT] - Comm - GD2 check box next VVD | 2021-12-28 09:13 | 2022-01-20 | 2022-01-13 12:07 | 2022-05-10 07:24 | 2022-05-10 07:27 |  | 2022-05-24 08:00 | 2022-05-24 08:00 | 2022-05-19 07:54 | 2022-06-01 12:00 | CR0014537 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W21 | 2022-05 | 51 | 51 | 146.9495 | 4 | 1 | 2 | 0.01 | 153106 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.22951 | 0 | 2021-12 | 0 | 0
2639 | CR0014537 | CTASK0031311 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2022-01-14 20:19 | 2022-01-04 00:19 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Testing] [LA ENHANCEMENT] - Comm - GD2 check box next VVD | 2021-12-28 09:13 | 2022-01-20 | 2022-01-13 12:07 | 2022-05-10 07:24 | 2022-05-10 07:27 |  | 2022-05-24 08:00 | 2022-05-24 08:00 | 2022-05-19 07:54 | 2022-06-01 12:00 | CR0014537 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W21 | 2022-05 | 51 | 51 | 146.9495 | 4 | 1 | 2 | 0.01 | 153106 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.22951 | 0 | 2021-12 | 0 | 0
2640 | CR0014537 | CTASK0031309 | Closed | OPUS-BKG-M | Kieu Le | 24 | 24 | 2021-12-31 20:18 | 2021-12-27 00:17 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Development] [LA ENHANCEMENT] - Comm - GD2 check box next VVD | 2021-12-28 09:13 | 2022-01-20 | 2022-01-13 12:07 | 2022-05-10 07:24 | 2022-05-10 07:27 |  | 2022-05-24 08:00 | 2022-05-24 08:00 | 2022-05-19 07:54 | 2022-06-01 12:00 | CR0014537 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W21 | 2022-05 | 51 | 51 | 146.9495 | 4 | 1 | 2 | 0.01 | 153106 | 3.2 | 2 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0.22951 | 0 | 2021-12 | 0 | 0
2641 | CR0014537 | CTASK0031313 | Closed | OPUS-BKG-M | Khoi Bui | 3 | 3 | 2022-05-24 13:20 | 2022-05-16 00:20 | Container | Service Management | Booking/Documentation | Booking | Booking | Booking Creation [Alt+1] | [Deployment] [LA ENHANCEMENT] - Comm - GD2 check box next VVD | 2021-12-28 09:13 | 2022-01-20 | 2022-01-13 12:07 | 2022-05-10 07:24 | 2022-05-10 07:27 |  | 2022-05-24 08:00 | 2022-05-24 08:00 | 2022-05-19 07:54 | 2022-06-01 12:00 | CR0014537 | Service ManagementBooking/DocumentationBookingBookingBooking Creation [Alt+1] | OPUS-BKG-M | 2022-W21 | 2022-05 | 51 | 51 | 146.9495 | 4 | 1 | 2 | 0.01 | 203713 | 1.1 | 2 | 0 | 0 | 1 |  | 2 | 5 | 26 | 0 | 0 | 2021-12 | 0 | 0
2642 | CR0014240 | CTASK0029273 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 | 2021-09-08 | 2021-09-07 | Container | Service Management | Booking/Documentation |  |  |  | [Design] (HBA) EUA AUTH ¦ Add Egypt ACI reference options to Booking flatfile and booking load process | 2021-09-10 07:26 | 2021-09-30 22:00 | 2021-09-29 15:11 | 2021-10-08 07:15 | 2021-10-08 07:31 |  | 2021-10-19 08:00 | 2021-10-13 08:30 | 2021-10-08 15:40 | 2021-10-20 12:00 | CR0014240 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W42 | 2021-10 | 4 | 15 | 39.0234 | 3 | 1 | 1 | 0.02 | 193525 | 2.3 | 0 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0 | 0.16667 | 2021-09 | 0 | 0
2643 | CR0014240 | CTASK0029276 | Closed | OPUS-BKG-EBKG | Vinh Tran | 4 | 4 |  |  | Container | Service Management | Booking/Documentation |  |  |  | [Deployment] (HBA) EUA AUTH ¦ Add Egypt ACI reference options to Booking flatfile and booking load process | 2021-09-10 07:26 | 2021-09-30 22:00 | 2021-09-29 15:11 | 2021-10-08 07:15 | 2021-10-08 07:31 |  | 2021-10-19 08:00 | 2021-10-13 08:30 | 2021-10-08 15:40 | 2021-10-20 12:00 | CR0014240 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W42 | 2021-10 | 4 | 15 | 39.0234 | 3 | 1 | 1 | 0.02 | 193525 | 2.3 | 0 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0 | 0.16667 | 2021-09 | 0 | 0
2644 | CR0014240 | CTASK0029275 | Closed | OPUS-BKG-EBKG | Vinh Tran | 7 | 7 |  |  | Container | Service Management | Booking/Documentation |  |  |  | [Development+Testing] (HBA) EUA AUTH ¦ Add Egypt ACI reference options to Booking flatfile and booking load process | 2021-09-10 07:26 | 2021-09-30 22:00 | 2021-09-29 15:11 | 2021-10-08 07:15 | 2021-10-08 07:31 |  | 2021-10-19 08:00 | 2021-10-13 08:30 | 2021-10-08 15:40 | 2021-10-20 12:00 | CR0014240 | Service ManagementBooking/Documentation | OPUS-BKG-MFT-M | 2021-W42 | 2021-10 | 4 | 15 | 39.0234 | 3 | 1 | 1 | 0.02 | 193525 | 2.3 | 0 | 0 | 0 | 1 |  | 1 | 6 | 26 | 0 | 0.16667 | 2021-09 | 0 | 0
2645 | CR0015249 | CTASK0033052 | Closed | OPUS-BKG-OB | Nam Nguyen | 12 | 12 | 2022-06-10 21:00 | 2022-04-01 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Approval | [Development + Testing] [CLT Internal] to prevent the undefined case in C/A Approval | 2022-03-31 06:18 | 2022-04-11 22:00 | 2022-04-11 14:52 | 2022-04-13 15:11 | 2022-04-14 12:20 |  | 2022-04-26 08:00 | 2022-04-26 09:40 | 2022-04-14 13:09 | 2022-05-03 12:00 | CR0015249 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Approval | OPUS-BKG-M | 2022-W17 | 2022-04 | 16 | 22 | 26.0705 | 3 | 1 | 1 | 0.04 | 123048 | 3.5 | 1 | 0 | 0 | 1 |  | 1 | 6 | 18 | 0.22222 | 0 | 2022-03 | 0 | 0
2646 | CR0015249 | CTASK0033053 | Closed | OPUS-BKG-OB | Nam Nguyen | 6 | 6 |  |  | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Approval | [Deployment] [CLT Internal] to prevent the undefined case in C/A Approval | 2022-03-31 06:18 | 2022-04-11 22:00 | 2022-04-11 14:52 | 2022-04-13 15:11 | 2022-04-14 12:20 |  | 2022-04-26 08:00 | 2022-04-26 09:40 | 2022-04-14 13:09 | 2022-05-03 12:00 | CR0015249 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Approval | OPUS-BKG-M | 2022-W17 | 2022-04 | 16 | 22 | 26.0705 | 3 | 1 | 1 | 0.04 | 123048 | 3.5 | 1 | 0 | 0 | 1 |  | 1 | 6 | 18 | 0.22222 | 0 | 2022-03 | 0 | 0
2647 | CR0015249 | CTASK0033037 | Closed | OPUS-BKG-OB | Nam Nguyen | 4 | 4 | 2022-03-25 21:00 | 2022-03-21 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | C/A (Correction Advice) | C/A Approval | [Design][CLT Internal] to prevent the undefined case in C/A Approval | 2022-03-31 06:18 | 2022-04-11 22:00 | 2022-04-11 14:52 | 2022-04-13 15:11 | 2022-04-14 12:20 |  | 2022-04-26 08:00 | 2022-04-26 09:40 | 2022-04-14 13:09 | 2022-05-03 12:00 | CR0015249 | Service ManagementBooking/DocumentationOutbound DocC/A (Correction Advice)C/A Approval | OPUS-BKG-M | 2022-W17 | 2022-04 | 16 | 22 | 26.0705 | 3 | 1 | 1 | 0.04 | 123048 | 3.5 | 1 | 0 | 0 | 1 |  | 1 | 6 | 18 | 0.22222 | 0 | 2022-03 | 0 | 0
2648 | CR0014079 | CTASK0028411 | Closed | OPUS-BKG-M | Trang Le Minh | 8 | 8 | 2021-11-30 20:39 | 2021-11-01 00:38 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Deployment] Multiple EQ related enhancements for Standby | 2021-08-01 17:04 | 2021-08-25 22:00 | 2021-08-24 15:27 | 2021-10-28 07:09 | 2021-10-28 15:36 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-10-29 08:37 | 2021-11-30 12:01 | CR0014079 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W47 | 2021-11 | 71 | 70 | 113.6221 | 4 | 1 | 2 | 0.03 | 193594 | 1.9 | 1 | 0 | 1 | 1 |  | 2 | 7 | 38 | 0 | 0 | 2021-08 | 1 | 1
2649 | CR0014079 | CTASK0028110 | Closed | OPUS-BKG-M | Kieu Le | 24 | 24 | 2021-07-30 23:53 | 2021-07-13 00:53 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Design] Multiple EQ related enhancements for Standby | 2021-08-01 17:04 | 2021-08-25 22:00 | 2021-08-24 15:27 | 2021-10-28 07:09 | 2021-10-28 15:36 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-10-29 08:37 | 2021-11-30 12:01 | CR0014079 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W47 | 2021-11 | 71 | 70 | 113.6221 | 4 | 1 | 2 | 0.03 | 153106 | 2.8 | 1 | 0 | 1 | 1 |  | 2 | 7 | 38 | 0.22951 | 0.13043 | 2021-08 | 1 | 1
2650 | CR0014079 | CTASK0028409 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-08-31 20:37 | 2021-08-05 15:37 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Testing] Multiple EQ related enhancements for Standby | 2021-08-01 17:04 | 2021-08-25 22:00 | 2021-08-24 15:27 | 2021-10-28 07:09 | 2021-10-28 15:36 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-10-29 08:37 | 2021-11-30 12:01 | CR0014079 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W47 | 2021-11 | 71 | 70 | 113.6221 | 4 | 1 | 2 | 0.03 | 153106 | 2.8 | 1 | 0 | 1 | 1 |  | 2 | 7 | 38 | 0.22951 | 0.13043 | 2021-08 | 1 | 1
2651 | CR0014079 | CTASK0028408 | Closed | OPUS-BKG-M | Kieu Le | 31 | 30 | 2021-08-31 20:36 | 2021-08-05 00:36 | Container | Service Management | Booking/Documentation | Booking | Standby Booking |  | [Development] Multiple EQ related enhancements for Standby | 2021-08-01 17:04 | 2021-08-25 22:00 | 2021-08-24 15:27 | 2021-10-28 07:09 | 2021-10-28 15:36 |  | 2021-11-23 08:00 | 2021-11-23 08:00 | 2021-10-29 08:37 | 2021-11-30 12:01 | CR0014079 | Service ManagementBooking/DocumentationBookingStandby Booking | OPUS-BKG-M | 2021-W47 | 2021-11 | 71 | 70 | 113.6221 | 4 | 1 | 2 | 0.03 | 153106 | 2.8 | 1 | 0 | 1 | 1 |  | 2 | 7 | 38 | 0.22951 | 0.13043 | 2021-08 | 1 | 1
2652 | CR0014607 | CTASK0034348 | Closed | OPUS-INV | Nguyen Ha Vi | 33 | 30 | 2022-05-31 11:54 | 2022-05-23 11:54 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Deployment] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 203664 | 1.4 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 1.8182 | 2.5 | 2021-11 | 2 | 1
2653 | CR0014607 | CTASK0032206 | Closed | OPUS-INV | Nguyen Ha Vi | 67 | 60 | 2022-02-28 16:48 | 2022-02-07 16:48 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Feb-2022]Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 203664 | 1.4 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 1.8182 | 2.5 | 2021-11 | 2 | 1
2654 | CR0014607 | CTASK0032734 | Closed | OPUS-TRS | Giang Nguyen Hoang | 30 | 30 | 2022-03-20 08:25 | 2022-03-01 08:25 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [202203][Asia *AR INV* Send invoice & receipt data via FTP for MNLBB] | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 183440 | 2.7 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0 | 0 | 2021-11 | 2 | 1
2655 | CR0014607 | CTASK0035196 | Closed | OPUS-DMT | Cuong Nguyen | 16 | 40 | 2022-07-16 18:16 | 2022-06-28 18:16 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [DMT-202206] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 193529 | 2.4 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.11538 | 0.22222 | 2021-11 | 2 | 1
2656 | CR0014607 | CTASK0032718 | Closed | OPUS-TRS | Nhat Phan Dinh Minh | 19 | 20 | 2022-03-31 18:17 | 2022-03-04 18:17 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [202203][Asia *AR INV* Send invoice & receipt data via FTP for MNLBB] | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 183432 | 2.7 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.043478 | 0.22222 | 2021-11 | 2 | 1
2657 | CR0014607 | CTASK0030194 | Closed | OPUS-DMT | Cuong Nguyen | 120 | 120 | 2022-03-31 09:45 | 2021-11-08 09:44 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [DMT-TASK1] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 193529 | 2.4 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.11538 | 0.22222 | 2021-11 | 2 | 1
2658 | CR0014607 | CTASK0032577 | Closed | OPUS-INV | Nguyen Ha Vi | 46 | 40 | 2022-03-31 11:31 | 2022-03-01 11:31 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Mar 2022] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 203664 | 1.4 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 1.8182 | 2.5 | 2021-11 | 2 | 1
2659 | CR0014607 | CTASK0030188 | Closed | OPUS-TPB | Manh Nguyen | 1 | 1 | 2021-10-29 20:00 | 2021-10-04 08:18 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [202110] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 153138 | 3.1 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.16667 | 0 | 2021-11 | 2 | 1
2660 | CR0014607 | CTASK0033285 | Closed | OPUS-TPB | Manh Nguyen | 34 | 35 | 2022-07-29 15:36 | 2022-04-01 15:36 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Test] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 153138 | 3.1 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.16667 | 0 | 2021-11 | 2 | 1
2661 | CR0014607 | CTASK0034125 | Closed | OPUS-INV | Nguyen Ha Vi | 22 | 20 | 2022-05-31 11:26 | 2022-05-09 11:26 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Development] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 203664 | 1.4 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 1.8182 | 2.5 | 2021-11 | 2 | 1
2662 | CR0014607 | CTASK0031285 | Closed | OPUS-TPB | Manh Nguyen | 20 | 20 | 2021-12-31 19:00 | 2021-12-01 06:00 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [202112] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 153138 | 3.1 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.16667 | 0 | 2021-11 | 2 | 1
2663 | CR0014607 | CTASK0034252 | Closed | OPUS-INV | Nguyen Ha Vi | 22 | 20 | 2022-05-24 14:53 | 2022-05-16 14:53 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Development] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 203664 | 1.4 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 1.8182 | 2.5 | 2021-11 | 2 | 1
2664 | CR0014607 | CTASK0032578 | Closed | OPUS-INV | Lien Le | 16 | 15 | 2022-03-31 11:32 | 2022-03-01 11:32 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Mar 2022] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 193441 | 2.7 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.42308 | 0 | 2021-11 | 2 | 1
2665 | CR0014607 | CTASK0031419 | Closed | OPUS-TPB | Manh Nguyen | 69 | 70 | 2022-01-31 20:00 | 2022-01-03 06:00 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [202201] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 153138 | 3.1 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.16667 | 0 | 2021-11 | 2 | 1
2666 | CR0014607 | CTASK0033453 | Closed | OPUS-TRS | Giang Nguyen Hoang | 12 | 15 | 2022-04-30 15:36 | 2022-04-01 15:36 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Development][TRS][Asia *AR INV* Send invoice & receipt data via FTP for MNLBB] | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 183440 | 2.7 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0 | 0 | 2021-11 | 2 | 1
2667 | CR0014607 | CTASK0032431 | Closed | OPUS-INV | Lien Le | 38 | 35 | 2022-02-28 18:38 | 2022-02-14 18:38 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Feb 2022] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 193441 | 2.7 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.42308 | 0 | 2021-11 | 2 | 1
2668 | CR0014607 | CTASK0032078 | Closed | OPUS-TPB | Manh Nguyen | 33 | 33 | 2022-02-28 19:00 | 2022-02-03 06:00 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [202202] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 153138 | 3.1 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.16667 | 0 | 2021-11 | 2 | 1
2669 | CR0014607 | CTASK0034254 | Closed | OPUS-INV | Lien Le | 34 | 30 | 2022-05-24 14:54 | 2022-05-17 14:54 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [Test] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 193441 | 2.7 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.42308 | 0 | 2021-11 | 2 | 1
2670 | CR0014607 | CTASK0032602 | Closed | OPUS-TPB | Manh Nguyen | 29 | 30 | 2022-03-31 13:06 | 2022-03-02 13:06 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [202203] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 153138 | 3.1 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.16667 | 0 | 2021-11 | 2 | 1
2671 | CR0014607 | CTASK0030239 | Closed | OPUS-TPB | Manh Nguyen | 1 | 1 | 2021-11-30 20:00 | 2021-11-01 06:00 | Container | Service Management | A/R Invoice | Invoice Issue | Invoice Issue |  | [202111] Asia *AR INV* Send invoice & receipt data via FTP for MNLBB | 2021-11-05 11:46 | 2022-03-11 22:00 | 2022-03-11 09:26 | 2022-05-17 11:13 | 2022-05-26 15:10 |  | 2022-05-31 08:00 | 2022-05-31 14:00 | 2022-05-27 11:16 | 2022-07-13 12:00 | CR0014607 | Service ManagementA/R InvoiceInvoice IssueInvoice Issue | OPUS-INV | 2022-W22 | 2022-05 | 660 | 665 | 206.8431 | 20 | 4 | 6 | 0.13 | 153138 | 3.1 | 4 | 2 | 0 | 4 |  | 3 | 7 | 26 | 0.16667 | 0 | 2021-11 | 2 | 1
2672 | CR0014814 | CTASK0030846 | Closed | OPUS-BKG-M | Kieu Le | 8 | 8 | 2021-12-17 20:16 | 2021-12-13 00:16 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Testing] [CLT Internal] Missing interface to COA and INV when booking is changed from firm to standby | 2021-12-15 14:07 | 2021-12-23 | 2021-12-16 12:59 | 2021-12-24 07:19 | 2021-12-24 07:24 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:03 | 2022-01-25 12:00 | CR0014814 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2022-W3 | 2022-01 | 28 | 28 | 33.7451 | 4 | 1 | 1 | 0.03 | 153106 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 11 | 33 | 0.22951 | 0 | 2021-12 | 0 | 0
2673 | CR0014814 | CTASK0030845 | Closed | OPUS-BKG-M | Kieu Le | 12 | 12 | 2021-12-06 20:15 | 2021-12-01 00:15 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Development] [CLT Internal] Missing interface to COA and INV when booking is changed from firm to standby | 2021-12-15 14:07 | 2021-12-23 | 2021-12-16 12:59 | 2021-12-24 07:19 | 2021-12-24 07:24 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:03 | 2022-01-25 12:00 | CR0014814 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2022-W3 | 2022-01 | 28 | 28 | 33.7451 | 4 | 1 | 1 | 0.03 | 153106 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 11 | 33 | 0.22951 | 0 | 2021-12 | 0 | 0
2674 | CR0014814 | CTASK0030844 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2021-12-03 20:14 | 2021-12-01 00:14 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Design] [CLT Internal] Missing interface to COA and INV when booking is changed from firm to standby | 2021-12-15 14:07 | 2021-12-23 | 2021-12-16 12:59 | 2021-12-24 07:19 | 2021-12-24 07:24 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:03 | 2022-01-25 12:00 | CR0014814 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2022-W3 | 2022-01 | 28 | 28 | 33.7451 | 4 | 1 | 1 | 0.03 | 153106 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 11 | 33 | 0.22951 | 0 | 2021-12 | 0 | 0
2675 | CR0014814 | CTASK0030848 | Closed | OPUS-BKG-M | Kieu Le | 4 | 4 | 2022-01-31 11:17 | 2022-01-03 11:17 | Container | Service Management | Booking/Documentation | Booking | Standby Booking | Standby Booking Status Report | [Deployment] [CLT Internal] Missing interface to COA and INV when booking is changed from firm to standby | 2021-12-15 14:07 | 2021-12-23 | 2021-12-16 12:59 | 2021-12-24 07:19 | 2021-12-24 07:24 |  | 2022-01-18 08:00 | 2022-01-18 09:30 | 2022-01-04 16:03 | 2022-01-25 12:00 | CR0014814 | Service ManagementBooking/DocumentationBookingStandby BookingStandby Booking Status Report | OPUS-BKG-M | 2022-W3 | 2022-01 | 28 | 28 | 33.7451 | 4 | 1 | 1 | 0.03 | 153106 | 3.2 | 1 | 0 | 0 | 1 |  | 1 | 11 | 33 | 0.22951 | 0 | 2021-12 | 0 | 0
2676 | CR0015208 | CTASK0033140 | Closed | OPUS-BKG-IB | Linh Dinh Bo | 52 | 48 | 2022-04-26 14:47 | 2022-03-23 14:47 | Container | Service Management | Booking/Documentation | Inbound Doc | Cargo Release | EU Full Container Release | [Analysis+Development+Testing+Deployment]EUA - Cancel Release in EU Full Cntr Release - M/H - eMail & Search criteria | 2022-03-30 07:21 | 2022-04-26 22:00 | 2022-04-25 12:27 | 2022-05-12 09:19 | 2022-05-17 15:10 |  | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-05-17 15:57 | 2022-06-07 12:00 | CR0015208 | Service ManagementBooking/DocumentationInbound DocCargo ReleaseEU Full Container Release | OPUS-BKG-IB | 2022-W22 | 2022-05 | 52 | 48 | 62.0272 | 1 | 1 | 1 | 0.03 | 193522 | 2.8 | 1 | 1 | 0 | 1 |  | 2 | 7 | 26 | 0 | 0 | 2022-03 | 1 | 1
2677 | CR0014638 | CTASK0030063 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 6 | 6 | 2021-12-20 22:00 | 2021-12-15 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Deployment] [CLT-Internal] show the full text for black list customer reason on Freight & Charge screen | 2021-10-26 09:35 | 2021-11-11 22:00 | 2021-11-10 07:36 | 2021-12-09 08:20 | 2021-12-09 09:33 |  | 2021-12-21 08:00 | 2021-12-21 08:50 | 2021-12-09 11:21 | 2021-12-28 12:01 | CR0014638 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W51 | 2021-12 | 21 | 24 | 55.9342 | 3 | 1 | 1 | 0.02 | 193470 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 3 | 26 | 0.36842 | 0.11111 | 2021-10 | 0 | 0
2678 | CR0014638 | CTASK0030062 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 11 | 14 | 2021-10-29 17:30 | 2021-10-26 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Dev + Test] [CLT-Internal] show the full text for black list customer reason on Freight & Charge screen | 2021-10-26 09:35 | 2021-11-11 22:00 | 2021-11-10 07:36 | 2021-12-09 08:20 | 2021-12-09 09:33 |  | 2021-12-21 08:00 | 2021-12-21 08:50 | 2021-12-09 11:21 | 2021-12-28 12:01 | CR0014638 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W51 | 2021-12 | 21 | 24 | 55.9342 | 3 | 1 | 1 | 0.02 | 193470 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 3 | 26 | 0.36842 | 0.11111 | 2021-10 | 0 | 0
2679 | CR0014638 | CTASK0030061 | Closed | OPUS-BKG-OB | Thai Nguyen Quoc | 4 | 4 | 2021-10-25 17:30 | 2021-10-21 08:30 | Container | Service Management | Booking/Documentation | Outbound Doc | B/L Creation | Freight & Charge [Alt+7] | [Desgin] [CLT-Internal] show the full text for black list customer reason on Freight & Charge screen | 2021-10-26 09:35 | 2021-11-11 22:00 | 2021-11-10 07:36 | 2021-12-09 08:20 | 2021-12-09 09:33 |  | 2021-12-21 08:00 | 2021-12-21 08:50 | 2021-12-09 11:21 | 2021-12-28 12:01 | CR0014638 | Service ManagementBooking/DocumentationOutbound DocB/L CreationFreight & Charge [Alt+7] | OPUS-BKG-CHG | 2021-W51 | 2021-12 | 21 | 24 | 55.9342 | 3 | 1 | 1 | 0.02 | 193470 | 2.6 | 1 | 0 | 0 | 1 |  | 2 | 3 | 26 | 0.36842 | 0.11111 | 2021-10 | 0 | 0
2680 | CR0014749 | CTASK0032233 | Closed | OPUS-BKG-IB | Linh Dinh Bo | 8 | 10 | 2022-02-22 13:50 | 2022-02-09 13:50 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Information | [Deployment+Testing] EUA: SSR No. and Article No. To Show on Arrival Notice when POD is BEANR | 2021-12-14 15:02 | 2022-01-21 21:01 | 2022-01-20 13:53 | 2022-01-26 06:55 | 2022-02-08 14:58 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-09 07:11 | 2022-03-01 12:00 | CR0014749 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Information | OPUS-BKG-IB | 2022-W8 | 2022-02 | 37 | 38 | 69.7071 | 2 | 1 | 1 | 0.02 | 193522 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
2681 | CR0014749 | CTASK0031382 | Closed | OPUS-BKG-IB | Linh Dinh Bo | 29 | 28 | 2022-01-07 12:42 | 2021-12-27 12:42 | Container | Service Management | Booking/Documentation | Inbound Doc | Arrival Notice | Arrival Information | [Development+ Testing+ Deployment] EUA: SSR No. and Article No. To Show on Arrival Notice when POD is BEANR | 2021-12-14 15:02 | 2022-01-21 21:01 | 2022-01-20 13:53 | 2022-01-26 06:55 | 2022-02-08 14:58 |  | 2022-02-22 08:00 | 2022-02-22 08:00 | 2022-02-09 07:11 | 2022-03-01 12:00 | CR0014749 | Service ManagementBooking/DocumentationInbound DocArrival NoticeArrival Information | OPUS-BKG-IB | 2022-W8 | 2022-02 | 37 | 38 | 69.7071 | 2 | 1 | 1 | 0.02 | 193522 | 2.5 | 1 | 0 | 0 | 1 |  | 2 | 14 | 30 | 0 | 0 | 2021-12 | 0 | 0
2682 | CR0014275 | CTASK0028565 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 8 | 8 | 2021-08-10 14:49 | 2021-08-02 14:49 | Container | Service Management | Booking/Documentation | Manifest | Japan(SEA-NACCS) | Transmit History to SEA_NACCS | [Estimate] [CLT Internal] *ESA-JPN* Trasmit History to SEA_NACCS shows different results for MSG Type =DOR when the users search every time | 2021-08-11 12:47 | 2021-09-30 22:00 | 2021-08-25 12:18 | 2021-09-28 16:01 | 2021-10-13 11:25 |  | 2021-10-19 08:01 | 2021-10-19 08:03 | 2021-10-14 11:30 | 2021-10-26 12:00 | CR0014275 | Service ManagementBooking/DocumentationManifestJapan(SEA-NACCS)Transmit History to SEA_NACCS | OPUS-BKG-MFT-A | 2021-W42 | 2021-10 | 34 | 40 | 68.8009 | 3 | 1 | 1 | 0.02 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 4.25 | 2.25 | 2021-08 | 0 | 0
2683 | CR0014275 | CTASK0028612 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 8 | 8 | 2021-08-31 08:58 | 2021-08-02 08:58 | Container | Service Management | Booking/Documentation | Manifest | Japan(SEA-NACCS) | Transmit History to SEA_NACCS | [Develop] [CLT Internal] *ESA-JPN* Trasmit History to SEA_NACCS shows different results for MSG Type =DOR when the users search every time | 2021-08-11 12:47 | 2021-09-30 22:00 | 2021-08-25 12:18 | 2021-09-28 16:01 | 2021-10-13 11:25 |  | 2021-10-19 08:01 | 2021-10-19 08:03 | 2021-10-14 11:30 | 2021-10-26 12:00 | CR0014275 | Service ManagementBooking/DocumentationManifestJapan(SEA-NACCS)Transmit History to SEA_NACCS | OPUS-BKG-MFT-A | 2021-W42 | 2021-10 | 34 | 40 | 68.8009 | 3 | 1 | 1 | 0.02 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 4.25 | 2.25 | 2021-08 | 0 | 0
2684 | CR0014275 | CTASK0028614 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 18 | 24 | 2021-08-31 09:00 | 2021-08-02 09:00 | Container | Service Management | Booking/Documentation | Manifest | Japan(SEA-NACCS) | Transmit History to SEA_NACCS | [Test + Deploy] [CLT Internal] *ESA-JPN* Trasmit History to SEA_NACCS shows different results for MSG Type =DOR when the users search every time | 2021-08-11 12:47 | 2021-09-30 22:00 | 2021-08-25 12:18 | 2021-09-28 16:01 | 2021-10-13 11:25 |  | 2021-10-19 08:01 | 2021-10-19 08:03 | 2021-10-14 11:30 | 2021-10-26 12:00 | CR0014275 | Service ManagementBooking/DocumentationManifestJapan(SEA-NACCS)Transmit History to SEA_NACCS | OPUS-BKG-MFT-A | 2021-W42 | 2021-10 | 34 | 40 | 68.8009 | 3 | 1 | 1 | 0.02 | 193606 | 1.8 | 1 | 0 | 0 | 1 |  | 2 | 6 | 26 | 4.25 | 2.25 | 2021-08 | 0 | 0
2685 | CR0014442 | CTASK0029247 | Closed | OPUS-SCO | Chuong Ta | 37 | 36 | 2021-09-30 09:58 | 2021-09-01 09:58 | Container | Statement Management | Statement Account Receivable |  |  |  | [Sep 2021][Chuong Ta]ONE DDE Project - PK logic Update for SAR (Additional) | 2021-09-07 09:38 | 2021-09-30 09:38 | 2021-09-30 12:51 | 2021-10-06 12:46 | 2021-10-06 12:49 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-07 11:27 | 2021-10-20 12:00 | CR0014442 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2021-W41 | 2021-10 | 48 | 46 | 34.9733 | 2 | 1 | 2 | 0.05 | 183379 | 2.5 | 2 | 0 | 0 | 1 |  | 1 | 9 | 26 | 0.32 | 0.375 | 2021-09 | 0 | 0
2686 | CR0014442 | CTASK0029250 | Closed | OPUS-SCO | Lien Le | 11 | 10 | 2021-09-30 10:00 | 2021-09-01 09:59 | Container | Statement Management | Statement Account Receivable |  |  |  | [Sep 2021][Lien Le] ONE DDE Project - PK logic Update for SAR (Additional) | 2021-09-07 09:38 | 2021-09-30 09:38 | 2021-09-30 12:51 | 2021-10-06 12:46 | 2021-10-06 12:49 |  | 2021-10-12 09:00 | 2021-10-12 09:00 | 2021-10-07 11:27 | 2021-10-20 12:00 | CR0014442 | Statement ManagementStatement Account Receivable | OPUS-SAR | 2021-W41 | 2021-10 | 48 | 46 | 34.9733 | 2 | 1 | 2 | 0.05 | 193441 | 2.5 | 2 | 0 | 0 | 1 |  | 1 | 9 | 26 | 0.42308 | 0 | 2021-09 | 0 | 0
2687 | CR0014670 | CTASK0030279 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 8 | 20 | 2022-01-31 18:11 | 2022-01-01 18:11 | Container | Service Management | Booking/Documentation | Manifest |  |  | [DEV][CLT Internal] Some shipment data cannot be loaded in HK Manifest UI | 2021-11-04 07:10 | 2021-11-30 22:00 | 2021-11-26 15:07 | 2021-12-24 09:17 | 2021-12-29 06:49 |  | 2022-01-11 08:00 | 2022-01-11 08:24 | 2021-12-29 16:20 | 2022-01-19 12:00 | CR0014670 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2022-W2 | 2022-01 | 18 | 30 | 68.0348 | 4 | 2 | 2 | 0.02 | 193606 | 2 | 1 | 0 | 0 | 1 |  | 2 | 7 | 33 | 4.25 | 0 | 2021-11 | 0 | 0
2688 | CR0014670 | CTASK0030278 | Closed | OPUS-BKG-MFT-A | Tung Nguyen Thanh | 2 | 2 | 2021-12-31 10:35 | 2021-12-01 10:34 | Container | Service Management | Booking/Documentation | Manifest |  |  | [EST][CLT Internal] Some shipment data cannot be loaded in HK Manifest UI | 2021-11-04 07:10 | 2021-11-30 22:00 | 2021-11-26 15:07 | 2021-12-24 09:17 | 2021-12-29 06:49 |  | 2022-01-11 08:00 | 2022-01-11 08:24 | 2021-12-29 16:20 | 2022-01-19 12:00 | CR0014670 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2022-W2 | 2022-01 | 18 | 30 | 68.0348 | 4 | 2 | 2 | 0.02 | 193606 | 2 | 1 | 0 | 0 | 1 |  | 2 | 7 | 33 | 4.25 | 0 | 2021-11 | 0 | 0
2689 | CR0014670 | CTASK0030280 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 4 | 4 | 2021-12-31 10:45 | 2021-12-01 10:45 | Container | Service Management | Booking/Documentation | Manifest |  |  | [TEST][CLT Internal] Some shipment data cannot be loaded in HK Manifest UI | 2021-11-04 07:10 | 2021-11-30 22:00 | 2021-11-26 15:07 | 2021-12-24 09:17 | 2021-12-29 06:49 |  | 2022-01-11 08:00 | 2022-01-11 08:24 | 2021-12-29 16:20 | 2022-01-19 12:00 | CR0014670 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2022-W2 | 2022-01 | 18 | 30 | 68.0348 | 4 | 2 | 2 | 0.02 | 193512 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 33 | 0.2963 | 0 | 2021-11 | 0 | 0
2690 | CR0014670 | CTASK0030281 | Closed | OPUS-BKG-IB | Nhut Nguyen Minh | 4 | 4 | 2021-12-31 10:45 | 2021-12-01 10:45 | Container | Service Management | Booking/Documentation | Manifest |  |  | [DEPLOY][CLT Internal] Some shipment data cannot be loaded in HK Manifest UI | 2021-11-04 07:10 | 2021-11-30 22:00 | 2021-11-26 15:07 | 2021-12-24 09:17 | 2021-12-29 06:49 |  | 2022-01-11 08:00 | 2022-01-11 08:24 | 2021-12-29 16:20 | 2022-01-19 12:00 | CR0014670 | Service ManagementBooking/DocumentationManifest | OPUS-BKG-MFT-E | 2022-W2 | 2022-01 | 18 | 30 | 68.0348 | 4 | 2 | 2 | 0.02 | 193512 | 2.3 | 1 | 0 | 0 | 1 |  | 2 | 7 | 33 | 0.2963 | 0 | 2021-11 | 0 | 0